## Outage Plan EirGrid
2019 GENERATION OUTAGE PLAN (EIRGRID)
|  | Month | Jan '2019 |  |  |  |  | Feb '2019 |  |  |  | Mar '2019 |  |  |  | Apr '2019 |  |  |  |  | May '2019 |  |  |  | Jun '2019 |  |  |  | Jul '2019 |  |  |  |  | Aug '2019 |  |  |  | Sep '2019 |  |  |  |  | Oct '2019 |  |  |  | Nov '2019 |  |  |  | Dec '2019
|  | Week | 1 '2019 | 2 '2019 | 3 '2019 | 4 '2019 | 5 '2019 | 6 '2019 | 7 '2019 | 8 '2019 | 9 '2019 | 10 '2019 | 11 '2019 | 12 '2019 | 13 '2019 | 14 '2019 | 15 '2019 | 16 '2019 | 17 '2019 | 18 '2019 | 19 '2019 | 20 '2019 | 21 '2019 | 22 '2019 | 23 '2019 | 24 '2019 | 25 '2019 | 26 '2019 | 27 '2019 | 28 '2019 | 29 '2019 | 30 '2019 | 31 '2019 | 32 '2019 | 33 '2019 | 34 '2019 | 35 '2019 | 36 '2019 | 37 '2019 | 38 '2019 | 39 '2019 | 40 '2019 | 41 '2019 | 42 '2019 | 43 '2019 | 44 '2019 | 45 '2019 | 46 '2019 | 47 '2019 | 48 '2019 | 49 '2019 | 50 '2019 | 51 '2019 | 52 '2019 | 1 '2020
Station | Unit | NPR
Activation Energy | AE1 | 77
Activation Energy | AE2 | 8
Activation Energy | AE3 | 14
Activation Energy | AE4 | 11
Activation Energy | AE5 | 15
Activation Energy | EN5 | 6
Activation Energy | EN6 | 10
Aghada | AD2 | 431 | [34 empty] | S | S | S | S | S | S | S | S
Aghada | AT1 | 90
Aghada | AT2 | 90 | [40 empty] | S | S | S
Aghada | AT4 | 90
Ardnacrusha | AA1 | 21 | [23 empty] | S
Ardnacrusha | AA2 | 22 | [34 empty] | S | S | S
Ardnacrusha | AA3 | 19 | [19 empty] | S
Ardnacrusha | AA4 | 24 | [14 empty] | S
DAE Virtual Power Plant | DP1 | 19
DAE Virtual Power Plant | DP2 | 20
Dublin Bay | DB1 | 405 | [12 empty] | S | S | S
Dublin Waste To Energy | DW1 | 62
Edenderry | ED1 | 118 | [23 empty] | S | S | S | S | S | S | S | S | S | S | [18 empty] | S | S
Edenderry | ED3 | 58
Edenderry | ED5 | 58
Electric Ireland | EI1 | 20
Electricity Exchange DSU | EE1 | 39
Electricity Exchange DSU | EE2 | 17
Electricity Exchange DSU | EE3 | 7
Electricity Exchange DSU | EE4 | 9
Electricity Exchange DSU | EE5 | 7
Endeco Technologies | EC1 | 37
Endeco Technologies | EC2 | 10
Endeco Technologies | EC5 | 16
Energy Trading | ET1 | 13
Erne | ER1 | 10 | [35 empty] | S
Erne | ER2 | 10 | [33 empty] | S
Erne | ER3 | 22 | [19 empty] | S
Erne | ER4 | 22 | [23 empty] | S | S | S
EWIC | EW1 | 500 | [18 empty] | S
Great Island | GI4 | 461
Huntstown | HN2 | 400 | [16 empty] | S | S | S
Huntstown | HNC | 342
Indaver | IW1 | 17 | [13 empty] | S | S
Lanesboro | LR4 | 91 | [11 empty] | S | S | S
Lee | LE1 | 15 | [19 empty] | S
Lee | LE2 | 4 | [13 empty] | S
Lee | LE3 | 8 | [23 empty] | S
Liffey | LI1 | 15
Liffey | LI2 | 15
Liffey | LI4 | 4
Liffey | LI5 | 4
Moneypoint | MP1 | 285 | [19 empty] | S
Moneypoint | MP2 | 285 | F | F | F | F | F | F | F | F | F | F | F | F | F | F |  |  |  | S | S | S | S | S | S | S | S
Moneypoint | MP3 | 285 | [32 empty] | S
North Wall | NW5 | 104 | [39 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Poolbeg | PB4 | 154 | [30 empty] | S |  |  |  |  | S | S | S | S | S
Poolbeg | PB5 | 146 | [30 empty] | S |  |  |  |  | S
Poolbeg | PB6 | 168 | [30 empty] | S |  |  |  |  | S
Powerhouse Generation | PG1 | 11
Rhode | RP1 | 52 | [31 empty] | S
Rhode | RP2 | 52 | [31 empty] | S
Seal Rock | SK3 | 85 | [36 empty] | S
Seal Rock | SK4 | 85 | [26 empty] | S | S | S
Tarbert | TB1 | 54 | [21 empty] | S
Tarbert | TB2 | 54 | [21 empty] | S
Tarbert | TB3 | 241 | [22 empty] | S
Tarbert | TB4 | 243
Tawnaghmore | TP1 | 52
Tawnaghmore | TP3 | 52
Turlough Hill | TH1 | 73 | [9 empty] | S
Turlough Hill | TH2 | 73 | [9 empty] | S
Turlough Hill | TH3 | 73 | [24 empty] | S | S
Turlough Hill | TH4 | 73 | [24 empty] | S | S
Tynagh | TYC | 384
Viridian Energy | VE1 | 19
Viridian Energy DSU | VE2 | 6
West Offaly | WO4 | 137 | [18 empty] | S | S | S
Whitegate | WG1 | 444

## EirGrid Outages
Upcoming Outages including STMOs and Annual Outages
Station | Unit | NPR | Start Date | End Date | Value | Duration
Moneypoint | MP2 | 285 | 2018-09-26 23:00 | 2019-04-05 18:00 | F | 190.75
Edenderry | ED1 | 118 | 2018-12-26 12:00 | 2019-01-02 08:00 | S | 6.83
Seal Rock | SK3 | 85 | 2019-01-13 07:00 | 2019-01-15 17:00 | S | 2.42
EWIC | EW1 | 500 | 2019-02-16 12:00 | 2019-02-17 23:00 | S | 1.42
Seal Rock | SK4 | 85 | 2019-03-03 07:00 | 2019-03-05 17:00 | S | 2.42
Turlough Hill | TH2 | 73 | 2019-03-03 08:00 | 2019-03-09 17:00 | S | 6.33
Turlough Hill | TH1 | 73 | 2019-03-03 08:00 | 2019-03-09 17:00 | S | 6.33
Lanesboro | LR4 | 91 | 2019-03-19 16:00 | 2019-04-07 16:00 | S | 19
Dublin Bay | DB1 | 405 | 2019-03-22 13:00 | 2019-04-14 13:00 | S | 23
Aghada | AT2 | 90 | 2019-03-25 | 2019-03-28 | S | 3
Indaver | IW1 | 17 | 2019-04-01 | 2019-04-16 | S | 15
Lee | LE2 | 4 | 2019-04-01 08:00 | 2019-04-05 20:00 | S | 4.5
Liffey | LI1 | 15 | 2019-04-02 08:00 | 2019-04-04 17:00 | S | 2.33
Liffey | LI2 | 15 | 2019-04-02 08:00 | 2019-04-04 17:00 | S | 2.33
Ardnacrusha | AA4 | 24 | 2019-04-08 08:00 | 2019-04-12 20:00 | S | 4.5
Liffey | LI4 | 4 | 2019-04-09 08:00 | 2019-04-11 17:00 | S | 2.33
Whitegate | WG1 | 444 | 2019-04-12 | 2019-04-19 | S | 7
Edenderry | ED1 | 118 | 2019-04-18 18:00 | 2019-04-24 08:00 | S | 5.58
Huntstown | HN2 | 400 | 2019-04-23 | 2019-05-13 | S | 20
Moneypoint | MP2 | 285 | 2019-04-26 22:00 | 2019-06-23 22:00 | S | 58
EWIC | EW1 | 500 | 2019-05-06 19:00 | 2019-05-10 19:00 | S | 4
West Offaly | WO4 | 137 | 2019-05-09 16:00 | 2019-05-27 16:00 | S | 18
Moneypoint | MP1 | 285 | 2019-05-10 22:00 | 2019-05-19 22:00 | S | 9
Ardnacrusha | AA3 | 19 | 2019-05-13 08:00 | 2019-05-17 20:00 | S | 4.5
Erne | ER3 | 22.5 | 2019-05-13 08:00 | 2019-05-17 20:00 | S | 4.5
Lee | LE1 | 15 | 2019-05-13 08:00 | 2019-05-17 20:00 | S | 4.5
Seal Rock | SK3 | 85 | 2019-05-13 21:00 | 2019-05-15 12:00 | S | 1.58
Seal Rock | SK4 | 85 | 2019-05-13 23:00 | 2019-05-14 21:00 | S | 0.92
Edenderry | ED3 | 58 | 2019-05-18 08:00 | 2019-05-18 18:00 | S | 0.42
Edenderry | ED5 | 58 | 2019-05-18 08:00 | 2019-05-18 18:00 | S | 0.42
EWIC | EW1 | 500 | 2019-05-21 08:00 | 2019-05-21 20:00 | S | 0.5
Tarbert | TB2 | 54 | 2019-05-27 | 2019-06-03 | S | 7
Tarbert | TB1 | 54 | 2019-05-27 | 2019-06-03 | S | 7
EWIC | EW1 | 500 | 2019-05-28 08:00 | 2019-05-28 20:00 | S | 0.5
Tarbert | TB3 | 241 | 2019-06-03 | 2019-06-10 | S | 7
Edenderry | ED1 | 118 | 2019-06-07 12:00 | 2019-08-20 08:00 | S | 73.83
Erne | ER4 | 22.5 | 2019-06-10 08:00 | 2019-06-30 20:00 | S | 20.5
Ardnacrusha | AA1 | 21 | 2019-06-10 08:00 | 2019-06-14 20:00 | S | 4.5
Lee | LE3 | 8 | 2019-06-10 08:00 | 2019-06-14 20:00 | S | 4.5
Turlough Hill | TH4 | 73 | 2019-06-15 08:00 | 2019-06-29 17:00 | S | 14.33
Turlough Hill | TH3 | 73 | 2019-06-15 08:00 | 2019-06-29 17:00 | S | 14.33
Aghada | AT4 | 90 | 2019-06-18 | 2019-06-21 | S | 3
Seal Rock | SK4 | 85 | 2019-06-30 07:00 | 2019-07-18 07:00 | S | 18
Poolbeg | PB5 | 146 | 2019-07-29 | 2019-08-03 | S | 5
Poolbeg | PB4 | 154 | 2019-07-29 | 2019-08-03 | S | 5
Poolbeg | PB6 | 168 | 2019-07-29 | 2019-08-03 | S | 5
Rhode | RP1 | 52 | 2019-08-05 | 2019-08-12 | S | 7
Rhode | RP2 | 52 | 2019-08-05 | 2019-08-12 | S | 7
Moneypoint | MP3 | 285 | 2019-08-09 22:00 | 2019-08-18 22:00 | S | 9
Aghada | AT1 | 90 | 2019-08-19 | 2019-08-22 | S | 3
Erne | ER2 | 10 | 2019-08-19 08:00 | 2019-08-23 20:00 | S | 4.5
EWIC | EW1 | 500 | 2019-08-19 19:00 | 2019-08-20 16:00 | S | 0.83
Aghada | AD2 | 431 | 2019-08-23 20:00 | 2019-10-18 08:00 | S | 55.5
Ardnacrusha | AA2 | 22 | 2019-08-26 08:00 | 2019-09-17 20:00 | S | 22.5
Poolbeg | PB5 | 146 | 2019-09-02 | 2019-09-06 20:00 | S | 4.83
Poolbeg | PB4 | 154 | 2019-09-02 | 2019-10-07 | S | 35
Poolbeg | PB6 | 168 | 2019-09-02 | 2019-09-06 20:00 | S | 4.83
Erne | ER1 | 10 | 2019-09-02 08:00 | 2019-09-06 20:00 | S | 4.5
Poolbeg | PB6 | 168 | 2019-09-06 20:00 | 2019-10-07 | 84 | 30.17
Seal Rock | SK3 | 85 | 2019-09-09 07:00 | 2019-09-13 17:00 | S | 4.42
Liffey | LI5 | 4 | 2019-09-10 08:00 | 2019-09-12 17:00 | S | 2.33
Tynagh | TYC | 384 | 2019-09-20 22:00 | 2019-09-24 22:00 | S | 4
North Wall | NW5 | 104 | 2019-10-01 | 2022-10-01 | S | 1096
Aghada | AT2 | 90 | 2019-10-07 06:00 | 2019-10-26 20:00 | S | 19.58
EWIC | EW1 | 500 | 2019-10-31 20:00 | 2019-11-01 17:00 | S | 0.83
Seal Rock | SK4 | 85 | 2019-11-17 07:00 | 2019-11-19 17:00 | S | 2.42
Turlough Hill | TH1 | 73 | 2019-11-26 08:00 | 2019-11-28 17:00 | S | 2.33
Turlough Hill | TH2 | 73 | 2019-11-26 08:00 | 2019-11-28 17:00 | S | 2.33
Edenderry | ED1 | 118 | 2019-12-26 13:00 | 2020-01-02 08:00 | S | 6.75
|  |  | Scheduled Outage | S
|  |  | Forced Outage | F
|  |  | Unit partially available | 10

## Outage Plan SONI
2019 GENERATION OUTAGE PLAN (SONI)
|  | Month | Jan '2019 |  |  |  |  | Feb '2019 |  |  |  | Mar '2019 |  |  |  | Apr '2019 |  |  |  |  | May '2019 |  |  |  | Jun '2019 |  |  |  | Jul '2019 |  |  |  |  | Aug '2019 |  |  |  | Sep '2019 |  |  |  |  | Oct '2019 |  |  |  | Nov '2019 |  |  |  | Dec '2019
|  | Week | 1 '2019 | 2 '2019 | 3 '2019 | 4 '2019 | 5 '2019 | 6 '2019 | 7 '2019 | 8 '2019 | 9 '2019 | 10 '2019 | 11 '2019 | 12 '2019 | 13 '2019 | 14 '2019 | 15 '2019 | 16 '2019 | 17 '2019 | 18 '2019 | 19 '2019 | 20 '2019 | 21 '2019 | 22 '2019 | 23 '2019 | 24 '2019 | 25 '2019 | 26 '2019 | 27 '2019 | 28 '2019 | 29 '2019 | 30 '2019 | 31 '2019 | 32 '2019 | 33 '2019 | 34 '2019 | 35 '2019 | 36 '2019 | 37 '2019 | 38 '2019 | 39 '2019 | 40 '2019 | 41 '2019 | 42 '2019 | 43 '2019 | 44 '2019 | 45 '2019 | 46 '2019 | 47 '2019 | 48 '2019 | 49 '2019 | 50 '2019 | 51 '2019 | 52 '2019 | 1 '2020
Station | Unit | NPR
AC Automation | NIACA | 8
Activation Energy | NIAEA | 9
Ballylumford | NIB10 | 94 |  |  | S | [24 empty] | S | S
Ballylumford | NIB31 | 249 | [27 empty] | S | S
Ballylumford | NIB32 | 249 | [27 empty] | S | S
Ballylumford | NIB4 | 144 | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F
Ballylumford | NIB5 | 147 | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F
Ballylumford | NIBGT1 | 58 | [6 empty] | S
Ballylumford | NIBGT2 | 58 | [5 empty] | S
Contour Global | NICG2 | 3
Contour Global | NICGA | 12
Coolkeeragh | NIC30 | 408 | [34 empty] | S | S | S | S
Coolkeeragh | NICGT8 | 53 | [19 empty] | S | S | S | S
Empower | NIEMP | 3
Endeco Technologies | NIECA | 11
Energy Trading | NIETB | 9
Energy Trading | NIETD | 5
Energy Trading | NIETR | 19
iPower | NIAGU | 74
Kilroot | NIK1 | 256 | [14 empty] | S | S | S | S | S | S | S | S | S
Kilroot | NIK2 | 258 |  |  |  |  | S | S | S | S | S | S | S | S | S
Kilroot | NIKGT1 | 29 | [15 empty] | S | S | S | S | S | S
Kilroot | NIKGT2 | 29
Kilroot | NIKGT3 | 42 | [13 empty] | S
Kilroot | NIKGT4 | 42 | [14 empty] | S
Lisahally | NILPS | 18
Moyle | MOYLE | 450 | [23 empty] | S | S
Powerhouse Generation | NIPH1 | 31

## SONI Outages
Upcoming Outages including STMOs and Annual Outages
Station | Unit | NPR | Start Date | End Date | Value | Duration
Ballylumford | NIB4 | 144 | 2018-11-14 | 2020-01-01 | F | 413
Ballylumford | NIB5 | 147 | 2019-01-01 | 2101-01-01 | F | 29950
Ballylumford | NIB32 | 249 | 2019-01-07 19:00 | 2019-01-10 19:00 | S | 3
Ballylumford | NIB32 | 249 | 2019-01-07 19:00 | 2019-01-10 19:00 | S | 3
Ballylumford | NIB10 | 94 | 2019-01-14 19:00 | 2019-01-21 19:00 | S | 7
Ballylumford | NIB10 | 94 | 2019-01-14 19:00 | 2019-01-20 19:00 | S | 6
Coolkeeragh | NIC30 | 408 | 2019-01-26 | 2019-01-28 | S | 2
Kilroot | NIK2 | 258 | 2019-01-30 | 2019-03-30 | S | 59
Ballylumford | NIBGT2 | 58 | 2019-02-04 | 2019-02-11 | S | 7
Ballylumford | NIBGT1 | 58 | 2019-02-11 | 2019-02-18 | S | 7
Kilroot | NIKGT3 | 42 | 2019-04-01 | 2019-04-06 | S | 5
Kilroot | NIKGT4 | 42 | 2019-04-08 | 2019-04-13 | S | 5
Kilroot | NIK1 | 256 | 2019-04-11 | 2019-06-08 | S | 58
Kilroot | NIKGT1 | 29 | 2019-04-15 | 2019-05-27 | S | 42
Coolkeeragh | NICGT8 | 53 | 2019-05-10 | 2019-05-11 | S | 1
Coolkeeragh | NIC30 | 408 | 2019-05-11 | 2019-05-13 | S | 2
Coolkeeragh | NICGT8 | 53 | 2019-05-13 | 2019-06-10 | S | 28
Moyle | MOYLE | 450 | 2019-06-11 23:00 | 2019-06-20 23:00 | S | 9
Ballylumford | NIB31 | 249 | 2019-06-28 | 2019-07-08 | 161 | 10
Ballylumford | NIB32 | 249 | 2019-06-28 | 2019-07-06 | 161 | 8
Ballylumford | NIB32 | 249 | 2019-07-06 | 2019-07-22 | S | 16
Ballylumford | NIB31 | 249 | 2019-07-08 | 2019-07-22 | S | 14
Ballylumford | NIB10 | 94 | 2019-07-08 | 2019-07-22 | S | 14
Ballylumford | NIB32 | 249 | 2019-07-22 | 2019-08-12 | 161 | 21
Ballylumford | NIB31 | 249 | 2019-07-22 | 2019-08-12 | 161 | 21
Coolkeeragh | NIC30 | 408 | 2019-08-27 | 2019-09-21 | S | 25
Ballylumford | NIB4 | 144 | 2019-09-23 | 2019-11-22 | S | 60
Coolkeeragh | NICGT8 | 53 | 2019-11-10 | 2019-11-12 | S | 2
Coolkeeragh | NIC30 | 408 | 2019-11-23 | 2019-11-25 | S | 2
|  |  | Scheduled Outage | S
|  |  | Forced Outage | F
|  |  | Unit partially available | 10

## Outage Plan All Island
2019 GENERATION OUTAGE PLAN (All Island)
|  | Month | Jan '2019 |  |  |  |  | Feb '2019 |  |  |  | Mar '2019 |  |  |  | Apr '2019 |  |  |  |  | May '2019 |  |  |  | Jun '2019 |  |  |  | Jul '2019 |  |  |  |  | Aug '2019 |  |  |  | Sep '2019 |  |  |  |  | Oct '2019 |  |  |  | Nov '2019 |  |  |  | Dec '2019
|  | Week | 1 '2019 | 2 '2019 | 3 '2019 | 4 '2019 | 5 '2019 | 6 '2019 | 7 '2019 | 8 '2019 | 9 '2019 | 10 '2019 | 11 '2019 | 12 '2019 | 13 '2019 | 14 '2019 | 15 '2019 | 16 '2019 | 17 '2019 | 18 '2019 | 19 '2019 | 20 '2019 | 21 '2019 | 22 '2019 | 23 '2019 | 24 '2019 | 25 '2019 | 26 '2019 | 27 '2019 | 28 '2019 | 29 '2019 | 30 '2019 | 31 '2019 | 32 '2019 | 33 '2019 | 34 '2019 | 35 '2019 | 36 '2019 | 37 '2019 | 38 '2019 | 39 '2019 | 40 '2019 | 41 '2019 | 42 '2019 | 43 '2019 | 44 '2019 | 45 '2019 | 46 '2019 | 47 '2019 | 48 '2019 | 49 '2019 | 50 '2019 | 51 '2019 | 52 '2019 | 1 '2020
Station | Unit | NPR
AC Automation | NIACA | 8
Activation Energy | AE1 | 77
Activation Energy | AE2 | 8
Activation Energy | AE3 | 14
Activation Energy | AE4 | 11
Activation Energy | AE5 | 15
Activation Energy | EN5 | 6
Activation Energy | EN6 | 10
Activation Energy | NIAEA | 9
Aghada | AD2 | 431 | [34 empty] | S | S | S | S | S | S | S | S
Aghada | AT1 | 90
Aghada | AT2 | 90 | [40 empty] | S | S | S
Aghada | AT4 | 90
Ardnacrusha | AA1 | 21 | [23 empty] | S
Ardnacrusha | AA2 | 22 | [34 empty] | S | S | S
Ardnacrusha | AA3 | 19 | [19 empty] | S
Ardnacrusha | AA4 | 24 | [14 empty] | S
Ballylumford | NIB10 | 94 |  |  | S | [24 empty] | S | S
Ballylumford | NIB31 | 249 | [27 empty] | S | S
Ballylumford | NIB32 | 249 | [27 empty] | S | S
Ballylumford | NIB4 | 144 | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F
Ballylumford | NIB5 | 147 | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F
Ballylumford | NIBGT1 | 58 | [6 empty] | S
Ballylumford | NIBGT2 | 58 | [5 empty] | S
Contour Global | NICG2 | 3
Contour Global | NICGA | 12
Coolkeeragh | NIC30 | 408 | [34 empty] | S | S | S | S
Coolkeeragh | NICGT8 | 53 | [19 empty] | S | S | S | S
DAE Virtual Power Plant | DP1 | 19
DAE Virtual Power Plant | DP2 | 20
Dublin Bay | DB1 | 405 | [12 empty] | S | S | S
Dublin Waste To Energy | DW1 | 62
Edenderry | ED1 | 118 | [23 empty] | S | S | S | S | S | S | S | S | S | S | [18 empty] | S | S
Edenderry | ED3 | 58
Edenderry | ED5 | 58
Electric Ireland | EI1 | 20
Electricity Exchange DSU | EE1 | 39
Electricity Exchange DSU | EE2 | 17
Electricity Exchange DSU | EE3 | 7
Electricity Exchange DSU | EE4 | 9
Electricity Exchange DSU | EE5 | 7
Empower | NIEMP | 3
Endeco Technologies | EC1 | 37
Endeco Technologies | EC2 | 10
Endeco Technologies | EC5 | 16
Endeco Technologies | NIECA | 11
Energy Trading | ET1 | 13
Energy Trading | NIETB | 9
Energy Trading | NIETD | 5
Energy Trading | NIETR | 19
Erne | ER1 | 10 | [35 empty] | S
Erne | ER2 | 10 | [33 empty] | S
Erne | ER3 | 22 | [19 empty] | S
Erne | ER4 | 22 | [23 empty] | S | S | S
EWIC | EW1 | 500 | [18 empty] | S
Great Island | GI4 | 461
Huntstown | HN2 | 400 | [16 empty] | S | S | S
Huntstown | HNC | 342
Indaver | IW1 | 17 | [13 empty] | S | S
iPower | NIAGU | 74
Kilroot | NIK1 | 256 | [14 empty] | S | S | S | S | S | S | S | S | S
Kilroot | NIK2 | 258 |  |  |  |  | S | S | S | S | S | S | S | S | S
Kilroot | NIKGT1 | 29 | [15 empty] | S | S | S | S | S | S
Kilroot | NIKGT2 | 29
Kilroot | NIKGT3 | 42 | [13 empty] | S
Kilroot | NIKGT4 | 42 | [14 empty] | S
Lanesboro | LR4 | 91 | [11 empty] | S | S | S
Lee | LE1 | 15 | [19 empty] | S
Lee | LE2 | 4 | [13 empty] | S
Lee | LE3 | 8 | [23 empty] | S
Liffey | LI1 | 15
Liffey | LI2 | 15
Liffey | LI4 | 4
Liffey | LI5 | 4
Lisahally | NILPS | 18
Moneypoint | MP1 | 285 | [19 empty] | S
Moneypoint | MP2 | 285 | F | F | F | F | F | F | F | F | F | F | F | F | F | F |  |  |  | S | S | S | S | S | S | S | S
Moneypoint | MP3 | 285 | [32 empty] | S
Moyle | MOYLE | 450 | [23 empty] | S | S
North Wall | NW5 | 104 | [39 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Poolbeg | PB4 | 154 | [30 empty] | S |  |  |  |  | S | S | S | S | S
Poolbeg | PB5 | 146 | [30 empty] | S |  |  |  |  | S
Poolbeg | PB6 | 168 | [30 empty] | S |  |  |  |  | S
Powerhouse Generation | NIPH1 | 31
Powerhouse Generation | PG1 | 11
Rhode | RP1 | 52 | [31 empty] | S
Rhode | RP2 | 52 | [31 empty] | S
Seal Rock | SK3 | 85 | [36 empty] | S
Seal Rock | SK4 | 85 | [26 empty] | S | S | S
Tarbert | TB1 | 54 | [21 empty] | S
Tarbert | TB2 | 54 | [21 empty] | S
Tarbert | TB3 | 241 | [22 empty] | S
Tarbert | TB4 | 243
Tawnaghmore | TP1 | 52
Tawnaghmore | TP3 | 52
Turlough Hill | TH1 | 73 | [9 empty] | S
Turlough Hill | TH2 | 73 | [9 empty] | S
Turlough Hill | TH3 | 73 | [24 empty] | S | S
Turlough Hill | TH4 | 73 | [24 empty] | S | S
Tynagh | TYC | 384
Viridian Energy | VE1 | 19
Viridian Energy DSU | VE2 | 6
West Offaly | WO4 | 137 | [18 empty] | S | S | S
Whitegate | WG1 | 444

## All Island Outages
Upcoming Outages including STMOs and Annual Outages
Station | Unit | NPR | Start Date | End Date | Value | Duration
Moneypoint | MP2 | 285 | 2018-09-26 23:00 | 2019-04-05 18:00 | F | 190.75
Ballylumford | NIB4 | 144 | 2018-11-14 | 2020-01-01 | F | 413
Edenderry | ED1 | 118 | 2018-12-26 12:00 | 2019-01-02 08:00 | S | 6.83
Ballylumford | NIB5 | 147 | 2019-01-01 | 2101-01-01 | F | 29950
Ballylumford | NIB32 | 249 | 2019-01-07 19:00 | 2019-01-10 19:00 | S | 3
Ballylumford | NIB32 | 249 | 2019-01-07 19:00 | 2019-01-10 19:00 | S | 3
Seal Rock | SK3 | 85 | 2019-01-13 07:00 | 2019-01-15 17:00 | S | 2.42
Ballylumford | NIB10 | 94 | 2019-01-14 19:00 | 2019-01-21 19:00 | S | 7
Ballylumford | NIB10 | 94 | 2019-01-14 19:00 | 2019-01-20 19:00 | S | 6
Coolkeeragh | NIC30 | 408 | 2019-01-26 | 2019-01-28 | S | 2
Kilroot | NIK2 | 258 | 2019-01-30 | 2019-03-30 | S | 59
Ballylumford | NIBGT2 | 58 | 2019-02-04 | 2019-02-11 | S | 7
Ballylumford | NIBGT1 | 58 | 2019-02-11 | 2019-02-18 | S | 7
EWIC | EW1 | 500 | 2019-02-16 12:00 | 2019-02-17 23:00 | S | 1.42
Seal Rock | SK4 | 85 | 2019-03-03 07:00 | 2019-03-05 17:00 | S | 2.42
Turlough Hill | TH2 | 73 | 2019-03-03 08:00 | 2019-03-09 17:00 | S | 6.33
Turlough Hill | TH1 | 73 | 2019-03-03 08:00 | 2019-03-09 17:00 | S | 6.33
Lanesboro | LR4 | 91 | 2019-03-19 16:00 | 2019-04-07 16:00 | S | 19
Dublin Bay | DB1 | 405 | 2019-03-22 13:00 | 2019-04-14 13:00 | S | 23
Aghada | AT2 | 90 | 2019-03-25 | 2019-03-28 | S | 3
Indaver | IW1 | 17 | 2019-04-01 | 2019-04-16 | S | 15
Kilroot | NIKGT3 | 42 | 2019-04-01 | 2019-04-06 | S | 5
Lee | LE2 | 4 | 2019-04-01 08:00 | 2019-04-05 20:00 | S | 4.5
Liffey | LI1 | 15 | 2019-04-02 08:00 | 2019-04-04 17:00 | S | 2.33
Liffey | LI2 | 15 | 2019-04-02 08:00 | 2019-04-04 17:00 | S | 2.33
Kilroot | NIKGT4 | 42 | 2019-04-08 | 2019-04-13 | S | 5
Ardnacrusha | AA4 | 24 | 2019-04-08 08:00 | 2019-04-12 20:00 | S | 4.5
Liffey | LI4 | 4 | 2019-04-09 08:00 | 2019-04-11 17:00 | S | 2.33
Kilroot | NIK1 | 256 | 2019-04-11 | 2019-06-08 | S | 58
Whitegate | WG1 | 444 | 2019-04-12 | 2019-04-19 | S | 7
Kilroot | NIKGT1 | 29 | 2019-04-15 | 2019-05-27 | S | 42
Edenderry | ED1 | 118 | 2019-04-18 18:00 | 2019-04-24 08:00 | S | 5.58
Huntstown | HN2 | 400 | 2019-04-23 | 2019-05-13 | S | 20
Moneypoint | MP2 | 285 | 2019-04-26 22:00 | 2019-06-23 22:00 | S | 58
EWIC | EW1 | 500 | 2019-05-06 19:00 | 2019-05-10 19:00 | S | 4
West Offaly | WO4 | 137 | 2019-05-09 16:00 | 2019-05-27 16:00 | S | 18
Coolkeeragh | NICGT8 | 53 | 2019-05-10 | 2019-05-11 | S | 1
Moneypoint | MP1 | 285 | 2019-05-10 22:00 | 2019-05-19 22:00 | S | 9
Coolkeeragh | NIC30 | 408 | 2019-05-11 | 2019-05-13 | S | 2
Coolkeeragh | NICGT8 | 53 | 2019-05-13 | 2019-06-10 | S | 28
Ardnacrusha | AA3 | 19 | 2019-05-13 08:00 | 2019-05-17 20:00 | S | 4.5
Erne | ER3 | 22.5 | 2019-05-13 08:00 | 2019-05-17 20:00 | S | 4.5
Lee | LE1 | 15 | 2019-05-13 08:00 | 2019-05-17 20:00 | S | 4.5
Seal Rock | SK3 | 85 | 2019-05-13 21:00 | 2019-05-15 12:00 | S | 1.58
Seal Rock | SK4 | 85 | 2019-05-13 23:00 | 2019-05-14 21:00 | S | 0.92
Edenderry | ED3 | 58 | 2019-05-18 08:00 | 2019-05-18 18:00 | S | 0.42
Edenderry | ED5 | 58 | 2019-05-18 08:00 | 2019-05-18 18:00 | S | 0.42
EWIC | EW1 | 500 | 2019-05-21 08:00 | 2019-05-21 20:00 | S | 0.5
Tarbert | TB2 | 54 | 2019-05-27 | 2019-06-03 | S | 7
Tarbert | TB1 | 54 | 2019-05-27 | 2019-06-03 | S | 7
EWIC | EW1 | 500 | 2019-05-28 08:00 | 2019-05-28 20:00 | S | 0.5
Tarbert | TB3 | 241 | 2019-06-03 | 2019-06-10 | S | 7
Edenderry | ED1 | 118 | 2019-06-07 12:00 | 2019-08-20 08:00 | S | 73.83
Erne | ER4 | 22.5 | 2019-06-10 08:00 | 2019-06-30 20:00 | S | 20.5
Ardnacrusha | AA1 | 21 | 2019-06-10 08:00 | 2019-06-14 20:00 | S | 4.5
Lee | LE3 | 8 | 2019-06-10 08:00 | 2019-06-14 20:00 | S | 4.5
Moyle | MOYLE | 450 | 2019-06-11 23:00 | 2019-06-20 23:00 | S | 9
Turlough Hill | TH4 | 73 | 2019-06-15 08:00 | 2019-06-29 17:00 | S | 14.33
Turlough Hill | TH3 | 73 | 2019-06-15 08:00 | 2019-06-29 17:00 | S | 14.33
Aghada | AT4 | 90 | 2019-06-18 | 2019-06-21 | S | 3
Ballylumford | NIB31 | 249 | 2019-06-28 | 2019-07-08 | 161 | 10
Ballylumford | NIB32 | 249 | 2019-06-28 | 2019-07-06 | 161 | 8
Seal Rock | SK4 | 85 | 2019-06-30 07:00 | 2019-07-18 07:00 | S | 18
Ballylumford | NIB32 | 249 | 2019-07-06 | 2019-07-22 | S | 16
Ballylumford | NIB31 | 249 | 2019-07-08 | 2019-07-22 | S | 14
Ballylumford | NIB10 | 94 | 2019-07-08 | 2019-07-22 | S | 14
Ballylumford | NIB32 | 249 | 2019-07-22 | 2019-08-12 | 161 | 21
Ballylumford | NIB31 | 249 | 2019-07-22 | 2019-08-12 | 161 | 21
Poolbeg | PB5 | 146 | 2019-07-29 | 2019-08-03 | S | 5
Poolbeg | PB4 | 154 | 2019-07-29 | 2019-08-03 | S | 5
Poolbeg | PB6 | 168 | 2019-07-29 | 2019-08-03 | S | 5
Rhode | RP1 | 52 | 2019-08-05 | 2019-08-12 | S | 7
Rhode | RP2 | 52 | 2019-08-05 | 2019-08-12 | S | 7
Moneypoint | MP3 | 285 | 2019-08-09 22:00 | 2019-08-18 22:00 | S | 9
Aghada | AT1 | 90 | 2019-08-19 | 2019-08-22 | S | 3
Erne | ER2 | 10 | 2019-08-19 08:00 | 2019-08-23 20:00 | S | 4.5
EWIC | EW1 | 500 | 2019-08-19 19:00 | 2019-08-20 16:00 | S | 0.83
Aghada | AD2 | 431 | 2019-08-23 20:00 | 2019-10-18 08:00 | S | 55.5
Ardnacrusha | AA2 | 22 | 2019-08-26 08:00 | 2019-09-17 20:00 | S | 22.5
Coolkeeragh | NIC30 | 408 | 2019-08-27 | 2019-09-21 | S | 25
Poolbeg | PB5 | 146 | 2019-09-02 | 2019-09-06 20:00 | S | 4.83
Poolbeg | PB4 | 154 | 2019-09-02 | 2019-10-07 | S | 35
Poolbeg | PB6 | 168 | 2019-09-02 | 2019-09-06 20:00 | S | 4.83
Erne | ER1 | 10 | 2019-09-02 08:00 | 2019-09-06 20:00 | S | 4.5
Poolbeg | PB6 | 168 | 2019-09-06 20:00 | 2019-10-07 | 84 | 30.17
Seal Rock | SK3 | 85 | 2019-09-09 07:00 | 2019-09-13 17:00 | S | 4.42
Liffey | LI5 | 4 | 2019-09-10 08:00 | 2019-09-12 17:00 | S | 2.33
Tynagh | TYC | 384 | 2019-09-20 22:00 | 2019-09-24 22:00 | S | 4
Ballylumford | NIB4 | 144 | 2019-09-23 | 2019-11-22 | S | 60
North Wall | NW5 | 104 | 2019-10-01 | 2022-10-01 | S | 1096
Aghada | AT2 | 90 | 2019-10-07 06:00 | 2019-10-26 20:00 | S | 19.58
EWIC | EW1 | 500 | 2019-10-31 20:00 | 2019-11-01 17:00 | S | 0.83
Coolkeeragh | NICGT8 | 53 | 2019-11-10 | 2019-11-12 | S | 2
Seal Rock | SK4 | 85 | 2019-11-17 07:00 | 2019-11-19 17:00 | S | 2.42
Coolkeeragh | NIC30 | 408 | 2019-11-23 | 2019-11-25 | S | 2
Turlough Hill | TH1 | 73 | 2019-11-26 08:00 | 2019-11-28 17:00 | S | 2.33
Turlough Hill | TH2 | 73 | 2019-11-26 08:00 | 2019-11-28 17:00 | S | 2.33
Edenderry | ED1 | 118 | 2019-12-26 13:00 | 2020-01-02 08:00 | S | 6.75
|  |  | Scheduled Outage | S
|  |  | Forced Outage | F
|  |  | Unit partially available | 10