## Outage Plan EirGrid
2020 GENERATION OUTAGE PLAN (EIRGRID)
|  | Month | Jan '2020 |  |  |  |  | Feb '2020 |  |  |  | Mar '2020 |  |  |  |  | Apr '2020 |  |  |  | May '2020 |  |  |  | Jun '2020 |  |  |  |  | Jul '2020 |  |  |  | Aug '2020 |  |  |  |  | Sep '2020 |  |  |  | Oct '2020 |  |  |  | Nov '2020 |  |  |  |  | Dec '2020
|  | Week | 1 '2020 | 2 '2020 | 3 '2020 | 4 '2020 | 5 '2020 | 6 '2020 | 7 '2020 | 8 '2020 | 9 '2020 | 10 '2020 | 11 '2020 | 12 '2020 | 13 '2020 | 14 '2020 | 15 '2020 | 16 '2020 | 17 '2020 | 18 '2020 | 19 '2020 | 20 '2020 | 21 '2020 | 22 '2020 | 23 '2020 | 24 '2020 | 25 '2020 | 26 '2020 | 27 '2020 | 28 '2020 | 29 '2020 | 30 '2020 | 31 '2020 | 32 '2020 | 33 '2020 | 34 '2020 | 35 '2020 | 36 '2020 | 37 '2020 | 38 '2020 | 39 '2020 | 40 '2020 | 41 '2020 | 42 '2020 | 43 '2020 | 44 '2020 | 45 '2020 | 46 '2020 | 47 '2020 | 48 '2020 | 49 '2020 | 50 '2020 | 51 '2020 | 52 '2020 | 53 '2020
Station | Unit | NPR
Activation Energy | AE1 | 95
Activation Energy | AE2 | 8
Activation Energy | AE3 | 14
Activation Energy | AE4 | 15
Activation Energy | AE5 | 15
Activation Energy | EN5 | 6
Activation Energy | EN6 | 11
Aghada | AD2 | 431 | [29 empty] | S
Aghada | AT1 | 90 | [16 empty] | S
Aghada | AT2 | 90 | [17 empty] | S | S | S | S | S | S | S
Aghada | AT4 | 90
Ardnacrusha | AA1 | 21 | [34 empty] | S | S | S | S
Ardnacrusha | AA2 | 22 | [32 empty] | S
Ardnacrusha | AA3 | 19 | [16 empty] | S
Ardnacrusha | AA4 | 24 | [18 empty] | S | S | S | S | S | S | S
DAE Virtual Power Plant | DP1 | 19
DAE Virtual Power Plant | DP2 | 26
Dublin Bay | DB1 | 405 | [37 empty] | S | S | S | S | S | S | S | S | S
Dublin Waste To Energy | DW1 | 62
Edenderry | ED1 | 118 | S | [23 empty] | S | S | S | S | S | S | [22 empty] | S
Edenderry | ED3 | 58
Edenderry | ED5 | 58
Electric Ireland | EI1 | 20
Electricity Exchange DSU | EE1 | 51
Electricity Exchange DSU | EE2 | 28
Electricity Exchange DSU | EE3 | 8
Electricity Exchange DSU | EE4 | 9
Electricity Exchange DSU | EE5 | 6
Endeco Technologies | EC1 | 42
Endeco Technologies | EC2 | 11
Endeco Technologies | EC5 | 15
Energy Trading | ET1 | 13
Erne | ER1 | 10 | [23 empty] | S | S
Erne | ER2 | 10 | [34 empty] | S
Erne | ER3 | 22 | [19 empty] | S
Erne | ER4 | 22 | [16 empty] | S
EWIC | EW1 | 500 | [15 empty] | S | S | S | S | S | S | S
Great Island | GI4 | 461 | [40 empty] | S | S | S
Huntstown | HN2 | 400
Huntstown | HNC | 342 | [32 empty] | F | F | S | S | S | F
Indaver | IW1 | 17 | [19 empty] | S | S | S | S | S | S | S
Knockacummer | KC1 | 100
Lanesboro | LR4 | 91 | [31 empty] | S | S
Lee | LE1 | 15 | [18 empty] | S
Lee | LE2 | 4 | [16 empty] | S
Lee | LE3 | 8 | [23 empty] | S | S | S
Liffey | LI1 | 15 | [34 empty] | S
Liffey | LI2 | 15 | [34 empty] | S
Liffey | LI4 | 4
Liffey | LI5 | 4
Moneypoint | MP1 | 285 | [18 empty] | S
Moneypoint | MP2 | 285 | [19 empty] | S
Moneypoint | MP3 | 285 | [32 empty] | S
North Wall | NW5 | 104 | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Poolbeg | PB4 | 154 | [24 empty] | S | S | S | S | S | S | S | S
Poolbeg | PB5 | 146
Poolbeg | PB6 | 168 | [25 empty] | S | S | S | S
Powerhouse Generation | PG1 | 11
Rhode | RP1 | 52
Rhode | RP2 | 52
Seal Rock | SK3 | 85 | [36 empty] | S | S | S
Seal Rock | SK4 | 85
Seecon | SO1 | 105
Tarbert | TB1 | 54
Tarbert | TB2 | 54
Tarbert | TB3 | 241
Tarbert | TB4 | 243 | [24 empty] | S
Tawnaghmore | TP1 | 52 | [32 empty] | S
Tawnaghmore | TP3 | 52 | [32 empty] | S
Turlough Hill | TH1 | 73 | [24 empty] | S
Turlough Hill | TH2 | 73 | [24 empty] | S
Turlough Hill | TH3 | 73 | [26 empty] | S
Turlough Hill | TH4 | 73 | [26 empty] | S
Tynagh | TYC | 384 | [12 empty] | S | S | S
Viridian Energy | VE1 | 20
Viridian Energy DSU | VE2 | 13
West Offaly | WO4 | 137 | [19 empty] | S | S | S
Whitegate | WG1 | 444

## EirGrid Outages
Upcoming Outages including STMOs and Annual Outages
Station | Unit | NPR | Start Date | End Date | Value | Duration
North Wall | NW5 | 104 | 2019-10-01 | 2022-10-01 | S | 1096
Edenderry | ED1 | 118 | 2019-12-26 13:00 | 2020-01-02 08:00 | S | 6.75
Seal Rock | SK3 | 85 | 2020-01-06 06:00 | 2020-01-09 18:00 | S | 3.5
EWIC | EW1 | 500 | 2020-02-05 09:00 | 2020-02-06 23:00 | S | 1.58
Seal Rock | SK4 | 85 | 2020-03-08 07:00 | 2020-03-10 17:00 | S | 2.42
Tynagh | TYC | 384 | 2020-03-22 20:00 | 2020-04-12 20:00 | S | 21
Edenderry | ED1 | 118 | 2020-04-09 18:00 | 2020-04-15 08:00 | S | 5.58
EWIC | EW1 | 500 | 2020-04-14 12:00 | 2020-06-03 23:00 | S | 50.42
Aghada | AT1 | 90 | 2020-04-20 | 2020-04-27 | S | 7
Lee | LE2 | 4 | 2020-04-20 08:00 | 2020-04-24 20:00 | S | 4.5
Ardnacrusha | AA3 | 19 | 2020-04-20 08:00 | 2020-04-24 20:00 | S | 4.5
Erne | ER4 | 22.5 | 2020-04-20 08:00 | 2020-04-24 20:00 | S | 4.5
Aghada | AT2 | 90 | 2020-04-27 | 2020-06-14 | S | 48
Liffey | LI5 | 4 | 2020-04-27 08:00 | 2020-04-29 17:00 | S | 2.33
Moneypoint | MP1 | 285 | 2020-05-01 22:00 | 2020-05-13 22:00 | S | 12
Lee | LE1 | 15 | 2020-05-05 08:00 | 2020-05-09 20:00 | S | 4.5
Ardnacrusha | AA4 | 24 | 2020-05-05 08:00 | 2020-06-19 20:00 | S | 45.5
Moneypoint | MP2 | 285 | 2020-05-08 22:00 | 2020-05-17 22:00 | S | 9
Indaver | IW1 | 17 | 2020-05-11 | 2020-07-01 | S | 51
Erne | ER3 | 22.5 | 2020-05-11 08:00 | 2020-05-15 20:00 | S | 4.5
Seal Rock | SK3 | 85 | 2020-05-11 21:00 | 2020-05-13 12:00 | S | 1.58
Seal Rock | SK4 | 85 | 2020-05-11 23:00 | 2020-05-12 21:00 | S | 0.92
West Offaly | WO4 | 137 | 2020-05-14 16:00 | 2020-06-01 16:00 | S | 18
Edenderry | ED3 | 58 | 2020-05-16 08:00 | 2020-05-16 18:00 | S | 0.42
Edenderry | ED5 | 58 | 2020-05-16 08:00 | 2020-05-16 18:00 | S | 0.42
Erne | ER1 | 10 | 2020-06-08 08:00 | 2020-06-21 20:00 | S | 13.5
Lee | LE3 | 8 | 2020-06-08 08:00 | 2020-06-28 20:00 | S | 20.5
Edenderry | ED1 | 118 | 2020-06-12 12:00 | 2020-07-28 08:00 | S | 45.83
Tarbert | TB4 | 243 | 2020-06-14 | 2020-06-21 | S | 7
Turlough Hill | TH1 | 73 | 2020-06-14 08:00 | 2020-06-20 17:00 | S | 6.33
Turlough Hill | TH2 | 73 | 2020-06-14 08:00 | 2020-06-20 17:00 | S | 6.33
Poolbeg | PB6 | 168 | 2020-06-16 | 2020-06-21 | 84 | 5
Poolbeg | PB4 | 154 | 2020-06-16 | 2020-08-10 | S | 55
Poolbeg | PB6 | 168 | 2020-06-21 | 2020-07-19 | S | 28
Turlough Hill | TH4 | 73 | 2020-06-28 08:00 | 2020-07-04 17:00 | S | 6.33
Turlough Hill | TH3 | 73 | 2020-06-28 08:00 | 2020-07-04 17:00 | S | 6.33
Seal Rock | SK4 | 85 | 2020-07-13 07:00 | 2020-07-16 07:00 | S | 3
Poolbeg | PB6 | 168 | 2020-07-19 | 2020-08-10 | 84 | 22
Huntstown | HNC | 342 | 2020-07-20 09:00 | 2020-08-11 | 210 | 21.58
Aghada | AD2 | 431 | 2020-07-20 20:00 | 2020-07-25 20:00 | S | 5
Lanesboro | LR4 | 91 | 2020-08-05 16:00 | 2020-08-15 16:00 | S | 10
Whitegate | WG1 | 444 | 2020-08-07 21:00 | 2020-08-14 21:00 | S | 7
Moneypoint | MP3 | 285 | 2020-08-07 22:00 | 2020-08-19 22:00 | S | 12
Tawnaghmore | TP3 | 52 | 2020-08-10 | 2020-08-17 17:00 | S | 7.67
Ardnacrusha | AA2 | 22 | 2020-08-10 08:00 | 2020-08-14 20:00 | S | 4.5
Tawnaghmore | TP1 | 52 | 2020-08-10 08:00 | 2020-08-17 17:00 | S | 7.33
Huntstown | HNC | 342 | 2020-08-11 | 2020-08-21 | F | 10
EWIC | EW1 | 500 | 2020-08-19 10:00 | 2020-08-20 23:00 | S | 1.5
Huntstown | HNC | 342 | 2020-08-21 | 2020-09-11 | S | 21
Erne | ER2 | 10 | 2020-08-24 08:00 | 2020-08-28 20:00 | S | 4.5
Liffey | LI2 | 15 | 2020-08-24 08:00 | 2020-08-29 17:00 | S | 5.33
Liffey | LI1 | 15 | 2020-08-24 08:00 | 2020-08-29 17:00 | S | 5.33
Ardnacrusha | AA1 | 21 | 2020-08-24 08:00 | 2020-09-18 20:00 | S | 25.5
Seal Rock | SK3 | 85 | 2020-09-06 07:00 | 2020-09-24 07:00 | S | 18
Aghada | AT4 | 90 | 2020-09-07 | 2020-09-10 | S | 3
Liffey | LI4 | 4 | 2020-09-07 08:00 | 2020-09-09 17:00 | S | 2.33
Huntstown | HNC | 342 | 2020-09-11 | 2020-09-22 | F | 11
Dublin Bay | DB1 | 405 | 2020-09-11 13:00 | 2020-11-16 06:00 | S | 65.67
Great Island | GI4 | 461 | 2020-10-03 | 2020-10-24 | S | 21
Seal Rock | SK4 | 85 | 2020-11-08 07:00 | 2020-11-10 17:00 | S | 2.42
Turlough Hill | TH1 | 73 | 2020-11-17 08:00 | 2020-11-19 17:00 | S | 2.33
Turlough Hill | TH2 | 73 | 2020-11-17 08:00 | 2020-11-19 17:00 | S | 2.33
Edenderry | ED1 | 118 | 2020-12-26 13:00 | 2021-01-02 08:00 | S | 6.75
|  |  | Scheduled Outage | S
|  |  | Forced Outage | F
|  |  | Unit partially available | 10

## Outage Plan SONI
2020 GENERATION OUTAGE PLAN (SONI)
|  | Month | Jan '2020 |  |  |  |  | Feb '2020 |  |  |  | Mar '2020 |  |  |  |  | Apr '2020 |  |  |  | May '2020 |  |  |  | Jun '2020 |  |  |  |  | Jul '2020 |  |  |  | Aug '2020 |  |  |  |  | Sep '2020 |  |  |  | Oct '2020 |  |  |  | Nov '2020 |  |  |  |  | Dec '2020
|  | Week | 1 '2020 | 2 '2020 | 3 '2020 | 4 '2020 | 5 '2020 | 6 '2020 | 7 '2020 | 8 '2020 | 9 '2020 | 10 '2020 | 11 '2020 | 12 '2020 | 13 '2020 | 14 '2020 | 15 '2020 | 16 '2020 | 17 '2020 | 18 '2020 | 19 '2020 | 20 '2020 | 21 '2020 | 22 '2020 | 23 '2020 | 24 '2020 | 25 '2020 | 26 '2020 | 27 '2020 | 28 '2020 | 29 '2020 | 30 '2020 | 31 '2020 | 32 '2020 | 33 '2020 | 34 '2020 | 35 '2020 | 36 '2020 | 37 '2020 | 38 '2020 | 39 '2020 | 40 '2020 | 41 '2020 | 42 '2020 | 43 '2020 | 44 '2020 | 45 '2020 | 46 '2020 | 47 '2020 | 48 '2020 | 49 '2020 | 50 '2020 | 51 '2020 | 52 '2020 | 53 '2020
Station | Unit | NPR
AC Automation | NIACA | 8
Activation Energy | NIAEA | 9
Ballylumford | NIB10 | 94 |  |  | S | S | S | S | S | S | S | S | S
Ballylumford | NIB31 | 249 | [38 empty] | S | S | S | S | S | S | S | S | S
Ballylumford | NIB32 | 249
Ballylumford | NIBGT1 | 58
Ballylumford | NIBGT2 | 58
Contour Global | NICG2 | 3
Contour Global | NICGA | 12
Coolkeeragh | NIC30 | 408 | [35 empty] | S | S
Coolkeeragh | NICGT8 | 53 | [18 empty] | S
Empower | NIEMP | 3
Endeco Technologies | NIECA | 13
Energy Trading | NIETB | 9
Energy Trading | NIETD | 5
Energy Trading | NIETR | 19
iPower | NIAGU | 74
Kilroot | NIK1 | 256 | [29 empty] | S | S | S | S
Kilroot | NIK2 | 258 | [20 empty] | S | S | S | S | [5 empty] | S
Kilroot | NIKGT1 | 29 | [29 empty] | S | S | S | S
Kilroot | NIKGT2 | 29 | [20 empty] | S | S | S | S | [5 empty] | S
Kilroot | NIKGT3 | 42 | [46 empty] | S
Kilroot | NIKGT4 | 42 | [47 empty] | S
Lisahally | NILPS | 18
Moyle | MOYLE | 450 | [26 empty] | S
Powerhouse Generation | NIPH1 | 34

## SONI Outages
Upcoming Outages including STMOs and Annual Outages
Station | Unit | NPR | Start Date | End Date | Value | Duration
Kilroot | NIKGT1 | 29 | 2020-01-07 08:00 | 2020-01-09 20:00 | S | 2.5
Ballylumford | NIB10 | 94 | 2020-01-15 | 2020-03-16 | S | 61
Coolkeeragh | NIC30 | 408 | 2020-03-21 | 2020-03-23 | S | 2
Ballylumford | NIBGT2 | 58 | 2020-03-28 | 2020-04-04 | S | 7
Ballylumford | NIBGT1 | 58 | 2020-04-04 | 2020-04-10 23:30 | S | 6.96
Coolkeeragh | NICGT8 | 53 | 2020-05-04 | 2020-05-11 | S | 7
Kilroot | NIKGT2 | 29 | 2020-05-18 | 2020-06-15 | S | 28
Kilroot | NIK2 | 258 | 2020-05-18 | 2020-06-15 | S | 28
Moyle | MOYLE | 450 | 2020-06-29 07:30 | 2020-07-07 16:00 | S | 8.33
Coolkeeragh | NIC30 | 408 | 2020-07-11 | 2020-07-13 | S | 2
Kilroot | NIKGT2 | 29 | 2020-07-20 | 2020-07-30 | S | 10
Kilroot | NIK2 | 258 | 2020-07-20 | 2020-07-30 | S | 10
Kilroot | NIKGT1 | 29 | 2020-07-20 | 2020-08-17 | S | 28
Kilroot | NIK1 | 256 | 2020-07-20 | 2020-08-16 | S | 27
Coolkeeragh | NIC30 | 408 | 2020-08-29 | 2020-09-14 | S | 16
Ballylumford | NIB31 | 249 | 2020-09-21 | 2020-11-20 | S | 60
Ballylumford | NIB32 | 249 | 2020-09-21 | 2020-10-05 | 161 | 14
Coolkeeragh | NICGT8 | 53 | 2020-10-24 | 2020-10-26 | S | 2
Kilroot | NIKGT3 | 42 | 2020-11-16 | 2020-11-21 | S | 5
Kilroot | NIKGT4 | 42 | 2020-11-23 | 2020-11-28 | S | 5
Coolkeeragh | NIC30 | 408 | 2020-11-28 | 2020-11-30 | S | 2
|  |  | Scheduled Outage | S
|  |  | Forced Outage | F
|  |  | Unit partially available | 10

## Outage Plan All Island
2020 GENERATION OUTAGE PLAN (All Island)
|  | Month | Jan '2020 |  |  |  |  | Feb '2020 |  |  |  | Mar '2020 |  |  |  |  | Apr '2020 |  |  |  | May '2020 |  |  |  | Jun '2020 |  |  |  |  | Jul '2020 |  |  |  | Aug '2020 |  |  |  |  | Sep '2020 |  |  |  | Oct '2020 |  |  |  | Nov '2020 |  |  |  |  | Dec '2020
|  | Week | 1 '2020 | 2 '2020 | 3 '2020 | 4 '2020 | 5 '2020 | 6 '2020 | 7 '2020 | 8 '2020 | 9 '2020 | 10 '2020 | 11 '2020 | 12 '2020 | 13 '2020 | 14 '2020 | 15 '2020 | 16 '2020 | 17 '2020 | 18 '2020 | 19 '2020 | 20 '2020 | 21 '2020 | 22 '2020 | 23 '2020 | 24 '2020 | 25 '2020 | 26 '2020 | 27 '2020 | 28 '2020 | 29 '2020 | 30 '2020 | 31 '2020 | 32 '2020 | 33 '2020 | 34 '2020 | 35 '2020 | 36 '2020 | 37 '2020 | 38 '2020 | 39 '2020 | 40 '2020 | 41 '2020 | 42 '2020 | 43 '2020 | 44 '2020 | 45 '2020 | 46 '2020 | 47 '2020 | 48 '2020 | 49 '2020 | 50 '2020 | 51 '2020 | 52 '2020 | 53 '2020
Station | Unit | NPR
AC Automation | NIACA | 8
Activation Energy | AE1 | 95
Activation Energy | AE2 | 8
Activation Energy | AE3 | 14
Activation Energy | AE4 | 15
Activation Energy | AE5 | 15
Activation Energy | EN5 | 6
Activation Energy | EN6 | 11
Activation Energy | NIAEA | 9
Aghada | AD2 | 431 | [29 empty] | S
Aghada | AT1 | 90 | [16 empty] | S
Aghada | AT2 | 90 | [17 empty] | S | S | S | S | S | S | S
Aghada | AT4 | 90
Ardnacrusha | AA1 | 21 | [34 empty] | S | S | S | S
Ardnacrusha | AA2 | 22 | [32 empty] | S
Ardnacrusha | AA3 | 19 | [16 empty] | S
Ardnacrusha | AA4 | 24 | [18 empty] | S | S | S | S | S | S | S
Ballylumford | NIB10 | 94 |  |  | S | S | S | S | S | S | S | S | S
Ballylumford | NIB31 | 249 | [38 empty] | S | S | S | S | S | S | S | S | S
Ballylumford | NIB32 | 249
Ballylumford | NIBGT1 | 58
Ballylumford | NIBGT2 | 58
Contour Global | NICG2 | 3
Contour Global | NICGA | 12
Coolkeeragh | NIC30 | 408 | [35 empty] | S | S
Coolkeeragh | NICGT8 | 53 | [18 empty] | S
DAE Virtual Power Plant | DP1 | 19
DAE Virtual Power Plant | DP2 | 26
Dublin Bay | DB1 | 405 | [37 empty] | S | S | S | S | S | S | S | S | S
Dublin Waste To Energy | DW1 | 62
Edenderry | ED1 | 118 | S | [23 empty] | S | S | S | S | S | S | [22 empty] | S
Edenderry | ED3 | 58
Edenderry | ED5 | 58
Electric Ireland | EI1 | 20
Electricity Exchange DSU | EE1 | 51
Electricity Exchange DSU | EE2 | 28
Electricity Exchange DSU | EE3 | 8
Electricity Exchange DSU | EE4 | 9
Electricity Exchange DSU | EE5 | 6
Empower | NIEMP | 3
Endeco Technologies | EC1 | 42
Endeco Technologies | EC2 | 11
Endeco Technologies | EC5 | 15
Endeco Technologies | NIECA | 13
Energy Trading | ET1 | 13
Energy Trading | NIETB | 9
Energy Trading | NIETD | 5
Energy Trading | NIETR | 19
Erne | ER1 | 10 | [23 empty] | S | S
Erne | ER2 | 10 | [34 empty] | S
Erne | ER3 | 22 | [19 empty] | S
Erne | ER4 | 22 | [16 empty] | S
EWIC | EW1 | 500 | [15 empty] | S | S | S | S | S | S | S
Great Island | GI4 | 461 | [40 empty] | S | S | S
Huntstown | HN2 | 400
Huntstown | HNC | 342 | [32 empty] | F | F | S | S | S | F
Indaver | IW1 | 17 | [19 empty] | S | S | S | S | S | S | S
iPower | NIAGU | 74
Kilroot | NIK1 | 256 | [29 empty] | S | S | S | S
Kilroot | NIK2 | 258 | [20 empty] | S | S | S | S | [5 empty] | S
Kilroot | NIKGT1 | 29 | [29 empty] | S | S | S | S
Kilroot | NIKGT2 | 29 | [20 empty] | S | S | S | S | [5 empty] | S
Kilroot | NIKGT3 | 42 | [46 empty] | S
Kilroot | NIKGT4 | 42 | [47 empty] | S
Knockacummer | KC1 | 100
Lanesboro | LR4 | 91 | [31 empty] | S | S
Lee | LE1 | 15 | [18 empty] | S
Lee | LE2 | 4 | [16 empty] | S
Lee | LE3 | 8 | [23 empty] | S | S | S
Liffey | LI1 | 15 | [34 empty] | S
Liffey | LI2 | 15 | [34 empty] | S
Liffey | LI4 | 4
Liffey | LI5 | 4
Lisahally | NILPS | 18
Moneypoint | MP1 | 285 | [18 empty] | S
Moneypoint | MP2 | 285 | [19 empty] | S
Moneypoint | MP3 | 285 | [32 empty] | S
Moyle | MOYLE | 450 | [26 empty] | S
North Wall | NW5 | 104 | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Poolbeg | PB4 | 154 | [24 empty] | S | S | S | S | S | S | S | S
Poolbeg | PB5 | 146
Poolbeg | PB6 | 168 | [25 empty] | S | S | S | S
Powerhouse Generation | NIPH1 | 34
Powerhouse Generation | PG1 | 11
Rhode | RP1 | 52
Rhode | RP2 | 52
Seal Rock | SK3 | 85 | [36 empty] | S | S | S
Seal Rock | SK4 | 85
Seecon | SO1 | 105
Tarbert | TB1 | 54
Tarbert | TB2 | 54
Tarbert | TB3 | 241
Tarbert | TB4 | 243 | [24 empty] | S
Tawnaghmore | TP1 | 52 | [32 empty] | S
Tawnaghmore | TP3 | 52 | [32 empty] | S
Turlough Hill | TH1 | 73 | [24 empty] | S
Turlough Hill | TH2 | 73 | [24 empty] | S
Turlough Hill | TH3 | 73 | [26 empty] | S
Turlough Hill | TH4 | 73 | [26 empty] | S
Tynagh | TYC | 384 | [12 empty] | S | S | S
Viridian Energy | VE1 | 20
Viridian Energy DSU | VE2 | 13
West Offaly | WO4 | 137 | [19 empty] | S | S | S
Whitegate | WG1 | 444

## All Island Outages
Upcoming Outages including STMOs and Annual Outages
Station | Unit | NPR | Start Date | End Date | Value | Duration
North Wall | NW5 | 104 | 2019-10-01 | 2022-10-01 | S | 1096
Edenderry | ED1 | 118 | 2019-12-26 13:00 | 2020-01-02 08:00 | S | 6.75
Seal Rock | SK3 | 85 | 2020-01-06 06:00 | 2020-01-09 18:00 | S | 3.5
Kilroot | NIKGT1 | 29 | 2020-01-07 08:00 | 2020-01-09 20:00 | S | 2.5
Ballylumford | NIB10 | 94 | 2020-01-15 | 2020-03-16 | S | 61
EWIC | EW1 | 500 | 2020-02-05 09:00 | 2020-02-06 23:00 | S | 1.58
Seal Rock | SK4 | 85 | 2020-03-08 07:00 | 2020-03-10 17:00 | S | 2.42
Coolkeeragh | NIC30 | 408 | 2020-03-21 | 2020-03-23 | S | 2
Tynagh | TYC | 384 | 2020-03-22 20:00 | 2020-04-12 20:00 | S | 21
Ballylumford | NIBGT2 | 58 | 2020-03-28 | 2020-04-04 | S | 7
Ballylumford | NIBGT1 | 58 | 2020-04-04 | 2020-04-10 23:30 | S | 6.96
Edenderry | ED1 | 118 | 2020-04-09 18:00 | 2020-04-15 08:00 | S | 5.58
EWIC | EW1 | 500 | 2020-04-14 12:00 | 2020-06-03 23:00 | S | 50.42
Aghada | AT1 | 90 | 2020-04-20 | 2020-04-27 | S | 7
Lee | LE2 | 4 | 2020-04-20 08:00 | 2020-04-24 20:00 | S | 4.5
Ardnacrusha | AA3 | 19 | 2020-04-20 08:00 | 2020-04-24 20:00 | S | 4.5
Erne | ER4 | 22.5 | 2020-04-20 08:00 | 2020-04-24 20:00 | S | 4.5
Aghada | AT2 | 90 | 2020-04-27 | 2020-06-14 | S | 48
Liffey | LI5 | 4 | 2020-04-27 08:00 | 2020-04-29 17:00 | S | 2.33
Moneypoint | MP1 | 285 | 2020-05-01 22:00 | 2020-05-13 22:00 | S | 12
Coolkeeragh | NICGT8 | 53 | 2020-05-04 | 2020-05-11 | S | 7
Lee | LE1 | 15 | 2020-05-05 08:00 | 2020-05-09 20:00 | S | 4.5
Ardnacrusha | AA4 | 24 | 2020-05-05 08:00 | 2020-06-19 20:00 | S | 45.5
Moneypoint | MP2 | 285 | 2020-05-08 22:00 | 2020-05-17 22:00 | S | 9
Indaver | IW1 | 17 | 2020-05-11 | 2020-07-01 | S | 51
Erne | ER3 | 22.5 | 2020-05-11 08:00 | 2020-05-15 20:00 | S | 4.5
Seal Rock | SK3 | 85 | 2020-05-11 21:00 | 2020-05-13 12:00 | S | 1.58
Seal Rock | SK4 | 85 | 2020-05-11 23:00 | 2020-05-12 21:00 | S | 0.92
West Offaly | WO4 | 137 | 2020-05-14 16:00 | 2020-06-01 16:00 | S | 18
Edenderry | ED3 | 58 | 2020-05-16 08:00 | 2020-05-16 18:00 | S | 0.42
Edenderry | ED5 | 58 | 2020-05-16 08:00 | 2020-05-16 18:00 | S | 0.42
Kilroot | NIKGT2 | 29 | 2020-05-18 | 2020-06-15 | S | 28
Kilroot | NIK2 | 258 | 2020-05-18 | 2020-06-15 | S | 28
Erne | ER1 | 10 | 2020-06-08 08:00 | 2020-06-21 20:00 | S | 13.5
Lee | LE3 | 8 | 2020-06-08 08:00 | 2020-06-28 20:00 | S | 20.5
Edenderry | ED1 | 118 | 2020-06-12 12:00 | 2020-07-28 08:00 | S | 45.83
Tarbert | TB4 | 243 | 2020-06-14 | 2020-06-21 | S | 7
Turlough Hill | TH1 | 73 | 2020-06-14 08:00 | 2020-06-20 17:00 | S | 6.33
Turlough Hill | TH2 | 73 | 2020-06-14 08:00 | 2020-06-20 17:00 | S | 6.33
Poolbeg | PB6 | 168 | 2020-06-16 | 2020-06-21 | 84 | 5
Poolbeg | PB4 | 154 | 2020-06-16 | 2020-08-10 | S | 55
Poolbeg | PB6 | 168 | 2020-06-21 | 2020-07-19 | S | 28
Turlough Hill | TH4 | 73 | 2020-06-28 08:00 | 2020-07-04 17:00 | S | 6.33
Turlough Hill | TH3 | 73 | 2020-06-28 08:00 | 2020-07-04 17:00 | S | 6.33
Moyle | MOYLE | 450 | 2020-06-29 07:30 | 2020-07-07 16:00 | S | 8.33
Coolkeeragh | NIC30 | 408 | 2020-07-11 | 2020-07-13 | S | 2
Seal Rock | SK4 | 85 | 2020-07-13 07:00 | 2020-07-16 07:00 | S | 3
Poolbeg | PB6 | 168 | 2020-07-19 | 2020-08-10 | 84 | 22
Kilroot | NIKGT2 | 29 | 2020-07-20 | 2020-07-30 | S | 10
Kilroot | NIK2 | 258 | 2020-07-20 | 2020-07-30 | S | 10
Kilroot | NIKGT1 | 29 | 2020-07-20 | 2020-08-17 | S | 28
Kilroot | NIK1 | 256 | 2020-07-20 | 2020-08-16 | S | 27
Huntstown | HNC | 342 | 2020-07-20 09:00 | 2020-08-11 | 210 | 21.58
Aghada | AD2 | 431 | 2020-07-20 20:00 | 2020-07-25 20:00 | S | 5
Lanesboro | LR4 | 91 | 2020-08-05 16:00 | 2020-08-15 16:00 | S | 10
Whitegate | WG1 | 444 | 2020-08-07 21:00 | 2020-08-14 21:00 | S | 7
Moneypoint | MP3 | 285 | 2020-08-07 22:00 | 2020-08-19 22:00 | S | 12
Tawnaghmore | TP3 | 52 | 2020-08-10 | 2020-08-17 17:00 | S | 7.67
Ardnacrusha | AA2 | 22 | 2020-08-10 08:00 | 2020-08-14 20:00 | S | 4.5
Tawnaghmore | TP1 | 52 | 2020-08-10 08:00 | 2020-08-17 17:00 | S | 7.33
Huntstown | HNC | 342 | 2020-08-11 | 2020-08-21 | F | 10
EWIC | EW1 | 500 | 2020-08-19 10:00 | 2020-08-20 23:00 | S | 1.5
Huntstown | HNC | 342 | 2020-08-21 | 2020-09-11 | S | 21
Erne | ER2 | 10 | 2020-08-24 08:00 | 2020-08-28 20:00 | S | 4.5
Liffey | LI2 | 15 | 2020-08-24 08:00 | 2020-08-29 17:00 | S | 5.33
Liffey | LI1 | 15 | 2020-08-24 08:00 | 2020-08-29 17:00 | S | 5.33
Ardnacrusha | AA1 | 21 | 2020-08-24 08:00 | 2020-09-18 20:00 | S | 25.5
Coolkeeragh | NIC30 | 408 | 2020-08-29 | 2020-09-14 | S | 16
Seal Rock | SK3 | 85 | 2020-09-06 07:00 | 2020-09-24 07:00 | S | 18
Aghada | AT4 | 90 | 2020-09-07 | 2020-09-10 | S | 3
Liffey | LI4 | 4 | 2020-09-07 08:00 | 2020-09-09 17:00 | S | 2.33
Huntstown | HNC | 342 | 2020-09-11 | 2020-09-22 | F | 11
Dublin Bay | DB1 | 405 | 2020-09-11 13:00 | 2020-11-16 06:00 | S | 65.67
Ballylumford | NIB31 | 249 | 2020-09-21 | 2020-11-20 | S | 60
Ballylumford | NIB32 | 249 | 2020-09-21 | 2020-10-05 | 161 | 14
Great Island | GI4 | 461 | 2020-10-03 | 2020-10-24 | S | 21
Coolkeeragh | NICGT8 | 53 | 2020-10-24 | 2020-10-26 | S | 2
Seal Rock | SK4 | 85 | 2020-11-08 07:00 | 2020-11-10 17:00 | S | 2.42
Kilroot | NIKGT3 | 42 | 2020-11-16 | 2020-11-21 | S | 5
Turlough Hill | TH1 | 73 | 2020-11-17 08:00 | 2020-11-19 17:00 | S | 2.33
Turlough Hill | TH2 | 73 | 2020-11-17 08:00 | 2020-11-19 17:00 | S | 2.33
Kilroot | NIKGT4 | 42 | 2020-11-23 | 2020-11-28 | S | 5
Coolkeeragh | NIC30 | 408 | 2020-11-28 | 2020-11-30 | S | 2
Edenderry | ED1 | 118 | 2020-12-26 13:00 | 2021-01-02 08:00 | S | 6.75
|  |  | Scheduled Outage | S
|  |  | Forced Outage | F
|  |  | Unit partially available | 10