## Outage Plan EirGrid
2020 GENERATION OUTAGE PLAN (EIRGRID)
|  | Month | Jan '2020 |  |  |  |  | Feb '2020 |  |  |  | Mar '2020 |  |  |  |  | Apr '2020 |  |  |  | May '2020 |  |  |  | Jun '2020 |  |  |  |  | Jul '2020 |  |  |  | Aug '2020 |  |  |  |  | Sep '2020 |  |  |  | Oct '2020 |  |  |  | Nov '2020 |  |  |  |  | Dec '2020
|  | Week | 1 '2020 | 2 '2020 | 3 '2020 | 4 '2020 | 5 '2020 | 6 '2020 | 7 '2020 | 8 '2020 | 9 '2020 | 10 '2020 | 11 '2020 | 12 '2020 | 13 '2020 | 14 '2020 | 15 '2020 | 16 '2020 | 17 '2020 | 18 '2020 | 19 '2020 | 20 '2020 | 21 '2020 | 22 '2020 | 23 '2020 | 24 '2020 | 25 '2020 | 26 '2020 | 27 '2020 | 28 '2020 | 29 '2020 | 30 '2020 | 31 '2020 | 32 '2020 | 33 '2020 | 34 '2020 | 35 '2020 | 36 '2020 | 37 '2020 | 38 '2020 | 39 '2020 | 40 '2020 | 41 '2020 | 42 '2020 | 43 '2020 | 44 '2020 | 45 '2020 | 46 '2020 | 47 '2020 | 48 '2020 | 49 '2020 | 50 '2020 | 51 '2020 | 52 '2020 | 53 '2020
Station | Unit | NPR
Activation Energy | AE1 | 77
Activation Energy | AE2 | 8
Activation Energy | AE3 | 14
Activation Energy | AE4 | 11
Activation Energy | AE5 | 15
Activation Energy | EN6 | 9
Aghada | AD1 | 258 | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F
Aghada | AD2 | 431
Aghada | AT1 | 90
Aghada | AT2 | 90
Aghada | AT4 | 90
Ardnacrusha | AA1 | 21 | [20 empty] | S
Ardnacrusha | AA2 | 22 | [24 empty] | S
Ardnacrusha | AA3 | 19 | [16 empty] | S
Ardnacrusha | AA4 | 24 | [34 empty] | S | S | S
DAE Virtual Power Plant | DP1 | 19
DAE Virtual Power Plant | DP2 | 20
Dublin Bay | DB1 | 405
Dublin Waste To Energy | DW1 | 62
Edenderry | ED1 | 118 | S | [22 empty] | S | S | S | [26 empty] | S
Edenderry | ED3 | 58
Edenderry | ED5 | 58
Electric Ireland | EI1 | 20
Electricity Exchange DSU | EE1 | 39
Electricity Exchange DSU | EE2 | 17
Electricity Exchange DSU | EE3 | 7
Electricity Exchange DSU | EE4 | 9
Electricity Exchange DSU | EE5 | 7
Endeco Technologies | EC1 | 37
Endeco Technologies | EC2 | 10
Endeco Technologies | EC5 | 14
Energy Trading | ET1 | 13
Erne | ER1 | 10 | [23 empty] | S | S
Erne | ER2 | 10 | [34 empty] | S
Erne | ER3 | 22 | [19 empty] | S
Erne | ER4 | 22 | [16 empty] | S
EWIC | EW1 | 500
Great Island | GI4 | 461 | [10 empty] | S | S
Huntstown | HN2 | 400
Huntstown | HNC | 342
Indaver | IW1 | 17 | [19 empty] | S | S | S | S | S | S | S
Lanesboro | LR4 | 91 | [11 empty] | S | S | S
Lee | LE1 | 15 | [18 empty] | S | S | S
Lee | LE2 | 4 | [16 empty] | S
Lee | LE3 | 8 | [23 empty] | S
Liffey | LI1 | 15 | [16 empty] | S | S | S
Liffey | LI2 | 15 | [16 empty] | S | S | S
Liffey | LI4 | 4 | [36 empty] | S
Liffey | LI5 | 4
Marina | MRC | 95 | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F
Moneypoint | MP1 | 285 | [18 empty] | S
Moneypoint | MP2 | 285 | [19 empty] | S
Moneypoint | MP3 | 285 | [32 empty] | S
North Wall | NW5 | 104 | [9 empty] | S | S
Poolbeg | PB4 | 154 | [12 empty] | S
Poolbeg | PB5 | 146 | [14 empty] | S | S | S | S | S
Poolbeg | PB6 | 168
Powerhouse Generation | PG1 | 11
Rhode | RP1 | 52 | [31 empty] | S | S | S | S
Rhode | RP2 | 52 | [31 empty] | S | S | S | S
Seal Rock | SK3 | 85 | [36 empty] | S | S | S
Seal Rock | SK4 | 85
Tarbert | TB1 | 54
Tarbert | TB2 | 54
Tarbert | TB3 | 241
Tarbert | TB4 | 243 | [21 empty] | S
Tawnaghmore | TP1 | 52 | [18 empty] | S
Tawnaghmore | TP3 | 52 | [19 empty] | S
Turlough Hill | TH1 | 73 | [23 empty] | S
Turlough Hill | TH2 | 73 | [23 empty] | S
Turlough Hill | TH3 | 73 | [25 empty] | S
Turlough Hill | TH4 | 73 | [25 empty] | S
Tynagh | TYC | 384
Viridian Energy | VE1 | 19
Viridian Energy DSU | VE2 | 6
West Offaly | WO4 | 137 |  |  |  |  | S | S | [12 empty] | S | S | S
Whitegate | WG1 | 444 | [30 empty] | S | S

## EirGrid Outages
Upcoming Outages including STMOs and Annual Outages
Station | Unit | NPR | Start Date | End Date | Value | Duration
Marina | MRC | 95 | 2018-09-10 08:00 | 2023-01-01 | F | 1573.67
Aghada | AD1 | 258 | 2018-09-30 23:00 | 2023-01-01 | F | 1553
Edenderry | ED1 | 118 | 2019-12-26 13:00 | 2020-01-02 08:00 | S | 6.75
Seal Rock | SK3 | 85 | 2020-01-12 07:00 | 2020-01-14 17:00 | S | 2.42
West Offaly | WO4 | 137 | 2020-01-30 16:00 | 2020-02-06 16:00 | S | 7
North Wall | NW5 | 104 | 2020-03-02 | 2020-03-16 | S | 14
Great Island | GI4 | 461 | 2020-03-06 | 2020-03-23 | S | 17
Seal Rock | SK4 | 85 | 2020-03-08 07:00 | 2020-03-10 17:00 | S | 2.42
Lanesboro | LR4 | 91 | 2020-03-18 16:00 | 2020-04-06 16:00 | S | 19
Poolbeg | PB6 | 168 | 2020-03-24 | 2020-03-28 | 84 | 4
Poolbeg | PB4 | 154 | 2020-03-24 | 2020-03-28 | S | 4
Huntstown | HNC | 342 | 2020-03-28 | 2020-04-02 | S | 5
Dublin Bay | DB1 | 405 | 2020-04-03 13:00 | 2020-04-07 06:00 | S | 3.67
Poolbeg | PB5 | 146 | 2020-04-05 | 2020-05-10 | S | 35
Poolbeg | PB6 | 168 | 2020-04-05 | 2020-05-10 | 84 | 35
Edenderry | ED1 | 118 | 2020-04-09 18:00 | 2020-04-15 08:00 | S | 5.58
Liffey | LI2 | 15 | 2020-04-20 08:00 | 2020-05-11 17:00 | S | 21.33
Lee | LE2 | 4 | 2020-04-20 08:00 | 2020-04-24 20:00 | S | 4.5
Ardnacrusha | AA3 | 19 | 2020-04-20 08:00 | 2020-04-24 20:00 | S | 4.5
Erne | ER4 | 22.5 | 2020-04-20 08:00 | 2020-04-24 20:00 | S | 4.5
Liffey | LI1 | 15 | 2020-04-20 08:00 | 2020-05-11 17:00 | S | 21.33
Moneypoint | MP1 | 285 | 2020-05-01 22:00 | 2020-05-13 22:00 | S | 12
Tawnaghmore | TP1 | 52 | 2020-05-04 | 2020-05-11 | S | 7
Lee | LE1 | 15 | 2020-05-05 08:00 | 2020-05-25 20:00 | S | 20.5
West Offaly | WO4 | 137 | 2020-05-07 16:00 | 2020-05-25 16:00 | S | 18
Moneypoint | MP2 | 285 | 2020-05-08 22:00 | 2020-05-17 22:00 | S | 9
Tawnaghmore | TP3 | 52 | 2020-05-11 | 2020-05-18 | S | 7
Indaver | IW1 | 17 | 2020-05-11 | 2020-07-01 | S | 51
Erne | ER3 | 22.5 | 2020-05-11 08:00 | 2020-05-15 20:00 | S | 4.5
Seal Rock | SK3 | 85 | 2020-05-11 21:00 | 2020-05-13 12:00 | S | 1.58
Seal Rock | SK4 | 85 | 2020-05-11 23:00 | 2020-05-12 21:00 | S | 0.92
Edenderry | ED3 | 58 | 2020-05-16 08:00 | 2020-05-16 18:00 | S | 0.42
Edenderry | ED5 | 58 | 2020-05-16 08:00 | 2020-05-16 18:00 | S | 0.42
Ardnacrusha | AA1 | 21 | 2020-05-18 08:00 | 2020-05-22 20:00 | S | 4.5
EWIC | EW1 | 500 | 2020-05-19 | 2020-05-21 21:00 | S | 2.83
Tarbert | TB4 | 243 | 2020-05-25 | 2020-06-01 | S | 7
Edenderry | ED1 | 118 | 2020-06-05 12:00 | 2020-06-30 08:00 | S | 24.83
Turlough Hill | TH2 | 73 | 2020-06-07 08:00 | 2020-06-13 17:00 | S | 6.33
Turlough Hill | TH1 | 73 | 2020-06-07 08:00 | 2020-06-13 17:00 | S | 6.33
Lee | LE3 | 8 | 2020-06-08 08:00 | 2020-06-12 20:00 | S | 4.5
Erne | ER1 | 10 | 2020-06-08 08:00 | 2020-06-21 20:00 | S | 13.5
Ardnacrusha | AA2 | 22 | 2020-06-15 08:00 | 2020-06-19 20:00 | S | 4.5
Turlough Hill | TH4 | 73 | 2020-06-21 08:00 | 2020-06-27 17:00 | S | 6.33
Turlough Hill | TH3 | 73 | 2020-06-21 08:00 | 2020-06-27 17:00 | S | 6.33
Marina | MRC | 95 | 2020-07-06 | 2020-07-10 | S | 4
Seal Rock | SK4 | 85 | 2020-07-13 07:00 | 2020-07-16 17:00 | S | 3.42
Aghada | AD2 | 431 | 2020-07-20 | 2020-07-23 | S | 3
Whitegate | WG1 | 444 | 2020-07-30 | 2020-08-10 | S | 11
Rhode | RP1 | 52 | 2020-08-03 | 2020-08-31 | S | 28
Rhode | RP2 | 52 | 2020-08-03 | 2020-08-31 | S | 28
Moneypoint | MP3 | 285 | 2020-08-07 22:00 | 2020-08-19 22:00 | S | 12
Aghada | AT1 | 90 | 2020-08-10 | 2020-08-13 | S | 3
Aghada | AT4 | 90 | 2020-08-17 | 2020-08-20 | S | 3
Aghada | AD1 | 258 | 2020-08-22 | 2020-10-03 | S | 42
Erne | ER2 | 10 | 2020-08-24 08:00 | 2020-08-28 20:00 | S | 4.5
Ardnacrusha | AA4 | 24 | 2020-08-24 08:00 | 2020-09-15 20:00 | S | 22.5
Seal Rock | SK3 | 85 | 2020-09-06 07:00 | 2020-09-24 07:00 | S | 18
Liffey | LI4 | 4 | 2020-09-07 08:00 | 2020-09-11 17:00 | S | 4.33
Liffey | LI5 | 4 | 2020-09-21 08:00 | 2020-09-23 17:00 | S | 2.33
Tynagh | TYC | 384 | 2020-10-23 22:00 | 2020-10-28 22:00 | S | 5
Seal Rock | SK4 | 85 | 2020-11-08 07:00 | 2020-11-10 17:00 | S | 2.42
Turlough Hill | TH1 | 73 | 2020-11-17 08:00 | 2020-11-19 17:00 | S | 2.33
Turlough Hill | TH2 | 73 | 2020-11-17 08:00 | 2020-11-19 17:00 | S | 2.33
Edenderry | ED1 | 118 | 2020-12-26 13:00 | 2021-01-02 08:00 | S | 6.75
|  |  | Scheduled Outage | S
|  |  | Forced Outage | F
|  |  | Unit partially available | 10

## Outage Plan SONI
2020 GENERATION OUTAGE PLAN (SONI)
|  | Month | Jan '2020 |  |  |  |  | Feb '2020 |  |  |  | Mar '2020 |  |  |  |  | Apr '2020 |  |  |  | May '2020 |  |  |  | Jun '2020 |  |  |  |  | Jul '2020 |  |  |  | Aug '2020 |  |  |  |  | Sep '2020 |  |  |  | Oct '2020 |  |  |  | Nov '2020 |  |  |  |  | Dec '2020
|  | Week | 1 '2020 | 2 '2020 | 3 '2020 | 4 '2020 | 5 '2020 | 6 '2020 | 7 '2020 | 8 '2020 | 9 '2020 | 10 '2020 | 11 '2020 | 12 '2020 | 13 '2020 | 14 '2020 | 15 '2020 | 16 '2020 | 17 '2020 | 18 '2020 | 19 '2020 | 20 '2020 | 21 '2020 | 22 '2020 | 23 '2020 | 24 '2020 | 25 '2020 | 26 '2020 | 27 '2020 | 28 '2020 | 29 '2020 | 30 '2020 | 31 '2020 | 32 '2020 | 33 '2020 | 34 '2020 | 35 '2020 | 36 '2020 | 37 '2020 | 38 '2020 | 39 '2020 | 40 '2020 | 41 '2020 | 42 '2020 | 43 '2020 | 44 '2020 | 45 '2020 | 46 '2020 | 47 '2020 | 48 '2020 | 49 '2020 | 50 '2020 | 51 '2020 | 52 '2020 | 53 '2020
Station | Unit | NPR
Ballylumford | NIB10 | 94 | [18 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S
Ballylumford | NIB31 | 249 | [10 empty] | S | S | S | S | S | S | S
Ballylumford | NIB32 | 249 | [32 empty] | S | S | S | S | S | S | S | S
Ballylumford | NIB4 | 144
Ballylumford | NIB5 | 147
Ballylumford | NIBGT1 | 58 | [6 empty] | S
Ballylumford | NIBGT2 | 58 | [5 empty] | S
Contour Global | NICG2 | 3
Contour Global | NICGA | 12
Coolkeeragh | NIC30 | 408 | [31 empty] | S
Coolkeeragh | NICGT8 | 53 | [18 empty] | S
Empower | NIEMP | 3
iPower | NIAGU | 74
Kilroot | NIK1 | 256
Kilroot | NIK2 | 258
Kilroot | NIKGT1 | 29 | [35 empty] | S
Kilroot | NIKGT2 | 29 | [35 empty] | S
Kilroot | NIKGT3 | 42 | [36 empty] | S
Kilroot | NIKGT4 | 42
Lisahally | NILPS | 18
Moyle | MOYLE | 450
Powerhouse Generation | NIPH1 | 18

## SONI Outages
Upcoming Outages including STMOs and Annual Outages
Station | Unit | NPR | Start Date | End Date | Value | Duration
Ballylumford | NIBGT2 | 58 | 2020-02-03 | 2020-02-10 | S | 7
Ballylumford | NIBGT1 | 58 | 2020-02-10 | 2020-02-17 | S | 7
Coolkeeragh | NIC30 | 408 | 2020-02-22 | 2020-02-24 | S | 2
Ballylumford | NIB31 | 249 | 2020-03-07 | 2020-04-26 | S | 50
Coolkeeragh | NIC30 | 408 | 2020-05-02 | 2020-05-04 | S | 2
Coolkeeragh | NICGT8 | 53 | 2020-05-04 | 2020-05-11 | S | 7
Ballylumford | NIB10 | 94 | 2020-05-05 | 2020-08-03 | S | 90
Moyle | MOYLE | 450 | 2020-06-16 | 2020-06-19 | S | 3
Coolkeeragh | NIC30 | 408 | 2020-08-05 | 2020-08-10 | S | 5
Ballylumford | NIB32 | 249 | 2020-08-10 | 2020-10-07 | S | 58
Ballylumford | NIB31 | 249 | 2020-08-17 | 2020-08-31 | 161 | 14
Kilroot | NIKGT1 | 29 | 2020-08-31 | 2020-09-04 | S | 4
Kilroot | NIKGT2 | 29 | 2020-09-03 | 2020-09-07 | S | 4
Kilroot | NIKGT3 | 42 | 2020-09-07 | 2020-09-12 | S | 5
Kilroot | NIKGT4 | 42 | 2020-09-12 | 2020-09-17 | S | 5
Coolkeeragh | NIC30 | 408 | 2020-11-07 | 2020-11-09 | S | 2
|  |  | Scheduled Outage | S
|  |  | Forced Outage | F
|  |  | Unit partially available | 10

## Outage Plan All Island
2020 GENERATION OUTAGE PLAN (All Island)
|  | Month | Jan '2020 |  |  |  |  | Feb '2020 |  |  |  | Mar '2020 |  |  |  |  | Apr '2020 |  |  |  | May '2020 |  |  |  | Jun '2020 |  |  |  |  | Jul '2020 |  |  |  | Aug '2020 |  |  |  |  | Sep '2020 |  |  |  | Oct '2020 |  |  |  | Nov '2020 |  |  |  |  | Dec '2020
|  | Week | 1 '2020 | 2 '2020 | 3 '2020 | 4 '2020 | 5 '2020 | 6 '2020 | 7 '2020 | 8 '2020 | 9 '2020 | 10 '2020 | 11 '2020 | 12 '2020 | 13 '2020 | 14 '2020 | 15 '2020 | 16 '2020 | 17 '2020 | 18 '2020 | 19 '2020 | 20 '2020 | 21 '2020 | 22 '2020 | 23 '2020 | 24 '2020 | 25 '2020 | 26 '2020 | 27 '2020 | 28 '2020 | 29 '2020 | 30 '2020 | 31 '2020 | 32 '2020 | 33 '2020 | 34 '2020 | 35 '2020 | 36 '2020 | 37 '2020 | 38 '2020 | 39 '2020 | 40 '2020 | 41 '2020 | 42 '2020 | 43 '2020 | 44 '2020 | 45 '2020 | 46 '2020 | 47 '2020 | 48 '2020 | 49 '2020 | 50 '2020 | 51 '2020 | 52 '2020 | 53 '2020
Station | Unit | NPR
Activation Energy | AE1 | 77
Activation Energy | AE2 | 8
Activation Energy | AE3 | 14
Activation Energy | AE4 | 11
Activation Energy | AE5 | 15
Activation Energy | EN6 | 9
Aghada | AD1 | 258 | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F
Aghada | AD2 | 431
Aghada | AT1 | 90
Aghada | AT2 | 90
Aghada | AT4 | 90
Ardnacrusha | AA1 | 21 | [20 empty] | S
Ardnacrusha | AA2 | 22 | [24 empty] | S
Ardnacrusha | AA3 | 19 | [16 empty] | S
Ardnacrusha | AA4 | 24 | [34 empty] | S | S | S
Ballylumford | NIB10 | 94 | [18 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S
Ballylumford | NIB31 | 249 | [10 empty] | S | S | S | S | S | S | S
Ballylumford | NIB32 | 249 | [32 empty] | S | S | S | S | S | S | S | S
Ballylumford | NIB4 | 144
Ballylumford | NIB5 | 147
Ballylumford | NIBGT1 | 58 | [6 empty] | S
Ballylumford | NIBGT2 | 58 | [5 empty] | S
Contour Global | NICG2 | 3
Contour Global | NICGA | 12
Coolkeeragh | NIC30 | 408 | [31 empty] | S
Coolkeeragh | NICGT8 | 53 | [18 empty] | S
DAE Virtual Power Plant | DP1 | 19
DAE Virtual Power Plant | DP2 | 20
Dublin Bay | DB1 | 405
Dublin Waste To Energy | DW1 | 62
Edenderry | ED1 | 118 | S | [22 empty] | S | S | S | [26 empty] | S
Edenderry | ED3 | 58
Edenderry | ED5 | 58
Electric Ireland | EI1 | 20
Electricity Exchange DSU | EE1 | 39
Electricity Exchange DSU | EE2 | 17
Electricity Exchange DSU | EE3 | 7
Electricity Exchange DSU | EE4 | 9
Electricity Exchange DSU | EE5 | 7
Empower | NIEMP | 3
Endeco Technologies | EC1 | 37
Endeco Technologies | EC2 | 10
Endeco Technologies | EC5 | 14
Energy Trading | ET1 | 13
Erne | ER1 | 10 | [23 empty] | S | S
Erne | ER2 | 10 | [34 empty] | S
Erne | ER3 | 22 | [19 empty] | S
Erne | ER4 | 22 | [16 empty] | S
EWIC | EW1 | 500
Great Island | GI4 | 461 | [10 empty] | S | S
Huntstown | HN2 | 400
Huntstown | HNC | 342
Indaver | IW1 | 17 | [19 empty] | S | S | S | S | S | S | S
iPower | NIAGU | 74
Kilroot | NIK1 | 256
Kilroot | NIK2 | 258
Kilroot | NIKGT1 | 29 | [35 empty] | S
Kilroot | NIKGT2 | 29 | [35 empty] | S
Kilroot | NIKGT3 | 42 | [36 empty] | S
Kilroot | NIKGT4 | 42
Lanesboro | LR4 | 91 | [11 empty] | S | S | S
Lee | LE1 | 15 | [18 empty] | S | S | S
Lee | LE2 | 4 | [16 empty] | S
Lee | LE3 | 8 | [23 empty] | S
Liffey | LI1 | 15 | [16 empty] | S | S | S
Liffey | LI2 | 15 | [16 empty] | S | S | S
Liffey | LI4 | 4 | [36 empty] | S
Liffey | LI5 | 4
Lisahally | NILPS | 18
Marina | MRC | 95 | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F
Moneypoint | MP1 | 285 | [18 empty] | S
Moneypoint | MP2 | 285 | [19 empty] | S
Moneypoint | MP3 | 285 | [32 empty] | S
Moyle | MOYLE | 450
North Wall | NW5 | 104 | [9 empty] | S | S
Poolbeg | PB4 | 154 | [12 empty] | S
Poolbeg | PB5 | 146 | [14 empty] | S | S | S | S | S
Poolbeg | PB6 | 168
Powerhouse Generation | NIPH1 | 18
Powerhouse Generation | PG1 | 11
Rhode | RP1 | 52 | [31 empty] | S | S | S | S
Rhode | RP2 | 52 | [31 empty] | S | S | S | S
Seal Rock | SK3 | 85 | [36 empty] | S | S | S
Seal Rock | SK4 | 85
Tarbert | TB1 | 54
Tarbert | TB2 | 54
Tarbert | TB3 | 241
Tarbert | TB4 | 243 | [21 empty] | S
Tawnaghmore | TP1 | 52 | [18 empty] | S
Tawnaghmore | TP3 | 52 | [19 empty] | S
Turlough Hill | TH1 | 73 | [23 empty] | S
Turlough Hill | TH2 | 73 | [23 empty] | S
Turlough Hill | TH3 | 73 | [25 empty] | S
Turlough Hill | TH4 | 73 | [25 empty] | S
Tynagh | TYC | 384
Viridian Energy | VE1 | 19
Viridian Energy DSU | VE2 | 6
West Offaly | WO4 | 137 |  |  |  |  | S | S | [12 empty] | S | S | S
Whitegate | WG1 | 444 | [30 empty] | S | S

## All Island Outages
Upcoming Outages including STMOs and Annual Outages
Station | Unit | NPR | Start Date | End Date | Value | Duration
Marina | MRC | 95 | 2018-09-10 08:00 | 2023-01-01 | F | 1573.67
Aghada | AD1 | 258 | 2018-09-30 23:00 | 2023-01-01 | F | 1553
Edenderry | ED1 | 118 | 2019-12-26 13:00 | 2020-01-02 08:00 | S | 6.75
Seal Rock | SK3 | 85 | 2020-01-12 07:00 | 2020-01-14 17:00 | S | 2.42
West Offaly | WO4 | 137 | 2020-01-30 16:00 | 2020-02-06 16:00 | S | 7
Ballylumford | NIBGT2 | 58 | 2020-02-03 | 2020-02-10 | S | 7
Ballylumford | NIBGT1 | 58 | 2020-02-10 | 2020-02-17 | S | 7
Coolkeeragh | NIC30 | 408 | 2020-02-22 | 2020-02-24 | S | 2
North Wall | NW5 | 104 | 2020-03-02 | 2020-03-16 | S | 14
Great Island | GI4 | 461 | 2020-03-06 | 2020-03-23 | S | 17
Ballylumford | NIB31 | 249 | 2020-03-07 | 2020-04-26 | S | 50
Seal Rock | SK4 | 85 | 2020-03-08 07:00 | 2020-03-10 17:00 | S | 2.42
Lanesboro | LR4 | 91 | 2020-03-18 16:00 | 2020-04-06 16:00 | S | 19
Poolbeg | PB6 | 168 | 2020-03-24 | 2020-03-28 | 84 | 4
Poolbeg | PB4 | 154 | 2020-03-24 | 2020-03-28 | S | 4
Huntstown | HNC | 342 | 2020-03-28 | 2020-04-02 | S | 5
Dublin Bay | DB1 | 405 | 2020-04-03 13:00 | 2020-04-07 06:00 | S | 3.67
Poolbeg | PB5 | 146 | 2020-04-05 | 2020-05-10 | S | 35
Poolbeg | PB6 | 168 | 2020-04-05 | 2020-05-10 | 84 | 35
Edenderry | ED1 | 118 | 2020-04-09 18:00 | 2020-04-15 08:00 | S | 5.58
Liffey | LI2 | 15 | 2020-04-20 08:00 | 2020-05-11 17:00 | S | 21.33
Lee | LE2 | 4 | 2020-04-20 08:00 | 2020-04-24 20:00 | S | 4.5
Ardnacrusha | AA3 | 19 | 2020-04-20 08:00 | 2020-04-24 20:00 | S | 4.5
Erne | ER4 | 22.5 | 2020-04-20 08:00 | 2020-04-24 20:00 | S | 4.5
Liffey | LI1 | 15 | 2020-04-20 08:00 | 2020-05-11 17:00 | S | 21.33
Moneypoint | MP1 | 285 | 2020-05-01 22:00 | 2020-05-13 22:00 | S | 12
Coolkeeragh | NIC30 | 408 | 2020-05-02 | 2020-05-04 | S | 2
Tawnaghmore | TP1 | 52 | 2020-05-04 | 2020-05-11 | S | 7
Coolkeeragh | NICGT8 | 53 | 2020-05-04 | 2020-05-11 | S | 7
Ballylumford | NIB10 | 94 | 2020-05-05 | 2020-08-03 | S | 90
Lee | LE1 | 15 | 2020-05-05 08:00 | 2020-05-25 20:00 | S | 20.5
West Offaly | WO4 | 137 | 2020-05-07 16:00 | 2020-05-25 16:00 | S | 18
Moneypoint | MP2 | 285 | 2020-05-08 22:00 | 2020-05-17 22:00 | S | 9
Tawnaghmore | TP3 | 52 | 2020-05-11 | 2020-05-18 | S | 7
Indaver | IW1 | 17 | 2020-05-11 | 2020-07-01 | S | 51
Erne | ER3 | 22.5 | 2020-05-11 08:00 | 2020-05-15 20:00 | S | 4.5
Seal Rock | SK3 | 85 | 2020-05-11 21:00 | 2020-05-13 12:00 | S | 1.58
Seal Rock | SK4 | 85 | 2020-05-11 23:00 | 2020-05-12 21:00 | S | 0.92
Edenderry | ED3 | 58 | 2020-05-16 08:00 | 2020-05-16 18:00 | S | 0.42
Edenderry | ED5 | 58 | 2020-05-16 08:00 | 2020-05-16 18:00 | S | 0.42
Ardnacrusha | AA1 | 21 | 2020-05-18 08:00 | 2020-05-22 20:00 | S | 4.5
EWIC | EW1 | 500 | 2020-05-19 | 2020-05-21 21:00 | S | 2.83
Tarbert | TB4 | 243 | 2020-05-25 | 2020-06-01 | S | 7
Edenderry | ED1 | 118 | 2020-06-05 12:00 | 2020-06-30 08:00 | S | 24.83
Turlough Hill | TH2 | 73 | 2020-06-07 08:00 | 2020-06-13 17:00 | S | 6.33
Turlough Hill | TH1 | 73 | 2020-06-07 08:00 | 2020-06-13 17:00 | S | 6.33
Lee | LE3 | 8 | 2020-06-08 08:00 | 2020-06-12 20:00 | S | 4.5
Erne | ER1 | 10 | 2020-06-08 08:00 | 2020-06-21 20:00 | S | 13.5
Ardnacrusha | AA2 | 22 | 2020-06-15 08:00 | 2020-06-19 20:00 | S | 4.5
Moyle | MOYLE | 450 | 2020-06-16 | 2020-06-19 | S | 3
Turlough Hill | TH4 | 73 | 2020-06-21 08:00 | 2020-06-27 17:00 | S | 6.33
Turlough Hill | TH3 | 73 | 2020-06-21 08:00 | 2020-06-27 17:00 | S | 6.33
Marina | MRC | 95 | 2020-07-06 | 2020-07-10 | S | 4
Seal Rock | SK4 | 85 | 2020-07-13 07:00 | 2020-07-16 17:00 | S | 3.42
Aghada | AD2 | 431 | 2020-07-20 | 2020-07-23 | S | 3
Whitegate | WG1 | 444 | 2020-07-30 | 2020-08-10 | S | 11
Rhode | RP1 | 52 | 2020-08-03 | 2020-08-31 | S | 28
Rhode | RP2 | 52 | 2020-08-03 | 2020-08-31 | S | 28
Coolkeeragh | NIC30 | 408 | 2020-08-05 | 2020-08-10 | S | 5
Moneypoint | MP3 | 285 | 2020-08-07 22:00 | 2020-08-19 22:00 | S | 12
Aghada | AT1 | 90 | 2020-08-10 | 2020-08-13 | S | 3
Ballylumford | NIB32 | 249 | 2020-08-10 | 2020-10-07 | S | 58
Aghada | AT4 | 90 | 2020-08-17 | 2020-08-20 | S | 3
Ballylumford | NIB31 | 249 | 2020-08-17 | 2020-08-31 | 161 | 14
Aghada | AD1 | 258 | 2020-08-22 | 2020-10-03 | S | 42
Erne | ER2 | 10 | 2020-08-24 08:00 | 2020-08-28 20:00 | S | 4.5
Ardnacrusha | AA4 | 24 | 2020-08-24 08:00 | 2020-09-15 20:00 | S | 22.5
Kilroot | NIKGT1 | 29 | 2020-08-31 | 2020-09-04 | S | 4
Kilroot | NIKGT2 | 29 | 2020-09-03 | 2020-09-07 | S | 4
Seal Rock | SK3 | 85 | 2020-09-06 07:00 | 2020-09-24 07:00 | S | 18
Kilroot | NIKGT3 | 42 | 2020-09-07 | 2020-09-12 | S | 5
Liffey | LI4 | 4 | 2020-09-07 08:00 | 2020-09-11 17:00 | S | 4.33
Kilroot | NIKGT4 | 42 | 2020-09-12 | 2020-09-17 | S | 5
Liffey | LI5 | 4 | 2020-09-21 08:00 | 2020-09-23 17:00 | S | 2.33
Tynagh | TYC | 384 | 2020-10-23 22:00 | 2020-10-28 22:00 | S | 5
Coolkeeragh | NIC30 | 408 | 2020-11-07 | 2020-11-09 | S | 2
Seal Rock | SK4 | 85 | 2020-11-08 07:00 | 2020-11-10 17:00 | S | 2.42
Turlough Hill | TH1 | 73 | 2020-11-17 08:00 | 2020-11-19 17:00 | S | 2.33
Turlough Hill | TH2 | 73 | 2020-11-17 08:00 | 2020-11-19 17:00 | S | 2.33
Edenderry | ED1 | 118 | 2020-12-26 13:00 | 2021-01-02 08:00 | S | 6.75
|  |  | Scheduled Outage | S
|  |  | Forced Outage | F
|  |  | Unit partially available | 10