## Outage Plan EirGrid
2021 GENERATION OUTAGE PLAN (EIRGRID)
|  | Month | Jan '2021 |  |  |  |  | Feb '2021 |  |  |  | Mar '2021 |  |  |  |  | Apr '2021 |  |  |  | May '2021 |  |  |  |  | Jun '2021 |  |  |  | Jul '2021 |  |  |  | Aug '2021 |  |  |  |  | Sep '2021 |  |  |  | Oct '2021 |  |  |  | Nov '2021 |  |  |  |  | Dec '2021
|  | Week | 53 '2021 | 1 '2021 | 2 '2021 | 3 '2021 | 4 '2021 | 5 '2021 | 6 '2021 | 7 '2021 | 8 '2021 | 9 '2021 | 10 '2021 | 11 '2021 | 12 '2021 | 13 '2021 | 14 '2021 | 15 '2021 | 16 '2021 | 17 '2021 | 18 '2021 | 19 '2021 | 20 '2021 | 21 '2021 | 22 '2021 | 23 '2021 | 24 '2021 | 25 '2021 | 26 '2021 | 27 '2021 | 28 '2021 | 29 '2021 | 30 '2021 | 31 '2021 | 32 '2021 | 33 '2021 | 34 '2021 | 35 '2021 | 36 '2021 | 37 '2021 | 38 '2021 | 39 '2021 | 40 '2021 | 41 '2021 | 42 '2021 | 43 '2021 | 44 '2021 | 45 '2021 | 46 '2021 | 47 '2021 | 48 '2021 | 49 '2021 | 50 '2021 | 51 '2021 | 52 '2021
Station | Unit | NPR
Activation Energy | AE1 | 95
Activation Energy | AE2 | 12
Activation Energy | AE3 | 14
Activation Energy | AE4 | 15
Activation Energy | AE5 | 15
Activation Energy | EN1 | 15
Activation Energy | EN2 | 16
Activation Energy | EN3 | 16
Activation Energy | EN4 | 16
Activation Energy | EN5 | 6
Activation Energy | EN6 | 11
Aghada | AD2 | 449 | [7 empty] | F | [11 empty] | S | S | S
Aghada | AT1 | 90 | [33 empty] | S | S
Aghada | AT2 | 90 | [31 empty] | S | S | S | S | S | S | S
Aghada | AT4 | 90 | [15 empty] | F | F
Ardnacrusha | AA1 | 21 | [28 empty] | S
Ardnacrusha | AA2 | 22 | [23 empty] | S | S | S
Ardnacrusha | AA3 | 19 | [32 empty] | S | S | S | S | S | S | S | S
Ardnacrusha | AA4 | 24 | [7 empty] | F | F | F | F | F | F | F | S | S | S | S | S | S | S | S | F | F | F | F | F | F | F | F | F
DAE Virtual Power Plant | DP1 | 19
DAE Virtual Power Plant | DP2 | 26
Dublin Bay | DB1 | 405 | [17 empty] | S | S | S | S | S | S | S | S | S | F | F | F | F | F | F
Dublin Waste To Energy | DW1 | 62 | [22 empty] | F |  | S | S | S
Edenderry | ED1 | 118 | [13 empty] | F | [12 empty] | F | S | S | S | S | S | S | S | S | [17 empty] | S
Edenderry | ED3 | 58 | [27 empty] | F
Edenderry | ED5 | 58
Electric Ireland | EI1 | 20
Electricity Exchange DSU | EE1 | 47
Electricity Exchange DSU | EE2 | 20
Electricity Exchange DSU | EE3 | 8
Electricity Exchange DSU | EE4 | 9
Electricity Exchange DSU | EE5 | 7
Electricity Exchange DSU | EE6 | 14
Endeco Technologies | EC1 | 47
Endeco Technologies | EC2 | 11
Endeco Technologies | EC5 | 15
Energy Trading | ET1 | 13
Erne | ER1 | 10 | [15 empty] | S | S | F | [16 empty] | S
Erne | ER2 | 10 | [34 empty] | S
Erne | ER3 | 22 | [24 empty] | S | S | S
Erne | ER4 | 22 | [36 empty] | S
EWIC | EW1 | 500 | [34 empty] | S | S | S | S | S | S | S
Great Island | GI4 | 461
Huntstown | HN2 | 400 | [5 empty] | F | F | F | F | S | S | S | S | S | S | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F
Huntstown | HNC | 342
Indaver | IW1 | 17
Knockacummer | KC1 | 100
Lee | LE1 | 15 | [12 empty] | F |  |  | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F
Lee | LE2 | 4 | [11 empty] | F |  |  | S | S | F | F | F | F | F | F | F | F | F | F | F | F | F
Lee | LE3 | 8 | [24 empty] | S | S | S | S | S | F
Liffey | LI1 | 15 | [15 empty] | S | S | S | S | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F
Liffey | LI2 | 15 | [15 empty] | S | S | S | S | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F
Liffey | LI4 | 4
Liffey | LI5 | 4 | [20 empty] | F | F | F | F | F | F | F | F | F | F | [5 empty] | S
Moneypoint | MP1 | 285 | [10 empty] | F | F | [11 empty] | F | [14 empty] | S | F | F
Moneypoint | MP2 | 285 |  | F | F | [6 empty] | F |  |  | F | [5 empty] | F | F |  |  |  |  | F | [5 empty] | S
Moneypoint | MP3 | 285 | [6 empty] | F | [21 empty] | F | S
Poolbeg | PB4 | 154 |  |  |  | F | F | [30 empty] | S | S | S
Poolbeg | PB5 | 146 | [14 empty] | S | [25 empty] | S | S | S | S | S | S | F | F
Poolbeg | PB6 | 168 | [5 empty] | F | F | F | F | [28 empty] | S | S | S | S | S | S
Powerhouse Generation | PG1 | 10
Rhode | RP1 | 52 | [22 empty] | S | S | S | S | F | F | F
Rhode | RP2 | 52 | [22 empty] | S | S | S | S
Seal Rock | SK3 | 85 | [24 empty] | S | S
Seal Rock | SK4 | 85 | [27 empty] | S
Seecon | SO1 | 105
Tarbert | TB1 | 54 | [21 empty] | F | F | F
Tarbert | TB2 | 54 | [21 empty] | F | F | F
Tarbert | TB3 | 241 | [32 empty] | S | S | S | S
Tarbert | TB4 | 243 | [7 empty] | F | F | [6 empty] | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F
Tawnaghmore | TP1 | 52 | [15 empty] | S | S | S | S | F | F
Tawnaghmore | TP3 | 52 | [15 empty] | S | S | S | S | F | F
Turlough Hill | TH1 | 73 | [12 empty] | S
Turlough Hill | TH2 | 73 | [12 empty] | S
Turlough Hill | TH3 | 73 | [12 empty] | S
Turlough Hill | TH4 | 73 | [12 empty] | S
Tynagh | TYC | 384 | [15 empty] | S | S | S | F
Viridian Energy | VE1 | 20
Viridian Energy DSU | VE2 | 13
Whitegate | WG1 | 444 | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F

## EirGrid Outages
Upcoming Outages including STMOs and Annual Outages
Station | Unit | NPR | Start Date | End Date | Value | Duration
Whitegate | WG1 | 444 | 2020-12-02 08:00 | 2021-11-04 23:00 | F | 337.58
Tarbert | TB3 | 241 | 2020-12-08 14:30 | 2021-01-08 21:30 | 226 | 31.25
Moneypoint | MP1 | 285 | 2020-12-20 20:00 | 2021-01-04 17:00 | 200 | 14.83
Moneypoint | MP2 | 285 | 2020-12-24 18:00 | 2021-01-04 15:00 | 120 | 10.83
Moneypoint | MP3 | 285 | 2020-12-30 06:30 | 2021-01-04 11:00 | 240 | 5.17
EWIC | EW1 | 500 | 2021-01-02 09:00 | 2021-01-02 20:00 | F | 0.42
Tarbert | TB4 | 243 | 2021-01-02 09:30 | 2021-01-02 11:30 | F | 0.08
Turlough Hill | TH1 | 73 | 2021-01-02 16:30 | 2021-01-03 11:00 | F | 0.75
Liffey | LI2 | 15 | 2021-01-04 08:00 | 2021-01-04 09:30 | F | 0.04
Moneypoint | MP3 | 285 | 2021-01-04 10:30 | 2021-01-19 21:00 | 270 | 15.42
Moneypoint | MP2 | 285 | 2021-01-04 15:00 | 2021-01-06 15:30 | F | 2
Moneypoint | MP1 | 285 | 2021-01-04 17:00 | 2021-01-06 15:30 | 220 | 1.92
Tarbert | TB2 | 54 | 2021-01-06 09:00 | 2021-01-06 11:00 | F | 0.08
Moneypoint | MP2 | 285 | 2021-01-06 15:30 | 2021-01-07 10:30 | 120 | 0.75
Moneypoint | MP1 | 285 | 2021-01-06 15:30 | 2021-01-06 16:30 | F | 0
Tarbert | TB2 | 54 | 2021-01-06 15:30 | 2021-01-06 17:30 | F | 0.08
Tarbert | TB4 | 243 | 2021-01-06 16:00 | 2021-01-07 12:00 | 222 | 0.83
Moneypoint | MP1 | 285 | 2021-01-06 16:30 | 2021-01-09 12:00 | 220 | 2.79
Aghada | AT1 | 90 | 2021-01-07 04:00 | 2021-01-08 07:30 | F | 1.12
Aghada | AT2 | 90 | 2021-01-07 04:00 | 2021-01-07 19:30 | F | 0.62
Moneypoint | MP2 | 285 | 2021-01-07 10:30 | 2021-01-19 22:00 | F | 12.46
Tarbert | TB4 | 243 | 2021-01-07 12:00 | 2021-01-08 12:00 | F | 1
Tarbert | TB2 | 54 | 2021-01-07 16:00 | 2021-01-08 19:30 | F | 1.12
Dublin Waste To Energy | DW1 | 61.5 | 2021-01-08 05:00 | 2021-01-08 06:30 | S | 0.04
Tarbert | TB4 | 243 | 2021-01-08 12:00 | 2021-01-11 12:00 | 222 | 3
Huntstown | HN2 | 400 | 2021-01-08 21:00 | 2021-01-10 21:00 | S | 2
Tarbert | TB3 | 241 | 2021-01-08 21:30 | 2021-01-08 22:30 | F | 0
Tarbert | TB3 | 241 | 2021-01-08 22:30 | 2021-02-04 09:00 | 226 | 26.42
Erne | ER1 | 10 | 2021-01-09 08:30 | 2021-01-09 17:00 | S | 0.33
Erne | ER2 | 10 | 2021-01-09 08:30 | 2021-01-09 17:00 | S | 0.33
Seal Rock | SK4 | 85 | 2021-01-09 09:30 | 2021-02-09 12:30 | 60 | 31.08
Seal Rock | SK3 | 85 | 2021-01-09 09:30 | 2021-01-09 12:30 | 60 | 0.08
Moneypoint | MP1 | 285 | 2021-01-09 12:00 | 2021-01-09 16:30 | 230 | 0.17
Moneypoint | MP1 | 285 | 2021-01-09 16:30 | 2021-01-19 21:00 | 240 | 10.17
Rhode | RP2 | 52 | 2021-01-09 17:00 | 2021-01-11 10:30 | 25 | 1.71
Erne | ER1 | 10 | 2021-01-09 23:30 | 2021-01-10 09:00 | 6 | 0.38
Erne | ER1 | 10 | 2021-01-10 08:30 | 2021-01-10 18:00 | S | 0.38
Erne | ER2 | 10 | 2021-01-10 08:30 | 2021-01-10 17:00 | S | 0.33
Turlough Hill | TH1 | 73 | 2021-01-10 16:30 | 2021-01-11 12:00 | F | 0.79
Erne | ER3 | 22.5 | 2021-01-11 03:30 | 2021-01-11 09:00 | 10 | 0.21
Liffey | LI4 | 4 | 2021-01-11 07:00 | 2021-01-11 18:00 | S | 0.42
Liffey | LI2 | 15 | 2021-01-11 07:00 | 2021-01-11 18:00 | S | 0.42
Liffey | LI1 | 15 | 2021-01-11 07:00 | 2021-01-11 18:00 | S | 0.42
Erne | ER1 | 10 | 2021-01-11 08:30 | 2021-01-11 17:00 | S | 0.33
Erne | ER2 | 10 | 2021-01-11 08:30 | 2021-01-11 17:00 | S | 0.33
Lee | LE2 | 4 | 2021-01-11 09:00 | 2021-01-11 13:00 | F | 0.17
Tarbert | TB4 | 243 | 2021-01-11 12:00 | 2021-01-11 22:00 | 209 | 0.42
Tarbert | TB4 | 243 | 2021-01-11 22:00 | 2021-01-11 23:30 | F | 0.04
Tarbert | TB4 | 243 | 2021-01-11 23:30 | 2021-01-15 10:00 | 209 | 3.42
Erne | ER1 | 10 | 2021-01-12 08:30 | 2021-01-12 17:00 | S | 0.33
Erne | ER2 | 10 | 2021-01-12 08:30 | 2021-01-12 17:00 | S | 0.33
Tarbert | TB2 | 54 | 2021-01-12 17:30 | 2021-01-12 19:30 | F | 0.08
Tarbert | TB2 | 54 | 2021-01-14 12:00 | 2021-01-14 14:00 | F | 0.08
Tarbert | TB4 | 243 | 2021-01-15 10:00 | 2021-01-19 03:00 | F | 3.67
Poolbeg | PB6 | 168 | 2021-01-18 17:30 | 2021-02-02 17:00 | 84 | 14.96
Tarbert | TB4 | 243 | 2021-01-19 03:00 | 2021-01-20 09:30 | 237 | 1.25
Poolbeg | PB4 | 154 | 2021-01-19 12:00 | 2021-02-02 17:00 | F | 14.17
Moneypoint | MP3 | 285 | 2021-01-19 21:00 | 2021-01-21 09:00 | 230 | 1.5
Moneypoint | MP1 | 285 | 2021-01-19 21:00 | 2021-01-21 09:00 | 200 | 1.5
Moneypoint | MP2 | 285 | 2021-01-19 22:00 | 2021-02-03 13:00 | 120 | 14.58
Dublin Waste To Energy | DW1 | 61.5 | 2021-01-21 05:00 | 2021-01-24 07:00 | 52 | 3.08
Great Island | GI4 | 461 | 2021-01-21 06:00 | 2021-01-21 08:30 | F | 0.08
Moneypoint | MP3 | 285 | 2021-01-21 09:00 | 2021-02-04 03:00 | 260 | 13.75
Moneypoint | MP1 | 285 | 2021-01-21 09:00 | 2021-01-27 12:00 | 230 | 6.08
Edenderry | ED1 | 118 | 2021-01-22 09:00 | 2021-01-22 15:00 | 65 | 0.25
Tarbert | TB4 | 243 | 2021-01-23 19:30 | 2021-01-25 01:00 | F | 1.21
Dublin Waste To Energy | DW1 | 61.5 | 2021-01-24 07:00 | 2021-01-26 09:00 | 22 | 2.08
Ardnacrusha | AA3 | 19 | 2021-01-24 10:00 | 2021-01-24 11:30 | F | 0.04
Huntstown | HNC | 342 | 2021-01-24 10:00 | 2021-01-24 11:00 | F | 0
Huntstown | HNC | 342 | 2021-01-24 11:00 | 2021-01-24 17:00 | F | 0.25
Tawnaghmore | TP1 | 52 | 2021-01-24 13:00 | 2021-01-24 14:30 | F | 0.04
Edenderry | ED1 | 118 | 2021-01-25 | 2021-01-25 12:00 | 55 | 0.5
Seal Rock | SK4 | 85 | 2021-01-26 06:00 | 2021-01-29 17:00 | S | 3.42
Tarbert | TB4 | 243 | 2021-01-26 13:00 | 2021-02-03 10:30 | 217 | 7.88
Huntstown | HNC | 342 | 2021-01-26 15:00 | 2021-01-26 17:00 | F | 0.08
Moneypoint | MP1 | 285 | 2021-01-27 12:00 | 2021-01-27 13:00 | 205 | 0
Moneypoint | MP1 | 285 | 2021-01-27 13:00 | 2021-01-29 17:30 | 235 | 2.17
Huntstown | HNC | 342 | 2021-01-28 07:00 | 2021-01-28 11:30 | F | 0.17
Turlough Hill | TH2 | 73 | 2021-01-28 10:00 | 2021-01-28 15:00 | S | 0.17
Moneypoint | MP1 | 285 | 2021-01-29 17:30 | 2021-01-31 13:30 | 250 | 1.83
Huntstown | HN2 | 400 | 2021-01-29 22:00 | 2021-02-28 23:00 | F | 30
Moneypoint | MP1 | 285 | 2021-01-31 13:30 | 2021-01-31 19:30 | 200 | 0.25
Moneypoint | MP1 | 285 | 2021-01-31 19:30 | 2021-02-04 17:00 | 220 | 3.88
Dublin Waste To Energy | DW1 | 61.5 | 2021-02-01 04:30 | 2021-02-01 09:00 | 45 | 0.17
Tarbert | TB1 | 54 | 2021-02-01 09:00 | 2021-02-01 12:00 | F | 0.08
Turlough Hill | TH1 | 73 | 2021-02-02 10:00 | 2021-02-02 12:30 | S | 0.08
Liffey | LI5 | 4 | 2021-02-03 09:00 | 2021-02-03 13:00 | F | 0.17
Poolbeg | PB6 | 168 | 2021-02-03 11:30 | 2021-03-03 16:30 | F | 28.17
Poolbeg | PB4 | 154 | 2021-02-03 11:30 | 2021-02-03 17:00 | F | 0.21
Tarbert | TB1 | 54 | 2021-02-03 16:00 | 2021-02-03 17:00 | F | 0
Moneypoint | MP3 | 285 | 2021-02-04 03:00 | 2021-02-04 13:30 | 190 | 0.42
Tarbert | TB3 | 241 | 2021-02-04 08:00 | 2021-02-09 03:30 | F | 4.79
Seecon | SO1 | 105 | 2021-02-04 10:00 | 2021-02-04 17:00 | S | 0.25
Tarbert | TB2 | 54 | 2021-02-04 13:00 | 2021-02-04 14:00 | F | 0
Moneypoint | MP3 | 285 | 2021-02-04 13:30 | 2021-02-04 15:30 | 240 | 0.08
Moneypoint | MP3 | 285 | 2021-02-04 15:30 | 2021-02-04 17:00 | 260 | 0.04
Moneypoint | MP3 | 285 | 2021-02-04 17:00 | 2021-02-09 10:00 | 270 | 4.67
Moneypoint | MP1 | 285 | 2021-02-04 17:00 | 2021-02-10 17:30 | 240 | 6
Moneypoint | MP2 | 285 | 2021-02-05 11:00 | 2021-02-12 18:00 | 99 | 7.25
Tarbert | TB2 | 54 | 2021-02-05 15:00 | 2021-02-05 16:00 | F | 0
Tarbert | TB2 | 54 | 2021-02-05 17:30 | 2021-02-05 20:00 | F | 0.08
Tarbert | TB3 | 241 | 2021-02-09 03:30 | 2021-02-10 08:00 | 226 | 1.17
Dublin Waste To Energy | DW1 | 61.5 | 2021-02-09 05:00 | 2021-02-09 23:00 | 22 | 0.75
Turlough Hill | TH4 | 73 | 2021-02-09 09:00 | 2021-02-09 14:00 | S | 0.17
Moneypoint | MP3 | 285 | 2021-02-09 15:00 | 2021-02-17 10:00 | F | 7.75
Dublin Waste To Energy | DW1 | 61.5 | 2021-02-10 07:00 | 2021-02-10 09:00 | F | 0.08
Tarbert | TB3 | 241 | 2021-02-10 08:00 | 2021-02-10 09:00 | F | 0
Ardnacrusha | AA1 | 21 | 2021-02-10 08:30 | 2021-02-10 10:00 | F | 0.04
Tarbert | TB3 | 241 | 2021-02-10 09:00 | 2021-02-25 13:00 | 226 | 15.17
Turlough Hill | TH3 | 73 | 2021-02-10 10:00 | 2021-02-10 15:00 | S | 0.17
Lee | LE3 | 8 | 2021-02-10 16:00 | 2021-02-12 17:30 | 3 | 2.04
Moneypoint | MP1 | 285 | 2021-02-10 17:30 | 2021-02-13 05:30 | 220 | 2.5
Liffey | LI4 | 4 | 2021-02-10 17:30 | 2021-02-11 09:30 | F | 0.67
Liffey | LI2 | 15 | 2021-02-10 21:00 | 2021-02-11 04:00 | F | 0.25
Dublin Waste To Energy | DW1 | 61.5 | 2021-02-11 12:00 | 2021-02-14 13:30 | 58 | 3.04
Lee | LE1 | 15 | 2021-02-12 08:00 | 2021-02-12 09:00 | 3 | 0
Moneypoint | MP2 | 285 | 2021-02-12 18:00 | 2021-02-13 05:30 | 120 | 0.46
Tynagh | TYC | 384 | 2021-02-12 20:00 | 2021-02-15 | S | 2.17
Moneypoint | MP2 | 285 | 2021-02-13 05:30 | 2021-02-14 17:00 | F | 1.46
Moneypoint | MP1 | 285 | 2021-02-13 05:30 | 2021-02-13 21:00 | F | 0.62
Tarbert | TB4 | 243 | 2021-02-13 17:00 | 2021-02-25 02:00 | F | 11.33
Moneypoint | MP1 | 285 | 2021-02-13 22:30 | 2021-02-24 22:00 | 210 | 10.96
Aghada | AD2 | 449 | 2021-02-14 02:00 | 2021-02-20 18:00 | F | 6.67
Dublin Waste To Energy | DW1 | 61.5 | 2021-02-14 13:30 | 2021-02-14 15:30 | F | 0.08
Dublin Waste To Energy | DW1 | 61.5 | 2021-02-14 15:30 | 2021-02-16 23:00 | 58 | 2.29
Moneypoint | MP2 | 285 | 2021-02-14 17:00 | 2021-02-14 18:00 | 100 | 0
Moneypoint | MP2 | 285 | 2021-02-14 18:00 | 2021-02-24 22:00 | 120 | 10.17
Dublin Bay | DB1 | 405 | 2021-02-16 | 2021-02-16 19:30 | F | 0.79
Dublin Waste To Energy | DW1 | 61.5 | 2021-02-16 23:00 | 2021-03-01 23:00 | 51 | 13
Moneypoint | MP3 | 285 | 2021-02-17 10:00 | 2021-02-17 13:30 | F | 0.12
Ardnacrusha | AA4 | 24 | 2021-02-17 10:00 | 2021-04-06 08:00 | F | 47.92
Edenderry | ED1 | 118 | 2021-02-18 10:30 | 2021-02-18 16:00 | 55 | 0.21
Huntstown | HNC | 342 | 2021-02-18 23:00 | 2021-02-19 22:00 | 225 | 0.92
Lee | LE3 | 8 | 2021-02-19 | 2021-02-19 02:30 | 3 | 0.08
Liffey | LI5 | 4 | 2021-02-19 20:30 | 2021-02-22 11:00 | F | 2.58
Indaver | IW1 | 17 | 2021-02-21 14:00 | 2021-02-25 07:00 | F | 3.67
Moneypoint | MP1 | 285 | 2021-02-24 16:00 | 2021-02-25 13:00 | F | 0.83
Moneypoint | MP3 | 285 | 2021-02-24 22:00 | 2021-02-28 20:30 | F | 3.92
Moneypoint | MP2 | 285 | 2021-02-24 22:00 | 2021-02-26 12:00 | F | 1.58
Moneypoint | MP1 | 285 | 2021-02-25 13:00 | 2021-02-27 08:00 | 220 | 1.75
Tarbert | TB3 | 241 | 2021-02-25 13:00 | 2021-02-25 15:00 | F | 0.08
Moneypoint | MP2 | 285 | 2021-02-25 13:00 | 2021-03-01 10:00 | 120 | 3.83
Tarbert | TB3 | 241 | 2021-02-25 15:00 | 2021-03-26 19:30 | 226 | 29.17
Moneypoint | MP1 | 285 | 2021-02-27 08:00 | 2021-02-27 10:00 | F | 0.08
Moneypoint | MP1 | 285 | 2021-02-27 10:00 | 2021-03-04 14:00 | 220 | 5.17
Aghada | AT4 | 90 | 2021-02-27 17:30 | 2021-02-27 19:00 | F | 0.04
Tarbert | TB4 | 243 | 2021-02-27 20:30 | 2021-02-27 21:30 | F | 0
Tarbert | TB4 | 243 | 2021-02-28 20:00 | 2021-03-01 13:00 | F | 0.67
Moneypoint | MP3 | 285 | 2021-02-28 20:30 | 2021-03-05 22:00 | 245 | 5.04
Huntstown | HN2 | 400 | 2021-02-28 23:00 | 2021-04-13 17:00 | S | 43.75
Seal Rock | SK3 | 85 | 2021-03-01 06:00 | 2021-03-03 18:00 | S | 2.5
Moneypoint | MP2 | 285 | 2021-03-01 10:00 | 2021-03-06 06:00 | F | 4.83
Indaver | IW1 | 17 | 2021-03-01 17:00 | 2021-03-02 01:00 | 12 | 0.33
Liffey | LI2 | 15 | 2021-03-02 07:30 | 2021-03-02 08:30 | F | 0
Tarbert | TB1 | 54 | 2021-03-02 11:00 | 2021-03-02 12:30 | F | 0.04
Tarbert | TB2 | 54 | 2021-03-02 14:00 | 2021-03-02 16:00 | F | 0.08
Tarbert | TB1 | 54 | 2021-03-02 17:30 | 2021-03-03 16:30 | F | 0.92
Aghada | AT2 | 90 | 2021-03-02 18:30 | 2021-03-02 19:30 | 40 | 0
Aghada | AT2 | 90 | 2021-03-02 19:30 | 2021-03-02 20:30 | 60 | 0
Edenderry | ED1 | 118 | 2021-03-03 17:30 | 2021-03-03 20:00 | 49 | 0.08
Moneypoint | MP1 | 285 | 2021-03-04 14:00 | 2021-03-11 23:00 | 245 | 7.33
Dublin Waste To Energy | DW1 | 61.5 | 2021-03-05 07:00 | 2021-03-05 09:00 | F | 0.08
Tawnaghmore | TP1 | 52 | 2021-03-05 10:00 | 2021-03-05 20:30 | F | 0.42
Moneypoint | MP3 | 285 | 2021-03-05 22:00 | 2021-03-11 12:00 | F | 5.58
Moneypoint | MP2 | 285 | 2021-03-06 06:00 | 2021-03-23 08:00 | 120 | 17.08
Ardnacrusha | AA3 | 19 | 2021-03-06 09:00 | 2021-03-06 11:00 | 12 | 0.08
Ardnacrusha | AA2 | 22 | 2021-03-06 09:30 | 2021-03-06 11:00 | 12 | 0.04
Tarbert | TB4 | 243 | 2021-03-06 18:00 | 2021-03-12 10:00 | 226 | 5.67
Seal Rock | SK3 | 85 | 2021-03-09 11:00 | 2021-03-09 16:30 | F | 0.21
Aghada | AT4 | 90 | 2021-03-10 06:00 | 2021-03-12 20:00 | S | 2.58
Moneypoint | MP3 | 285 | 2021-03-11 12:00 | 2021-03-13 17:00 | 260 | 2.17
Moneypoint | MP1 | 285 | 2021-03-11 23:00 | 2021-03-18 09:00 | F | 6.42
Aghada | AT4 | 90 | 2021-03-12 23:30 | 2021-03-13 15:30 | F | 0.67
Indaver | IW1 | 17 | 2021-03-13 02:00 | 2021-03-19 01:00 | F | 5.92
Moneypoint | MP3 | 285 | 2021-03-13 17:00 | 2021-03-13 19:30 | F | 0.08
EWIC | EW1 | 500 | 2021-03-13 19:00 | 2021-03-14 23:00 | S | 1.17
Moneypoint | MP3 | 285 | 2021-03-13 19:30 | 2021-03-15 10:00 | 260 | 1.58
Lee | LE1 | 15 | 2021-03-14 07:00 | 2021-03-16 12:00 | F | 2.17
Poolbeg | PB5 | 146 | 2021-03-15 08:00 | 2021-03-15 12:00 | F | 0.17
Poolbeg | PB6 | 168 | 2021-03-15 08:00 | 2021-03-15 12:00 | 84 | 0.17
Lee | LE2 | 4 | 2021-03-15 13:30 | 2021-03-15 18:00 | F | 0.17
Poolbeg | PB6 | 168 | 2021-03-16 06:30 | 2021-03-16 18:00 | 84 | 0.46
Poolbeg | PB5 | 146 | 2021-03-16 06:30 | 2021-03-16 18:00 | F | 0.46
Lee | LE2 | 4 | 2021-03-16 09:30 | 2021-03-20 19:00 | F | 4.38
Ardnacrusha | AA3 | 19 | 2021-03-16 14:30 | 2021-03-16 15:30 | 12 | 0
Dublin Bay | DB1 | 405 | 2021-03-16 15:30 | 2021-03-17 14:30 | 180 | 0.92
Lee | LE1 | 15 | 2021-03-17 20:00 | 2021-03-17 21:00 | F | 0
Seal Rock | SK3 | 85 | 2021-03-17 22:30 | 2021-03-18 16:30 | F | 0.75
Moneypoint | MP1 | 285 | 2021-03-18 09:00 | 2021-03-18 10:00 | 250 | 0
Lee | LE1 | 15 | 2021-03-18 10:00 | 2021-03-18 14:30 | F | 0.17
Moneypoint | MP1 | 285 | 2021-03-18 10:00 | 2021-03-18 15:30 | F | 0.21
Edenderry | ED1 | 118 | 2021-03-19 | 2021-03-19 23:00 | 65 | 0.92
Ardnacrusha | AA2 | 22 | 2021-03-19 12:30 | 2021-03-19 14:00 | 12 | 0.04
Ardnacrusha | AA1 | 21 | 2021-03-19 12:30 | 2021-03-19 15:00 | 12 | 0.08
Ardnacrusha | AA3 | 19 | 2021-03-19 12:30 | 2021-03-19 13:30 | 12 | 0
Moneypoint | MP1 | 285 | 2021-03-19 14:30 | 2021-03-26 09:00 | F | 6.75
Tarbert | TB4 | 243 | 2021-03-19 17:00 | 2021-03-19 18:30 | F | 0.04
Rhode | RP1 | 52 | 2021-03-19 17:30 | 2021-03-25 13:00 | 26 | 5.79
Tarbert | TB4 | 243 | 2021-03-19 18:30 | 2021-03-31 12:30 | 106 | 11.75
Edenderry | ED1 | 118 | 2021-03-19 23:00 | 2021-03-22 11:30 | 75 | 2.5
Turlough Hill | TH2 | 73 | 2021-03-20 06:00 | 2021-03-28 17:00 | S | 8.42
Turlough Hill | TH3 | 73 | 2021-03-20 06:00 | 2021-03-28 17:00 | S | 8.42
Turlough Hill | TH4 | 73 | 2021-03-20 06:00 | 2021-03-28 17:00 | S | 8.42
Turlough Hill | TH1 | 73 | 2021-03-20 06:00 | 2021-03-28 17:00 | S | 8.42
Ardnacrusha | AA1 | 21 | 2021-03-20 09:30 | 2021-03-20 11:00 | 12 | 0.04
Ardnacrusha | AA2 | 22 | 2021-03-20 10:00 | 2021-03-20 11:00 | 12 | 0
Lee | LE1 | 15 | 2021-03-20 16:30 | 2021-03-31 17:00 | F | 11
Tawnaghmore | TP1 | 52 | 2021-03-21 17:30 | 2021-03-21 20:00 | 26 | 0.08
Edenderry | ED1 | 118 | 2021-03-22 11:30 | 2021-03-23 10:00 | 85 | 0.92
Moneypoint | MP2 | 285 | 2021-03-23 08:00 | 2021-03-31 21:00 | F | 8.5
Edenderry | ED1 | 118 | 2021-03-23 10:00 | 2021-03-24 10:00 | 95 | 1
Edenderry | ED1 | 118 | 2021-03-24 10:00 | 2021-03-25 10:30 | 100 | 1
Edenderry | ED1 | 118 | 2021-03-25 10:30 | 2021-03-29 09:30 | 105 | 3.92
Lee | LE2 | 4 | 2021-03-26 09:00 | 2021-03-26 13:00 | S | 0.17
Tarbert | TB3 | 241 | 2021-03-26 19:30 | 2021-03-30 03:30 | F | 3.33
Indaver | IW1 | 17 | 2021-03-27 11:30 | 2021-03-28 19:00 | F | 1.29
Liffey | LI5 | 4 | 2021-03-27 19:00 | 2021-03-28 07:00 | F | 0.5
Turlough Hill | TH4 | 73 | 2021-03-28 17:00 | 2021-03-29 17:00 | F | 1
Turlough Hill | TH3 | 73 | 2021-03-28 17:00 | 2021-03-29 15:00 | F | 0.92
Turlough Hill | TH2 | 73 | 2021-03-28 17:00 | 2021-03-29 15:00 | F | 0.92
Turlough Hill | TH1 | 73 | 2021-03-28 17:00 | 2021-03-29 17:00 | F | 1
Indaver | IW1 | 17 | 2021-03-28 20:30 | 2021-03-29 07:00 | 9 | 0.42
Aghada | AT1 | 90 | 2021-03-29 06:00 | 2021-03-31 18:00 | S | 2.5
Edenderry | ED1 | 118 | 2021-03-29 09:30 | 2021-03-30 14:00 | 110 | 1.17
Indaver | IW1 | 17 | 2021-03-29 20:00 | 2021-03-31 02:30 | 15 | 1.25
Tarbert | TB3 | 241 | 2021-03-30 03:30 | 2021-03-31 17:30 | 226 | 1.58
Turlough Hill | TH3 | 73 | 2021-03-30 10:00 | 2021-03-30 11:30 | F | 0.04
Edenderry | ED1 | 118 | 2021-03-30 14:00 | 2021-03-30 15:00 | 65 | 0
Edenderry | ED1 | 118 | 2021-03-30 15:00 | 2021-03-31 19:00 | 45 | 1.17
Aghada | AD2 | 449 | 2021-03-31 05:30 | 2021-03-31 12:00 | 340 | 0.25
Indaver | IW1 | 17 | 2021-03-31 13:00 | 2021-03-31 17:00 | 14 | 0.17
Aghada | AD2 | 449 | 2021-03-31 13:30 | 2021-03-31 15:00 | 340 | 0.04
Aghada | AD2 | 449 | 2021-03-31 15:00 | 2021-03-31 16:00 | 120 | 0
Aghada | AD2 | 449 | 2021-03-31 16:00 | 2021-03-31 17:00 | 200 | 0
Aghada | AD2 | 449 | 2021-03-31 17:00 | 2021-03-31 18:00 | 300 | 0
Tarbert | TB3 | 241 | 2021-03-31 17:30 | 2021-04-02 02:00 | F | 1.33
Edenderry | ED1 | 118 | 2021-03-31 19:00 | 2021-04-06 02:30 | F | 5.29
Lee | LE1 | 15 | 2021-04-01 12:00 | 2021-04-01 13:00 | F | 0
Moneypoint | MP2 | 285 | 2021-04-01 20:00 | 2021-04-14 08:30 | 120 | 12.5
Tarbert | TB3 | 241 | 2021-04-02 02:00 | 2021-04-15 13:00 | 226 | 13.42
Aghada | AD2 | 449 | 2021-04-02 12:00 | 2021-04-04 | 415 | 1.5
Ardnacrusha | AA2 | 22 | 2021-04-02 14:00 | 2021-04-02 17:00 | 12 | 0.08
Ardnacrusha | AA3 | 19 | 2021-04-02 14:30 | 2021-04-02 17:30 | 12 | 0.08
Aghada | AD2 | 449 | 2021-04-04 | 2021-04-05 20:30 | S | 1.83
Tarbert | TB4 | 243 | 2021-04-04 10:00 | 2021-04-04 12:30 | F | 0.08
Tarbert | TB4 | 243 | 2021-04-04 12:30 | 2021-04-06 14:00 | 121 | 2.04
Poolbeg | PB6 | 168 | 2021-04-05 09:00 | 2021-04-10 17:00 | 84 | 5.33
Poolbeg | PB5 | 146 | 2021-04-05 09:00 | 2021-04-10 17:00 | S | 5.33
Moneypoint | MP1 | 285 | 2021-04-05 09:30 | 2021-04-07 07:30 | F | 1.92
Tynagh | TYC | 384 | 2021-04-06 03:00 | 2021-04-06 17:00 | F | 0.58
Tawnaghmore | TP1 | 52 | 2021-04-06 06:00 | 2021-04-06 09:00 | F | 0.08
Ardnacrusha | AA4 | 24 | 2021-04-06 08:00 | 2021-05-28 20:00 | S | 52.5
Lee | LE2 | 4 | 2021-04-06 08:00 | 2021-04-16 20:00 | S | 10.5
Tawnaghmore | TP3 | 52 | 2021-04-06 09:00 | 2021-04-06 10:00 | F | 0
Tarbert | TB4 | 243 | 2021-04-06 14:00 | 2021-04-06 18:00 | F | 0.17
Ardnacrusha | AA3 | 19 | 2021-04-06 17:00 | 2021-04-07 15:30 | F | 0.92
Tarbert | TB4 | 243 | 2021-04-06 18:00 | 2021-04-07 01:30 | 121 | 0.29
Tynagh | TYC | 384 | 2021-04-06 21:30 | 2021-04-07 15:30 | F | 0.75
Tarbert | TB4 | 243 | 2021-04-07 01:30 | 2021-04-10 17:00 | F | 3.62
Tarbert | TB1 | 54 | 2021-04-07 08:30 | 2021-04-07 12:00 | F | 0.12
Edenderry | ED1 | 118 | 2021-04-07 08:30 | 2021-04-07 15:00 | 45 | 0.25
Tarbert | TB2 | 54 | 2021-04-07 10:30 | 2021-04-07 12:00 | F | 0.04
Moneypoint | MP1 | 285 | 2021-04-09 07:30 | 2021-04-09 14:00 | 220 | 0.25
Moneypoint | MP1 | 285 | 2021-04-09 14:00 | 2021-04-09 20:00 | 245 | 0.25
Moneypoint | MP1 | 285 | 2021-04-09 20:00 | 2021-04-12 12:00 | 220 | 2.67
Tarbert | TB4 | 243 | 2021-04-10 17:00 | 2021-04-13 10:00 | 121 | 2.67
Aghada | AT4 | 90 | 2021-04-11 17:00 | 2021-04-27 11:30 | F | 15.75
Tynagh | TYC | 384 | 2021-04-11 20:00 | 2021-05-03 | S | 21.17
Liffey | LI2 | 15 | 2021-04-12 08:00 | 2021-05-09 17:00 | S | 27.33
Liffey | LI1 | 15 | 2021-04-12 08:00 | 2021-05-09 17:00 | S | 27.33
Erne | ER1 | 10 | 2021-04-12 08:00 | 2021-04-26 20:00 | S | 14.5
Tawnaghmore | TP3 | 52 | 2021-04-12 09:00 | 2021-05-09 17:00 | S | 27.33
Tawnaghmore | TP1 | 52 | 2021-04-12 09:00 | 2021-05-09 17:00 | S | 27.33
Moneypoint | MP1 | 285 | 2021-04-12 12:00 | 2021-04-14 09:00 | 245 | 1.83
Lee | LE1 | 15 | 2021-04-12 14:30 | 2021-04-26 08:00 | F | 13.71
Tarbert | TB4 | 243 | 2021-04-13 10:00 | 2021-04-13 11:00 | F | 0
Dublin Waste To Energy | DW1 | 61.5 | 2021-04-13 10:00 | 2021-04-14 01:00 | 28 | 0.58
Tarbert | TB4 | 243 | 2021-04-13 11:00 | 2021-04-13 12:00 | 121 | 0
Tarbert | TB4 | 243 | 2021-04-13 12:00 | 2021-04-13 13:30 | F | 0.04
Tarbert | TB4 | 243 | 2021-04-13 13:30 | 2021-04-13 15:00 | 121 | 0.04
Tarbert | TB4 | 243 | 2021-04-13 15:00 | 2021-08-08 17:00 | F | 117.08
Huntstown | HN2 | 400 | 2021-04-13 17:00 | 2021-10-18 08:00 | F | 187.58
Tarbert | TB1 | 54 | 2021-04-13 19:30 | 2021-04-13 21:30 | F | 0.08
Dublin Waste To Energy | DW1 | 61.5 | 2021-04-14 01:00 | 2021-04-14 03:00 | F | 0.08
Dublin Waste To Energy | DW1 | 61.5 | 2021-04-14 03:00 | 2021-04-15 03:00 | 28 | 1
Moneypoint | MP2 | 285 | 2021-04-14 08:30 | 2021-04-14 20:00 | F | 0.46
Moneypoint | MP1 | 285 | 2021-04-14 09:00 | 2021-04-15 16:00 | 280 | 1.25
Moneypoint | MP2 | 285 | 2021-04-14 20:00 | 2021-04-30 21:00 | 120 | 16
Aghada | AT2 | 90 | 2021-04-15 | 2021-04-17 15:00 | S | 2.58
Tarbert | TB3 | 241 | 2021-04-15 13:00 | 2021-04-15 14:30 | F | 0.04
Tarbert | TB3 | 241 | 2021-04-15 14:30 | 2021-05-17 09:00 | 226 | 31.75
Moneypoint | MP1 | 285 | 2021-04-15 16:00 | 2021-04-18 21:00 | 245 | 3.17
Poolbeg | PB5 | 146 | 2021-04-16 14:30 | 2021-04-16 18:00 | F | 0.12
Poolbeg | PB6 | 168 | 2021-04-16 14:30 | 2021-04-16 18:00 | 84 | 0.12
Lee | LE2 | 4 | 2021-04-16 20:00 | 2021-07-20 | F | 94.17
Great Island | GI4 | 461 | 2021-04-16 21:00 | 2021-04-18 16:00 | S | 1.75
Dublin Waste To Energy | DW1 | 61.5 | 2021-04-17 06:30 | 2021-04-17 11:30 | 24 | 0.17
Moneypoint | MP1 | 285 | 2021-04-18 21:00 | 2021-04-21 09:00 | 225 | 2.5
Erne | ER2 | 10 | 2021-04-19 20:30 | 2021-04-19 21:30 | F | 0
Poolbeg | PB6 | 168 | 2021-04-20 05:30 | 2021-04-20 08:00 | 76 | 0.08
Moneypoint | MP3 | 285 | 2021-04-20 06:00 | 2021-04-20 18:00 | 255 | 0.5
Moneypoint | MP1 | 285 | 2021-04-21 09:00 | 2021-04-30 21:00 | 245 | 9.5
Erne | ER2 | 10 | 2021-04-21 09:30 | 2021-04-21 18:00 | F | 0.33
Erne | ER2 | 10 | 2021-04-22 10:30 | 2021-04-22 16:30 | F | 0.25
Dublin Bay | DB1 | 405 | 2021-04-23 13:00 | 2021-06-28 06:00 | S | 65.67
Lee | LE1 | 15 | 2021-04-26 08:00 | 2021-07-30 20:00 | F | 95.5
Erne | ER1 | 10 | 2021-04-26 20:00 | 2021-04-30 20:00 | F | 4
Tarbert | TB1 | 54 | 2021-04-29 08:00 | 2021-04-29 09:30 | F | 0.04
Tarbert | TB1 | 54 | 2021-04-30 07:30 | 2021-04-30 08:30 | F | 0
Tarbert | TB1 | 54 | 2021-04-30 07:30 | 2021-04-30 08:30 | F | 0
Moneypoint | MP2 | 285 | 2021-04-30 21:00 | 2021-05-02 12:30 | F | 1.62
Moneypoint | MP3 | 285 | 2021-05-01 | 2021-05-04 06:00 | F | 3.25
Moneypoint | MP2 | 285 | 2021-05-02 12:30 | 2021-05-06 01:00 | 120 | 3.5
Tynagh | TYC | 384 | 2021-05-03 | 2021-05-12 19:00 | F | 9.75
Erne | ER1 | 10 | 2021-05-03 09:00 | 2021-05-03 18:00 | F | 0.33
Moneypoint | MP3 | 285 | 2021-05-04 06:00 | 2021-05-05 21:30 | 260 | 1.62
Ardnacrusha | AA3 | 19 | 2021-05-04 08:00 | 2021-05-07 17:00 | F | 3.33
Ardnacrusha | AA1 | 21 | 2021-05-04 08:00 | 2021-05-04 15:00 | F | 0.25
Moneypoint | MP3 | 285 | 2021-05-05 21:30 | 2021-05-06 16:00 | 205 | 0.75
Moneypoint | MP2 | 285 | 2021-05-06 01:00 | 2021-05-13 18:00 | F | 7.67
Moneypoint | MP3 | 285 | 2021-05-06 16:00 | 2021-05-12 13:00 | 200 | 5.83
Edenderry | ED1 | 118 | 2021-05-08 07:00 | 2021-05-08 08:00 | 65 | 0
Erne | ER2 | 10 | 2021-05-09 15:30 | 2021-05-09 17:00 | F | 0.04
Liffey | LI2 | 15 | 2021-05-09 17:00 | 2021-09-12 17:00 | F | 126
Liffey | LI1 | 15 | 2021-05-09 17:00 | 2021-09-12 17:00 | F | 126
Tawnaghmore | TP1 | 52 | 2021-05-09 17:00 | 2021-05-21 17:00 | F | 12
Tawnaghmore | TP3 | 52 | 2021-05-09 17:00 | 2021-05-26 17:00 | F | 17
Seal Rock | SK4 | 85 | 2021-05-10 18:00 | 2021-05-13 21:00 | S | 3.08
Seal Rock | SK3 | 85 | 2021-05-11 01:00 | 2021-05-13 18:00 | S | 2.67
Aghada | AD2 | 449 | 2021-05-12 20:00 | 2021-05-30 20:00 | S | 18
Tynagh | TYC | 384 | 2021-05-13 | 2021-05-13 02:30 | F | 0.08
Moneypoint | MP2 | 285 | 2021-05-13 18:00 | 2021-05-17 11:30 | 220 | 3.71
Seal Rock | SK3 | 85 | 2021-05-14 01:00 | 2021-05-14 14:00 | F | 0.5
Tarbert | TB1 | 54 | 2021-05-14 10:00 | 2021-05-15 | F | 0.58
Poolbeg | PB6 | 168 | 2021-05-14 21:00 | 2021-05-19 23:00 | 84 | 5.08
Tarbert | TB2 | 54 | 2021-05-15 | 2021-05-22 | S | 7
Tarbert | TB1 | 54 | 2021-05-15 | 2021-05-22 | S | 7
Moneypoint | MP1 | 285 | 2021-05-15 09:30 | 2021-05-15 15:00 | 98 | 0.21
Moneypoint | MP1 | 285 | 2021-05-15 15:00 | 2021-05-16 00:30 | F | 0.38
Liffey | LI5 | 4 | 2021-05-17 08:00 | 2021-07-23 16:00 | F | 67.33
Tarbert | TB3 | 241 | 2021-05-17 09:00 | 2021-05-17 11:00 | F | 0.08
Tarbert | TB3 | 241 | 2021-05-17 11:00 | 2021-05-25 11:00 | 226 | 8
Moneypoint | MP2 | 285 | 2021-05-17 11:30 | 2021-05-17 13:00 | 120 | 0.04
Moneypoint | MP2 | 285 | 2021-05-17 13:00 | 2021-05-17 19:00 | 165 | 0.25
Moneypoint | MP2 | 285 | 2021-05-17 19:00 | 2021-05-19 10:30 | 200 | 1.62
Moneypoint | MP2 | 285 | 2021-05-19 10:30 | 2021-06-01 14:00 | 220 | 13.12
Turlough Hill | TH3 | 73 | 2021-05-20 10:00 | 2021-05-20 15:00 | S | 0.17
Tynagh | TYC | 384 | 2021-05-20 23:00 | 2021-05-21 15:00 | F | 0.67
Turlough Hill | TH1 | 73 | 2021-05-21 10:00 | 2021-05-21 15:00 | S | 0.17
Tynagh | TYC | 384 | 2021-05-21 15:30 | 2021-05-21 16:30 | F | 0
Tarbert | TB1 | 54 | 2021-05-22 | 2021-06-14 03:30 | F | 23.12
Tarbert | TB2 | 54 | 2021-05-22 | 2021-06-12 17:00 | F | 21.67
Tawnaghmore | TP1 | 52 | 2021-05-22 00:30 | 2021-05-22 08:30 | F | 0.33
Turlough Hill | TH2 | 73 | 2021-05-24 10:00 | 2021-05-24 15:00 | S | 0.17
Tarbert | TB3 | 241 | 2021-05-25 11:00 | 2021-06-03 08:00 | 209 | 8.83
Lee | LE3 | 8 | 2021-05-26 08:00 | 2021-05-26 16:00 | F | 0.33
Turlough Hill | TH4 | 73 | 2021-05-27 10:00 | 2021-05-27 15:00 | S | 0.17
Aghada | AT4 | 90 | 2021-05-28 08:00 | 2021-05-28 09:00 | F | 0
Ardnacrusha | AA4 | 24 | 2021-05-28 20:00 | 2021-07-31 17:00 | F | 63.83
Moneypoint | MP3 | 285 | 2021-05-28 21:00 | 2021-06-04 17:00 | F | 6.83
Dublin Waste To Energy | DW1 | 61.5 | 2021-05-30 02:00 | 2021-06-04 03:00 | F | 5
Aghada | AD2 | 449 | 2021-05-30 20:00 | 2021-06-02 13:00 | F | 2.67
Ardnacrusha | AA3 | 19 | 2021-05-31 08:00 | 2021-06-03 17:00 | F | 3.33
Rhode | RP2 | 52 | 2021-05-31 09:00 | 2021-06-24 19:30 | S | 24.42
Rhode | RP1 | 52 | 2021-05-31 09:00 | 2021-06-26 17:00 | S | 26.33
Moneypoint | MP2 | 285 | 2021-06-01 14:00 | 2021-06-10 13:00 | 220 | 8.92
Aghada | AD2 | 449 | 2021-06-02 05:00 | 2021-06-02 17:00 | S | 0.5
Tarbert | TB3 | 241 | 2021-06-03 08:00 | 2021-06-05 18:00 | S | 2.42
Dublin Waste To Energy | DW1 | 61.5 | 2021-06-04 03:00 | 2021-06-04 23:00 | 22 | 0.83
Tarbert | TB3 | 241 | 2021-06-05 18:00 | 2021-06-11 21:00 | 209 | 6.08
Tawnaghmore | TP1 | 52 | 2021-06-05 20:00 | 2021-06-05 22:30 | F | 0.08
Tawnaghmore | TP3 | 52 | 2021-06-05 20:00 | 2021-06-05 23:00 | F | 0.08
Moneypoint | MP1 | 285 | 2021-06-05 22:00 | 2021-06-12 09:30 | F | 6.46
Edenderry | ED1 | 118 | 2021-06-07 17:00 | 2021-06-15 11:00 | 105 | 7.75
Ardnacrusha | AA2 | 22 | 2021-06-08 16:30 | 2021-06-29 17:00 | S | 21
Moneypoint | MP2 | 285 | 2021-06-10 13:00 | 2021-06-19 14:00 | F | 9
Great Island | GI4 | 461 | 2021-06-11 04:00 | 2021-06-11 22:00 | F | 0.75
Tarbert | TB3 | 241 | 2021-06-11 21:00 | 2021-06-16 08:00 | 180 | 4.42
Moneypoint | MP1 | 285 | 2021-06-12 14:00 | 2021-06-12 19:00 | 120 | 0.17
Seal Rock | SK3 | 85 | 2021-06-13 06:00 | 2021-06-29 18:00 | S | 16.5
Dublin Waste To Energy | DW1 | 61.5 | 2021-06-13 18:30 | 2021-06-14 04:00 | F | 0.38
Dublin Waste To Energy | DW1 | 61.5 | 2021-06-14 04:00 | 2021-07-07 06:00 | S | 23.08
Lee | LE3 | 8 | 2021-06-14 08:00 | 2021-07-16 20:00 | S | 32.5
Erne | ER3 | 22.5 | 2021-06-14 08:00 | 2021-07-04 20:00 | S | 20.5
Edenderry | ED1 | 118 | 2021-06-15 11:00 | 2021-06-15 16:00 | 55 | 0.17
Edenderry | ED1 | 118 | 2021-06-15 16:00 | 2021-06-22 00:30 | 105 | 6.33
Tarbert | TB3 | 241 | 2021-06-16 08:00 | 2021-06-16 18:00 | F | 0.42
Tarbert | TB3 | 241 | 2021-06-16 18:00 | 2021-06-20 14:30 | F | 3.83
Tarbert | TB1 | 54 | 2021-06-18 06:00 | 2021-06-18 07:00 | F | 0
Tarbert | TB1 | 54 | 2021-06-18 18:30 | 2021-06-18 22:00 | F | 0.12
Moneypoint | MP2 | 285 | 2021-06-19 14:00 | 2021-06-21 10:30 | 220 | 1.83
Moneypoint | MP3 | 285 | 2021-06-20 03:00 | 2021-06-20 17:00 | 210 | 0.58
Tarbert | TB3 | 241 | 2021-06-20 16:30 | 2021-06-29 10:00 | 180 | 8.71
Moneypoint | MP2 | 285 | 2021-06-21 10:30 | 2021-06-21 11:30 | F | 0
Moneypoint | MP2 | 285 | 2021-06-21 11:30 | 2021-07-23 22:00 | 220 | 32.42
Edenderry | ED1 | 118 | 2021-06-22 00:30 | 2021-06-22 02:30 | F | 0.08
Edenderry | ED1 | 118 | 2021-06-22 02:30 | 2021-07-01 12:30 | 105 | 9.42
Turlough Hill | TH4 | 73 | 2021-06-25 11:00 | 2021-06-25 13:00 | S | 0.08
Seal Rock | SK4 | 85 | 2021-06-25 11:00 | 2021-06-25 15:30 | F | 0.17
Rhode | RP1 | 52 | 2021-06-26 17:00 | 2021-07-16 17:00 | F | 20
Dublin Bay | DB1 | 405 | 2021-06-28 06:00 | 2021-08-10 18:00 | F | 43.5
Poolbeg | PB6 | 168 | 2021-06-28 06:00 | 2021-06-28 07:00 | F | 0
Poolbeg | PB5 | 146 | 2021-06-28 06:00 | 2021-06-28 07:00 | F | 0
Tarbert | TB3 | 241 | 2021-06-29 10:00 | 2021-07-09 15:00 | 150 | 10.17
Ardnacrusha | AA2 | 22 | 2021-06-29 17:00 | 2021-06-30 09:00 | F | 0.67
Seal Rock | SK3 | 85 | 2021-06-29 18:00 | 2021-07-02 | S | 2.25
Edenderry | ED1 | 118 | 2021-07-01 12:00 | 2021-08-30 18:00 | S | 60.25
Aghada | AD2 | 449 | 2021-07-03 08:00 | 2021-07-03 18:00 | F | 0.42
Tynagh | TYC | 384 | 2021-07-03 17:00 | 2021-07-03 23:30 | F | 0.25
Seal Rock | SK4 | 85 | 2021-07-05 06:00 | 2021-07-09 18:00 | S | 4.5
Edenderry | ED3 | 58 | 2021-07-05 16:00 | 2021-07-11 08:30 | F | 5.67
Erne | ER4 | 22.5 | 2021-07-06 09:00 | 2021-07-07 17:00 | F | 1.33
Indaver | IW1 | 17 | 2021-07-06 18:00 | 2021-07-07 03:00 | F | 0.33
Dublin Waste To Energy | DW1 | 61.5 | 2021-07-07 06:00 | 2021-07-07 18:00 | 28 | 0.5
Moneypoint | MP3 | 285 | 2021-07-07 10:00 | 2021-07-08 10:00 | 240 | 1
Moneypoint | MP1 | 285 | 2021-07-07 10:00 | 2021-07-12 08:00 | 270 | 4.92
Turlough Hill | TH2 | 73 | 2021-07-07 10:00 | 2021-07-07 15:00 | F | 0.17
Turlough Hill | TH2 | 73 | 2021-07-07 10:00 | 2021-07-07 15:00 | F | 0.17
Moneypoint | MP3 | 285 | 2021-07-08 10:00 | 2021-07-09 10:00 | 250 | 1
Moneypoint | MP3 | 285 | 2021-07-09 10:00 | 2021-07-12 08:00 | 265 | 2.92
Tarbert | TB3 | 241 | 2021-07-09 15:00 | 2021-08-09 09:00 | 122 | 30.75
Aghada | AT1 | 90 | 2021-07-09 18:00 | 2021-07-12 23:00 | F | 3.17
Aghada | AT2 | 90 | 2021-07-09 18:00 | 2021-07-12 23:00 | F | 3.17
Huntstown | HNC | 342 | 2021-07-09 22:00 | 2021-07-11 23:00 | 220 | 2
Tawnaghmore | TP1 | 52 | 2021-07-10 14:00 | 2021-07-10 16:00 | F | 0.08
Moneypoint | MP1 | 285 | 2021-07-12 08:00 | 2021-07-12 22:00 | 180 | 0.58
Moneypoint | MP3 | 285 | 2021-07-12 08:00 | 2021-07-12 21:00 | 235 | 0.5
Ardnacrusha | AA1 | 21 | 2021-07-12 08:00 | 2021-07-16 20:00 | S | 4.5
Rhode | RP2 | 52 | 2021-07-12 10:30 | 2021-07-12 12:30 | F | 0.08
Tarbert | TB1 | 54 | 2021-07-12 15:00 | 2021-07-13 12:00 | F | 0.83
Tarbert | TB2 | 54 | 2021-07-12 15:00 | 2021-07-13 14:00 | F | 0.92
Poolbeg | PB5 | 146 | 2021-07-12 17:00 | 2021-08-14 21:00 | 134 | 33.17
Moneypoint | MP3 | 285 | 2021-07-12 21:00 | 2021-07-16 23:00 | F | 4.08
Moneypoint | MP1 | 285 | 2021-07-12 22:00 | 2021-07-14 22:30 | 280 | 2
Tarbert | TB2 | 54 | 2021-07-13 18:00 | 2021-07-14 17:00 | 44 | 0.92
Tarbert | TB1 | 54 | 2021-07-13 18:00 | 2021-07-14 17:00 | 33 | 0.92
Tawnaghmore | TP3 | 52 | 2021-07-15 10:00 | 2021-07-15 12:00 | F | 0.08
Dublin Waste To Energy | DW1 | 61.5 | 2021-07-16 04:00 | 2021-07-16 16:00 | F | 0.5
Turlough Hill | TH2 | 73 | 2021-07-16 06:00 | 2021-07-16 12:00 | F | 0.25
Moneypoint | MP1 | 285 | 2021-07-16 08:30 | 2021-07-16 19:00 | 230 | 0.42
Lee | LE3 | 8 | 2021-07-16 20:00 | 2021-07-25 17:00 | F | 8.83
Moneypoint | MP3 | 285 | 2021-07-16 22:00 | 2021-07-28 22:00 | S | 12
Rhode | RP1 | 52 | 2021-07-17 15:30 | 2021-07-17 18:30 | F | 0.08
Rhode | RP2 | 52 | 2021-07-17 19:00 | 2021-07-19 10:00 | F | 1.58
Turlough Hill | TH2 | 73 | 2021-07-18 04:30 | 2021-07-18 13:00 | F | 0.33
Rhode | RP1 | 52 | 2021-07-18 11:30 | 2021-07-19 11:00 | F | 0.96
Tarbert | TB2 | 54 | 2021-07-19 | 2021-07-20 | F | 1
Turlough Hill | TH3 | 73 | 2021-07-20 10:00 | 2021-07-20 15:00 | S | 0.17
Moneypoint | MP2 | 285 | 2021-07-23 22:00 | 2021-08-01 22:00 | S | 9
Aghada | AT2 | 90 | 2021-08-01 18:00 | 2021-09-18 20:00 | S | 48.08
Tynagh | TYC | 384 | 2021-08-06 20:00 | 2021-08-08 20:00 | F | 2
Ardnacrusha | AA3 | 19 | 2021-08-09 08:00 | 2021-10-01 20:00 | S | 53.5
Tarbert | TB3 | 241 | 2021-08-09 09:00 | 2021-09-05 17:00 | S | 27.33
Aghada | AT1 | 90 | 2021-08-13 08:00 | 2021-08-28 20:00 | S | 15.5
Poolbeg | PB6 | 168 | 2021-08-14 21:00 | 2021-08-16 20:00 | 84 | 1.92
Poolbeg | PB5 | 146 | 2021-08-14 21:00 | 2021-08-16 20:00 | F | 1.92
Erne | ER2 | 10 | 2021-08-23 08:00 | 2021-08-27 20:00 | S | 4.5
Erne | ER1 | 10 | 2021-08-23 08:00 | 2021-08-27 20:00 | S | 4.5
EWIC | EW1 | 500 | 2021-08-23 09:00 | 2021-10-12 23:00 | S | 50.58
Poolbeg | PB4 | 154 | 2021-08-29 12:00 | 2021-09-17 18:00 | S | 19.25
Poolbeg | PB6 | 168 | 2021-08-29 12:00 | 2021-09-15 | 84 | 16.5
Liffey | LI5 | 4 | 2021-08-30 08:00 | 2021-09-03 17:00 | S | 4.33
Edenderry | ED5 | 58 | 2021-09-03 08:00 | 2021-09-03 18:00 | S | 0.42
Edenderry | ED3 | 58 | 2021-09-03 08:00 | 2021-09-03 18:00 | S | 0.42
Erne | ER4 | 22.5 | 2021-09-06 08:00 | 2021-09-10 20:00 | S | 4.5
Poolbeg | PB6 | 168 | 2021-09-15 | 2021-10-24 23:30 | S | 39.96
Moneypoint | MP1 | 285 | 2021-09-17 22:00 | 2021-09-29 22:00 | S | 12
Seal Rock | SK4 | 85 | 2021-09-27 06:00 | 2021-09-29 18:00 | S | 2.5
Moneypoint | MP1 | 285 | 2021-09-29 22:00 | 2021-10-07 22:00 | F | 8
Dublin Waste To Energy | DW1 | 61.5 | 2021-10-01 | 2021-10-10 | 26 | 9
Poolbeg | PB5 | 146 | 2021-10-02 | 2021-11-16 23:30 | S | 45.96
Turlough Hill | TH1 | 73 | 2021-10-04 08:00 | 2021-10-06 17:00 | S | 2.33
Turlough Hill | TH2 | 73 | 2021-10-04 08:00 | 2021-10-06 17:00 | S | 2.33
Dublin Waste To Energy | DW1 | 61.5 | 2021-10-10 | 2021-10-13 | S | 3
Dublin Waste To Energy | DW1 | 61.5 | 2021-10-13 | 2021-10-23 | 26 | 10
Poolbeg | PB6 | 168 | 2021-10-25 | 2021-11-16 23:30 | 84 | 22.96
Seal Rock | SK3 | 85 | 2021-11-08 06:00 | 2021-11-10 18:00 | S | 2.5
Poolbeg | PB5 | 146 | 2021-11-16 23:30 | 2021-11-28 | F | 11
Poolbeg | PB6 | 168 | 2021-11-16 23:30 | 2021-11-28 | 84 | 11
Edenderry | ED1 | 118 | 2021-12-26 13:00 | 2022-01-02 08:00 | S | 6.75
|  |  | Scheduled Outage | S
|  |  | Forced Outage | F
|  |  | Unit partially available | 10

## Outage Plan SONI
2021 GENERATION OUTAGE PLAN (SONI)
|  | Month | Jan '2021 |  |  |  |  | Feb '2021 |  |  |  | Mar '2021 |  |  |  |  | Apr '2021 |  |  |  | May '2021 |  |  |  |  | Jun '2021 |  |  |  | Jul '2021 |  |  |  | Aug '2021 |  |  |  |  | Sep '2021 |  |  |  | Oct '2021 |  |  |  | Nov '2021 |  |  |  |  | Dec '2021
|  | Week | 53 '2021 | 1 '2021 | 2 '2021 | 3 '2021 | 4 '2021 | 5 '2021 | 6 '2021 | 7 '2021 | 8 '2021 | 9 '2021 | 10 '2021 | 11 '2021 | 12 '2021 | 13 '2021 | 14 '2021 | 15 '2021 | 16 '2021 | 17 '2021 | 18 '2021 | 19 '2021 | 20 '2021 | 21 '2021 | 22 '2021 | 23 '2021 | 24 '2021 | 25 '2021 | 26 '2021 | 27 '2021 | 28 '2021 | 29 '2021 | 30 '2021 | 31 '2021 | 32 '2021 | 33 '2021 | 34 '2021 | 35 '2021 | 36 '2021 | 37 '2021 | 38 '2021 | 39 '2021 | 40 '2021 | 41 '2021 | 42 '2021 | 43 '2021 | 44 '2021 | 45 '2021 | 46 '2021 | 47 '2021 | 48 '2021 | 49 '2021 | 50 '2021 | 51 '2021 | 52 '2021
Station | Unit | NPR
AC Automation | NIACA | 8
Activation Energy | NIAEA | 9
Ballylumford | NIB10 | 94 | [25 empty] | S | S
Ballylumford | NIB31 | 249
Ballylumford | NIB32 | 249
Ballylumford | NIBGT1 | 58 | [33 empty] | S | [10 empty] | S
Ballylumford | NIBGT2 | 58 | [45 empty] | S
Contour Global | NICG2 | 3
Contour Global | NICGA | 12
Coolkeeragh | NIC30 | 408 | [8 empty] | F | F | [30 empty] | S | S | S | S
Coolkeeragh | NICGT8 | 53 | [19 empty] | S
Empower | NIEMP | 3
Endeco Technologies | NIECA | 13
Energy Trading | NIETB | 9
Energy Trading | NIETD | 5
Energy Trading | NIETR | 19
iPower | NIAGU | 74
Kilroot | NIK1 | 256 | [16 empty] | F
Kilroot | NIK2 | 258 | [20 empty] | S | S | S | S | S | S | S | S | F | F | F
Kilroot | NIKGT1 | 29 | [38 empty] | S | S | S | S | S | S
Kilroot | NIKGT2 | 29 | [20 empty] | S | S | S | S | S | S | S | S | F | F | F
Kilroot | NIKGT3 | 42 | [18 empty] | F | [27 empty] | S
Kilroot | NIKGT4 | 42 | [46 empty] | S
Lisahally | NILPS | 18 | [9 empty] | S | S
Moyle | MOYLE | 450 | [28 empty] | S
Powerhouse Generation | NIPH1 | 34

## SONI Outages
Upcoming Outages including STMOs and Annual Outages
Station | Unit | NPR | Start Date | End Date | Value | Duration
Lisahally | NILPS | 17.6 | 2021-01-03 02:00 | 2021-01-11 09:00 | 16 | 8.25
Kilroot | NIKGT4 | 42 | 2021-01-06 13:30 | 2021-01-06 17:00 | F | 0.12
Kilroot | NIK2 | 258 | 2021-01-06 15:30 | 2021-01-18 13:00 | 180 | 11.88
Kilroot | NIKGT4 | 42 | 2021-01-06 23:30 | 2021-01-07 16:30 | F | 0.67
Ballylumford | NIB32 | 249 | 2021-01-10 23:00 | 2021-01-11 19:00 | S | 0.83
Lisahally | NILPS | 17.6 | 2021-01-11 09:00 | 2021-01-12 07:30 | 15 | 0.92
Ballylumford | NIB32 | 249 | 2021-01-12 08:30 | 2021-01-12 09:30 | 60 | 0
Lisahally | NILPS | 17.6 | 2021-01-12 10:00 | 2021-01-12 14:30 | S | 0.17
Ballylumford | NIBGT1 | 58 | 2021-01-12 12:30 | 2021-01-12 15:00 | F | 0.08
Lisahally | NILPS | 17.6 | 2021-01-12 14:30 | 2021-01-12 22:00 | F | 0.29
Kilroot | NIKGT2 | 29 | 2021-01-12 16:30 | 2021-01-12 18:00 | F | 0.04
Kilroot | NIKGT1 | 29 | 2021-01-12 17:30 | 2021-01-12 18:30 | F | 0
Kilroot | NIKGT1 | 29 | 2021-01-12 19:00 | 2021-01-13 19:00 | F | 1
Lisahally | NILPS | 17.6 | 2021-01-12 23:30 | 2021-01-13 12:30 | 16 | 0.5
Lisahally | NILPS | 17.6 | 2021-01-13 12:30 | 2021-01-13 13:30 | 13 | 0
Lisahally | NILPS | 17.6 | 2021-01-13 13:30 | 2021-01-22 13:00 | 16 | 8.96
Kilroot | NIKGT2 | 29 | 2021-01-13 14:00 | 2021-01-13 16:00 | F | 0.08
Coolkeeragh | NIC30 | 408 | 2021-01-14 21:00 | 2021-01-15 06:30 | S | 0.38
Kilroot | NIKGT4 | 42 | 2021-01-15 06:30 | 2021-01-15 14:30 | F | 0.33
Coolkeeragh | NIC30 | 408 | 2021-01-15 20:00 | 2021-01-16 04:30 | S | 0.33
Moyle | MOYLE | 450 | 2021-01-16 08:00 | 2021-01-16 12:00 | 250 | 0.17
Ballylumford | NIB10 | 94 | 2021-01-16 11:00 | 2021-01-21 01:00 | F | 4.58
Ballylumford | NIB32 | 249 | 2021-01-17 09:00 | 2021-01-18 01:00 | 160 | 0.67
Lisahally | NILPS | 17.6 | 2021-01-22 13:00 | 2021-01-22 16:30 | 13 | 0.12
Lisahally | NILPS | 17.6 | 2021-01-22 16:30 | 2021-02-01 | 15 | 9.29
Ballylumford | NIB31 | 249 | 2021-01-22 20:00 | 2021-01-23 15:00 | S | 0.75
Kilroot | NIKGT2 | 29 | 2021-01-27 06:00 | 2021-01-27 10:30 | F | 0.17
Kilroot | NIKGT1 | 29 | 2021-01-28 06:00 | 2021-01-28 13:00 | S | 0.25
Kilroot | NIKGT1 | 29 | 2021-01-28 13:00 | 2021-01-28 14:00 | F | 0
Kilroot | NIKGT4 | 42 | 2021-01-29 06:00 | 2021-01-29 18:30 | S | 0.5
Kilroot | NIKGT3 | 42 | 2021-01-29 06:00 | 2021-01-29 18:30 | S | 0.5
Ballylumford | NIB31 | 249 | 2021-01-29 22:00 | 2021-01-30 14:30 | S | 0.67
Coolkeeragh | NIC30 | 408 | 2021-01-30 21:30 | 2021-01-31 05:00 | F | 0.29
Lisahally | NILPS | 17.6 | 2021-02-01 08:30 | 2021-02-01 23:00 | 13 | 0.58
Contour Global | NICGA | 12.08 | 2021-02-01 12:30 | 2021-02-02 09:00 | 6 | 0.83
Kilroot | NIK1 | 256 | 2021-02-01 18:30 | 2021-02-01 21:30 | 130 | 0.08
Kilroot | NIK2 | 258 | 2021-02-01 18:30 | 2021-02-01 21:30 | 130 | 0.08
Lisahally | NILPS | 17.6 | 2021-02-01 23:00 | 2021-02-01 23:30 | 14 | 0
Lisahally | NILPS | 17.6 | 2021-02-01 23:30 | 2021-02-03 10:00 | 15 | 1.42
Contour Global | NICGA | 12.08 | 2021-02-02 09:00 | 2021-03-05 23:30 | 9 | 31.58
Lisahally | NILPS | 17.6 | 2021-02-03 10:00 | 2021-02-03 23:30 | 13 | 0.54
Kilroot | NIK2 | 258 | 2021-02-03 12:30 | 2021-02-08 15:30 | 150 | 5.08
Kilroot | NIK1 | 256 | 2021-02-03 13:00 | 2021-02-08 13:30 | 175 | 5
Lisahally | NILPS | 17.6 | 2021-02-03 23:30 | 2021-02-04 00:30 | 14 | 0
Lisahally | NILPS | 17.6 | 2021-02-04 00:30 | 2021-02-04 05:00 | 15 | 0.17
Lisahally | NILPS | 17.6 | 2021-02-04 05:00 | 2021-02-04 12:00 | 16 | 0.25
Lisahally | NILPS | 17.6 | 2021-02-04 12:00 | 2021-02-09 08:30 | 15 | 4.83
Ballylumford | NIB32 | 249 | 2021-02-06 09:30 | 2021-02-06 15:00 | 159 | 0.21
Ballylumford | NIB31 | 249 | 2021-02-06 09:30 | 2021-02-06 13:00 | 159 | 0.12
Ballylumford | NIB31 | 249 | 2021-02-06 13:00 | 2021-02-06 14:00 | 15 | 0
Ballylumford | NIB32 | 249 | 2021-02-06 15:00 | 2021-02-06 16:00 | 15 | 0
Kilroot | NIK1 | 256 | 2021-02-08 13:30 | 2021-02-09 17:00 | 100 | 1.12
Lisahally | NILPS | 17.6 | 2021-02-09 08:30 | 2021-02-09 23:30 | 13 | 0.58
Lisahally | NILPS | 17.6 | 2021-02-09 23:30 | 2021-02-10 09:00 | 15 | 0.38
Lisahally | NILPS | 17.6 | 2021-02-10 09:00 | 2021-02-10 20:30 | 13 | 0.46
Lisahally | NILPS | 17.6 | 2021-02-10 20:30 | 2021-02-10 22:30 | 14 | 0.08
Lisahally | NILPS | 17.6 | 2021-02-10 22:30 | 2021-02-11 15:30 | 15 | 0.67
Lisahally | NILPS | 17.6 | 2021-02-11 15:30 | 2021-02-16 | 16 | 4.33
Kilroot | NIKGT3 | 42 | 2021-02-13 07:00 | 2021-02-13 18:30 | F | 0.46
Kilroot | NIKGT4 | 42 | 2021-02-14 07:00 | 2021-02-14 18:30 | F | 0.46
Ballylumford | NIB32 | 249 | 2021-02-15 14:00 | 2021-02-15 16:30 | F | 0.08
Lisahally | NILPS | 17.6 | 2021-02-16 | 2021-02-22 17:00 | 15 | 6.67
Ballylumford | NIB32 | 249 | 2021-02-16 21:30 | 2021-02-16 22:00 | F | 0
Ballylumford | NIB10 | 94 | 2021-02-16 22:00 | 2021-02-16 23:00 | F | 0
Ballylumford | NIB32 | 249 | 2021-02-16 22:00 | 2021-02-17 04:30 | S | 0.25
Coolkeeragh | NIC30 | 408 | 2021-02-19 20:00 | 2021-02-23 21:00 | S | 4
Lisahally | NILPS | 17.6 | 2021-02-22 17:00 | 2021-02-26 01:30 | 16 | 3.33
Coolkeeragh | NIC30 | 408 | 2021-02-23 21:00 | 2021-03-04 18:30 | F | 8.88
Ballylumford | NIB32 | 249 | 2021-02-24 11:30 | 2021-02-24 13:00 | F | 0.04
Lisahally | NILPS | 17.6 | 2021-02-26 01:30 | 2021-03-01 | 15 | 2.92
Kilroot | NIKGT3 | 42 | 2021-02-26 09:30 | 2021-02-27 00:30 | F | 0.58
Kilroot | NIK1 | 256 | 2021-02-26 17:30 | 2021-02-26 23:00 | 150 | 0.21
Ballylumford | NIB31 | 249 | 2021-02-27 04:00 | 2021-02-27 05:00 | 15 | 0
Kilroot | NIK1 | 256 | 2021-02-27 17:30 | 2021-02-27 22:30 | 120 | 0.17
Lisahally | NILPS | 17.6 | 2021-03-04 08:00 | 2021-03-14 18:30 | S | 10.42
Ballylumford | NIB32 | 249 | 2021-03-04 12:00 | 2021-03-04 14:00 | 130 | 0.08
Ballylumford | NIB31 | 249 | 2021-03-04 12:00 | 2021-03-04 14:30 | 155 | 0.08
Ballylumford | NIB32 | 249 | 2021-03-04 14:00 | 2021-03-04 20:00 | 161 | 0.25
Kilroot | NIK2 | 258 | 2021-03-04 22:00 | 2021-03-06 21:30 | F | 1.96
Ballylumford | NIBGT2 | 58 | 2021-03-06 20:00 | 2021-03-06 21:30 | F | 0.04
Ballylumford | NIBGT1 | 58 | 2021-03-06 20:00 | 2021-03-06 21:30 | F | 0.04
Ballylumford | NIB31 | 249 | 2021-03-06 20:00 | 2021-03-09 02:00 | F | 2.25
Kilroot | NIK2 | 258 | 2021-03-06 21:30 | 2021-03-11 04:30 | F | 4.25
Ballylumford | NIBGT1 | 58 | 2021-03-08 12:00 | 2021-03-08 13:30 | F | 0.04
Ballylumford | NIBGT2 | 58 | 2021-03-08 12:00 | 2021-03-08 13:30 | F | 0.04
Ballylumford | NIB31 | 249 | 2021-03-10 19:00 | 2021-03-10 22:00 | F | 0.08
Kilroot | NIK2 | 258 | 2021-03-11 14:00 | 2021-03-11 16:30 | F | 0.08
Kilroot | NIK1 | 256 | 2021-03-11 22:00 | 2021-03-14 | F | 2.08
Kilroot | NIKGT1 | 29 | 2021-03-12 06:00 | 2021-03-12 16:30 | F | 0.42
Kilroot | NIK1 | 256 | 2021-03-14 | 2021-03-14 23:30 | F | 0.96
Lisahally | NILPS | 17.6 | 2021-03-14 18:30 | 2021-03-15 18:30 | F | 1
Kilroot | NIK2 | 258 | 2021-03-15 08:00 | 2021-03-16 08:30 | 93 | 1
Kilroot | NIKGT3 | 42 | 2021-03-25 08:00 | 2021-03-25 11:30 | F | 0.12
Kilroot | NIKGT3 | 42 | 2021-04-02 11:00 | 2021-04-02 17:30 | F | 0.25
Ballylumford | NIB10 | 94 | 2021-04-02 13:00 | 2021-04-02 14:00 | F | 0
Coolkeeragh | NICGT8 | 53 | 2021-04-06 17:00 | 2021-04-06 18:00 | F | 0
Ballylumford | NIB31 | 249 | 2021-04-09 20:00 | 2021-04-11 00:30 | 159 | 1.17
Kilroot | NIK1 | 256 | 2021-04-15 22:00 | 2021-04-16 22:30 | F | 1
Coolkeeragh | NIC30 | 408 | 2021-04-17 04:00 | 2021-04-18 | S | 0.83
Kilroot | NIK1 | 256 | 2021-04-17 04:30 | 2021-04-18 04:30 | F | 1
Kilroot | NIK2 | 258 | 2021-04-18 | 2021-04-19 02:30 | F | 1.08
Kilroot | NIK1 | 256 | 2021-04-18 20:30 | 2021-04-23 07:00 | F | 4.42
Moyle | MOYLE | 450 | 2021-04-21 09:00 | 2021-04-21 12:30 | 250 | 0.12
Kilroot | NIKGT3 | 42 | 2021-04-22 20:30 | 2021-04-23 10:30 | F | 0.58
Ballylumford | NIB31 | 249 | 2021-04-22 20:30 | 2021-04-23 01:30 | F | 0.17
Kilroot | NIKGT3 | 42 | 2021-04-23 10:30 | 2021-04-23 13:00 | F | 0.08
Kilroot | NIKGT3 | 42 | 2021-04-29 06:00 | 2021-04-29 18:30 | F | 0.5
Kilroot | NIKGT4 | 42 | 2021-04-30 14:00 | 2021-04-30 15:30 | F | 0.04
Kilroot | NIKGT3 | 42 | 2021-05-03 20:30 | 2021-05-12 15:00 | F | 8.75
Ballylumford | NIBGT2 | 58 | 2021-05-04 15:30 | 2021-05-04 17:30 | F | 0.08
Coolkeeragh | NIC30 | 408 | 2021-05-04 20:00 | 2021-05-05 00:30 | F | 0.17
Coolkeeragh | NICGT8 | 53 | 2021-05-04 20:30 | 2021-05-05 00:30 | F | 0.17
Kilroot | NIK1 | 256 | 2021-05-06 20:00 | 2021-05-09 | F | 2.17
Coolkeeragh | NICGT8 | 53 | 2021-05-07 09:00 | 2021-05-07 13:30 | S | 0.17
Kilroot | NIKGT4 | 42 | 2021-05-07 09:30 | 2021-05-07 11:30 | F | 0.08
Kilroot | NIK1 | 256 | 2021-05-09 | 2021-05-10 13:00 | 199 | 1.5
Coolkeeragh | NICGT8 | 53 | 2021-05-10 04:00 | 2021-05-17 21:00 | S | 7.67
Kilroot | NIK1 | 256 | 2021-05-10 13:00 | 2021-05-11 08:30 | F | 0.79
Ballylumford | NIB32 | 249 | 2021-05-10 16:00 | 2021-05-10 17:00 | 157 | 0
Ballylumford | NIB31 | 249 | 2021-05-10 16:00 | 2021-05-10 17:00 | 157 | 0
Kilroot | NIK2 | 258 | 2021-05-10 22:00 | 2021-05-14 20:00 | 93 | 3.92
Ballylumford | NIBGT1 | 58 | 2021-05-12 08:00 | 2021-05-12 09:30 | F | 0.04
Kilroot | NIK2 | 258 | 2021-05-14 20:00 | 2021-07-09 20:30 | S | 56
Kilroot | NIKGT2 | 29 | 2021-05-16 06:00 | 2021-07-09 20:30 | S | 54.58
Ballylumford | NIBGT2 | 58 | 2021-05-19 08:00 | 2021-05-19 12:30 | F | 0.17
Ballylumford | NIB10 | 94 | 2021-05-22 19:00 | 2021-05-23 19:30 | F | 1
Coolkeeragh | NICGT8 | 53 | 2021-05-24 10:30 | 2021-05-24 15:00 | S | 0.17
Ballylumford | NIBGT1 | 58 | 2021-05-24 15:30 | 2021-05-24 21:30 | F | 0.25
Coolkeeragh | NICGT8 | 53 | 2021-05-25 06:30 | 2021-05-26 14:30 | S | 1.33
Coolkeeragh | NIC30 | 408 | 2021-05-26 04:30 | 2021-05-26 07:00 | F | 0.08
Kilroot | NIKGT3 | 42 | 2021-05-27 10:00 | 2021-05-27 15:30 | S | 0.21
Ballylumford | NIB32 | 249 | 2021-05-27 16:00 | 2021-05-28 06:00 | 176 | 0.58
Ballylumford | NIB32 | 249 | 2021-05-28 06:00 | 2021-05-28 18:30 | F | 0.5
Ballylumford | NIB31 | 249 | 2021-06-01 06:00 | 2021-06-01 14:30 | S | 0.33
Ballylumford | NIBGT1 | 58 | 2021-06-02 08:00 | 2021-06-02 10:30 | F | 0.08
Moyle | MOYLE | 450 | 2021-06-03 12:00 | 2021-06-03 17:00 | 250 | 0.17
Kilroot | NIKGT1 | 29 | 2021-06-04 20:00 | 2021-06-09 08:30 | S | 4.5
Kilroot | NIK1 | 256 | 2021-06-04 20:00 | 2021-06-10 12:30 | S | 5.67
Kilroot | NIKGT1 | 29 | 2021-06-09 08:30 | 2021-06-10 08:00 | F | 0.96
Kilroot | NIK1 | 256 | 2021-06-10 12:30 | 2021-06-16 20:30 | F | 6.33
Ballylumford | NIB10 | 94 | 2021-06-16 04:30 | 2021-06-17 05:30 | F | 1
Ballylumford | NIB31 | 249 | 2021-06-17 19:00 | 2021-06-20 23:30 | S | 3.17
Coolkeeragh | NIC30 | 408 | 2021-06-19 08:00 | 2021-06-19 21:30 | S | 0.54
Ballylumford | NIB10 | 94 | 2021-06-21 20:00 | 2021-07-01 20:30 | S | 10
Coolkeeragh | NIC30 | 408 | 2021-06-21 22:00 | 2021-06-22 04:30 | S | 0.25
Coolkeeragh | NIC30 | 408 | 2021-06-22 04:30 | 2021-06-22 14:30 | F | 0.42
Kilroot | NIKGT3 | 42 | 2021-06-30 06:00 | 2021-06-30 18:30 | F | 0.5
Kilroot | NIKGT4 | 42 | 2021-07-03 06:00 | 2021-07-03 18:30 | F | 0.5
Ballylumford | NIB10 | 94 | 2021-07-07 02:30 | 2021-07-08 14:00 | F | 1.46
Kilroot | NIK2 | 258 | 2021-07-09 20:30 | 2021-07-30 20:30 | F | 21
Kilroot | NIKGT2 | 29 | 2021-07-09 20:30 | 2021-07-30 20:30 | F | 21
Moyle | MOYLE | 450 | 2021-07-12 08:30 | 2021-07-19 17:00 | S | 7.33
Ballylumford | NIB31 | 249 | 2021-07-19 20:00 | 2021-08-02 20:30 | 161 | 14
Ballylumford | NIB32 | 249 | 2021-07-19 20:00 | 2021-08-02 20:30 | 161 | 14
Coolkeeragh | NIC30 | 408 | 2021-08-07 16:00 | 2021-08-08 22:30 | S | 1.25
Ballylumford | NIBGT2 | 58 | 2021-08-10 08:00 | 2021-08-11 08:30 | S | 1
Ballylumford | NIBGT1 | 58 | 2021-08-16 07:00 | 2021-08-21 07:00 | S | 5
Ballylumford | NIBGT2 | 58 | 2021-08-21 07:00 | 2021-08-26 07:30 | S | 5
Kilroot | NIKGT1 | 29 | 2021-09-18 06:00 | 2021-10-30 17:30 | S | 42.46
Coolkeeragh | NIC30 | 408 | 2021-10-05 | 2021-10-30 | S | 25
Coolkeeragh | NICGT8 | 53 | 2021-10-30 | 2021-11-01 | S | 2
Ballylumford | NIBGT1 | 58 | 2021-11-02 03:00 | 2021-11-08 | S | 5.83
Ballylumford | NIBGT2 | 58 | 2021-11-08 | 2021-11-15 | S | 7
Kilroot | NIKGT4 | 42 | 2021-11-15 | 2021-11-22 | S | 7
Kilroot | NIKGT3 | 42 | 2021-11-15 | 2021-11-22 | S | 7
Coolkeeragh | NIC30 | 408 | 2021-11-28 | 2021-11-29 | S | 1
|  |  | Scheduled Outage | S
|  |  | Forced Outage | F
|  |  | Unit partially available | 10

## Outage Plan All Island
2021 GENERATION OUTAGE PLAN (All Island)
|  | Month | Jan '2021 |  |  |  |  | Feb '2021 |  |  |  | Mar '2021 |  |  |  |  | Apr '2021 |  |  |  | May '2021 |  |  |  |  | Jun '2021 |  |  |  | Jul '2021 |  |  |  | Aug '2021 |  |  |  |  | Sep '2021 |  |  |  | Oct '2021 |  |  |  | Nov '2021 |  |  |  |  | Dec '2021
|  | Week | 53 '2021 | 1 '2021 | 2 '2021 | 3 '2021 | 4 '2021 | 5 '2021 | 6 '2021 | 7 '2021 | 8 '2021 | 9 '2021 | 10 '2021 | 11 '2021 | 12 '2021 | 13 '2021 | 14 '2021 | 15 '2021 | 16 '2021 | 17 '2021 | 18 '2021 | 19 '2021 | 20 '2021 | 21 '2021 | 22 '2021 | 23 '2021 | 24 '2021 | 25 '2021 | 26 '2021 | 27 '2021 | 28 '2021 | 29 '2021 | 30 '2021 | 31 '2021 | 32 '2021 | 33 '2021 | 34 '2021 | 35 '2021 | 36 '2021 | 37 '2021 | 38 '2021 | 39 '2021 | 40 '2021 | 41 '2021 | 42 '2021 | 43 '2021 | 44 '2021 | 45 '2021 | 46 '2021 | 47 '2021 | 48 '2021 | 49 '2021 | 50 '2021 | 51 '2021 | 52 '2021
Station | Unit | NPR
AC Automation | NIACA | 8
Activation Energy | AE1 | 95
Activation Energy | AE2 | 12
Activation Energy | AE3 | 14
Activation Energy | AE4 | 15
Activation Energy | AE5 | 15
Activation Energy | EN1 | 15
Activation Energy | EN2 | 16
Activation Energy | EN3 | 16
Activation Energy | EN4 | 16
Activation Energy | EN5 | 6
Activation Energy | EN6 | 11
Activation Energy | NIAEA | 9
Aghada | AD2 | 449 | [7 empty] | F | [11 empty] | S | S | S
Aghada | AT1 | 90 | [33 empty] | S | S
Aghada | AT2 | 90 | [31 empty] | S | S | S | S | S | S | S
Aghada | AT4 | 90 | [15 empty] | F | F
Ardnacrusha | AA1 | 21 | [28 empty] | S
Ardnacrusha | AA2 | 22 | [23 empty] | S | S | S
Ardnacrusha | AA3 | 19 | [32 empty] | S | S | S | S | S | S | S | S
Ardnacrusha | AA4 | 24 | [7 empty] | F | F | F | F | F | F | F | S | S | S | S | S | S | S | S | F | F | F | F | F | F | F | F | F
Ballylumford | NIB10 | 94 | [25 empty] | S | S
Ballylumford | NIB31 | 249
Ballylumford | NIB32 | 249
Ballylumford | NIBGT1 | 58 | [33 empty] | S | [10 empty] | S
Ballylumford | NIBGT2 | 58 | [45 empty] | S
Contour Global | NICG2 | 3
Contour Global | NICGA | 12
Coolkeeragh | NIC30 | 408 | [8 empty] | F | F | [30 empty] | S | S | S | S
Coolkeeragh | NICGT8 | 53 | [19 empty] | S
DAE Virtual Power Plant | DP1 | 19
DAE Virtual Power Plant | DP2 | 26
Dublin Bay | DB1 | 405 | [17 empty] | S | S | S | S | S | S | S | S | S | F | F | F | F | F | F
Dublin Waste To Energy | DW1 | 62 | [22 empty] | F |  | S | S | S
Edenderry | ED1 | 118 | [13 empty] | F | [12 empty] | F | S | S | S | S | S | S | S | S | [17 empty] | S
Edenderry | ED3 | 58 | [27 empty] | F
Edenderry | ED5 | 58
Electric Ireland | EI1 | 20
Electricity Exchange DSU | EE1 | 47
Electricity Exchange DSU | EE2 | 20
Electricity Exchange DSU | EE3 | 8
Electricity Exchange DSU | EE4 | 9
Electricity Exchange DSU | EE5 | 7
Electricity Exchange DSU | EE6 | 14
Empower | NIEMP | 3
Endeco Technologies | EC1 | 47
Endeco Technologies | EC2 | 11
Endeco Technologies | EC5 | 15
Endeco Technologies | NIECA | 13
Energy Trading | ET1 | 13
Energy Trading | NIETB | 9
Energy Trading | NIETD | 5
Energy Trading | NIETR | 19
Erne | ER1 | 10 | [15 empty] | S | S | F | [16 empty] | S
Erne | ER2 | 10 | [34 empty] | S
Erne | ER3 | 22 | [24 empty] | S | S | S
Erne | ER4 | 22 | [36 empty] | S
EWIC | EW1 | 500 | [34 empty] | S | S | S | S | S | S | S
Great Island | GI4 | 461
Huntstown | HN2 | 400 | [5 empty] | F | F | F | F | S | S | S | S | S | S | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F
Huntstown | HNC | 342
Indaver | IW1 | 17
iPower | NIAGU | 74
Kilroot | NIK1 | 256 | [16 empty] | F
Kilroot | NIK2 | 258 | [20 empty] | S | S | S | S | S | S | S | S | F | F | F
Kilroot | NIKGT1 | 29 | [38 empty] | S | S | S | S | S | S
Kilroot | NIKGT2 | 29 | [20 empty] | S | S | S | S | S | S | S | S | F | F | F
Kilroot | NIKGT3 | 42 | [18 empty] | F | [27 empty] | S
Kilroot | NIKGT4 | 42 | [46 empty] | S
Knockacummer | KC1 | 100
Lee | LE1 | 15 | [12 empty] | F |  |  | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F
Lee | LE2 | 4 | [11 empty] | F |  |  | S | S | F | F | F | F | F | F | F | F | F | F | F | F | F
Lee | LE3 | 8 | [24 empty] | S | S | S | S | S | F
Liffey | LI1 | 15 | [15 empty] | S | S | S | S | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F
Liffey | LI2 | 15 | [15 empty] | S | S | S | S | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F
Liffey | LI4 | 4
Liffey | LI5 | 4 | [20 empty] | F | F | F | F | F | F | F | F | F | F | [5 empty] | S
Lisahally | NILPS | 18 | [9 empty] | S | S
Moneypoint | MP1 | 285 | [10 empty] | F | F | [11 empty] | F | [14 empty] | S | F | F
Moneypoint | MP2 | 285 |  | F | F | [6 empty] | F |  |  | F | [5 empty] | F | F |  |  |  |  | F | [5 empty] | S
Moneypoint | MP3 | 285 | [6 empty] | F | [21 empty] | F | S
Moyle | MOYLE | 450 | [28 empty] | S
Poolbeg | PB4 | 154 |  |  |  | F | F | [30 empty] | S | S | S
Poolbeg | PB5 | 146 | [14 empty] | S | [25 empty] | S | S | S | S | S | S | F | F
Poolbeg | PB6 | 168 | [5 empty] | F | F | F | F | [28 empty] | S | S | S | S | S | S
Powerhouse Generation | NIPH1 | 34
Powerhouse Generation | PG1 | 10
Rhode | RP1 | 52 | [22 empty] | S | S | S | S | F | F | F
Rhode | RP2 | 52 | [22 empty] | S | S | S | S
Seal Rock | SK3 | 85 | [24 empty] | S | S
Seal Rock | SK4 | 85 | [27 empty] | S
Seecon | SO1 | 105
Tarbert | TB1 | 54 | [21 empty] | F | F | F
Tarbert | TB2 | 54 | [21 empty] | F | F | F
Tarbert | TB3 | 241 | [32 empty] | S | S | S | S
Tarbert | TB4 | 243 | [7 empty] | F | F | [6 empty] | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F
Tawnaghmore | TP1 | 52 | [15 empty] | S | S | S | S | F | F
Tawnaghmore | TP3 | 52 | [15 empty] | S | S | S | S | F | F
Turlough Hill | TH1 | 73 | [12 empty] | S
Turlough Hill | TH2 | 73 | [12 empty] | S
Turlough Hill | TH3 | 73 | [12 empty] | S
Turlough Hill | TH4 | 73 | [12 empty] | S
Tynagh | TYC | 384 | [15 empty] | S | S | S | F
Viridian Energy | VE1 | 20
Viridian Energy DSU | VE2 | 13
Whitegate | WG1 | 444 | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F

## All Island Outages
Upcoming Outages including STMOs and Annual Outages
Station | Unit | NPR | Start Date | End Date | Value | Duration
Whitegate | WG1 | 444 | 2020-12-02 08:00 | 2021-11-04 23:00 | F | 337.58
Tarbert | TB3 | 241 | 2020-12-08 14:30 | 2021-01-08 21:30 | 226 | 31.25
Moneypoint | MP1 | 285 | 2020-12-20 20:00 | 2021-01-04 17:00 | 200 | 14.83
Moneypoint | MP2 | 285 | 2020-12-24 18:00 | 2021-01-04 15:00 | 120 | 10.83
Moneypoint | MP3 | 285 | 2020-12-30 06:30 | 2021-01-04 11:00 | 240 | 5.17
EWIC | EW1 | 500 | 2021-01-02 09:00 | 2021-01-02 20:00 | F | 0.42
Tarbert | TB4 | 243 | 2021-01-02 09:30 | 2021-01-02 11:30 | F | 0.08
Turlough Hill | TH1 | 73 | 2021-01-02 16:30 | 2021-01-03 11:00 | F | 0.75
Lisahally | NILPS | 17.6 | 2021-01-03 02:00 | 2021-01-11 09:00 | 16 | 8.25
Liffey | LI2 | 15 | 2021-01-04 08:00 | 2021-01-04 09:30 | F | 0.04
Moneypoint | MP3 | 285 | 2021-01-04 10:30 | 2021-01-19 21:00 | 270 | 15.42
Moneypoint | MP2 | 285 | 2021-01-04 15:00 | 2021-01-06 15:30 | F | 2
Moneypoint | MP1 | 285 | 2021-01-04 17:00 | 2021-01-06 15:30 | 220 | 1.92
Tarbert | TB2 | 54 | 2021-01-06 09:00 | 2021-01-06 11:00 | F | 0.08
Kilroot | NIKGT4 | 42 | 2021-01-06 13:30 | 2021-01-06 17:00 | F | 0.12
Moneypoint | MP2 | 285 | 2021-01-06 15:30 | 2021-01-07 10:30 | 120 | 0.75
Moneypoint | MP1 | 285 | 2021-01-06 15:30 | 2021-01-06 16:30 | F | 0
Tarbert | TB2 | 54 | 2021-01-06 15:30 | 2021-01-06 17:30 | F | 0.08
Kilroot | NIK2 | 258 | 2021-01-06 15:30 | 2021-01-18 13:00 | 180 | 11.88
Tarbert | TB4 | 243 | 2021-01-06 16:00 | 2021-01-07 12:00 | 222 | 0.83
Moneypoint | MP1 | 285 | 2021-01-06 16:30 | 2021-01-09 12:00 | 220 | 2.79
Kilroot | NIKGT4 | 42 | 2021-01-06 23:30 | 2021-01-07 16:30 | F | 0.67
Aghada | AT1 | 90 | 2021-01-07 04:00 | 2021-01-08 07:30 | F | 1.12
Aghada | AT2 | 90 | 2021-01-07 04:00 | 2021-01-07 19:30 | F | 0.62
Moneypoint | MP2 | 285 | 2021-01-07 10:30 | 2021-01-19 22:00 | F | 12.46
Tarbert | TB4 | 243 | 2021-01-07 12:00 | 2021-01-08 12:00 | F | 1
Tarbert | TB2 | 54 | 2021-01-07 16:00 | 2021-01-08 19:30 | F | 1.12
Dublin Waste To Energy | DW1 | 61.5 | 2021-01-08 05:00 | 2021-01-08 06:30 | S | 0.04
Tarbert | TB4 | 243 | 2021-01-08 12:00 | 2021-01-11 12:00 | 222 | 3
Huntstown | HN2 | 400 | 2021-01-08 21:00 | 2021-01-10 21:00 | S | 2
Tarbert | TB3 | 241 | 2021-01-08 21:30 | 2021-01-08 22:30 | F | 0
Tarbert | TB3 | 241 | 2021-01-08 22:30 | 2021-02-04 09:00 | 226 | 26.42
Erne | ER1 | 10 | 2021-01-09 08:30 | 2021-01-09 17:00 | S | 0.33
Erne | ER2 | 10 | 2021-01-09 08:30 | 2021-01-09 17:00 | S | 0.33
Seal Rock | SK4 | 85 | 2021-01-09 09:30 | 2021-02-09 12:30 | 60 | 31.08
Seal Rock | SK3 | 85 | 2021-01-09 09:30 | 2021-01-09 12:30 | 60 | 0.08
Moneypoint | MP1 | 285 | 2021-01-09 12:00 | 2021-01-09 16:30 | 230 | 0.17
Moneypoint | MP1 | 285 | 2021-01-09 16:30 | 2021-01-19 21:00 | 240 | 10.17
Rhode | RP2 | 52 | 2021-01-09 17:00 | 2021-01-11 10:30 | 25 | 1.71
Erne | ER1 | 10 | 2021-01-09 23:30 | 2021-01-10 09:00 | 6 | 0.38
Erne | ER1 | 10 | 2021-01-10 08:30 | 2021-01-10 18:00 | S | 0.38
Erne | ER2 | 10 | 2021-01-10 08:30 | 2021-01-10 17:00 | S | 0.33
Turlough Hill | TH1 | 73 | 2021-01-10 16:30 | 2021-01-11 12:00 | F | 0.79
Ballylumford | NIB32 | 249 | 2021-01-10 23:00 | 2021-01-11 19:00 | S | 0.83
Erne | ER3 | 22.5 | 2021-01-11 03:30 | 2021-01-11 09:00 | 10 | 0.21
Liffey | LI4 | 4 | 2021-01-11 07:00 | 2021-01-11 18:00 | S | 0.42
Liffey | LI2 | 15 | 2021-01-11 07:00 | 2021-01-11 18:00 | S | 0.42
Liffey | LI1 | 15 | 2021-01-11 07:00 | 2021-01-11 18:00 | S | 0.42
Erne | ER1 | 10 | 2021-01-11 08:30 | 2021-01-11 17:00 | S | 0.33
Erne | ER2 | 10 | 2021-01-11 08:30 | 2021-01-11 17:00 | S | 0.33
Lee | LE2 | 4 | 2021-01-11 09:00 | 2021-01-11 13:00 | F | 0.17
Lisahally | NILPS | 17.6 | 2021-01-11 09:00 | 2021-01-12 07:30 | 15 | 0.92
Tarbert | TB4 | 243 | 2021-01-11 12:00 | 2021-01-11 22:00 | 209 | 0.42
Tarbert | TB4 | 243 | 2021-01-11 22:00 | 2021-01-11 23:30 | F | 0.04
Tarbert | TB4 | 243 | 2021-01-11 23:30 | 2021-01-15 10:00 | 209 | 3.42
Erne | ER1 | 10 | 2021-01-12 08:30 | 2021-01-12 17:00 | S | 0.33
Erne | ER2 | 10 | 2021-01-12 08:30 | 2021-01-12 17:00 | S | 0.33
Ballylumford | NIB32 | 249 | 2021-01-12 08:30 | 2021-01-12 09:30 | 60 | 0
Lisahally | NILPS | 17.6 | 2021-01-12 10:00 | 2021-01-12 14:30 | S | 0.17
Ballylumford | NIBGT1 | 58 | 2021-01-12 12:30 | 2021-01-12 15:00 | F | 0.08
Lisahally | NILPS | 17.6 | 2021-01-12 14:30 | 2021-01-12 22:00 | F | 0.29
Kilroot | NIKGT2 | 29 | 2021-01-12 16:30 | 2021-01-12 18:00 | F | 0.04
Tarbert | TB2 | 54 | 2021-01-12 17:30 | 2021-01-12 19:30 | F | 0.08
Kilroot | NIKGT1 | 29 | 2021-01-12 17:30 | 2021-01-12 18:30 | F | 0
Kilroot | NIKGT1 | 29 | 2021-01-12 19:00 | 2021-01-13 19:00 | F | 1
Lisahally | NILPS | 17.6 | 2021-01-12 23:30 | 2021-01-13 12:30 | 16 | 0.5
Lisahally | NILPS | 17.6 | 2021-01-13 12:30 | 2021-01-13 13:30 | 13 | 0
Lisahally | NILPS | 17.6 | 2021-01-13 13:30 | 2021-01-22 13:00 | 16 | 8.96
Kilroot | NIKGT2 | 29 | 2021-01-13 14:00 | 2021-01-13 16:00 | F | 0.08
Tarbert | TB2 | 54 | 2021-01-14 12:00 | 2021-01-14 14:00 | F | 0.08
Coolkeeragh | NIC30 | 408 | 2021-01-14 21:00 | 2021-01-15 06:30 | S | 0.38
Kilroot | NIKGT4 | 42 | 2021-01-15 06:30 | 2021-01-15 14:30 | F | 0.33
Tarbert | TB4 | 243 | 2021-01-15 10:00 | 2021-01-19 03:00 | F | 3.67
Coolkeeragh | NIC30 | 408 | 2021-01-15 20:00 | 2021-01-16 04:30 | S | 0.33
Moyle | MOYLE | 450 | 2021-01-16 08:00 | 2021-01-16 12:00 | 250 | 0.17
Ballylumford | NIB10 | 94 | 2021-01-16 11:00 | 2021-01-21 01:00 | F | 4.58
Ballylumford | NIB32 | 249 | 2021-01-17 09:00 | 2021-01-18 01:00 | 160 | 0.67
Poolbeg | PB6 | 168 | 2021-01-18 17:30 | 2021-02-02 17:00 | 84 | 14.96
Tarbert | TB4 | 243 | 2021-01-19 03:00 | 2021-01-20 09:30 | 237 | 1.25
Poolbeg | PB4 | 154 | 2021-01-19 12:00 | 2021-02-02 17:00 | F | 14.17
Moneypoint | MP3 | 285 | 2021-01-19 21:00 | 2021-01-21 09:00 | 230 | 1.5
Moneypoint | MP1 | 285 | 2021-01-19 21:00 | 2021-01-21 09:00 | 200 | 1.5
Moneypoint | MP2 | 285 | 2021-01-19 22:00 | 2021-02-03 13:00 | 120 | 14.58
Dublin Waste To Energy | DW1 | 61.5 | 2021-01-21 05:00 | 2021-01-24 07:00 | 52 | 3.08
Great Island | GI4 | 461 | 2021-01-21 06:00 | 2021-01-21 08:30 | F | 0.08
Moneypoint | MP3 | 285 | 2021-01-21 09:00 | 2021-02-04 03:00 | 260 | 13.75
Moneypoint | MP1 | 285 | 2021-01-21 09:00 | 2021-01-27 12:00 | 230 | 6.08
Edenderry | ED1 | 118 | 2021-01-22 09:00 | 2021-01-22 15:00 | 65 | 0.25
Lisahally | NILPS | 17.6 | 2021-01-22 13:00 | 2021-01-22 16:30 | 13 | 0.12
Lisahally | NILPS | 17.6 | 2021-01-22 16:30 | 2021-02-01 | 15 | 9.29
Ballylumford | NIB31 | 249 | 2021-01-22 20:00 | 2021-01-23 15:00 | S | 0.75
Tarbert | TB4 | 243 | 2021-01-23 19:30 | 2021-01-25 01:00 | F | 1.21
Dublin Waste To Energy | DW1 | 61.5 | 2021-01-24 07:00 | 2021-01-26 09:00 | 22 | 2.08
Ardnacrusha | AA3 | 19 | 2021-01-24 10:00 | 2021-01-24 11:30 | F | 0.04
Huntstown | HNC | 342 | 2021-01-24 10:00 | 2021-01-24 11:00 | F | 0
Huntstown | HNC | 342 | 2021-01-24 11:00 | 2021-01-24 17:00 | F | 0.25
Tawnaghmore | TP1 | 52 | 2021-01-24 13:00 | 2021-01-24 14:30 | F | 0.04
Edenderry | ED1 | 118 | 2021-01-25 | 2021-01-25 12:00 | 55 | 0.5
Seal Rock | SK4 | 85 | 2021-01-26 06:00 | 2021-01-29 17:00 | S | 3.42
Tarbert | TB4 | 243 | 2021-01-26 13:00 | 2021-02-03 10:30 | 217 | 7.88
Huntstown | HNC | 342 | 2021-01-26 15:00 | 2021-01-26 17:00 | F | 0.08
Kilroot | NIKGT2 | 29 | 2021-01-27 06:00 | 2021-01-27 10:30 | F | 0.17
Moneypoint | MP1 | 285 | 2021-01-27 12:00 | 2021-01-27 13:00 | 205 | 0
Moneypoint | MP1 | 285 | 2021-01-27 13:00 | 2021-01-29 17:30 | 235 | 2.17
Kilroot | NIKGT1 | 29 | 2021-01-28 06:00 | 2021-01-28 13:00 | S | 0.25
Huntstown | HNC | 342 | 2021-01-28 07:00 | 2021-01-28 11:30 | F | 0.17
Turlough Hill | TH2 | 73 | 2021-01-28 10:00 | 2021-01-28 15:00 | S | 0.17
Kilroot | NIKGT1 | 29 | 2021-01-28 13:00 | 2021-01-28 14:00 | F | 0
Kilroot | NIKGT4 | 42 | 2021-01-29 06:00 | 2021-01-29 18:30 | S | 0.5
Kilroot | NIKGT3 | 42 | 2021-01-29 06:00 | 2021-01-29 18:30 | S | 0.5
Moneypoint | MP1 | 285 | 2021-01-29 17:30 | 2021-01-31 13:30 | 250 | 1.83
Huntstown | HN2 | 400 | 2021-01-29 22:00 | 2021-02-28 23:00 | F | 30
Ballylumford | NIB31 | 249 | 2021-01-29 22:00 | 2021-01-30 14:30 | S | 0.67
Coolkeeragh | NIC30 | 408 | 2021-01-30 21:30 | 2021-01-31 05:00 | F | 0.29
Moneypoint | MP1 | 285 | 2021-01-31 13:30 | 2021-01-31 19:30 | 200 | 0.25
Moneypoint | MP1 | 285 | 2021-01-31 19:30 | 2021-02-04 17:00 | 220 | 3.88
Dublin Waste To Energy | DW1 | 61.5 | 2021-02-01 04:30 | 2021-02-01 09:00 | 45 | 0.17
Lisahally | NILPS | 17.6 | 2021-02-01 08:30 | 2021-02-01 23:00 | 13 | 0.58
Tarbert | TB1 | 54 | 2021-02-01 09:00 | 2021-02-01 12:00 | F | 0.08
Contour Global | NICGA | 12.08 | 2021-02-01 12:30 | 2021-02-02 09:00 | 6 | 0.83
Kilroot | NIK1 | 256 | 2021-02-01 18:30 | 2021-02-01 21:30 | 130 | 0.08
Kilroot | NIK2 | 258 | 2021-02-01 18:30 | 2021-02-01 21:30 | 130 | 0.08
Lisahally | NILPS | 17.6 | 2021-02-01 23:00 | 2021-02-01 23:30 | 14 | 0
Lisahally | NILPS | 17.6 | 2021-02-01 23:30 | 2021-02-03 10:00 | 15 | 1.42
Contour Global | NICGA | 12.08 | 2021-02-02 09:00 | 2021-03-05 23:30 | 9 | 31.58
Turlough Hill | TH1 | 73 | 2021-02-02 10:00 | 2021-02-02 12:30 | S | 0.08
Liffey | LI5 | 4 | 2021-02-03 09:00 | 2021-02-03 13:00 | F | 0.17
Lisahally | NILPS | 17.6 | 2021-02-03 10:00 | 2021-02-03 23:30 | 13 | 0.54
Poolbeg | PB6 | 168 | 2021-02-03 11:30 | 2021-03-03 16:30 | F | 28.17
Poolbeg | PB4 | 154 | 2021-02-03 11:30 | 2021-02-03 17:00 | F | 0.21
Kilroot | NIK2 | 258 | 2021-02-03 12:30 | 2021-02-08 15:30 | 150 | 5.08
Kilroot | NIK1 | 256 | 2021-02-03 13:00 | 2021-02-08 13:30 | 175 | 5
Tarbert | TB1 | 54 | 2021-02-03 16:00 | 2021-02-03 17:00 | F | 0
Lisahally | NILPS | 17.6 | 2021-02-03 23:30 | 2021-02-04 00:30 | 14 | 0
Lisahally | NILPS | 17.6 | 2021-02-04 00:30 | 2021-02-04 05:00 | 15 | 0.17
Moneypoint | MP3 | 285 | 2021-02-04 03:00 | 2021-02-04 13:30 | 190 | 0.42
Lisahally | NILPS | 17.6 | 2021-02-04 05:00 | 2021-02-04 12:00 | 16 | 0.25
Tarbert | TB3 | 241 | 2021-02-04 08:00 | 2021-02-09 03:30 | F | 4.79
Seecon | SO1 | 105 | 2021-02-04 10:00 | 2021-02-04 17:00 | S | 0.25
Lisahally | NILPS | 17.6 | 2021-02-04 12:00 | 2021-02-09 08:30 | 15 | 4.83
Tarbert | TB2 | 54 | 2021-02-04 13:00 | 2021-02-04 14:00 | F | 0
Moneypoint | MP3 | 285 | 2021-02-04 13:30 | 2021-02-04 15:30 | 240 | 0.08
Moneypoint | MP3 | 285 | 2021-02-04 15:30 | 2021-02-04 17:00 | 260 | 0.04
Moneypoint | MP3 | 285 | 2021-02-04 17:00 | 2021-02-09 10:00 | 270 | 4.67
Moneypoint | MP1 | 285 | 2021-02-04 17:00 | 2021-02-10 17:30 | 240 | 6
Moneypoint | MP2 | 285 | 2021-02-05 11:00 | 2021-02-12 18:00 | 99 | 7.25
Tarbert | TB2 | 54 | 2021-02-05 15:00 | 2021-02-05 16:00 | F | 0
Tarbert | TB2 | 54 | 2021-02-05 17:30 | 2021-02-05 20:00 | F | 0.08
Ballylumford | NIB32 | 249 | 2021-02-06 09:30 | 2021-02-06 15:00 | 159 | 0.21
Ballylumford | NIB31 | 249 | 2021-02-06 09:30 | 2021-02-06 13:00 | 159 | 0.12
Ballylumford | NIB31 | 249 | 2021-02-06 13:00 | 2021-02-06 14:00 | 15 | 0
Ballylumford | NIB32 | 249 | 2021-02-06 15:00 | 2021-02-06 16:00 | 15 | 0
Kilroot | NIK1 | 256 | 2021-02-08 13:30 | 2021-02-09 17:00 | 100 | 1.12
Tarbert | TB3 | 241 | 2021-02-09 03:30 | 2021-02-10 08:00 | 226 | 1.17
Dublin Waste To Energy | DW1 | 61.5 | 2021-02-09 05:00 | 2021-02-09 23:00 | 22 | 0.75
Lisahally | NILPS | 17.6 | 2021-02-09 08:30 | 2021-02-09 23:30 | 13 | 0.58
Turlough Hill | TH4 | 73 | 2021-02-09 09:00 | 2021-02-09 14:00 | S | 0.17
Moneypoint | MP3 | 285 | 2021-02-09 15:00 | 2021-02-17 10:00 | F | 7.75
Lisahally | NILPS | 17.6 | 2021-02-09 23:30 | 2021-02-10 09:00 | 15 | 0.38
Dublin Waste To Energy | DW1 | 61.5 | 2021-02-10 07:00 | 2021-02-10 09:00 | F | 0.08
Tarbert | TB3 | 241 | 2021-02-10 08:00 | 2021-02-10 09:00 | F | 0
Ardnacrusha | AA1 | 21 | 2021-02-10 08:30 | 2021-02-10 10:00 | F | 0.04
Tarbert | TB3 | 241 | 2021-02-10 09:00 | 2021-02-25 13:00 | 226 | 15.17
Lisahally | NILPS | 17.6 | 2021-02-10 09:00 | 2021-02-10 20:30 | 13 | 0.46
Turlough Hill | TH3 | 73 | 2021-02-10 10:00 | 2021-02-10 15:00 | S | 0.17
Lee | LE3 | 8 | 2021-02-10 16:00 | 2021-02-12 17:30 | 3 | 2.04
Moneypoint | MP1 | 285 | 2021-02-10 17:30 | 2021-02-13 05:30 | 220 | 2.5
Liffey | LI4 | 4 | 2021-02-10 17:30 | 2021-02-11 09:30 | F | 0.67
Lisahally | NILPS | 17.6 | 2021-02-10 20:30 | 2021-02-10 22:30 | 14 | 0.08
Liffey | LI2 | 15 | 2021-02-10 21:00 | 2021-02-11 04:00 | F | 0.25
Lisahally | NILPS | 17.6 | 2021-02-10 22:30 | 2021-02-11 15:30 | 15 | 0.67
Dublin Waste To Energy | DW1 | 61.5 | 2021-02-11 12:00 | 2021-02-14 13:30 | 58 | 3.04
Lisahally | NILPS | 17.6 | 2021-02-11 15:30 | 2021-02-16 | 16 | 4.33
Lee | LE1 | 15 | 2021-02-12 08:00 | 2021-02-12 09:00 | 3 | 0
Moneypoint | MP2 | 285 | 2021-02-12 18:00 | 2021-02-13 05:30 | 120 | 0.46
Tynagh | TYC | 384 | 2021-02-12 20:00 | 2021-02-15 | S | 2.17
Moneypoint | MP2 | 285 | 2021-02-13 05:30 | 2021-02-14 17:00 | F | 1.46
Moneypoint | MP1 | 285 | 2021-02-13 05:30 | 2021-02-13 21:00 | F | 0.62
Kilroot | NIKGT3 | 42 | 2021-02-13 07:00 | 2021-02-13 18:30 | F | 0.46
Tarbert | TB4 | 243 | 2021-02-13 17:00 | 2021-02-25 02:00 | F | 11.33
Moneypoint | MP1 | 285 | 2021-02-13 22:30 | 2021-02-24 22:00 | 210 | 10.96
Aghada | AD2 | 449 | 2021-02-14 02:00 | 2021-02-20 18:00 | F | 6.67
Kilroot | NIKGT4 | 42 | 2021-02-14 07:00 | 2021-02-14 18:30 | F | 0.46
Dublin Waste To Energy | DW1 | 61.5 | 2021-02-14 13:30 | 2021-02-14 15:30 | F | 0.08
Dublin Waste To Energy | DW1 | 61.5 | 2021-02-14 15:30 | 2021-02-16 23:00 | 58 | 2.29
Moneypoint | MP2 | 285 | 2021-02-14 17:00 | 2021-02-14 18:00 | 100 | 0
Moneypoint | MP2 | 285 | 2021-02-14 18:00 | 2021-02-24 22:00 | 120 | 10.17
Ballylumford | NIB32 | 249 | 2021-02-15 14:00 | 2021-02-15 16:30 | F | 0.08
Dublin Bay | DB1 | 405 | 2021-02-16 | 2021-02-16 19:30 | F | 0.79
Lisahally | NILPS | 17.6 | 2021-02-16 | 2021-02-22 17:00 | 15 | 6.67
Ballylumford | NIB32 | 249 | 2021-02-16 21:30 | 2021-02-16 22:00 | F | 0
Ballylumford | NIB10 | 94 | 2021-02-16 22:00 | 2021-02-16 23:00 | F | 0
Ballylumford | NIB32 | 249 | 2021-02-16 22:00 | 2021-02-17 04:30 | S | 0.25
Dublin Waste To Energy | DW1 | 61.5 | 2021-02-16 23:00 | 2021-03-01 23:00 | 51 | 13
Moneypoint | MP3 | 285 | 2021-02-17 10:00 | 2021-02-17 13:30 | F | 0.12
Ardnacrusha | AA4 | 24 | 2021-02-17 10:00 | 2021-04-06 08:00 | F | 47.92
Edenderry | ED1 | 118 | 2021-02-18 10:30 | 2021-02-18 16:00 | 55 | 0.21
Huntstown | HNC | 342 | 2021-02-18 23:00 | 2021-02-19 22:00 | 225 | 0.92
Lee | LE3 | 8 | 2021-02-19 | 2021-02-19 02:30 | 3 | 0.08
Coolkeeragh | NIC30 | 408 | 2021-02-19 20:00 | 2021-02-23 21:00 | S | 4
Liffey | LI5 | 4 | 2021-02-19 20:30 | 2021-02-22 11:00 | F | 2.58
Indaver | IW1 | 17 | 2021-02-21 14:00 | 2021-02-25 07:00 | F | 3.67
Lisahally | NILPS | 17.6 | 2021-02-22 17:00 | 2021-02-26 01:30 | 16 | 3.33
Coolkeeragh | NIC30 | 408 | 2021-02-23 21:00 | 2021-03-04 18:30 | F | 8.88
Ballylumford | NIB32 | 249 | 2021-02-24 11:30 | 2021-02-24 13:00 | F | 0.04
Moneypoint | MP1 | 285 | 2021-02-24 16:00 | 2021-02-25 13:00 | F | 0.83
Moneypoint | MP3 | 285 | 2021-02-24 22:00 | 2021-02-28 20:30 | F | 3.92
Moneypoint | MP2 | 285 | 2021-02-24 22:00 | 2021-02-26 12:00 | F | 1.58
Moneypoint | MP1 | 285 | 2021-02-25 13:00 | 2021-02-27 08:00 | 220 | 1.75
Tarbert | TB3 | 241 | 2021-02-25 13:00 | 2021-02-25 15:00 | F | 0.08
Moneypoint | MP2 | 285 | 2021-02-25 13:00 | 2021-03-01 10:00 | 120 | 3.83
Tarbert | TB3 | 241 | 2021-02-25 15:00 | 2021-03-26 19:30 | 226 | 29.17
Lisahally | NILPS | 17.6 | 2021-02-26 01:30 | 2021-03-01 | 15 | 2.92
Kilroot | NIKGT3 | 42 | 2021-02-26 09:30 | 2021-02-27 00:30 | F | 0.58
Kilroot | NIK1 | 256 | 2021-02-26 17:30 | 2021-02-26 23:00 | 150 | 0.21
Ballylumford | NIB31 | 249 | 2021-02-27 04:00 | 2021-02-27 05:00 | 15 | 0
Moneypoint | MP1 | 285 | 2021-02-27 08:00 | 2021-02-27 10:00 | F | 0.08
Moneypoint | MP1 | 285 | 2021-02-27 10:00 | 2021-03-04 14:00 | 220 | 5.17
Aghada | AT4 | 90 | 2021-02-27 17:30 | 2021-02-27 19:00 | F | 0.04
Kilroot | NIK1 | 256 | 2021-02-27 17:30 | 2021-02-27 22:30 | 120 | 0.17
Tarbert | TB4 | 243 | 2021-02-27 20:30 | 2021-02-27 21:30 | F | 0
Tarbert | TB4 | 243 | 2021-02-28 20:00 | 2021-03-01 13:00 | F | 0.67
Moneypoint | MP3 | 285 | 2021-02-28 20:30 | 2021-03-05 22:00 | 245 | 5.04
Huntstown | HN2 | 400 | 2021-02-28 23:00 | 2021-04-13 17:00 | S | 43.75
Seal Rock | SK3 | 85 | 2021-03-01 06:00 | 2021-03-03 18:00 | S | 2.5
Moneypoint | MP2 | 285 | 2021-03-01 10:00 | 2021-03-06 06:00 | F | 4.83
Indaver | IW1 | 17 | 2021-03-01 17:00 | 2021-03-02 01:00 | 12 | 0.33
Liffey | LI2 | 15 | 2021-03-02 07:30 | 2021-03-02 08:30 | F | 0
Tarbert | TB1 | 54 | 2021-03-02 11:00 | 2021-03-02 12:30 | F | 0.04
Tarbert | TB2 | 54 | 2021-03-02 14:00 | 2021-03-02 16:00 | F | 0.08
Tarbert | TB1 | 54 | 2021-03-02 17:30 | 2021-03-03 16:30 | F | 0.92
Aghada | AT2 | 90 | 2021-03-02 18:30 | 2021-03-02 19:30 | 40 | 0
Aghada | AT2 | 90 | 2021-03-02 19:30 | 2021-03-02 20:30 | 60 | 0
Edenderry | ED1 | 118 | 2021-03-03 17:30 | 2021-03-03 20:00 | 49 | 0.08
Lisahally | NILPS | 17.6 | 2021-03-04 08:00 | 2021-03-14 18:30 | S | 10.42
Ballylumford | NIB32 | 249 | 2021-03-04 12:00 | 2021-03-04 14:00 | 130 | 0.08
Ballylumford | NIB31 | 249 | 2021-03-04 12:00 | 2021-03-04 14:30 | 155 | 0.08
Moneypoint | MP1 | 285 | 2021-03-04 14:00 | 2021-03-11 23:00 | 245 | 7.33
Ballylumford | NIB32 | 249 | 2021-03-04 14:00 | 2021-03-04 20:00 | 161 | 0.25
Kilroot | NIK2 | 258 | 2021-03-04 22:00 | 2021-03-06 21:30 | F | 1.96
Dublin Waste To Energy | DW1 | 61.5 | 2021-03-05 07:00 | 2021-03-05 09:00 | F | 0.08
Tawnaghmore | TP1 | 52 | 2021-03-05 10:00 | 2021-03-05 20:30 | F | 0.42
Moneypoint | MP3 | 285 | 2021-03-05 22:00 | 2021-03-11 12:00 | F | 5.58
Moneypoint | MP2 | 285 | 2021-03-06 06:00 | 2021-03-23 08:00 | 120 | 17.08
Ardnacrusha | AA3 | 19 | 2021-03-06 09:00 | 2021-03-06 11:00 | 12 | 0.08
Ardnacrusha | AA2 | 22 | 2021-03-06 09:30 | 2021-03-06 11:00 | 12 | 0.04
Tarbert | TB4 | 243 | 2021-03-06 18:00 | 2021-03-12 10:00 | 226 | 5.67
Ballylumford | NIBGT2 | 58 | 2021-03-06 20:00 | 2021-03-06 21:30 | F | 0.04
Ballylumford | NIBGT1 | 58 | 2021-03-06 20:00 | 2021-03-06 21:30 | F | 0.04
Ballylumford | NIB31 | 249 | 2021-03-06 20:00 | 2021-03-09 02:00 | F | 2.25
Kilroot | NIK2 | 258 | 2021-03-06 21:30 | 2021-03-11 04:30 | F | 4.25
Ballylumford | NIBGT1 | 58 | 2021-03-08 12:00 | 2021-03-08 13:30 | F | 0.04
Ballylumford | NIBGT2 | 58 | 2021-03-08 12:00 | 2021-03-08 13:30 | F | 0.04
Seal Rock | SK3 | 85 | 2021-03-09 11:00 | 2021-03-09 16:30 | F | 0.21
Aghada | AT4 | 90 | 2021-03-10 06:00 | 2021-03-12 20:00 | S | 2.58
Ballylumford | NIB31 | 249 | 2021-03-10 19:00 | 2021-03-10 22:00 | F | 0.08
Moneypoint | MP3 | 285 | 2021-03-11 12:00 | 2021-03-13 17:00 | 260 | 2.17
Kilroot | NIK2 | 258 | 2021-03-11 14:00 | 2021-03-11 16:30 | F | 0.08
Kilroot | NIK1 | 256 | 2021-03-11 22:00 | 2021-03-14 | F | 2.08
Moneypoint | MP1 | 285 | 2021-03-11 23:00 | 2021-03-18 09:00 | F | 6.42
Kilroot | NIKGT1 | 29 | 2021-03-12 06:00 | 2021-03-12 16:30 | F | 0.42
Aghada | AT4 | 90 | 2021-03-12 23:30 | 2021-03-13 15:30 | F | 0.67
Indaver | IW1 | 17 | 2021-03-13 02:00 | 2021-03-19 01:00 | F | 5.92
Moneypoint | MP3 | 285 | 2021-03-13 17:00 | 2021-03-13 19:30 | F | 0.08
EWIC | EW1 | 500 | 2021-03-13 19:00 | 2021-03-14 23:00 | S | 1.17
Moneypoint | MP3 | 285 | 2021-03-13 19:30 | 2021-03-15 10:00 | 260 | 1.58
Kilroot | NIK1 | 256 | 2021-03-14 | 2021-03-14 23:30 | F | 0.96
Lee | LE1 | 15 | 2021-03-14 07:00 | 2021-03-16 12:00 | F | 2.17
Lisahally | NILPS | 17.6 | 2021-03-14 18:30 | 2021-03-15 18:30 | F | 1
Poolbeg | PB5 | 146 | 2021-03-15 08:00 | 2021-03-15 12:00 | F | 0.17
Poolbeg | PB6 | 168 | 2021-03-15 08:00 | 2021-03-15 12:00 | 84 | 0.17
Kilroot | NIK2 | 258 | 2021-03-15 08:00 | 2021-03-16 08:30 | 93 | 1
Lee | LE2 | 4 | 2021-03-15 13:30 | 2021-03-15 18:00 | F | 0.17
Poolbeg | PB6 | 168 | 2021-03-16 06:30 | 2021-03-16 18:00 | 84 | 0.46
Poolbeg | PB5 | 146 | 2021-03-16 06:30 | 2021-03-16 18:00 | F | 0.46
Lee | LE2 | 4 | 2021-03-16 09:30 | 2021-03-20 19:00 | F | 4.38
Ardnacrusha | AA3 | 19 | 2021-03-16 14:30 | 2021-03-16 15:30 | 12 | 0
Dublin Bay | DB1 | 405 | 2021-03-16 15:30 | 2021-03-17 14:30 | 180 | 0.92
Lee | LE1 | 15 | 2021-03-17 20:00 | 2021-03-17 21:00 | F | 0
Seal Rock | SK3 | 85 | 2021-03-17 22:30 | 2021-03-18 16:30 | F | 0.75
Moneypoint | MP1 | 285 | 2021-03-18 09:00 | 2021-03-18 10:00 | 250 | 0
Lee | LE1 | 15 | 2021-03-18 10:00 | 2021-03-18 14:30 | F | 0.17
Moneypoint | MP1 | 285 | 2021-03-18 10:00 | 2021-03-18 15:30 | F | 0.21
Edenderry | ED1 | 118 | 2021-03-19 | 2021-03-19 23:00 | 65 | 0.92
Ardnacrusha | AA2 | 22 | 2021-03-19 12:30 | 2021-03-19 14:00 | 12 | 0.04
Ardnacrusha | AA1 | 21 | 2021-03-19 12:30 | 2021-03-19 15:00 | 12 | 0.08
Ardnacrusha | AA3 | 19 | 2021-03-19 12:30 | 2021-03-19 13:30 | 12 | 0
Moneypoint | MP1 | 285 | 2021-03-19 14:30 | 2021-03-26 09:00 | F | 6.75
Tarbert | TB4 | 243 | 2021-03-19 17:00 | 2021-03-19 18:30 | F | 0.04
Rhode | RP1 | 52 | 2021-03-19 17:30 | 2021-03-25 13:00 | 26 | 5.79
Tarbert | TB4 | 243 | 2021-03-19 18:30 | 2021-03-31 12:30 | 106 | 11.75
Edenderry | ED1 | 118 | 2021-03-19 23:00 | 2021-03-22 11:30 | 75 | 2.5
Turlough Hill | TH2 | 73 | 2021-03-20 06:00 | 2021-03-28 17:00 | S | 8.42
Turlough Hill | TH3 | 73 | 2021-03-20 06:00 | 2021-03-28 17:00 | S | 8.42
Turlough Hill | TH4 | 73 | 2021-03-20 06:00 | 2021-03-28 17:00 | S | 8.42
Turlough Hill | TH1 | 73 | 2021-03-20 06:00 | 2021-03-28 17:00 | S | 8.42
Ardnacrusha | AA1 | 21 | 2021-03-20 09:30 | 2021-03-20 11:00 | 12 | 0.04
Ardnacrusha | AA2 | 22 | 2021-03-20 10:00 | 2021-03-20 11:00 | 12 | 0
Lee | LE1 | 15 | 2021-03-20 16:30 | 2021-03-31 17:00 | F | 11
Tawnaghmore | TP1 | 52 | 2021-03-21 17:30 | 2021-03-21 20:00 | 26 | 0.08
Edenderry | ED1 | 118 | 2021-03-22 11:30 | 2021-03-23 10:00 | 85 | 0.92
Moneypoint | MP2 | 285 | 2021-03-23 08:00 | 2021-03-31 21:00 | F | 8.5
Edenderry | ED1 | 118 | 2021-03-23 10:00 | 2021-03-24 10:00 | 95 | 1
Edenderry | ED1 | 118 | 2021-03-24 10:00 | 2021-03-25 10:30 | 100 | 1
Kilroot | NIKGT3 | 42 | 2021-03-25 08:00 | 2021-03-25 11:30 | F | 0.12
Edenderry | ED1 | 118 | 2021-03-25 10:30 | 2021-03-29 09:30 | 105 | 3.92
Lee | LE2 | 4 | 2021-03-26 09:00 | 2021-03-26 13:00 | S | 0.17
Tarbert | TB3 | 241 | 2021-03-26 19:30 | 2021-03-30 03:30 | F | 3.33
Indaver | IW1 | 17 | 2021-03-27 11:30 | 2021-03-28 19:00 | F | 1.29
Liffey | LI5 | 4 | 2021-03-27 19:00 | 2021-03-28 07:00 | F | 0.5
Turlough Hill | TH4 | 73 | 2021-03-28 17:00 | 2021-03-29 17:00 | F | 1
Turlough Hill | TH3 | 73 | 2021-03-28 17:00 | 2021-03-29 15:00 | F | 0.92
Turlough Hill | TH2 | 73 | 2021-03-28 17:00 | 2021-03-29 15:00 | F | 0.92
Turlough Hill | TH1 | 73 | 2021-03-28 17:00 | 2021-03-29 17:00 | F | 1
Indaver | IW1 | 17 | 2021-03-28 20:30 | 2021-03-29 07:00 | 9 | 0.42
Aghada | AT1 | 90 | 2021-03-29 06:00 | 2021-03-31 18:00 | S | 2.5
Edenderry | ED1 | 118 | 2021-03-29 09:30 | 2021-03-30 14:00 | 110 | 1.17
Indaver | IW1 | 17 | 2021-03-29 20:00 | 2021-03-31 02:30 | 15 | 1.25
Tarbert | TB3 | 241 | 2021-03-30 03:30 | 2021-03-31 17:30 | 226 | 1.58
Turlough Hill | TH3 | 73 | 2021-03-30 10:00 | 2021-03-30 11:30 | F | 0.04
Edenderry | ED1 | 118 | 2021-03-30 14:00 | 2021-03-30 15:00 | 65 | 0
Edenderry | ED1 | 118 | 2021-03-30 15:00 | 2021-03-31 19:00 | 45 | 1.17
Aghada | AD2 | 449 | 2021-03-31 05:30 | 2021-03-31 12:00 | 340 | 0.25
Indaver | IW1 | 17 | 2021-03-31 13:00 | 2021-03-31 17:00 | 14 | 0.17
Aghada | AD2 | 449 | 2021-03-31 13:30 | 2021-03-31 15:00 | 340 | 0.04
Aghada | AD2 | 449 | 2021-03-31 15:00 | 2021-03-31 16:00 | 120 | 0
Aghada | AD2 | 449 | 2021-03-31 16:00 | 2021-03-31 17:00 | 200 | 0
Aghada | AD2 | 449 | 2021-03-31 17:00 | 2021-03-31 18:00 | 300 | 0
Tarbert | TB3 | 241 | 2021-03-31 17:30 | 2021-04-02 02:00 | F | 1.33
Edenderry | ED1 | 118 | 2021-03-31 19:00 | 2021-04-06 02:30 | F | 5.29
Lee | LE1 | 15 | 2021-04-01 12:00 | 2021-04-01 13:00 | F | 0
Moneypoint | MP2 | 285 | 2021-04-01 20:00 | 2021-04-14 08:30 | 120 | 12.5
Tarbert | TB3 | 241 | 2021-04-02 02:00 | 2021-04-15 13:00 | 226 | 13.42
Kilroot | NIKGT3 | 42 | 2021-04-02 11:00 | 2021-04-02 17:30 | F | 0.25
Aghada | AD2 | 449 | 2021-04-02 12:00 | 2021-04-04 | 415 | 1.5
Ballylumford | NIB10 | 94 | 2021-04-02 13:00 | 2021-04-02 14:00 | F | 0
Ardnacrusha | AA2 | 22 | 2021-04-02 14:00 | 2021-04-02 17:00 | 12 | 0.08
Ardnacrusha | AA3 | 19 | 2021-04-02 14:30 | 2021-04-02 17:30 | 12 | 0.08
Aghada | AD2 | 449 | 2021-04-04 | 2021-04-05 20:30 | S | 1.83
Tarbert | TB4 | 243 | 2021-04-04 10:00 | 2021-04-04 12:30 | F | 0.08
Tarbert | TB4 | 243 | 2021-04-04 12:30 | 2021-04-06 14:00 | 121 | 2.04
Poolbeg | PB6 | 168 | 2021-04-05 09:00 | 2021-04-10 17:00 | 84 | 5.33
Poolbeg | PB5 | 146 | 2021-04-05 09:00 | 2021-04-10 17:00 | S | 5.33
Moneypoint | MP1 | 285 | 2021-04-05 09:30 | 2021-04-07 07:30 | F | 1.92
Tynagh | TYC | 384 | 2021-04-06 03:00 | 2021-04-06 17:00 | F | 0.58
Tawnaghmore | TP1 | 52 | 2021-04-06 06:00 | 2021-04-06 09:00 | F | 0.08
Ardnacrusha | AA4 | 24 | 2021-04-06 08:00 | 2021-05-28 20:00 | S | 52.5
Lee | LE2 | 4 | 2021-04-06 08:00 | 2021-04-16 20:00 | S | 10.5
Tawnaghmore | TP3 | 52 | 2021-04-06 09:00 | 2021-04-06 10:00 | F | 0
Tarbert | TB4 | 243 | 2021-04-06 14:00 | 2021-04-06 18:00 | F | 0.17
Ardnacrusha | AA3 | 19 | 2021-04-06 17:00 | 2021-04-07 15:30 | F | 0.92
Coolkeeragh | NICGT8 | 53 | 2021-04-06 17:00 | 2021-04-06 18:00 | F | 0
Tarbert | TB4 | 243 | 2021-04-06 18:00 | 2021-04-07 01:30 | 121 | 0.29
Tynagh | TYC | 384 | 2021-04-06 21:30 | 2021-04-07 15:30 | F | 0.75
Tarbert | TB4 | 243 | 2021-04-07 01:30 | 2021-04-10 17:00 | F | 3.62
Tarbert | TB1 | 54 | 2021-04-07 08:30 | 2021-04-07 12:00 | F | 0.12
Edenderry | ED1 | 118 | 2021-04-07 08:30 | 2021-04-07 15:00 | 45 | 0.25
Tarbert | TB2 | 54 | 2021-04-07 10:30 | 2021-04-07 12:00 | F | 0.04
Moneypoint | MP1 | 285 | 2021-04-09 07:30 | 2021-04-09 14:00 | 220 | 0.25
Moneypoint | MP1 | 285 | 2021-04-09 14:00 | 2021-04-09 20:00 | 245 | 0.25
Moneypoint | MP1 | 285 | 2021-04-09 20:00 | 2021-04-12 12:00 | 220 | 2.67
Ballylumford | NIB31 | 249 | 2021-04-09 20:00 | 2021-04-11 00:30 | 159 | 1.17
Tarbert | TB4 | 243 | 2021-04-10 17:00 | 2021-04-13 10:00 | 121 | 2.67
Aghada | AT4 | 90 | 2021-04-11 17:00 | 2021-04-27 11:30 | F | 15.75
Tynagh | TYC | 384 | 2021-04-11 20:00 | 2021-05-03 | S | 21.17
Liffey | LI2 | 15 | 2021-04-12 08:00 | 2021-05-09 17:00 | S | 27.33
Liffey | LI1 | 15 | 2021-04-12 08:00 | 2021-05-09 17:00 | S | 27.33
Erne | ER1 | 10 | 2021-04-12 08:00 | 2021-04-26 20:00 | S | 14.5
Tawnaghmore | TP3 | 52 | 2021-04-12 09:00 | 2021-05-09 17:00 | S | 27.33
Tawnaghmore | TP1 | 52 | 2021-04-12 09:00 | 2021-05-09 17:00 | S | 27.33
Moneypoint | MP1 | 285 | 2021-04-12 12:00 | 2021-04-14 09:00 | 245 | 1.83
Lee | LE1 | 15 | 2021-04-12 14:30 | 2021-04-26 08:00 | F | 13.71
Tarbert | TB4 | 243 | 2021-04-13 10:00 | 2021-04-13 11:00 | F | 0
Dublin Waste To Energy | DW1 | 61.5 | 2021-04-13 10:00 | 2021-04-14 01:00 | 28 | 0.58
Tarbert | TB4 | 243 | 2021-04-13 11:00 | 2021-04-13 12:00 | 121 | 0
Tarbert | TB4 | 243 | 2021-04-13 12:00 | 2021-04-13 13:30 | F | 0.04
Tarbert | TB4 | 243 | 2021-04-13 13:30 | 2021-04-13 15:00 | 121 | 0.04
Tarbert | TB4 | 243 | 2021-04-13 15:00 | 2021-08-08 17:00 | F | 117.08
Huntstown | HN2 | 400 | 2021-04-13 17:00 | 2021-10-18 08:00 | F | 187.58
Tarbert | TB1 | 54 | 2021-04-13 19:30 | 2021-04-13 21:30 | F | 0.08
Dublin Waste To Energy | DW1 | 61.5 | 2021-04-14 01:00 | 2021-04-14 03:00 | F | 0.08
Dublin Waste To Energy | DW1 | 61.5 | 2021-04-14 03:00 | 2021-04-15 03:00 | 28 | 1
Moneypoint | MP2 | 285 | 2021-04-14 08:30 | 2021-04-14 20:00 | F | 0.46
Moneypoint | MP1 | 285 | 2021-04-14 09:00 | 2021-04-15 16:00 | 280 | 1.25
Moneypoint | MP2 | 285 | 2021-04-14 20:00 | 2021-04-30 21:00 | 120 | 16
Aghada | AT2 | 90 | 2021-04-15 | 2021-04-17 15:00 | S | 2.58
Tarbert | TB3 | 241 | 2021-04-15 13:00 | 2021-04-15 14:30 | F | 0.04
Tarbert | TB3 | 241 | 2021-04-15 14:30 | 2021-05-17 09:00 | 226 | 31.75
Moneypoint | MP1 | 285 | 2021-04-15 16:00 | 2021-04-18 21:00 | 245 | 3.17
Kilroot | NIK1 | 256 | 2021-04-15 22:00 | 2021-04-16 22:30 | F | 1
Poolbeg | PB5 | 146 | 2021-04-16 14:30 | 2021-04-16 18:00 | F | 0.12
Poolbeg | PB6 | 168 | 2021-04-16 14:30 | 2021-04-16 18:00 | 84 | 0.12
Lee | LE2 | 4 | 2021-04-16 20:00 | 2021-07-20 | F | 94.17
Great Island | GI4 | 461 | 2021-04-16 21:00 | 2021-04-18 16:00 | S | 1.75
Coolkeeragh | NIC30 | 408 | 2021-04-17 04:00 | 2021-04-18 | S | 0.83
Kilroot | NIK1 | 256 | 2021-04-17 04:30 | 2021-04-18 04:30 | F | 1
Dublin Waste To Energy | DW1 | 61.5 | 2021-04-17 06:30 | 2021-04-17 11:30 | 24 | 0.17
Kilroot | NIK2 | 258 | 2021-04-18 | 2021-04-19 02:30 | F | 1.08
Kilroot | NIK1 | 256 | 2021-04-18 20:30 | 2021-04-23 07:00 | F | 4.42
Moneypoint | MP1 | 285 | 2021-04-18 21:00 | 2021-04-21 09:00 | 225 | 2.5
Erne | ER2 | 10 | 2021-04-19 20:30 | 2021-04-19 21:30 | F | 0
Poolbeg | PB6 | 168 | 2021-04-20 05:30 | 2021-04-20 08:00 | 76 | 0.08
Moneypoint | MP3 | 285 | 2021-04-20 06:00 | 2021-04-20 18:00 | 255 | 0.5
Moneypoint | MP1 | 285 | 2021-04-21 09:00 | 2021-04-30 21:00 | 245 | 9.5
Moyle | MOYLE | 450 | 2021-04-21 09:00 | 2021-04-21 12:30 | 250 | 0.12
Erne | ER2 | 10 | 2021-04-21 09:30 | 2021-04-21 18:00 | F | 0.33
Erne | ER2 | 10 | 2021-04-22 10:30 | 2021-04-22 16:30 | F | 0.25
Kilroot | NIKGT3 | 42 | 2021-04-22 20:30 | 2021-04-23 10:30 | F | 0.58
Ballylumford | NIB31 | 249 | 2021-04-22 20:30 | 2021-04-23 01:30 | F | 0.17
Kilroot | NIKGT3 | 42 | 2021-04-23 10:30 | 2021-04-23 13:00 | F | 0.08
Dublin Bay | DB1 | 405 | 2021-04-23 13:00 | 2021-06-28 06:00 | S | 65.67
Lee | LE1 | 15 | 2021-04-26 08:00 | 2021-07-30 20:00 | F | 95.5
Erne | ER1 | 10 | 2021-04-26 20:00 | 2021-04-30 20:00 | F | 4
Kilroot | NIKGT3 | 42 | 2021-04-29 06:00 | 2021-04-29 18:30 | F | 0.5
Tarbert | TB1 | 54 | 2021-04-29 08:00 | 2021-04-29 09:30 | F | 0.04
Tarbert | TB1 | 54 | 2021-04-30 07:30 | 2021-04-30 08:30 | F | 0
Tarbert | TB1 | 54 | 2021-04-30 07:30 | 2021-04-30 08:30 | F | 0
Kilroot | NIKGT4 | 42 | 2021-04-30 14:00 | 2021-04-30 15:30 | F | 0.04
Moneypoint | MP2 | 285 | 2021-04-30 21:00 | 2021-05-02 12:30 | F | 1.62
Moneypoint | MP3 | 285 | 2021-05-01 | 2021-05-04 06:00 | F | 3.25
Moneypoint | MP2 | 285 | 2021-05-02 12:30 | 2021-05-06 01:00 | 120 | 3.5
Tynagh | TYC | 384 | 2021-05-03 | 2021-05-12 19:00 | F | 9.75
Erne | ER1 | 10 | 2021-05-03 09:00 | 2021-05-03 18:00 | F | 0.33
Kilroot | NIKGT3 | 42 | 2021-05-03 20:30 | 2021-05-12 15:00 | F | 8.75
Moneypoint | MP3 | 285 | 2021-05-04 06:00 | 2021-05-05 21:30 | 260 | 1.62
Ardnacrusha | AA3 | 19 | 2021-05-04 08:00 | 2021-05-07 17:00 | F | 3.33
Ardnacrusha | AA1 | 21 | 2021-05-04 08:00 | 2021-05-04 15:00 | F | 0.25
Ballylumford | NIBGT2 | 58 | 2021-05-04 15:30 | 2021-05-04 17:30 | F | 0.08
Coolkeeragh | NIC30 | 408 | 2021-05-04 20:00 | 2021-05-05 00:30 | F | 0.17
Coolkeeragh | NICGT8 | 53 | 2021-05-04 20:30 | 2021-05-05 00:30 | F | 0.17
Moneypoint | MP3 | 285 | 2021-05-05 21:30 | 2021-05-06 16:00 | 205 | 0.75
Moneypoint | MP2 | 285 | 2021-05-06 01:00 | 2021-05-13 18:00 | F | 7.67
Moneypoint | MP3 | 285 | 2021-05-06 16:00 | 2021-05-12 13:00 | 200 | 5.83
Kilroot | NIK1 | 256 | 2021-05-06 20:00 | 2021-05-09 | F | 2.17
Coolkeeragh | NICGT8 | 53 | 2021-05-07 09:00 | 2021-05-07 13:30 | S | 0.17
Kilroot | NIKGT4 | 42 | 2021-05-07 09:30 | 2021-05-07 11:30 | F | 0.08
Edenderry | ED1 | 118 | 2021-05-08 07:00 | 2021-05-08 08:00 | 65 | 0
Kilroot | NIK1 | 256 | 2021-05-09 | 2021-05-10 13:00 | 199 | 1.5
Erne | ER2 | 10 | 2021-05-09 15:30 | 2021-05-09 17:00 | F | 0.04
Liffey | LI2 | 15 | 2021-05-09 17:00 | 2021-09-12 17:00 | F | 126
Liffey | LI1 | 15 | 2021-05-09 17:00 | 2021-09-12 17:00 | F | 126
Tawnaghmore | TP1 | 52 | 2021-05-09 17:00 | 2021-05-21 17:00 | F | 12
Tawnaghmore | TP3 | 52 | 2021-05-09 17:00 | 2021-05-26 17:00 | F | 17
Coolkeeragh | NICGT8 | 53 | 2021-05-10 04:00 | 2021-05-17 21:00 | S | 7.67
Kilroot | NIK1 | 256 | 2021-05-10 13:00 | 2021-05-11 08:30 | F | 0.79
Ballylumford | NIB32 | 249 | 2021-05-10 16:00 | 2021-05-10 17:00 | 157 | 0
Ballylumford | NIB31 | 249 | 2021-05-10 16:00 | 2021-05-10 17:00 | 157 | 0
Seal Rock | SK4 | 85 | 2021-05-10 18:00 | 2021-05-13 21:00 | S | 3.08
Kilroot | NIK2 | 258 | 2021-05-10 22:00 | 2021-05-14 20:00 | 93 | 3.92
Seal Rock | SK3 | 85 | 2021-05-11 01:00 | 2021-05-13 18:00 | S | 2.67
Ballylumford | NIBGT1 | 58 | 2021-05-12 08:00 | 2021-05-12 09:30 | F | 0.04
Aghada | AD2 | 449 | 2021-05-12 20:00 | 2021-05-30 20:00 | S | 18
Tynagh | TYC | 384 | 2021-05-13 | 2021-05-13 02:30 | F | 0.08
Moneypoint | MP2 | 285 | 2021-05-13 18:00 | 2021-05-17 11:30 | 220 | 3.71
Seal Rock | SK3 | 85 | 2021-05-14 01:00 | 2021-05-14 14:00 | F | 0.5
Tarbert | TB1 | 54 | 2021-05-14 10:00 | 2021-05-15 | F | 0.58
Kilroot | NIK2 | 258 | 2021-05-14 20:00 | 2021-07-09 20:30 | S | 56
Poolbeg | PB6 | 168 | 2021-05-14 21:00 | 2021-05-19 23:00 | 84 | 5.08
Tarbert | TB2 | 54 | 2021-05-15 | 2021-05-22 | S | 7
Tarbert | TB1 | 54 | 2021-05-15 | 2021-05-22 | S | 7
Moneypoint | MP1 | 285 | 2021-05-15 09:30 | 2021-05-15 15:00 | 98 | 0.21
Moneypoint | MP1 | 285 | 2021-05-15 15:00 | 2021-05-16 00:30 | F | 0.38
Kilroot | NIKGT2 | 29 | 2021-05-16 06:00 | 2021-07-09 20:30 | S | 54.58
Liffey | LI5 | 4 | 2021-05-17 08:00 | 2021-07-23 16:00 | F | 67.33
Tarbert | TB3 | 241 | 2021-05-17 09:00 | 2021-05-17 11:00 | F | 0.08
Tarbert | TB3 | 241 | 2021-05-17 11:00 | 2021-05-25 11:00 | 226 | 8
Moneypoint | MP2 | 285 | 2021-05-17 11:30 | 2021-05-17 13:00 | 120 | 0.04
Moneypoint | MP2 | 285 | 2021-05-17 13:00 | 2021-05-17 19:00 | 165 | 0.25
Moneypoint | MP2 | 285 | 2021-05-17 19:00 | 2021-05-19 10:30 | 200 | 1.62
Ballylumford | NIBGT2 | 58 | 2021-05-19 08:00 | 2021-05-19 12:30 | F | 0.17
Moneypoint | MP2 | 285 | 2021-05-19 10:30 | 2021-06-01 14:00 | 220 | 13.12
Turlough Hill | TH3 | 73 | 2021-05-20 10:00 | 2021-05-20 15:00 | S | 0.17
Tynagh | TYC | 384 | 2021-05-20 23:00 | 2021-05-21 15:00 | F | 0.67
Turlough Hill | TH1 | 73 | 2021-05-21 10:00 | 2021-05-21 15:00 | S | 0.17
Tynagh | TYC | 384 | 2021-05-21 15:30 | 2021-05-21 16:30 | F | 0
Tarbert | TB1 | 54 | 2021-05-22 | 2021-06-14 03:30 | F | 23.12
Tarbert | TB2 | 54 | 2021-05-22 | 2021-06-12 17:00 | F | 21.67
Tawnaghmore | TP1 | 52 | 2021-05-22 00:30 | 2021-05-22 08:30 | F | 0.33
Ballylumford | NIB10 | 94 | 2021-05-22 19:00 | 2021-05-23 19:30 | F | 1
Turlough Hill | TH2 | 73 | 2021-05-24 10:00 | 2021-05-24 15:00 | S | 0.17
Coolkeeragh | NICGT8 | 53 | 2021-05-24 10:30 | 2021-05-24 15:00 | S | 0.17
Ballylumford | NIBGT1 | 58 | 2021-05-24 15:30 | 2021-05-24 21:30 | F | 0.25
Coolkeeragh | NICGT8 | 53 | 2021-05-25 06:30 | 2021-05-26 14:30 | S | 1.33
Tarbert | TB3 | 241 | 2021-05-25 11:00 | 2021-06-03 08:00 | 209 | 8.83
Coolkeeragh | NIC30 | 408 | 2021-05-26 04:30 | 2021-05-26 07:00 | F | 0.08
Lee | LE3 | 8 | 2021-05-26 08:00 | 2021-05-26 16:00 | F | 0.33
Turlough Hill | TH4 | 73 | 2021-05-27 10:00 | 2021-05-27 15:00 | S | 0.17
Kilroot | NIKGT3 | 42 | 2021-05-27 10:00 | 2021-05-27 15:30 | S | 0.21
Ballylumford | NIB32 | 249 | 2021-05-27 16:00 | 2021-05-28 06:00 | 176 | 0.58
Ballylumford | NIB32 | 249 | 2021-05-28 06:00 | 2021-05-28 18:30 | F | 0.5
Aghada | AT4 | 90 | 2021-05-28 08:00 | 2021-05-28 09:00 | F | 0
Ardnacrusha | AA4 | 24 | 2021-05-28 20:00 | 2021-07-31 17:00 | F | 63.83
Moneypoint | MP3 | 285 | 2021-05-28 21:00 | 2021-06-04 17:00 | F | 6.83
Dublin Waste To Energy | DW1 | 61.5 | 2021-05-30 02:00 | 2021-06-04 03:00 | F | 5
Aghada | AD2 | 449 | 2021-05-30 20:00 | 2021-06-02 13:00 | F | 2.67
Ardnacrusha | AA3 | 19 | 2021-05-31 08:00 | 2021-06-03 17:00 | F | 3.33
Rhode | RP2 | 52 | 2021-05-31 09:00 | 2021-06-24 19:30 | S | 24.42
Rhode | RP1 | 52 | 2021-05-31 09:00 | 2021-06-26 17:00 | S | 26.33
Ballylumford | NIB31 | 249 | 2021-06-01 06:00 | 2021-06-01 14:30 | S | 0.33
Moneypoint | MP2 | 285 | 2021-06-01 14:00 | 2021-06-10 13:00 | 220 | 8.92
Aghada | AD2 | 449 | 2021-06-02 05:00 | 2021-06-02 17:00 | S | 0.5
Ballylumford | NIBGT1 | 58 | 2021-06-02 08:00 | 2021-06-02 10:30 | F | 0.08
Tarbert | TB3 | 241 | 2021-06-03 08:00 | 2021-06-05 18:00 | S | 2.42
Moyle | MOYLE | 450 | 2021-06-03 12:00 | 2021-06-03 17:00 | 250 | 0.17
Dublin Waste To Energy | DW1 | 61.5 | 2021-06-04 03:00 | 2021-06-04 23:00 | 22 | 0.83
Kilroot | NIKGT1 | 29 | 2021-06-04 20:00 | 2021-06-09 08:30 | S | 4.5
Kilroot | NIK1 | 256 | 2021-06-04 20:00 | 2021-06-10 12:30 | S | 5.67
Tarbert | TB3 | 241 | 2021-06-05 18:00 | 2021-06-11 21:00 | 209 | 6.08
Tawnaghmore | TP1 | 52 | 2021-06-05 20:00 | 2021-06-05 22:30 | F | 0.08
Tawnaghmore | TP3 | 52 | 2021-06-05 20:00 | 2021-06-05 23:00 | F | 0.08
Moneypoint | MP1 | 285 | 2021-06-05 22:00 | 2021-06-12 09:30 | F | 6.46
Edenderry | ED1 | 118 | 2021-06-07 17:00 | 2021-06-15 11:00 | 105 | 7.75
Ardnacrusha | AA2 | 22 | 2021-06-08 16:30 | 2021-06-29 17:00 | S | 21
Kilroot | NIKGT1 | 29 | 2021-06-09 08:30 | 2021-06-10 08:00 | F | 0.96
Kilroot | NIK1 | 256 | 2021-06-10 12:30 | 2021-06-16 20:30 | F | 6.33
Moneypoint | MP2 | 285 | 2021-06-10 13:00 | 2021-06-19 14:00 | F | 9
Great Island | GI4 | 461 | 2021-06-11 04:00 | 2021-06-11 22:00 | F | 0.75
Tarbert | TB3 | 241 | 2021-06-11 21:00 | 2021-06-16 08:00 | 180 | 4.42
Moneypoint | MP1 | 285 | 2021-06-12 14:00 | 2021-06-12 19:00 | 120 | 0.17
Seal Rock | SK3 | 85 | 2021-06-13 06:00 | 2021-06-29 18:00 | S | 16.5
Dublin Waste To Energy | DW1 | 61.5 | 2021-06-13 18:30 | 2021-06-14 04:00 | F | 0.38
Dublin Waste To Energy | DW1 | 61.5 | 2021-06-14 04:00 | 2021-07-07 06:00 | S | 23.08
Lee | LE3 | 8 | 2021-06-14 08:00 | 2021-07-16 20:00 | S | 32.5
Erne | ER3 | 22.5 | 2021-06-14 08:00 | 2021-07-04 20:00 | S | 20.5
Edenderry | ED1 | 118 | 2021-06-15 11:00 | 2021-06-15 16:00 | 55 | 0.17
Edenderry | ED1 | 118 | 2021-06-15 16:00 | 2021-06-22 00:30 | 105 | 6.33
Ballylumford | NIB10 | 94 | 2021-06-16 04:30 | 2021-06-17 05:30 | F | 1
Tarbert | TB3 | 241 | 2021-06-16 08:00 | 2021-06-16 18:00 | F | 0.42
Tarbert | TB3 | 241 | 2021-06-16 18:00 | 2021-06-20 14:30 | F | 3.83
Ballylumford | NIB31 | 249 | 2021-06-17 19:00 | 2021-06-20 23:30 | S | 3.17
Tarbert | TB1 | 54 | 2021-06-18 06:00 | 2021-06-18 07:00 | F | 0
Tarbert | TB1 | 54 | 2021-06-18 18:30 | 2021-06-18 22:00 | F | 0.12
Coolkeeragh | NIC30 | 408 | 2021-06-19 08:00 | 2021-06-19 21:30 | S | 0.54
Moneypoint | MP2 | 285 | 2021-06-19 14:00 | 2021-06-21 10:30 | 220 | 1.83
Moneypoint | MP3 | 285 | 2021-06-20 03:00 | 2021-06-20 17:00 | 210 | 0.58
Tarbert | TB3 | 241 | 2021-06-20 16:30 | 2021-06-29 10:00 | 180 | 8.71
Moneypoint | MP2 | 285 | 2021-06-21 10:30 | 2021-06-21 11:30 | F | 0
Moneypoint | MP2 | 285 | 2021-06-21 11:30 | 2021-07-23 22:00 | 220 | 32.42
Ballylumford | NIB10 | 94 | 2021-06-21 20:00 | 2021-07-01 20:30 | S | 10
Coolkeeragh | NIC30 | 408 | 2021-06-21 22:00 | 2021-06-22 04:30 | S | 0.25
Edenderry | ED1 | 118 | 2021-06-22 00:30 | 2021-06-22 02:30 | F | 0.08
Edenderry | ED1 | 118 | 2021-06-22 02:30 | 2021-07-01 12:30 | 105 | 9.42
Coolkeeragh | NIC30 | 408 | 2021-06-22 04:30 | 2021-06-22 14:30 | F | 0.42
Turlough Hill | TH4 | 73 | 2021-06-25 11:00 | 2021-06-25 13:00 | S | 0.08
Seal Rock | SK4 | 85 | 2021-06-25 11:00 | 2021-06-25 15:30 | F | 0.17
Rhode | RP1 | 52 | 2021-06-26 17:00 | 2021-07-16 17:00 | F | 20
Dublin Bay | DB1 | 405 | 2021-06-28 06:00 | 2021-08-10 18:00 | F | 43.5
Poolbeg | PB6 | 168 | 2021-06-28 06:00 | 2021-06-28 07:00 | F | 0
Poolbeg | PB5 | 146 | 2021-06-28 06:00 | 2021-06-28 07:00 | F | 0
Tarbert | TB3 | 241 | 2021-06-29 10:00 | 2021-07-09 15:00 | 150 | 10.17
Ardnacrusha | AA2 | 22 | 2021-06-29 17:00 | 2021-06-30 09:00 | F | 0.67
Seal Rock | SK3 | 85 | 2021-06-29 18:00 | 2021-07-02 | S | 2.25
Kilroot | NIKGT3 | 42 | 2021-06-30 06:00 | 2021-06-30 18:30 | F | 0.5
Edenderry | ED1 | 118 | 2021-07-01 12:00 | 2021-08-30 18:00 | S | 60.25
Kilroot | NIKGT4 | 42 | 2021-07-03 06:00 | 2021-07-03 18:30 | F | 0.5
Aghada | AD2 | 449 | 2021-07-03 08:00 | 2021-07-03 18:00 | F | 0.42
Tynagh | TYC | 384 | 2021-07-03 17:00 | 2021-07-03 23:30 | F | 0.25
Seal Rock | SK4 | 85 | 2021-07-05 06:00 | 2021-07-09 18:00 | S | 4.5
Edenderry | ED3 | 58 | 2021-07-05 16:00 | 2021-07-11 08:30 | F | 5.67
Erne | ER4 | 22.5 | 2021-07-06 09:00 | 2021-07-07 17:00 | F | 1.33
Indaver | IW1 | 17 | 2021-07-06 18:00 | 2021-07-07 03:00 | F | 0.33
Ballylumford | NIB10 | 94 | 2021-07-07 02:30 | 2021-07-08 14:00 | F | 1.46
Dublin Waste To Energy | DW1 | 61.5 | 2021-07-07 06:00 | 2021-07-07 18:00 | 28 | 0.5
Moneypoint | MP3 | 285 | 2021-07-07 10:00 | 2021-07-08 10:00 | 240 | 1
Moneypoint | MP1 | 285 | 2021-07-07 10:00 | 2021-07-12 08:00 | 270 | 4.92
Turlough Hill | TH2 | 73 | 2021-07-07 10:00 | 2021-07-07 15:00 | F | 0.17
Turlough Hill | TH2 | 73 | 2021-07-07 10:00 | 2021-07-07 15:00 | F | 0.17
Moneypoint | MP3 | 285 | 2021-07-08 10:00 | 2021-07-09 10:00 | 250 | 1
Moneypoint | MP3 | 285 | 2021-07-09 10:00 | 2021-07-12 08:00 | 265 | 2.92
Tarbert | TB3 | 241 | 2021-07-09 15:00 | 2021-08-09 09:00 | 122 | 30.75
Aghada | AT1 | 90 | 2021-07-09 18:00 | 2021-07-12 23:00 | F | 3.17
Aghada | AT2 | 90 | 2021-07-09 18:00 | 2021-07-12 23:00 | F | 3.17
Kilroot | NIK2 | 258 | 2021-07-09 20:30 | 2021-07-30 20:30 | F | 21
Kilroot | NIKGT2 | 29 | 2021-07-09 20:30 | 2021-07-30 20:30 | F | 21
Huntstown | HNC | 342 | 2021-07-09 22:00 | 2021-07-11 23:00 | 220 | 2
Tawnaghmore | TP1 | 52 | 2021-07-10 14:00 | 2021-07-10 16:00 | F | 0.08
Moneypoint | MP1 | 285 | 2021-07-12 08:00 | 2021-07-12 22:00 | 180 | 0.58
Moneypoint | MP3 | 285 | 2021-07-12 08:00 | 2021-07-12 21:00 | 235 | 0.5
Ardnacrusha | AA1 | 21 | 2021-07-12 08:00 | 2021-07-16 20:00 | S | 4.5
Moyle | MOYLE | 450 | 2021-07-12 08:30 | 2021-07-19 17:00 | S | 7.33
Rhode | RP2 | 52 | 2021-07-12 10:30 | 2021-07-12 12:30 | F | 0.08
Tarbert | TB1 | 54 | 2021-07-12 15:00 | 2021-07-13 12:00 | F | 0.83
Tarbert | TB2 | 54 | 2021-07-12 15:00 | 2021-07-13 14:00 | F | 0.92
Poolbeg | PB5 | 146 | 2021-07-12 17:00 | 2021-08-14 21:00 | 134 | 33.17
Moneypoint | MP3 | 285 | 2021-07-12 21:00 | 2021-07-16 23:00 | F | 4.08
Moneypoint | MP1 | 285 | 2021-07-12 22:00 | 2021-07-14 22:30 | 280 | 2
Tarbert | TB2 | 54 | 2021-07-13 18:00 | 2021-07-14 17:00 | 44 | 0.92
Tarbert | TB1 | 54 | 2021-07-13 18:00 | 2021-07-14 17:00 | 33 | 0.92
Tawnaghmore | TP3 | 52 | 2021-07-15 10:00 | 2021-07-15 12:00 | F | 0.08
Dublin Waste To Energy | DW1 | 61.5 | 2021-07-16 04:00 | 2021-07-16 16:00 | F | 0.5
Turlough Hill | TH2 | 73 | 2021-07-16 06:00 | 2021-07-16 12:00 | F | 0.25
Moneypoint | MP1 | 285 | 2021-07-16 08:30 | 2021-07-16 19:00 | 230 | 0.42
Lee | LE3 | 8 | 2021-07-16 20:00 | 2021-07-25 17:00 | F | 8.83
Moneypoint | MP3 | 285 | 2021-07-16 22:00 | 2021-07-28 22:00 | S | 12
Rhode | RP1 | 52 | 2021-07-17 15:30 | 2021-07-17 18:30 | F | 0.08
Rhode | RP2 | 52 | 2021-07-17 19:00 | 2021-07-19 10:00 | F | 1.58
Turlough Hill | TH2 | 73 | 2021-07-18 04:30 | 2021-07-18 13:00 | F | 0.33
Rhode | RP1 | 52 | 2021-07-18 11:30 | 2021-07-19 11:00 | F | 0.96
Tarbert | TB2 | 54 | 2021-07-19 | 2021-07-20 | F | 1
Ballylumford | NIB31 | 249 | 2021-07-19 20:00 | 2021-08-02 20:30 | 161 | 14
Ballylumford | NIB32 | 249 | 2021-07-19 20:00 | 2021-08-02 20:30 | 161 | 14
Turlough Hill | TH3 | 73 | 2021-07-20 10:00 | 2021-07-20 15:00 | S | 0.17
Moneypoint | MP2 | 285 | 2021-07-23 22:00 | 2021-08-01 22:00 | S | 9
Aghada | AT2 | 90 | 2021-08-01 18:00 | 2021-09-18 20:00 | S | 48.08
Tynagh | TYC | 384 | 2021-08-06 20:00 | 2021-08-08 20:00 | F | 2
Coolkeeragh | NIC30 | 408 | 2021-08-07 16:00 | 2021-08-08 22:30 | S | 1.25
Ardnacrusha | AA3 | 19 | 2021-08-09 08:00 | 2021-10-01 20:00 | S | 53.5
Tarbert | TB3 | 241 | 2021-08-09 09:00 | 2021-09-05 17:00 | S | 27.33
Ballylumford | NIBGT2 | 58 | 2021-08-10 08:00 | 2021-08-11 08:30 | S | 1
Aghada | AT1 | 90 | 2021-08-13 08:00 | 2021-08-28 20:00 | S | 15.5
Poolbeg | PB6 | 168 | 2021-08-14 21:00 | 2021-08-16 20:00 | 84 | 1.92
Poolbeg | PB5 | 146 | 2021-08-14 21:00 | 2021-08-16 20:00 | F | 1.92
Ballylumford | NIBGT1 | 58 | 2021-08-16 07:00 | 2021-08-21 07:00 | S | 5
Ballylumford | NIBGT2 | 58 | 2021-08-21 07:00 | 2021-08-26 07:30 | S | 5
Erne | ER2 | 10 | 2021-08-23 08:00 | 2021-08-27 20:00 | S | 4.5
Erne | ER1 | 10 | 2021-08-23 08:00 | 2021-08-27 20:00 | S | 4.5
EWIC | EW1 | 500 | 2021-08-23 09:00 | 2021-10-12 23:00 | S | 50.58
Poolbeg | PB4 | 154 | 2021-08-29 12:00 | 2021-09-17 18:00 | S | 19.25
Poolbeg | PB6 | 168 | 2021-08-29 12:00 | 2021-09-15 | 84 | 16.5
Liffey | LI5 | 4 | 2021-08-30 08:00 | 2021-09-03 17:00 | S | 4.33
Edenderry | ED5 | 58 | 2021-09-03 08:00 | 2021-09-03 18:00 | S | 0.42
Edenderry | ED3 | 58 | 2021-09-03 08:00 | 2021-09-03 18:00 | S | 0.42
Erne | ER4 | 22.5 | 2021-09-06 08:00 | 2021-09-10 20:00 | S | 4.5
Poolbeg | PB6 | 168 | 2021-09-15 | 2021-10-24 23:30 | S | 39.96
Moneypoint | MP1 | 285 | 2021-09-17 22:00 | 2021-09-29 22:00 | S | 12
Kilroot | NIKGT1 | 29 | 2021-09-18 06:00 | 2021-10-30 17:30 | S | 42.46
Seal Rock | SK4 | 85 | 2021-09-27 06:00 | 2021-09-29 18:00 | S | 2.5
Moneypoint | MP1 | 285 | 2021-09-29 22:00 | 2021-10-07 22:00 | F | 8
Dublin Waste To Energy | DW1 | 61.5 | 2021-10-01 | 2021-10-10 | 26 | 9
Poolbeg | PB5 | 146 | 2021-10-02 | 2021-11-16 23:30 | S | 45.96
Turlough Hill | TH1 | 73 | 2021-10-04 08:00 | 2021-10-06 17:00 | S | 2.33
Turlough Hill | TH2 | 73 | 2021-10-04 08:00 | 2021-10-06 17:00 | S | 2.33
Coolkeeragh | NIC30 | 408 | 2021-10-05 | 2021-10-30 | S | 25
Dublin Waste To Energy | DW1 | 61.5 | 2021-10-10 | 2021-10-13 | S | 3
Dublin Waste To Energy | DW1 | 61.5 | 2021-10-13 | 2021-10-23 | 26 | 10
Poolbeg | PB6 | 168 | 2021-10-25 | 2021-11-16 23:30 | 84 | 22.96
Coolkeeragh | NICGT8 | 53 | 2021-10-30 | 2021-11-01 | S | 2
Ballylumford | NIBGT1 | 58 | 2021-11-02 03:00 | 2021-11-08 | S | 5.83
Ballylumford | NIBGT2 | 58 | 2021-11-08 | 2021-11-15 | S | 7
Seal Rock | SK3 | 85 | 2021-11-08 06:00 | 2021-11-10 18:00 | S | 2.5
Kilroot | NIKGT4 | 42 | 2021-11-15 | 2021-11-22 | S | 7
Kilroot | NIKGT3 | 42 | 2021-11-15 | 2021-11-22 | S | 7
Poolbeg | PB5 | 146 | 2021-11-16 23:30 | 2021-11-28 | F | 11
Poolbeg | PB6 | 168 | 2021-11-16 23:30 | 2021-11-28 | 84 | 11
Coolkeeragh | NIC30 | 408 | 2021-11-28 | 2021-11-29 | S | 1
Edenderry | ED1 | 118 | 2021-12-26 13:00 | 2022-01-02 08:00 | S | 6.75
|  |  | Scheduled Outage | S
|  |  | Forced Outage | F
|  |  | Unit partially available | 10