## Outage Plan EirGrid
2021 GENERATION OUTAGE PLAN (EIRGRID)
|  | Month | Jan '2021 |  |  |  |  | Feb '2021 |  |  |  | Mar '2021 |  |  |  |  | Apr '2021 |  |  |  | May '2021 |  |  |  |  | Jun '2021 |  |  |  | Jul '2021 |  |  |  | Aug '2021 |  |  |  |  | Sep '2021 |  |  |  | Oct '2021 |  |  |  | Nov '2021 |  |  |  |  | Dec '2021
|  | Week | 53 '2021 | 1 '2021 | 2 '2021 | 3 '2021 | 4 '2021 | 5 '2021 | 6 '2021 | 7 '2021 | 8 '2021 | 9 '2021 | 10 '2021 | 11 '2021 | 12 '2021 | 13 '2021 | 14 '2021 | 15 '2021 | 16 '2021 | 17 '2021 | 18 '2021 | 19 '2021 | 20 '2021 | 21 '2021 | 22 '2021 | 23 '2021 | 24 '2021 | 25 '2021 | 26 '2021 | 27 '2021 | 28 '2021 | 29 '2021 | 30 '2021 | 31 '2021 | 32 '2021 | 33 '2021 | 34 '2021 | 35 '2021 | 36 '2021 | 37 '2021 | 38 '2021 | 39 '2021 | 40 '2021 | 41 '2021 | 42 '2021 | 43 '2021 | 44 '2021 | 45 '2021 | 46 '2021 | 47 '2021 | 48 '2021 | 49 '2021 | 50 '2021 | 51 '2021 | 52 '2021
Station | Unit | NPR
Activation Energy | AE1 | 95
Activation Energy | AE2 | 12
Activation Energy | AE3 | 14
Activation Energy | AE4 | 15
Activation Energy | AE5 | 15
Activation Energy | EN1 | 15
Activation Energy | EN2 | 16
Activation Energy | EN3 | 16
Activation Energy | EN4 | 16
Activation Energy | EN5 | 6
Activation Energy | EN6 | 11
Aghada | AD2 | 449 | [7 empty] | F | [11 empty] | S | S | S
Aghada | AT1 | 90 | [33 empty] | S | S
Aghada | AT2 | 90 | [31 empty] | S | S | S | S | S | S | S
Aghada | AT4 | 90
Ardnacrusha | AA1 | 21 | [28 empty] | S
Ardnacrusha | AA2 | 22 | [23 empty] | S | S | S | S
Ardnacrusha | AA3 | 19 | [32 empty] | S | S | S | S | S | S | S | S
Ardnacrusha | AA4 | 24 | [14 empty] | S | S | S | S | S | S | S | S
DAE Virtual Power Plant | DP1 | 19
DAE Virtual Power Plant | DP2 | 26
Dublin Bay | DB1 | 405 | [17 empty] | S | S | S | S | S | S | S | S | S
Dublin Waste To Energy | DW1 | 62 | [24 empty] | S | S | S | [8 empty] | S | S | S
Edenderry | ED1 | 118 | [26 empty] | S | S | S | S | S | S | S | S | S | [17 empty] | S
Edenderry | ED3 | 58
Edenderry | ED5 | 58
Electric Ireland | EI1 | 20
Electricity Exchange DSU | EE1 | 47
Electricity Exchange DSU | EE2 | 20
Electricity Exchange DSU | EE3 | 8
Electricity Exchange DSU | EE4 | 9
Electricity Exchange DSU | EE5 | 7
Electricity Exchange DSU | EE6 | 14
Endeco Technologies | EC1 | 47
Endeco Technologies | EC2 | 11
Endeco Technologies | EC5 | 15
Energy Trading | ET1 | 13
Erne | ER1 | 10 | [15 empty] | S | S
Erne | ER2 | 10 | [19 empty] | S
Erne | ER3 | 22 | [24 empty] | S | S | S
Erne | ER4 | 22 | [36 empty] | S
EWIC | EW1 | 500 | [34 empty] | S | S | S | S | S | S | S
Great Island | GI4 | 461 | [41 empty] | S
Huntstown | HN2 | 400 | [5 empty] | F | F | F | F | S | S | S | S | S | S
Huntstown | HNC | 342
Indaver | IW1 | 17 | [15 empty] | S | S
Knockacummer | KC1 | 100
Lee | LE1 | 15 | [24 empty] | S | S | S | S
Lee | LE2 | 4 | [14 empty] | S | S
Lee | LE3 | 8 | [17 empty] | S | S | S | S | S
Liffey | LI1 | 15 | [15 empty] | S | S | S | S
Liffey | LI2 | 15 | [15 empty] | S | S | S | S
Liffey | LI4 | 4 | [20 empty] | S | S | S
Liffey | LI5 | 4 | [35 empty] | S
Moneypoint | MP1 | 285 | [29 empty] | S
Moneypoint | MP2 | 285 |  | F | F
Moneypoint | MP3 | 285 | [6 empty] | F | [31 empty] | S
North Wall | NW5 | 104 | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Poolbeg | PB4 | 154 |  |  |  | F | F | [30 empty] | S | S | S
Poolbeg | PB5 | 146 | [14 empty] | S | [25 empty] | S | S | S | S | S | S
Poolbeg | PB6 | 168 | [37 empty] | S | S | S | S | S | S
Powerhouse Generation | PG1 | 10
Rhode | RP1 | 52 | [20 empty] | S | S | S | S
Rhode | RP2 | 52 | [20 empty] | S | S | S | S
Seal Rock | SK3 | 85 | [24 empty] | S | S | S
Seal Rock | SK4 | 85 | [29 empty] | S
Seecon | SO1 | 105
Tarbert | TB1 | 54
Tarbert | TB2 | 54
Tarbert | TB3 | 241 | [24 empty] | S | S | S | S
Tarbert | TB4 | 243 | [7 empty] | F
Tawnaghmore | TP1 | 52 | [15 empty] | S | S | S | S
Tawnaghmore | TP3 | 52 | [15 empty] | S | S | S | S
Turlough Hill | TH1 | 73 | [12 empty] | S
Turlough Hill | TH2 | 73 | [12 empty] | S
Turlough Hill | TH3 | 73 | [12 empty] | S
Turlough Hill | TH4 | 73 | [12 empty] | S
Tynagh | TYC | 384 | [15 empty] | S | S | S
Viridian Energy | VE1 | 20
Viridian Energy DSU | VE2 | 13
Whitegate | WG1 | 444 | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F

## EirGrid Outages
Upcoming Outages including STMOs and Annual Outages
Station | Unit | NPR | Start Date | End Date | Value | Duration
North Wall | NW5 | 104 | 2019-10-01 | 2022-10-01 | S | 1096
Whitegate | WG1 | 444 | 2020-12-02 08:00 | 2021-08-08 23:00 | F | 249.58
Tarbert | TB3 | 241 | 2020-12-08 14:30 | 2021-04-30 | 226 | 142.38
Moneypoint | MP1 | 285 | 2020-12-20 20:00 | 2021-01-04 17:00 | 200 | 14.83
Moneypoint | MP2 | 285 | 2020-12-24 18:00 | 2021-01-04 15:00 | 120 | 10.83
EWIC | EW1 | 500 | 2021-01-02 09:00 | 2021-01-02 20:00 | F | 0.42
Tarbert | TB4 | 243 | 2021-01-02 09:30 | 2021-01-02 11:30 | F | 0.08
Liffey | LI2 | 15 | 2021-01-04 08:00 | 2021-01-04 09:30 | F | 0.04
Moneypoint | MP3 | 285 | 2021-01-04 10:30 | 2021-01-19 21:00 | 270 | 15.42
Moneypoint | MP2 | 285 | 2021-01-04 15:00 | 2021-01-06 15:30 | F | 2
Moneypoint | MP1 | 285 | 2021-01-04 17:00 | 2021-01-06 15:30 | 220 | 1.92
Tarbert | TB2 | 54 | 2021-01-06 09:00 | 2021-01-06 11:00 | F | 0.08
Moneypoint | MP2 | 285 | 2021-01-06 15:30 | 2021-01-07 10:30 | 120 | 0.75
Tarbert | TB2 | 54 | 2021-01-06 15:30 | 2021-01-07 | F | 0.33
Moneypoint | MP1 | 285 | 2021-01-06 15:30 | 2021-01-06 16:30 | F | 0
Tarbert | TB4 | 243 | 2021-01-06 16:00 | 2021-01-07 12:00 | 222 | 0.83
Moneypoint | MP1 | 285 | 2021-01-06 16:30 | 2021-01-09 12:00 | 220 | 2.79
Aghada | AT2 | 90 | 2021-01-07 04:00 | 2021-01-08 07:30 | F | 1.12
Aghada | AT1 | 90 | 2021-01-07 04:00 | 2021-01-08 07:30 | F | 1.12
Moneypoint | MP2 | 285 | 2021-01-07 10:30 | 2021-01-19 22:00 | F | 12.46
Tarbert | TB4 | 243 | 2021-01-07 12:00 | 2021-01-08 12:00 | F | 1
Tarbert | TB2 | 54 | 2021-01-07 16:00 | 2021-01-08 14:00 | F | 0.92
Dublin Waste To Energy | DW1 | 61.5 | 2021-01-08 05:00 | 2021-01-08 08:00 | F | 0.08
Tarbert | TB4 | 243 | 2021-01-08 12:00 | 2021-01-11 12:00 | 222 | 3
Huntstown | HN2 | 400 | 2021-01-08 21:00 | 2021-01-10 21:00 | S | 2
Erne | ER1 | 10 | 2021-01-09 08:30 | 2021-01-09 17:00 | S | 0.33
Erne | ER2 | 10 | 2021-01-09 08:30 | 2021-01-09 17:00 | S | 0.33
Moneypoint | MP1 | 285 | 2021-01-09 12:00 | 2021-01-09 16:30 | 230 | 0.17
Moneypoint | MP1 | 285 | 2021-01-09 16:30 | 2021-01-19 21:00 | 240 | 10.17
Erne | ER1 | 10 | 2021-01-10 08:30 | 2021-01-10 18:00 | S | 0.38
Erne | ER2 | 10 | 2021-01-10 08:30 | 2021-01-10 17:00 | S | 0.33
Turlough Hill | TH1 | 73 | 2021-01-10 16:30 | 2021-01-11 12:00 | F | 0.79
Liffey | LI4 | 4 | 2021-01-11 07:00 | 2021-01-11 18:00 | S | 0.42
Liffey | LI2 | 15 | 2021-01-11 07:00 | 2021-01-11 18:00 | S | 0.42
Liffey | LI1 | 15 | 2021-01-11 07:00 | 2021-01-11 18:00 | S | 0.42
Erne | ER1 | 10 | 2021-01-11 08:30 | 2021-01-11 17:00 | S | 0.33
Erne | ER2 | 10 | 2021-01-11 08:30 | 2021-01-11 17:00 | S | 0.33
Tarbert | TB4 | 243 | 2021-01-11 12:00 | 2021-01-11 22:00 | 209 | 0.42
Tarbert | TB4 | 243 | 2021-01-11 22:00 | 2021-01-11 23:30 | F | 0.04
Tarbert | TB4 | 243 | 2021-01-11 23:30 | 2021-01-15 10:00 | 209 | 3.42
Erne | ER1 | 10 | 2021-01-12 08:30 | 2021-01-12 17:00 | S | 0.33
Erne | ER2 | 10 | 2021-01-12 08:30 | 2021-01-12 17:00 | S | 0.33
Tarbert | TB2 | 54 | 2021-01-12 17:30 | 2021-01-12 19:30 | F | 0.08
Tarbert | TB2 | 54 | 2021-01-14 12:00 | 2021-01-14 14:00 | F | 0.08
Tarbert | TB4 | 243 | 2021-01-15 10:00 | 2021-01-19 03:00 | F | 3.67
Poolbeg | PB6 | 168 | 2021-01-18 17:30 | 2021-02-02 17:00 | 84 | 14.96
Tarbert | TB4 | 243 | 2021-01-19 03:00 | 2021-01-20 09:30 | 237 | 1.25
Poolbeg | PB4 | 154 | 2021-01-19 12:00 | 2021-02-02 17:00 | F | 14.17
Moneypoint | MP3 | 285 | 2021-01-19 21:00 | 2021-01-21 09:00 | 230 | 1.5
Moneypoint | MP1 | 285 | 2021-01-19 21:00 | 2021-01-21 09:00 | 200 | 1.5
Moneypoint | MP2 | 285 | 2021-01-19 22:00 | 2021-02-03 13:00 | 120 | 14.58
Dublin Waste To Energy | DW1 | 61.5 | 2021-01-21 05:00 | 2021-01-24 07:00 | 52 | 3.08
Great Island | GI4 | 461 | 2021-01-21 06:00 | 2021-01-21 08:30 | F | 0.08
Moneypoint | MP3 | 285 | 2021-01-21 09:00 | 2021-02-04 03:30 | 260 | 13.75
Moneypoint | MP1 | 285 | 2021-01-21 09:00 | 2021-01-27 12:00 | 230 | 6.08
Edenderry | ED1 | 118 | 2021-01-22 09:00 | 2021-01-22 15:00 | 65 | 0.25
Tarbert | TB4 | 243 | 2021-01-23 19:30 | 2021-01-25 01:00 | F | 1.21
Dublin Waste To Energy | DW1 | 61.5 | 2021-01-24 07:00 | 2021-01-26 09:00 | 22 | 2.08
Ardnacrusha | AA3 | 19 | 2021-01-24 10:00 | 2021-01-24 11:30 | F | 0.04
Huntstown | HNC | 342 | 2021-01-24 10:00 | 2021-01-24 11:00 | F | 0
Huntstown | HNC | 342 | 2021-01-24 11:00 | 2021-01-24 16:30 | F | 0.21
Tawnaghmore | TP1 | 52 | 2021-01-24 13:00 | 2021-01-24 14:30 | F | 0.04
Edenderry | ED1 | 118 | 2021-01-25 | 2021-01-25 12:00 | 55 | 0.5
Seal Rock | SK4 | 85 | 2021-01-26 06:00 | 2021-01-29 17:00 | S | 3.42
Tarbert | TB4 | 243 | 2021-01-26 13:00 | 2021-02-04 17:00 | 217 | 9.17
Moneypoint | MP1 | 285 | 2021-01-27 12:00 | 2021-01-27 13:00 | 205 | 0
Moneypoint | MP1 | 285 | 2021-01-27 13:00 | 2021-01-29 17:30 | 235 | 2.17
Huntstown | HNC | 342 | 2021-01-28 07:00 | 2021-01-28 11:30 | F | 0.17
Turlough Hill | TH2 | 73 | 2021-01-28 10:00 | 2021-01-28 15:00 | S | 0.17
Moneypoint | MP1 | 285 | 2021-01-29 17:30 | 2021-01-31 13:30 | 250 | 1.83
Huntstown | HN2 | 400 | 2021-01-29 22:00 | 2021-02-28 23:00 | F | 30
Moneypoint | MP1 | 285 | 2021-01-31 13:30 | 2021-01-31 19:30 | 200 | 0.25
Moneypoint | MP1 | 285 | 2021-01-31 19:30 | 2021-02-04 17:00 | 220 | 3.88
Dublin Waste To Energy | DW1 | 61.5 | 2021-02-01 04:30 | 2021-02-01 09:00 | 45 | 0.17
Tarbert | TB1 | 54 | 2021-02-01 09:00 | 2021-02-01 12:00 | F | 0.08
Turlough Hill | TH1 | 73 | 2021-02-02 10:00 | 2021-02-02 12:30 | S | 0.08
Poolbeg | PB4 | 154 | 2021-02-03 11:30 | 2021-02-03 17:00 | F | 0.21
Moneypoint | MP2 | 285 | 2021-02-03 13:00 | 2021-02-12 18:00 | 99 | 9.17
Moneypoint | MP3 | 285 | 2021-02-04 03:00 | 2021-02-04 14:00 | 190 | 0.42
Tarbert | TB3 | 241 | 2021-02-04 08:00 | 2021-02-09 02:30 | F | 4.75
Seecon | SO1 | 105 | 2021-02-04 10:00 | 2021-02-04 17:00 | S | 0.25
Moneypoint | MP3 | 285 | 2021-02-04 13:30 | 2021-02-04 16:00 | 240 | 0.08
Moneypoint | MP3 | 285 | 2021-02-04 15:30 | 2021-02-04 17:30 | 260 | 0.08
Moneypoint | MP1 | 285 | 2021-02-04 17:00 | 2021-02-09 09:30 | 240 | 4.67
Moneypoint | MP3 | 285 | 2021-02-04 17:00 | 2021-02-09 10:00 | 270 | 4.67
Dublin Waste To Energy | DW1 | 61.5 | 2021-02-09 05:00 | 2021-02-09 23:00 | F | 0.75
Turlough Hill | TH4 | 73 | 2021-02-09 09:00 | 2021-02-09 14:00 | S | 0.17
Moneypoint | MP3 | 285 | 2021-02-09 15:00 | 2021-02-16 23:00 | F | 7.33
Tarbert | TB3 | 241 | 2021-02-10 08:00 | 2021-02-10 10:30 | F | 0.08
Turlough Hill | TH3 | 73 | 2021-02-10 10:00 | 2021-02-10 15:00 | S | 0.17
Moneypoint | MP1 | 285 | 2021-02-10 17:30 | 2021-02-13 05:30 | 220 | 2.5
Dublin Waste To Energy | DW1 | 61.5 | 2021-02-11 12:00 | 2021-02-16 23:00 | 58 | 5.42
Moneypoint | MP2 | 285 | 2021-02-12 18:00 | 2021-02-13 05:30 | 120 | 0.46
Tynagh | TYC | 384 | 2021-02-12 20:00 | 2021-02-15 | S | 2.17
Moneypoint | MP2 | 285 | 2021-02-13 05:30 | 2021-02-14 17:00 | F | 1.46
Moneypoint | MP1 | 285 | 2021-02-13 05:30 | 2021-02-13 21:00 | F | 0.62
Tarbert | TB4 | 243 | 2021-02-13 17:00 | 2021-02-21 17:00 | F | 8
Aghada | AD2 | 449 | 2021-02-13 20:00 | 2021-02-20 22:00 | F | 7.08
Moneypoint | MP1 | 285 | 2021-02-13 21:00 | 2021-02-26 23:00 | 220 | 13.08
Moneypoint | MP2 | 285 | 2021-02-14 17:00 | 2021-02-14 18:00 | 100 | 0
Moneypoint | MP2 | 285 | 2021-02-14 18:00 | 2021-03-26 23:00 | 120 | 40.17
Dublin Waste To Energy | DW1 | 61.5 | 2021-02-16 23:00 | 2021-02-26 | 51 | 9
Moneypoint | MP3 | 285 | 2021-02-17 10:00 | 2021-02-17 13:30 | F | 0.12
Edenderry | ED1 | 118 | 2021-02-18 10:30 | 2021-02-18 12:30 | 55 | 0.08
Huntstown | HNC | 342 | 2021-02-18 23:00 | 2021-02-19 18:00 | 225 | 0.75
EWIC | EW1 | 500 | 2021-02-25 09:00 | 2021-02-26 23:00 | S | 1.58
Huntstown | HN2 | 400 | 2021-02-28 23:00 | 2021-04-13 17:00 | S | 43.75
Seal Rock | SK3 | 85 | 2021-03-01 06:00 | 2021-03-03 18:00 | S | 2.5
Aghada | AT4 | 90 | 2021-03-08 | 2021-03-11 20:00 | S | 3.83
Turlough Hill | TH3 | 73 | 2021-03-20 06:00 | 2021-03-28 21:00 | S | 8.58
Turlough Hill | TH4 | 73 | 2021-03-20 06:00 | 2021-03-28 21:00 | S | 8.58
Turlough Hill | TH2 | 73 | 2021-03-20 06:00 | 2021-03-28 21:00 | S | 8.58
Turlough Hill | TH1 | 73 | 2021-03-20 06:00 | 2021-03-28 21:00 | S | 8.58
Edenderry | ED1 | 118 | 2021-04-01 18:00 | 2021-04-07 08:00 | S | 5.58
Poolbeg | PB6 | 168 | 2021-04-05 09:00 | 2021-04-10 17:00 | 84 | 5.33
Poolbeg | PB5 | 146 | 2021-04-05 09:00 | 2021-04-10 17:00 | S | 5.33
Ardnacrusha | AA4 | 24 | 2021-04-06 08:00 | 2021-05-28 20:00 | S | 52.5
Lee | LE2 | 4 | 2021-04-06 08:00 | 2021-04-16 20:00 | S | 10.5
Tynagh | TYC | 384 | 2021-04-11 | 2021-05-03 | S | 22
Indaver | IW1 | 17 | 2021-04-12 | 2021-04-27 | S | 15
Liffey | LI2 | 15 | 2021-04-12 08:00 | 2021-05-09 17:00 | S | 27.33
Liffey | LI1 | 15 | 2021-04-12 08:00 | 2021-05-09 17:00 | S | 27.33
Erne | ER1 | 10 | 2021-04-12 08:00 | 2021-04-26 20:00 | S | 14.5
Tawnaghmore | TP3 | 52 | 2021-04-12 09:00 | 2021-05-09 17:00 | S | 27.33
Tawnaghmore | TP1 | 52 | 2021-04-12 09:00 | 2021-05-09 17:00 | S | 27.33
Dublin Bay | DB1 | 405 | 2021-04-23 13:00 | 2021-06-28 06:00 | S | 65.67
Lee | LE3 | 8 | 2021-04-26 08:00 | 2021-05-28 20:00 | S | 32.5
Aghada | AD2 | 449 | 2021-05-09 01:00 | 2021-05-30 20:00 | S | 21.75
Erne | ER2 | 10 | 2021-05-10 08:00 | 2021-05-14 20:00 | S | 4.5
Seal Rock | SK3 | 85 | 2021-05-10 12:00 | 2021-05-12 12:00 | S | 2
Seal Rock | SK4 | 85 | 2021-05-10 18:00 | 2021-05-12 18:00 | S | 2
Edenderry | ED3 | 58 | 2021-05-12 08:00 | 2021-05-12 18:00 | S | 0.42
Edenderry | ED5 | 58 | 2021-05-12 08:00 | 2021-05-12 18:00 | S | 0.42
Tarbert | TB2 | 54 | 2021-05-15 | 2021-05-22 | S | 7
Tarbert | TB1 | 54 | 2021-05-15 | 2021-05-22 | S | 7
Liffey | LI4 | 4 | 2021-05-17 08:00 | 2021-06-06 17:00 | S | 20.33
Rhode | RP2 | 52 | 2021-05-17 09:00 | 2021-06-12 17:00 | S | 26.33
Rhode | RP1 | 52 | 2021-05-17 09:00 | 2021-06-12 17:00 | S | 26.33
EWIC | EW1 | 500 | 2021-05-26 09:00 | 2021-05-27 23:00 | S | 1.58
Ardnacrusha | AA2 | 22 | 2021-06-08 08:00 | 2021-07-02 20:00 | S | 24.5
Tarbert | TB3 | 241 | 2021-06-12 09:00 | 2021-07-10 17:00 | S | 28.33
Dublin Waste To Energy | DW1 | 61.5 | 2021-06-13 | 2021-07-07 | S | 24
Seal Rock | SK3 | 85 | 2021-06-13 06:00 | 2021-07-01 18:00 | S | 18.5
Lee | LE1 | 15 | 2021-06-14 08:00 | 2021-07-09 20:00 | S | 25.5
Erne | ER3 | 22.5 | 2021-06-14 08:00 | 2021-07-04 20:00 | S | 20.5
Edenderry | ED1 | 118 | 2021-06-25 12:00 | 2021-08-30 18:00 | S | 66.25
Ardnacrusha | AA1 | 21 | 2021-07-12 08:00 | 2021-07-16 20:00 | S | 4.5
Moneypoint | MP1 | 285 | 2021-07-16 22:00 | 2021-07-28 22:00 | S | 12
Seal Rock | SK4 | 85 | 2021-07-19 06:00 | 2021-07-23 18:00 | S | 4.5
Moneypoint | MP2 | 285 | 2021-07-23 22:00 | 2021-07-31 22:00 | S | 8
Aghada | AT2 | 90 | 2021-08-01 18:00 | 2021-09-18 20:00 | S | 48.08
Tarbert | TB4 | 243 | 2021-08-09 | 2021-08-10 | S | 1
Ardnacrusha | AA3 | 19 | 2021-08-09 08:00 | 2021-10-01 20:00 | S | 53.5
Aghada | AT1 | 90 | 2021-08-13 08:00 | 2021-08-28 20:00 | S | 15.5
EWIC | EW1 | 500 | 2021-08-23 09:00 | 2021-10-12 23:00 | S | 50.58
Poolbeg | PB4 | 154 | 2021-08-29 12:00 | 2021-09-17 18:00 | S | 19.25
Poolbeg | PB6 | 168 | 2021-08-29 12:00 | 2021-09-15 | 84 | 16.5
Liffey | LI5 | 4 | 2021-08-30 08:00 | 2021-09-03 17:00 | S | 4.33
Dublin Waste To Energy | DW1 | 61.5 | 2021-09-01 | 2021-09-22 00:30 | S | 21
Erne | ER4 | 22.5 | 2021-09-06 08:00 | 2021-09-10 20:00 | S | 4.5
Poolbeg | PB6 | 168 | 2021-09-15 | 2021-10-24 23:30 | S | 39.96
Moneypoint | MP3 | 285 | 2021-09-17 22:00 | 2021-09-29 22:00 | S | 12
Poolbeg | PB5 | 146 | 2021-10-02 | 2021-11-16 23:30 | S | 45.96
Turlough Hill | TH1 | 73 | 2021-10-04 08:00 | 2021-10-06 17:00 | S | 2.33
Turlough Hill | TH2 | 73 | 2021-10-04 08:00 | 2021-10-06 17:00 | S | 2.33
Great Island | GI4 | 461 | 2021-10-09 | 2021-10-16 00:30 | S | 7
Poolbeg | PB6 | 168 | 2021-10-25 | 2021-11-16 23:30 | 84 | 22.96
Seal Rock | SK3 | 85 | 2021-11-08 06:00 | 2021-11-10 18:00 | S | 2.5
Seal Rock | SK4 | 85 | 2021-12-06 06:00 | 2021-12-08 18:00 | S | 2.5
Edenderry | ED1 | 118 | 2021-12-26 13:00 | 2022-01-02 08:00 | S | 6.75
North Wall | NW5 | 104 | 2022-01-01 | 2022-10-01 00:30 | S | 273
|  |  | Scheduled Outage | S
|  |  | Forced Outage | F
|  |  | Unit partially available | 10

## Outage Plan SONI
2021 GENERATION OUTAGE PLAN (SONI)
|  | Month | Jan '2021 |  |  |  |  | Feb '2021 |  |  |  | Mar '2021 |  |  |  |  | Apr '2021 |  |  |  | May '2021 |  |  |  |  | Jun '2021 |  |  |  | Jul '2021 |  |  |  | Aug '2021 |  |  |  |  | Sep '2021 |  |  |  | Oct '2021 |  |  |  | Nov '2021 |  |  |  |  | Dec '2021
|  | Week | 53 '2021 | 1 '2021 | 2 '2021 | 3 '2021 | 4 '2021 | 5 '2021 | 6 '2021 | 7 '2021 | 8 '2021 | 9 '2021 | 10 '2021 | 11 '2021 | 12 '2021 | 13 '2021 | 14 '2021 | 15 '2021 | 16 '2021 | 17 '2021 | 18 '2021 | 19 '2021 | 20 '2021 | 21 '2021 | 22 '2021 | 23 '2021 | 24 '2021 | 25 '2021 | 26 '2021 | 27 '2021 | 28 '2021 | 29 '2021 | 30 '2021 | 31 '2021 | 32 '2021 | 33 '2021 | 34 '2021 | 35 '2021 | 36 '2021 | 37 '2021 | 38 '2021 | 39 '2021 | 40 '2021 | 41 '2021 | 42 '2021 | 43 '2021 | 44 '2021 | 45 '2021 | 46 '2021 | 47 '2021 | 48 '2021 | 49 '2021 | 50 '2021 | 51 '2021 | 52 '2021
Station | Unit | NPR
AC Automation | NIACA | 8
Activation Energy | NIAEA | 9
Ballylumford | NIB10 | 94 | [24 empty] | S | S | S | S
Ballylumford | NIB31 | 249
Ballylumford | NIB32 | 249 | [9 empty] | S | S | S | S | S | S | S | S | S
Ballylumford | NIBGT1 | 58
Ballylumford | NIBGT2 | 58 | [45 empty] | S
Contour Global | NICG2 | 3
Contour Global | NICGA | 12
Coolkeeragh | NIC30 | 408 | [40 empty] | S | S | S | S
Coolkeeragh | NICGT8 | 53 | [19 empty] | S
Empower | NIEMP | 3
Endeco Technologies | NIECA | 13
Energy Trading | NIETB | 9
Energy Trading | NIETD | 5
Energy Trading | NIETR | 19
iPower | NIAGU | 74
Kilroot | NIK1 | 256 | [32 empty] | S | S | S | S | S | S | S | S
Kilroot | NIK2 | 258 | [20 empty] | S | S | S | S | S | S | S | S
Kilroot | NIKGT1 | 29 | [38 empty] | S | S | S | S | S | S
Kilroot | NIKGT2 | 29
Kilroot | NIKGT3 | 42 | [46 empty] | S
Kilroot | NIKGT4 | 42 | [46 empty] | S
Lisahally | NILPS | 18 | [9 empty] | S | S
Moyle | MOYLE | 450 | [28 empty] | S
Powerhouse Generation | NIPH1 | 34

## SONI Outages
Upcoming Outages including STMOs and Annual Outages
Station | Unit | NPR | Start Date | End Date | Value | Duration
Lisahally | NILPS | 17.6 | 2021-01-03 02:00 | 2021-01-11 09:00 | 16 | 8.25
Kilroot | NIKGT4 | 42 | 2021-01-06 13:30 | 2021-01-06 17:00 | F | 0.12
Kilroot | NIK2 | 258 | 2021-01-06 15:30 | 2021-01-18 13:00 | 180 | 11.88
Kilroot | NIKGT4 | 42 | 2021-01-06 23:30 | 2021-01-07 16:30 | F | 0.67
Ballylumford | NIB32 | 249 | 2021-01-10 23:00 | 2021-01-11 19:00 | S | 0.83
Lisahally | NILPS | 17.6 | 2021-01-11 09:00 | 2021-01-12 07:30 | 15 | 0.92
Ballylumford | NIB32 | 249 | 2021-01-12 08:30 | 2021-01-12 09:30 | 60 | 0
Lisahally | NILPS | 17.6 | 2021-01-12 10:00 | 2021-01-12 14:30 | S | 0.17
Ballylumford | NIBGT1 | 58 | 2021-01-12 12:30 | 2021-01-12 15:00 | F | 0.08
Lisahally | NILPS | 17.6 | 2021-01-12 14:30 | 2021-01-12 22:00 | F | 0.29
Kilroot | NIKGT2 | 29 | 2021-01-12 16:30 | 2021-01-12 18:00 | F | 0.04
Kilroot | NIKGT1 | 29 | 2021-01-12 17:30 | 2021-01-12 18:30 | F | 0
Kilroot | NIKGT1 | 29 | 2021-01-12 19:00 | 2021-01-13 19:00 | F | 1
Lisahally | NILPS | 17.6 | 2021-01-12 23:30 | 2021-01-13 12:30 | 16 | 0.5
Lisahally | NILPS | 17.6 | 2021-01-13 12:30 | 2021-01-13 13:30 | 13 | 0
Lisahally | NILPS | 17.6 | 2021-01-13 13:30 | 2021-01-22 13:00 | 16 | 8.96
Kilroot | NIKGT2 | 29 | 2021-01-13 14:00 | 2021-01-13 16:00 | F | 0.08
Coolkeeragh | NIC30 | 408 | 2021-01-14 21:00 | 2021-01-15 06:30 | S | 0.38
Kilroot | NIKGT4 | 42 | 2021-01-15 06:30 | 2021-01-15 14:30 | F | 0.33
Coolkeeragh | NIC30 | 408 | 2021-01-15 20:00 | 2021-01-16 04:30 | S | 0.33
Moyle | MOYLE | 450 | 2021-01-16 08:00 | 2021-01-16 12:00 | 250 | 0.17
Ballylumford | NIB10 | 94 | 2021-01-16 11:00 | 2021-01-21 01:00 | F | 4.58
Ballylumford | NIB32 | 249 | 2021-01-17 09:00 | 2021-01-18 01:00 | 160 | 0.67
Lisahally | NILPS | 17.6 | 2021-01-22 13:00 | 2021-01-22 16:30 | 13 | 0.12
Lisahally | NILPS | 17.6 | 2021-01-22 16:30 | 2021-02-01 | 15 | 9.29
Ballylumford | NIB31 | 249 | 2021-01-22 20:00 | 2021-01-23 15:00 | S | 0.75
Kilroot | NIKGT2 | 29 | 2021-01-27 06:00 | 2021-01-27 10:30 | F | 0.17
Kilroot | NIKGT1 | 29 | 2021-01-28 06:00 | 2021-01-28 13:00 | S | 0.25
Kilroot | NIKGT1 | 29 | 2021-01-28 13:00 | 2021-01-28 14:00 | F | 0
Kilroot | NIKGT4 | 42 | 2021-01-29 06:00 | 2021-01-29 18:30 | S | 0.5
Kilroot | NIKGT3 | 42 | 2021-01-29 06:00 | 2021-01-29 18:30 | S | 0.5
Ballylumford | NIB31 | 249 | 2021-01-29 22:00 | 2021-01-31 12:30 | S | 1.58
Coolkeeragh | NIC30 | 408 | 2021-01-30 21:30 | 2021-01-31 05:00 | F | 0.29
Ballylumford | NIB31 | 249 | 2021-01-31 12:30 | 2021-01-31 17:00 | 85 | 0.17
Kilroot | NIK2 | 258 | 2021-02-01 18:30 | 2021-02-01 21:30 | 148 | 0.08
Kilroot | NIK2 | 258 | 2021-02-03 12:30 | 2021-02-08 15:30 | 169 | 5.08
Kilroot | NIK1 | 256 | 2021-02-08 13:30 | 2021-02-09 17:00 | 100 | 1.12
Kilroot | NIKGT3 | 42 | 2021-02-13 07:00 | 2021-02-13 18:30 | F | 0.46
Kilroot | NIKGT4 | 42 | 2021-02-14 07:00 | 2021-02-14 18:30 | F | 0.46
Ballylumford | NIB10 | 94 | 2021-02-16 22:00 | 2021-02-16 23:00 | F | 0
Ballylumford | NIB32 | 249 | 2021-02-16 22:00 | 2021-02-17 04:30 | S | 0.25
Coolkeeragh | NIC30 | 408 | 2021-02-19 20:00 | 2021-02-23 22:30 | S | 4.08
Ballylumford | NIB32 | 249 | 2021-02-28 20:00 | 2021-04-29 20:30 | S | 60
Lisahally | NILPS | 17.6 | 2021-03-04 18:00 | 2021-03-14 18:30 | S | 10
Coolkeeragh | NIC30 | 408 | 2021-05-07 16:00 | 2021-05-09 22:30 | S | 2.25
Coolkeeragh | NICGT8 | 53 | 2021-05-10 | 2021-05-17 | S | 7
Kilroot | NIK2 | 258 | 2021-05-15 | 2021-07-10 | S | 56
Ballylumford | NIB10 | 94 | 2021-06-14 | 2021-07-11 | S | 27
Moyle | MOYLE | 450 | 2021-07-12 | 2021-07-20 | S | 8
Ballylumford | NIB32 | 249 | 2021-07-20 | 2021-08-03 | 161 | 14
Ballylumford | NIB31 | 249 | 2021-07-20 | 2021-08-03 | 161 | 14
Coolkeeragh | NIC30 | 408 | 2021-08-08 | 2021-08-09 | S | 1
Kilroot | NIK1 | 256 | 2021-08-09 | 2021-10-05 | S | 57
Kilroot | NIKGT1 | 29 | 2021-09-18 06:00 | 2021-10-30 17:30 | S | 42.46
Coolkeeragh | NIC30 | 408 | 2021-10-05 | 2021-10-30 | S | 25
Coolkeeragh | NICGT8 | 53 | 2021-10-30 | 2021-11-01 | S | 2
Ballylumford | NIBGT2 | 58 | 2021-11-08 | 2021-11-15 | S | 7
Kilroot | NIKGT4 | 42 | 2021-11-15 | 2021-11-22 | S | 7
Kilroot | NIKGT3 | 42 | 2021-11-15 | 2021-11-22 | S | 7
Coolkeeragh | NIC30 | 408 | 2021-11-28 | 2021-11-29 | S | 1
|  |  | Scheduled Outage | S
|  |  | Forced Outage | F
|  |  | Unit partially available | 10

## Outage Plan All Island
2021 GENERATION OUTAGE PLAN (All Island)
|  | Month | Jan '2021 |  |  |  |  | Feb '2021 |  |  |  | Mar '2021 |  |  |  |  | Apr '2021 |  |  |  | May '2021 |  |  |  |  | Jun '2021 |  |  |  | Jul '2021 |  |  |  | Aug '2021 |  |  |  |  | Sep '2021 |  |  |  | Oct '2021 |  |  |  | Nov '2021 |  |  |  |  | Dec '2021
|  | Week | 53 '2021 | 1 '2021 | 2 '2021 | 3 '2021 | 4 '2021 | 5 '2021 | 6 '2021 | 7 '2021 | 8 '2021 | 9 '2021 | 10 '2021 | 11 '2021 | 12 '2021 | 13 '2021 | 14 '2021 | 15 '2021 | 16 '2021 | 17 '2021 | 18 '2021 | 19 '2021 | 20 '2021 | 21 '2021 | 22 '2021 | 23 '2021 | 24 '2021 | 25 '2021 | 26 '2021 | 27 '2021 | 28 '2021 | 29 '2021 | 30 '2021 | 31 '2021 | 32 '2021 | 33 '2021 | 34 '2021 | 35 '2021 | 36 '2021 | 37 '2021 | 38 '2021 | 39 '2021 | 40 '2021 | 41 '2021 | 42 '2021 | 43 '2021 | 44 '2021 | 45 '2021 | 46 '2021 | 47 '2021 | 48 '2021 | 49 '2021 | 50 '2021 | 51 '2021 | 52 '2021
Station | Unit | NPR
AC Automation | NIACA | 8
Activation Energy | AE1 | 95
Activation Energy | AE2 | 12
Activation Energy | AE3 | 14
Activation Energy | AE4 | 15
Activation Energy | AE5 | 15
Activation Energy | EN1 | 15
Activation Energy | EN2 | 16
Activation Energy | EN3 | 16
Activation Energy | EN4 | 16
Activation Energy | EN5 | 6
Activation Energy | EN6 | 11
Activation Energy | NIAEA | 9
Aghada | AD2 | 449 | [7 empty] | F | [11 empty] | S | S | S
Aghada | AT1 | 90 | [33 empty] | S | S
Aghada | AT2 | 90 | [31 empty] | S | S | S | S | S | S | S
Aghada | AT4 | 90
Ardnacrusha | AA1 | 21 | [28 empty] | S
Ardnacrusha | AA2 | 22 | [23 empty] | S | S | S | S
Ardnacrusha | AA3 | 19 | [32 empty] | S | S | S | S | S | S | S | S
Ardnacrusha | AA4 | 24 | [14 empty] | S | S | S | S | S | S | S | S
Ballylumford | NIB10 | 94 | [24 empty] | S | S | S | S
Ballylumford | NIB31 | 249
Ballylumford | NIB32 | 249 | [9 empty] | S | S | S | S | S | S | S | S | S
Ballylumford | NIBGT1 | 58
Ballylumford | NIBGT2 | 58 | [45 empty] | S
Contour Global | NICG2 | 3
Contour Global | NICGA | 12
Coolkeeragh | NIC30 | 408 | [40 empty] | S | S | S | S
Coolkeeragh | NICGT8 | 53 | [19 empty] | S
DAE Virtual Power Plant | DP1 | 19
DAE Virtual Power Plant | DP2 | 26
Dublin Bay | DB1 | 405 | [17 empty] | S | S | S | S | S | S | S | S | S
Dublin Waste To Energy | DW1 | 62 | [24 empty] | S | S | S | [8 empty] | S | S | S
Edenderry | ED1 | 118 | [26 empty] | S | S | S | S | S | S | S | S | S | [17 empty] | S
Edenderry | ED3 | 58
Edenderry | ED5 | 58
Electric Ireland | EI1 | 20
Electricity Exchange DSU | EE1 | 47
Electricity Exchange DSU | EE2 | 20
Electricity Exchange DSU | EE3 | 8
Electricity Exchange DSU | EE4 | 9
Electricity Exchange DSU | EE5 | 7
Electricity Exchange DSU | EE6 | 14
Empower | NIEMP | 3
Endeco Technologies | EC1 | 47
Endeco Technologies | EC2 | 11
Endeco Technologies | EC5 | 15
Endeco Technologies | NIECA | 13
Energy Trading | ET1 | 13
Energy Trading | NIETB | 9
Energy Trading | NIETD | 5
Energy Trading | NIETR | 19
Erne | ER1 | 10 | [15 empty] | S | S
Erne | ER2 | 10 | [19 empty] | S
Erne | ER3 | 22 | [24 empty] | S | S | S
Erne | ER4 | 22 | [36 empty] | S
EWIC | EW1 | 500 | [34 empty] | S | S | S | S | S | S | S
Great Island | GI4 | 461 | [41 empty] | S
Huntstown | HN2 | 400 | [5 empty] | F | F | F | F | S | S | S | S | S | S
Huntstown | HNC | 342
Indaver | IW1 | 17 | [15 empty] | S | S
iPower | NIAGU | 74
Kilroot | NIK1 | 256 | [32 empty] | S | S | S | S | S | S | S | S
Kilroot | NIK2 | 258 | [20 empty] | S | S | S | S | S | S | S | S
Kilroot | NIKGT1 | 29 | [38 empty] | S | S | S | S | S | S
Kilroot | NIKGT2 | 29
Kilroot | NIKGT3 | 42 | [46 empty] | S
Kilroot | NIKGT4 | 42 | [46 empty] | S
Knockacummer | KC1 | 100
Lee | LE1 | 15 | [24 empty] | S | S | S | S
Lee | LE2 | 4 | [14 empty] | S | S
Lee | LE3 | 8 | [17 empty] | S | S | S | S | S
Liffey | LI1 | 15 | [15 empty] | S | S | S | S
Liffey | LI2 | 15 | [15 empty] | S | S | S | S
Liffey | LI4 | 4 | [20 empty] | S | S | S
Liffey | LI5 | 4 | [35 empty] | S
Lisahally | NILPS | 18 | [9 empty] | S | S
Moneypoint | MP1 | 285 | [29 empty] | S
Moneypoint | MP2 | 285 |  | F | F
Moneypoint | MP3 | 285 | [6 empty] | F | [31 empty] | S
Moyle | MOYLE | 450 | [28 empty] | S
North Wall | NW5 | 104 | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Poolbeg | PB4 | 154 |  |  |  | F | F | [30 empty] | S | S | S
Poolbeg | PB5 | 146 | [14 empty] | S | [25 empty] | S | S | S | S | S | S
Poolbeg | PB6 | 168 | [37 empty] | S | S | S | S | S | S
Powerhouse Generation | NIPH1 | 34
Powerhouse Generation | PG1 | 10
Rhode | RP1 | 52 | [20 empty] | S | S | S | S
Rhode | RP2 | 52 | [20 empty] | S | S | S | S
Seal Rock | SK3 | 85 | [24 empty] | S | S | S
Seal Rock | SK4 | 85 | [29 empty] | S
Seecon | SO1 | 105
Tarbert | TB1 | 54
Tarbert | TB2 | 54
Tarbert | TB3 | 241 | [24 empty] | S | S | S | S
Tarbert | TB4 | 243 | [7 empty] | F
Tawnaghmore | TP1 | 52 | [15 empty] | S | S | S | S
Tawnaghmore | TP3 | 52 | [15 empty] | S | S | S | S
Turlough Hill | TH1 | 73 | [12 empty] | S
Turlough Hill | TH2 | 73 | [12 empty] | S
Turlough Hill | TH3 | 73 | [12 empty] | S
Turlough Hill | TH4 | 73 | [12 empty] | S
Tynagh | TYC | 384 | [15 empty] | S | S | S
Viridian Energy | VE1 | 20
Viridian Energy DSU | VE2 | 13
Whitegate | WG1 | 444 | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F

## All Island Outages
Upcoming Outages including STMOs and Annual Outages
Station | Unit | NPR | Start Date | End Date | Value | Duration
North Wall | NW5 | 104 | 2019-10-01 | 2022-10-01 | S | 1096
Whitegate | WG1 | 444 | 2020-12-02 08:00 | 2021-08-08 23:00 | F | 249.58
Tarbert | TB3 | 241 | 2020-12-08 14:30 | 2021-04-30 | 226 | 142.38
Moneypoint | MP1 | 285 | 2020-12-20 20:00 | 2021-01-04 17:00 | 200 | 14.83
Moneypoint | MP2 | 285 | 2020-12-24 18:00 | 2021-01-04 15:00 | 120 | 10.83
EWIC | EW1 | 500 | 2021-01-02 09:00 | 2021-01-02 20:00 | F | 0.42
Tarbert | TB4 | 243 | 2021-01-02 09:30 | 2021-01-02 11:30 | F | 0.08
Lisahally | NILPS | 17.6 | 2021-01-03 02:00 | 2021-01-11 09:00 | 16 | 8.25
Liffey | LI2 | 15 | 2021-01-04 08:00 | 2021-01-04 09:30 | F | 0.04
Moneypoint | MP3 | 285 | 2021-01-04 10:30 | 2021-01-19 21:00 | 270 | 15.42
Moneypoint | MP2 | 285 | 2021-01-04 15:00 | 2021-01-06 15:30 | F | 2
Moneypoint | MP1 | 285 | 2021-01-04 17:00 | 2021-01-06 15:30 | 220 | 1.92
Tarbert | TB2 | 54 | 2021-01-06 09:00 | 2021-01-06 11:00 | F | 0.08
Kilroot | NIKGT4 | 42 | 2021-01-06 13:30 | 2021-01-06 17:00 | F | 0.12
Moneypoint | MP2 | 285 | 2021-01-06 15:30 | 2021-01-07 10:30 | 120 | 0.75
Tarbert | TB2 | 54 | 2021-01-06 15:30 | 2021-01-07 | F | 0.33
Moneypoint | MP1 | 285 | 2021-01-06 15:30 | 2021-01-06 16:30 | F | 0
Kilroot | NIK2 | 258 | 2021-01-06 15:30 | 2021-01-18 13:00 | 180 | 11.88
Tarbert | TB4 | 243 | 2021-01-06 16:00 | 2021-01-07 12:00 | 222 | 0.83
Moneypoint | MP1 | 285 | 2021-01-06 16:30 | 2021-01-09 12:00 | 220 | 2.79
Kilroot | NIKGT4 | 42 | 2021-01-06 23:30 | 2021-01-07 16:30 | F | 0.67
Aghada | AT2 | 90 | 2021-01-07 04:00 | 2021-01-08 07:30 | F | 1.12
Aghada | AT1 | 90 | 2021-01-07 04:00 | 2021-01-08 07:30 | F | 1.12
Moneypoint | MP2 | 285 | 2021-01-07 10:30 | 2021-01-19 22:00 | F | 12.46
Tarbert | TB4 | 243 | 2021-01-07 12:00 | 2021-01-08 12:00 | F | 1
Tarbert | TB2 | 54 | 2021-01-07 16:00 | 2021-01-08 14:00 | F | 0.92
Dublin Waste To Energy | DW1 | 61.5 | 2021-01-08 05:00 | 2021-01-08 08:00 | F | 0.08
Tarbert | TB4 | 243 | 2021-01-08 12:00 | 2021-01-11 12:00 | 222 | 3
Huntstown | HN2 | 400 | 2021-01-08 21:00 | 2021-01-10 21:00 | S | 2
Erne | ER1 | 10 | 2021-01-09 08:30 | 2021-01-09 17:00 | S | 0.33
Erne | ER2 | 10 | 2021-01-09 08:30 | 2021-01-09 17:00 | S | 0.33
Moneypoint | MP1 | 285 | 2021-01-09 12:00 | 2021-01-09 16:30 | 230 | 0.17
Moneypoint | MP1 | 285 | 2021-01-09 16:30 | 2021-01-19 21:00 | 240 | 10.17
Erne | ER1 | 10 | 2021-01-10 08:30 | 2021-01-10 18:00 | S | 0.38
Erne | ER2 | 10 | 2021-01-10 08:30 | 2021-01-10 17:00 | S | 0.33
Turlough Hill | TH1 | 73 | 2021-01-10 16:30 | 2021-01-11 12:00 | F | 0.79
Ballylumford | NIB32 | 249 | 2021-01-10 23:00 | 2021-01-11 19:00 | S | 0.83
Liffey | LI4 | 4 | 2021-01-11 07:00 | 2021-01-11 18:00 | S | 0.42
Liffey | LI2 | 15 | 2021-01-11 07:00 | 2021-01-11 18:00 | S | 0.42
Liffey | LI1 | 15 | 2021-01-11 07:00 | 2021-01-11 18:00 | S | 0.42
Erne | ER1 | 10 | 2021-01-11 08:30 | 2021-01-11 17:00 | S | 0.33
Erne | ER2 | 10 | 2021-01-11 08:30 | 2021-01-11 17:00 | S | 0.33
Lisahally | NILPS | 17.6 | 2021-01-11 09:00 | 2021-01-12 07:30 | 15 | 0.92
Tarbert | TB4 | 243 | 2021-01-11 12:00 | 2021-01-11 22:00 | 209 | 0.42
Tarbert | TB4 | 243 | 2021-01-11 22:00 | 2021-01-11 23:30 | F | 0.04
Tarbert | TB4 | 243 | 2021-01-11 23:30 | 2021-01-15 10:00 | 209 | 3.42
Erne | ER1 | 10 | 2021-01-12 08:30 | 2021-01-12 17:00 | S | 0.33
Erne | ER2 | 10 | 2021-01-12 08:30 | 2021-01-12 17:00 | S | 0.33
Ballylumford | NIB32 | 249 | 2021-01-12 08:30 | 2021-01-12 09:30 | 60 | 0
Lisahally | NILPS | 17.6 | 2021-01-12 10:00 | 2021-01-12 14:30 | S | 0.17
Ballylumford | NIBGT1 | 58 | 2021-01-12 12:30 | 2021-01-12 15:00 | F | 0.08
Lisahally | NILPS | 17.6 | 2021-01-12 14:30 | 2021-01-12 22:00 | F | 0.29
Kilroot | NIKGT2 | 29 | 2021-01-12 16:30 | 2021-01-12 18:00 | F | 0.04
Tarbert | TB2 | 54 | 2021-01-12 17:30 | 2021-01-12 19:30 | F | 0.08
Kilroot | NIKGT1 | 29 | 2021-01-12 17:30 | 2021-01-12 18:30 | F | 0
Kilroot | NIKGT1 | 29 | 2021-01-12 19:00 | 2021-01-13 19:00 | F | 1
Lisahally | NILPS | 17.6 | 2021-01-12 23:30 | 2021-01-13 12:30 | 16 | 0.5
Lisahally | NILPS | 17.6 | 2021-01-13 12:30 | 2021-01-13 13:30 | 13 | 0
Lisahally | NILPS | 17.6 | 2021-01-13 13:30 | 2021-01-22 13:00 | 16 | 8.96
Kilroot | NIKGT2 | 29 | 2021-01-13 14:00 | 2021-01-13 16:00 | F | 0.08
Tarbert | TB2 | 54 | 2021-01-14 12:00 | 2021-01-14 14:00 | F | 0.08
Coolkeeragh | NIC30 | 408 | 2021-01-14 21:00 | 2021-01-15 06:30 | S | 0.38
Kilroot | NIKGT4 | 42 | 2021-01-15 06:30 | 2021-01-15 14:30 | F | 0.33
Tarbert | TB4 | 243 | 2021-01-15 10:00 | 2021-01-19 03:00 | F | 3.67
Coolkeeragh | NIC30 | 408 | 2021-01-15 20:00 | 2021-01-16 04:30 | S | 0.33
Moyle | MOYLE | 450 | 2021-01-16 08:00 | 2021-01-16 12:00 | 250 | 0.17
Ballylumford | NIB10 | 94 | 2021-01-16 11:00 | 2021-01-21 01:00 | F | 4.58
Ballylumford | NIB32 | 249 | 2021-01-17 09:00 | 2021-01-18 01:00 | 160 | 0.67
Poolbeg | PB6 | 168 | 2021-01-18 17:30 | 2021-02-02 17:00 | 84 | 14.96
Tarbert | TB4 | 243 | 2021-01-19 03:00 | 2021-01-20 09:30 | 237 | 1.25
Poolbeg | PB4 | 154 | 2021-01-19 12:00 | 2021-02-02 17:00 | F | 14.17
Moneypoint | MP3 | 285 | 2021-01-19 21:00 | 2021-01-21 09:00 | 230 | 1.5
Moneypoint | MP1 | 285 | 2021-01-19 21:00 | 2021-01-21 09:00 | 200 | 1.5
Moneypoint | MP2 | 285 | 2021-01-19 22:00 | 2021-02-03 13:00 | 120 | 14.58
Dublin Waste To Energy | DW1 | 61.5 | 2021-01-21 05:00 | 2021-01-24 07:00 | 52 | 3.08
Great Island | GI4 | 461 | 2021-01-21 06:00 | 2021-01-21 08:30 | F | 0.08
Moneypoint | MP3 | 285 | 2021-01-21 09:00 | 2021-02-04 03:30 | 260 | 13.75
Moneypoint | MP1 | 285 | 2021-01-21 09:00 | 2021-01-27 12:00 | 230 | 6.08
Edenderry | ED1 | 118 | 2021-01-22 09:00 | 2021-01-22 15:00 | 65 | 0.25
Lisahally | NILPS | 17.6 | 2021-01-22 13:00 | 2021-01-22 16:30 | 13 | 0.12
Lisahally | NILPS | 17.6 | 2021-01-22 16:30 | 2021-02-01 | 15 | 9.29
Ballylumford | NIB31 | 249 | 2021-01-22 20:00 | 2021-01-23 15:00 | S | 0.75
Tarbert | TB4 | 243 | 2021-01-23 19:30 | 2021-01-25 01:00 | F | 1.21
Dublin Waste To Energy | DW1 | 61.5 | 2021-01-24 07:00 | 2021-01-26 09:00 | 22 | 2.08
Ardnacrusha | AA3 | 19 | 2021-01-24 10:00 | 2021-01-24 11:30 | F | 0.04
Huntstown | HNC | 342 | 2021-01-24 10:00 | 2021-01-24 11:00 | F | 0
Huntstown | HNC | 342 | 2021-01-24 11:00 | 2021-01-24 16:30 | F | 0.21
Tawnaghmore | TP1 | 52 | 2021-01-24 13:00 | 2021-01-24 14:30 | F | 0.04
Edenderry | ED1 | 118 | 2021-01-25 | 2021-01-25 12:00 | 55 | 0.5
Seal Rock | SK4 | 85 | 2021-01-26 06:00 | 2021-01-29 17:00 | S | 3.42
Tarbert | TB4 | 243 | 2021-01-26 13:00 | 2021-02-04 17:00 | 217 | 9.17
Kilroot | NIKGT2 | 29 | 2021-01-27 06:00 | 2021-01-27 10:30 | F | 0.17
Moneypoint | MP1 | 285 | 2021-01-27 12:00 | 2021-01-27 13:00 | 205 | 0
Moneypoint | MP1 | 285 | 2021-01-27 13:00 | 2021-01-29 17:30 | 235 | 2.17
Kilroot | NIKGT1 | 29 | 2021-01-28 06:00 | 2021-01-28 13:00 | S | 0.25
Huntstown | HNC | 342 | 2021-01-28 07:00 | 2021-01-28 11:30 | F | 0.17
Turlough Hill | TH2 | 73 | 2021-01-28 10:00 | 2021-01-28 15:00 | S | 0.17
Kilroot | NIKGT1 | 29 | 2021-01-28 13:00 | 2021-01-28 14:00 | F | 0
Kilroot | NIKGT4 | 42 | 2021-01-29 06:00 | 2021-01-29 18:30 | S | 0.5
Kilroot | NIKGT3 | 42 | 2021-01-29 06:00 | 2021-01-29 18:30 | S | 0.5
Moneypoint | MP1 | 285 | 2021-01-29 17:30 | 2021-01-31 13:30 | 250 | 1.83
Huntstown | HN2 | 400 | 2021-01-29 22:00 | 2021-02-28 23:00 | F | 30
Ballylumford | NIB31 | 249 | 2021-01-29 22:00 | 2021-01-31 12:30 | S | 1.58
Coolkeeragh | NIC30 | 408 | 2021-01-30 21:30 | 2021-01-31 05:00 | F | 0.29
Ballylumford | NIB31 | 249 | 2021-01-31 12:30 | 2021-01-31 17:00 | 85 | 0.17
Moneypoint | MP1 | 285 | 2021-01-31 13:30 | 2021-01-31 19:30 | 200 | 0.25
Moneypoint | MP1 | 285 | 2021-01-31 19:30 | 2021-02-04 17:00 | 220 | 3.88
Dublin Waste To Energy | DW1 | 61.5 | 2021-02-01 04:30 | 2021-02-01 09:00 | 45 | 0.17
Tarbert | TB1 | 54 | 2021-02-01 09:00 | 2021-02-01 12:00 | F | 0.08
Kilroot | NIK2 | 258 | 2021-02-01 18:30 | 2021-02-01 21:30 | 148 | 0.08
Turlough Hill | TH1 | 73 | 2021-02-02 10:00 | 2021-02-02 12:30 | S | 0.08
Poolbeg | PB4 | 154 | 2021-02-03 11:30 | 2021-02-03 17:00 | F | 0.21
Kilroot | NIK2 | 258 | 2021-02-03 12:30 | 2021-02-08 15:30 | 169 | 5.08
Moneypoint | MP2 | 285 | 2021-02-03 13:00 | 2021-02-12 18:00 | 99 | 9.17
Moneypoint | MP3 | 285 | 2021-02-04 03:00 | 2021-02-04 14:00 | 190 | 0.42
Tarbert | TB3 | 241 | 2021-02-04 08:00 | 2021-02-09 02:30 | F | 4.75
Seecon | SO1 | 105 | 2021-02-04 10:00 | 2021-02-04 17:00 | S | 0.25
Moneypoint | MP3 | 285 | 2021-02-04 13:30 | 2021-02-04 16:00 | 240 | 0.08
Moneypoint | MP3 | 285 | 2021-02-04 15:30 | 2021-02-04 17:30 | 260 | 0.08
Moneypoint | MP1 | 285 | 2021-02-04 17:00 | 2021-02-09 09:30 | 240 | 4.67
Moneypoint | MP3 | 285 | 2021-02-04 17:00 | 2021-02-09 10:00 | 270 | 4.67
Kilroot | NIK1 | 256 | 2021-02-08 13:30 | 2021-02-09 17:00 | 100 | 1.12
Dublin Waste To Energy | DW1 | 61.5 | 2021-02-09 05:00 | 2021-02-09 23:00 | F | 0.75
Turlough Hill | TH4 | 73 | 2021-02-09 09:00 | 2021-02-09 14:00 | S | 0.17
Moneypoint | MP3 | 285 | 2021-02-09 15:00 | 2021-02-16 23:00 | F | 7.33
Tarbert | TB3 | 241 | 2021-02-10 08:00 | 2021-02-10 10:30 | F | 0.08
Turlough Hill | TH3 | 73 | 2021-02-10 10:00 | 2021-02-10 15:00 | S | 0.17
Moneypoint | MP1 | 285 | 2021-02-10 17:30 | 2021-02-13 05:30 | 220 | 2.5
Dublin Waste To Energy | DW1 | 61.5 | 2021-02-11 12:00 | 2021-02-16 23:00 | 58 | 5.42
Moneypoint | MP2 | 285 | 2021-02-12 18:00 | 2021-02-13 05:30 | 120 | 0.46
Tynagh | TYC | 384 | 2021-02-12 20:00 | 2021-02-15 | S | 2.17
Moneypoint | MP2 | 285 | 2021-02-13 05:30 | 2021-02-14 17:00 | F | 1.46
Moneypoint | MP1 | 285 | 2021-02-13 05:30 | 2021-02-13 21:00 | F | 0.62
Kilroot | NIKGT3 | 42 | 2021-02-13 07:00 | 2021-02-13 18:30 | F | 0.46
Tarbert | TB4 | 243 | 2021-02-13 17:00 | 2021-02-21 17:00 | F | 8
Aghada | AD2 | 449 | 2021-02-13 20:00 | 2021-02-20 22:00 | F | 7.08
Moneypoint | MP1 | 285 | 2021-02-13 21:00 | 2021-02-26 23:00 | 220 | 13.08
Kilroot | NIKGT4 | 42 | 2021-02-14 07:00 | 2021-02-14 18:30 | F | 0.46
Moneypoint | MP2 | 285 | 2021-02-14 17:00 | 2021-02-14 18:00 | 100 | 0
Moneypoint | MP2 | 285 | 2021-02-14 18:00 | 2021-03-26 23:00 | 120 | 40.17
Ballylumford | NIB10 | 94 | 2021-02-16 22:00 | 2021-02-16 23:00 | F | 0
Ballylumford | NIB32 | 249 | 2021-02-16 22:00 | 2021-02-17 04:30 | S | 0.25
Dublin Waste To Energy | DW1 | 61.5 | 2021-02-16 23:00 | 2021-02-26 | 51 | 9
Moneypoint | MP3 | 285 | 2021-02-17 10:00 | 2021-02-17 13:30 | F | 0.12
Edenderry | ED1 | 118 | 2021-02-18 10:30 | 2021-02-18 12:30 | 55 | 0.08
Huntstown | HNC | 342 | 2021-02-18 23:00 | 2021-02-19 18:00 | 225 | 0.75
Coolkeeragh | NIC30 | 408 | 2021-02-19 20:00 | 2021-02-23 22:30 | S | 4.08
EWIC | EW1 | 500 | 2021-02-25 09:00 | 2021-02-26 23:00 | S | 1.58
Ballylumford | NIB32 | 249 | 2021-02-28 20:00 | 2021-04-29 20:30 | S | 60
Huntstown | HN2 | 400 | 2021-02-28 23:00 | 2021-04-13 17:00 | S | 43.75
Seal Rock | SK3 | 85 | 2021-03-01 06:00 | 2021-03-03 18:00 | S | 2.5
Lisahally | NILPS | 17.6 | 2021-03-04 18:00 | 2021-03-14 18:30 | S | 10
Aghada | AT4 | 90 | 2021-03-08 | 2021-03-11 20:00 | S | 3.83
Turlough Hill | TH3 | 73 | 2021-03-20 06:00 | 2021-03-28 21:00 | S | 8.58
Turlough Hill | TH4 | 73 | 2021-03-20 06:00 | 2021-03-28 21:00 | S | 8.58
Turlough Hill | TH2 | 73 | 2021-03-20 06:00 | 2021-03-28 21:00 | S | 8.58
Turlough Hill | TH1 | 73 | 2021-03-20 06:00 | 2021-03-28 21:00 | S | 8.58
Edenderry | ED1 | 118 | 2021-04-01 18:00 | 2021-04-07 08:00 | S | 5.58
Poolbeg | PB6 | 168 | 2021-04-05 09:00 | 2021-04-10 17:00 | 84 | 5.33
Poolbeg | PB5 | 146 | 2021-04-05 09:00 | 2021-04-10 17:00 | S | 5.33
Ardnacrusha | AA4 | 24 | 2021-04-06 08:00 | 2021-05-28 20:00 | S | 52.5
Lee | LE2 | 4 | 2021-04-06 08:00 | 2021-04-16 20:00 | S | 10.5
Tynagh | TYC | 384 | 2021-04-11 | 2021-05-03 | S | 22
Indaver | IW1 | 17 | 2021-04-12 | 2021-04-27 | S | 15
Liffey | LI2 | 15 | 2021-04-12 08:00 | 2021-05-09 17:00 | S | 27.33
Liffey | LI1 | 15 | 2021-04-12 08:00 | 2021-05-09 17:00 | S | 27.33
Erne | ER1 | 10 | 2021-04-12 08:00 | 2021-04-26 20:00 | S | 14.5
Tawnaghmore | TP3 | 52 | 2021-04-12 09:00 | 2021-05-09 17:00 | S | 27.33
Tawnaghmore | TP1 | 52 | 2021-04-12 09:00 | 2021-05-09 17:00 | S | 27.33
Dublin Bay | DB1 | 405 | 2021-04-23 13:00 | 2021-06-28 06:00 | S | 65.67
Lee | LE3 | 8 | 2021-04-26 08:00 | 2021-05-28 20:00 | S | 32.5
Coolkeeragh | NIC30 | 408 | 2021-05-07 16:00 | 2021-05-09 22:30 | S | 2.25
Aghada | AD2 | 449 | 2021-05-09 01:00 | 2021-05-30 20:00 | S | 21.75
Coolkeeragh | NICGT8 | 53 | 2021-05-10 | 2021-05-17 | S | 7
Erne | ER2 | 10 | 2021-05-10 08:00 | 2021-05-14 20:00 | S | 4.5
Seal Rock | SK3 | 85 | 2021-05-10 12:00 | 2021-05-12 12:00 | S | 2
Seal Rock | SK4 | 85 | 2021-05-10 18:00 | 2021-05-12 18:00 | S | 2
Edenderry | ED3 | 58 | 2021-05-12 08:00 | 2021-05-12 18:00 | S | 0.42
Edenderry | ED5 | 58 | 2021-05-12 08:00 | 2021-05-12 18:00 | S | 0.42
Tarbert | TB2 | 54 | 2021-05-15 | 2021-05-22 | S | 7
Tarbert | TB1 | 54 | 2021-05-15 | 2021-05-22 | S | 7
Kilroot | NIK2 | 258 | 2021-05-15 | 2021-07-10 | S | 56
Liffey | LI4 | 4 | 2021-05-17 08:00 | 2021-06-06 17:00 | S | 20.33
Rhode | RP2 | 52 | 2021-05-17 09:00 | 2021-06-12 17:00 | S | 26.33
Rhode | RP1 | 52 | 2021-05-17 09:00 | 2021-06-12 17:00 | S | 26.33
EWIC | EW1 | 500 | 2021-05-26 09:00 | 2021-05-27 23:00 | S | 1.58
Ardnacrusha | AA2 | 22 | 2021-06-08 08:00 | 2021-07-02 20:00 | S | 24.5
Tarbert | TB3 | 241 | 2021-06-12 09:00 | 2021-07-10 17:00 | S | 28.33
Dublin Waste To Energy | DW1 | 61.5 | 2021-06-13 | 2021-07-07 | S | 24
Seal Rock | SK3 | 85 | 2021-06-13 06:00 | 2021-07-01 18:00 | S | 18.5
Ballylumford | NIB10 | 94 | 2021-06-14 | 2021-07-11 | S | 27
Lee | LE1 | 15 | 2021-06-14 08:00 | 2021-07-09 20:00 | S | 25.5
Erne | ER3 | 22.5 | 2021-06-14 08:00 | 2021-07-04 20:00 | S | 20.5
Edenderry | ED1 | 118 | 2021-06-25 12:00 | 2021-08-30 18:00 | S | 66.25
Moyle | MOYLE | 450 | 2021-07-12 | 2021-07-20 | S | 8
Ardnacrusha | AA1 | 21 | 2021-07-12 08:00 | 2021-07-16 20:00 | S | 4.5
Moneypoint | MP1 | 285 | 2021-07-16 22:00 | 2021-07-28 22:00 | S | 12
Seal Rock | SK4 | 85 | 2021-07-19 06:00 | 2021-07-23 18:00 | S | 4.5
Ballylumford | NIB32 | 249 | 2021-07-20 | 2021-08-03 | 161 | 14
Ballylumford | NIB31 | 249 | 2021-07-20 | 2021-08-03 | 161 | 14
Moneypoint | MP2 | 285 | 2021-07-23 22:00 | 2021-07-31 22:00 | S | 8
Aghada | AT2 | 90 | 2021-08-01 18:00 | 2021-09-18 20:00 | S | 48.08
Coolkeeragh | NIC30 | 408 | 2021-08-08 | 2021-08-09 | S | 1
Tarbert | TB4 | 243 | 2021-08-09 | 2021-08-10 | S | 1
Kilroot | NIK1 | 256 | 2021-08-09 | 2021-10-05 | S | 57
Ardnacrusha | AA3 | 19 | 2021-08-09 08:00 | 2021-10-01 20:00 | S | 53.5
Aghada | AT1 | 90 | 2021-08-13 08:00 | 2021-08-28 20:00 | S | 15.5
EWIC | EW1 | 500 | 2021-08-23 09:00 | 2021-10-12 23:00 | S | 50.58
Poolbeg | PB4 | 154 | 2021-08-29 12:00 | 2021-09-17 18:00 | S | 19.25
Poolbeg | PB6 | 168 | 2021-08-29 12:00 | 2021-09-15 | 84 | 16.5
Liffey | LI5 | 4 | 2021-08-30 08:00 | 2021-09-03 17:00 | S | 4.33
Dublin Waste To Energy | DW1 | 61.5 | 2021-09-01 | 2021-09-22 00:30 | S | 21
Erne | ER4 | 22.5 | 2021-09-06 08:00 | 2021-09-10 20:00 | S | 4.5
Poolbeg | PB6 | 168 | 2021-09-15 | 2021-10-24 23:30 | S | 39.96
Moneypoint | MP3 | 285 | 2021-09-17 22:00 | 2021-09-29 22:00 | S | 12
Kilroot | NIKGT1 | 29 | 2021-09-18 06:00 | 2021-10-30 17:30 | S | 42.46
Poolbeg | PB5 | 146 | 2021-10-02 | 2021-11-16 23:30 | S | 45.96
Turlough Hill | TH1 | 73 | 2021-10-04 08:00 | 2021-10-06 17:00 | S | 2.33
Turlough Hill | TH2 | 73 | 2021-10-04 08:00 | 2021-10-06 17:00 | S | 2.33
Coolkeeragh | NIC30 | 408 | 2021-10-05 | 2021-10-30 | S | 25
Great Island | GI4 | 461 | 2021-10-09 | 2021-10-16 00:30 | S | 7
Poolbeg | PB6 | 168 | 2021-10-25 | 2021-11-16 23:30 | 84 | 22.96
Coolkeeragh | NICGT8 | 53 | 2021-10-30 | 2021-11-01 | S | 2
Ballylumford | NIBGT2 | 58 | 2021-11-08 | 2021-11-15 | S | 7
Seal Rock | SK3 | 85 | 2021-11-08 06:00 | 2021-11-10 18:00 | S | 2.5
Kilroot | NIKGT4 | 42 | 2021-11-15 | 2021-11-22 | S | 7
Kilroot | NIKGT3 | 42 | 2021-11-15 | 2021-11-22 | S | 7
Coolkeeragh | NIC30 | 408 | 2021-11-28 | 2021-11-29 | S | 1
Seal Rock | SK4 | 85 | 2021-12-06 06:00 | 2021-12-08 18:00 | S | 2.5
Edenderry | ED1 | 118 | 2021-12-26 13:00 | 2022-01-02 08:00 | S | 6.75
North Wall | NW5 | 104 | 2022-01-01 | 2022-10-01 00:30 | S | 273
|  |  | Scheduled Outage | S
|  |  | Forced Outage | F
|  |  | Unit partially available | 10