## Outage Plan EirGrid
2022 GENERATION OUTAGE PLAN (EIRGRID)
|  | Month | Jan '2022 | [5 empty] | Feb '2022 |  |  |  | Mar '2022 |  |  |  | Apr '2022 |  |  |  | May '2022 |  |  |  |  | Jun '2022 |  |  |  | Jul '2022 |  |  |  | Aug '2022 |  |  |  |  | Sep '2022 |  |  |  | Oct '2022 |  |  |  |  | Nov '2022 |  |  |  | Dec '2022
|  | Week | 52 '2021 | 1 '2022 | 2 '2022 | 3 '2022 | 4 '2022 | 5 '2022 | 6 '2022 | 7 '2022 | 8 '2022 | 9 '2022 | 10 '2022 | 11 '2022 | 12 '2022 | 13 '2022 | 14 '2022 | 15 '2022 | 16 '2022 | 17 '2022 | 18 '2022 | 19 '2022 | 20 '2022 | 21 '2022 | 22 '2022 | 23 '2022 | 24 '2022 | 25 '2022 | 26 '2022 | 27 '2022 | 28 '2022 | 29 '2022 | 30 '2022 | 31 '2022 | 32 '2022 | 33 '2022 | 34 '2022 | 35 '2022 | 36 '2022 | 37 '2022 | 38 '2022 | 39 '2022 | 40 '2022 | 41 '2022 | 42 '2022 | 43 '2022 | 44 '2022 | 45 '2022 | 46 '2022 | 47 '2022 | 48 '2022 | 49 '2022 | 50 '2022 | 51 '2022 | 52 '2022
Station | Unit | NPR
Aghada | AD2 | 449 | [20 empty] | S | S | S | S | [20 empty] | S
Aghada | AT1 | 90
Aghada | AT2 | 90
Aghada | AT4 | 90
Ardnacrusha | AA1 | 21 | [17 empty] | S
Ardnacrusha | AA2 | 22 | [24 empty] | S
Ardnacrusha | AA3 | 19 | [36 empty] | S
Ardnacrusha | AA4 | 24 | [14 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Beenanaspuck Tobertoreen | XT2 | 11
DAE Virtual Power Plant | DP1 | 19
DAE Virtual Power Plant | DP2 | 26
Dublin Bay | DB1 | 405 | [26 empty] | S | S
Dublin Waste To Energy | DW1 | 62 | [19 empty] | S
Edenderry | ED1 | 118 | S | [26 empty] | S | S | S | S | S | S | S | S | [17 empty] | S
Edenderry | ED3 | 58
Edenderry | ED5 | 58
Electric Ireland | EI1 | 20
Endeco Technologies | EC1 | 47
Endeco Technologies | EC2 | 11
Endeco Technologies | EC5 | 15
Energy Trading | ET1 | 13
Enernoc | AE1 | 95
Enernoc | AE2 | 12
Enernoc | AE3 | 14
Enernoc | AE4 | 15
Enernoc | AE5 | 15
Enernoc | EN1 | 15
Enernoc | EN2 | 16
Enernoc | EN3 | 16
Enernoc | EN4 | 16
Enernoc | EN5 | 6
Enernoc | EN6 | 11
Enernoc | EN8 | 21
Enernoc | EN9 | 16
Erne | ER1 | 10 | [14 empty] | S
Erne | ER2 | 10 | [19 empty] | S
Erne | ER3 | 22 | [24 empty] | S
Erne | ER4 | 22 | [36 empty] | S
EWIC | EW1 | 500 | [11 empty] | S | S | S | S | S | S | S
Gardnershill | GP1 | 8
Great Island | GI4 | 461 | [25 empty] | S | S | S | S | S | S | S
Huntstown | HN2 | 400
Huntstown | HNC | 342 | [9 empty] | S | S
Indaver | IW1 | 17 | [12 empty] | S | S | S
Kelwin | KZ4 | 27
Knockacummer | KC1 | 100
Lee | LE1 | 15 | [18 empty] | S | S
Lee | LE2 | 4 | [13 empty] | S | S | S |  |  |  | S
Lee | LE3 | 8 | [21 empty] | S | S
Liffey | LI1 | 15 | [24 empty] | S
Liffey | LI2 | 15 | [24 empty] | S
Liffey | LI4 | 4 | [26 empty] | S
Liffey | LI5 | 4 | [28 empty] | S
Lumcloon | LU1 | 50
Lumcloon | LU2 | 50
Moneypoint | MP1 | 285 | [22 empty] | S | S
Moneypoint | MP2 | 285 | [9 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Moneypoint | MP3 | 285 | [39 empty] | S | S | S
Poolbeg | PB4 | 154 | [42 empty] | S
Poolbeg | PB5 | 146 | [21 empty] | S | S | S
Poolbeg | PB6 | 168 | [21 empty] | S | S | S
Powerhouse Generation | PG1 | 10
Rhode | RP1 | 52
Rhode | RP2 | 52
Seal Rock | SK3 | 85
Seal Rock | SK4 | 85
Seecon | SO1 | 105
Shannonbridge | SI1 | 50
Shannonbridge | SI2 | 50
Tarbert | TB1 | 54
Tarbert | TB2 | 54
Tarbert | TB3 | 241
Tarbert | TB4 | 243
Tawnaghmore | TP1 | 52 | [33 empty] | S | S | S | S | S | S | S | S | S | S
Tawnaghmore | TP3 | 52 | [33 empty] | S | S | S | S | S | S | S | S | S | S
Turlough Hill | TH1 | 73 | [18 empty] | S | S | S | S
Turlough Hill | TH2 | 73 | [18 empty] | S | S | S | S
Turlough Hill | TH3 | 73 | [18 empty] | S | S | S | S
Turlough Hill | TH4 | 73 | [18 empty] | S | S | S | S
Tynagh | TYC | 384 | [33 empty] | S
VIOTAS | EE1 | 47
VIOTAS | EE2 | 20
VIOTAS | EE3 | 8
VIOTAS | EE4 | 9
VIOTAS | EE5 | 7
VIOTAS | EE6 | 14
VIOTAS | EE7 | 9
Viridian Energy | VE1 | 20
Viridian Energy DSU | VE2 | 13
Whitegate | WG1 | 444 | [36 empty] | S

## EirGrid Outages
Upcoming Outages including STMOs and Annual Outages
Station | Unit | NPR | Start Date | End Date | Value | Duration
Edenderry | ED1 | 118 | 2021-12-26 13:00 | 2022-01-02 08:00 | S | 6.75
Ardnacrusha | AA4 | 24 | 2022-01-18 08:00 | 2022-01-19 20:00 | S | 1.5
Seal Rock | SK3 | 85 | 2022-01-31 06:00 | 2022-02-02 18:00 | S | 2.5
Moneypoint | MP2 | 285 | 2022-02-28 22:00 | 2022-09-04 22:00 | S | 188
Huntstown | HNC | 342 | 2022-03-01 | 2022-03-12 | S | 11
EWIC | EW1 | 500 | 2022-03-14 09:00 | 2022-03-14 17:00 | S | 0.33
EWIC | EW1 | 500 | 2022-03-14 17:00 | 2022-05-03 23:00 | S | 50.25
Indaver | IW1 | 17 | 2022-03-20 | 2022-04-14 | S | 25
Seal Rock | SK4 | 85 | 2022-03-21 06:00 | 2022-03-23 18:00 | S | 2.5
Lee | LE2 | 4 | 2022-03-26 08:00 | 2022-04-15 20:00 | S | 20.5
Aghada | AD2 | 449 | 2022-03-31 01:00 | 2022-04-05 20:00 | S | 5.75
Ardnacrusha | AA4 | 24 | 2022-04-04 08:00 | 2022-11-18 20:00 | S | 228.5
Erne | ER1 | 10 | 2022-04-04 08:00 | 2022-04-08 20:00 | S | 4.5
Edenderry | ED1 | 118 | 2022-04-14 18:00 | 2022-04-20 08:00 | S | 5.58
Ardnacrusha | AA1 | 21 | 2022-04-25 08:00 | 2022-04-29 20:00 | S | 4.5
Dublin Waste To Energy | DW1 | 61.5 | 2022-05-01 | 2022-05-06 | 26 | 5
Turlough Hill | TH3 | 73 | 2022-05-01 06:00 | 2022-05-28 21:00 | S | 27.58
Turlough Hill | TH1 | 73 | 2022-05-01 06:00 | 2022-05-28 21:00 | S | 27.58
Turlough Hill | TH2 | 73 | 2022-05-01 06:00 | 2022-05-28 21:00 | S | 27.58
Turlough Hill | TH4 | 73 | 2022-05-01 06:00 | 2022-05-28 21:00 | S | 27.58
Lee | LE1 | 15 | 2022-05-03 08:00 | 2022-05-13 20:00 | S | 10.5
Dublin Waste To Energy | DW1 | 61.5 | 2022-05-06 | 2022-05-16 | S | 10
Erne | ER2 | 10 | 2022-05-09 08:00 | 2022-05-13 20:00 | S | 4.5
Lee | LE2 | 4 | 2022-05-09 08:00 | 2022-05-15 20:00 | S | 6.5
Dublin Waste To Energy | DW1 | 61.5 | 2022-05-16 | 2022-05-21 | 26 | 5
Seal Rock | SK3 | 85 | 2022-05-16 18:00 | 2022-05-19 18:00 | S | 3
Seal Rock | SK4 | 85 | 2022-05-17 | 2022-05-19 12:00 | S | 2.5
Aghada | AD2 | 449 | 2022-05-17 01:00 | 2022-06-13 20:00 | S | 27.75
Lee | LE3 | 8 | 2022-05-23 08:00 | 2022-06-03 20:00 | S | 11.5
Poolbeg | PB6 | 168 | 2022-05-23 12:00 | 2022-06-11 20:00 | S | 19.33
Poolbeg | PB5 | 146 | 2022-05-23 12:00 | 2022-06-11 20:00 | S | 19.33
Moneypoint | MP1 | 285 | 2022-05-27 22:00 | 2022-06-15 22:00 | S | 19
Seal Rock | SK4 | 85 | 2022-06-06 06:00 | 2022-06-09 18:00 | S | 3.5
Liffey | LI2 | 15 | 2022-06-12 08:00 | 2022-06-17 17:00 | S | 5.33
Liffey | LI1 | 15 | 2022-06-12 08:00 | 2022-06-17 17:00 | S | 5.33
Ardnacrusha | AA2 | 22 | 2022-06-13 08:00 | 2022-06-20 20:00 | S | 7.5
Erne | ER3 | 22.5 | 2022-06-13 08:00 | 2022-06-17 20:00 | S | 4.5
Great Island | GI4 | 461 | 2022-06-21 | 2022-08-10 | S | 50
Dublin Bay | DB1 | 405 | 2022-06-24 20:00 | 2022-07-12 18:00 | S | 17.92
Tarbert | TB4 | 243 | 2022-06-25 | 2022-07-01 | S | 6
Liffey | LI4 | 4 | 2022-06-26 08:00 | 2022-07-01 17:00 | S | 5.33
Edenderry | ED1 | 118 | 2022-07-01 12:00 | 2022-08-29 08:00 | S | 58.83
Liffey | LI5 | 4 | 2022-07-10 08:00 | 2022-07-15 17:00 | S | 5.33
Aghada | AT2 | 90 | 2022-07-11 | 2022-07-14 | S | 3
Aghada | AT1 | 90 | 2022-07-11 | 2022-07-14 | S | 3
Aghada | AT4 | 90 | 2022-07-18 | 2022-07-21 | S | 3
Seal Rock | SK3 | 85 | 2022-07-25 06:00 | 2022-07-28 18:00 | S | 3.5
Tawnaghmore | TP3 | 52 | 2022-08-13 | 2022-10-22 | S | 70
Tawnaghmore | TP1 | 52 | 2022-08-13 | 2022-10-22 | S | 70
Tynagh | TYC | 384 | 2022-08-15 20:00 | 2022-08-20 20:00 | S | 5
EWIC | EW1 | 500 | 2022-08-18 09:00 | 2022-08-18 23:00 | S | 0.58
Whitegate | WG1 | 444 | 2022-09-02 21:00 | 2022-09-14 21:00 | S | 12
Erne | ER4 | 22.5 | 2022-09-05 08:00 | 2022-09-09 20:00 | S | 4.5
Ardnacrusha | AA3 | 19 | 2022-09-05 08:00 | 2022-09-09 20:00 | S | 4.5
Moneypoint | MP3 | 285 | 2022-09-23 22:00 | 2022-10-13 22:00 | S | 20
Dublin Waste To Energy | DW1 | 61.5 | 2022-10-01 | 2022-10-05 | 26 | 4
Dublin Waste To Energy | DW1 | 61.5 | 2022-10-05 | 2022-10-07 | S | 2
Dublin Waste To Energy | DW1 | 61.5 | 2022-10-07 | 2022-10-11 | 26 | 4
Poolbeg | PB6 | 168 | 2022-10-17 12:00 | 2022-10-22 20:00 | 84 | 5.33
Poolbeg | PB4 | 154 | 2022-10-17 12:00 | 2022-10-22 20:00 | S | 5.33
Seal Rock | SK4 | 85 | 2022-10-24 06:00 | 2022-10-26 18:00 | S | 2.5
Edenderry | ED5 | 58 | 2022-10-24 08:00 | 2022-10-24 18:00 | S | 0.42
Edenderry | ED3 | 58 | 2022-10-24 08:00 | 2022-10-24 18:00 | S | 0.42
Aghada | AD2 | 449 | 2022-10-31 01:00 | 2022-11-05 20:00 | S | 5.75
Seal Rock | SK3 | 85 | 2022-11-28 06:00 | 2022-11-30 18:00 | S | 2.5
Edenderry | ED1 | 118 | 2022-12-26 12:00 | 2023-01-01 08:00 | S | 5.83
|  |  | Scheduled Outage | S
|  |  | Forced Outage | F
|  |  | Unit partially available | 10

## Outage Plan SONI
2022 GENERATION OUTAGE PLAN (SONI)
|  | Month | Jan '2022 | [5 empty] | Feb '2022 |  |  |  | Mar '2022 |  |  |  | Apr '2022 |  |  |  | May '2022 |  |  |  |  | Jun '2022 |  |  |  | Jul '2022 |  |  |  | Aug '2022 |  |  |  |  | Sep '2022 |  |  |  | Oct '2022 |  |  |  |  | Nov '2022 |  |  |  | Dec '2022
|  | Week | 52 '2021 | 1 '2022 | 2 '2022 | 3 '2022 | 4 '2022 | 5 '2022 | 6 '2022 | 7 '2022 | 8 '2022 | 9 '2022 | 10 '2022 | 11 '2022 | 12 '2022 | 13 '2022 | 14 '2022 | 15 '2022 | 16 '2022 | 17 '2022 | 18 '2022 | 19 '2022 | 20 '2022 | 21 '2022 | 22 '2022 | 23 '2022 | 24 '2022 | 25 '2022 | 26 '2022 | 27 '2022 | 28 '2022 | 29 '2022 | 30 '2022 | 31 '2022 | 32 '2022 | 33 '2022 | 34 '2022 | 35 '2022 | 36 '2022 | 37 '2022 | 38 '2022 | 39 '2022 | 40 '2022 | 41 '2022 | 42 '2022 | 43 '2022 | 44 '2022 | 45 '2022 | 46 '2022 | 47 '2022 | 48 '2022 | 49 '2022 | 50 '2022 | 51 '2022 | 52 '2022
Station | Unit | NPR
AC Automation | NIACA | 8
Activation Energy | NIAEA | 9
Ballylumford | NIB10 | 94
Ballylumford | NIB31 | 249
Ballylumford | NIB32 | 249
Ballylumford | NIBGT1 | 58 | [18 empty] | S | S | S | S | S | S
Ballylumford | NIBGT2 | 58 | [36 empty] | S
Contour Global | NICG2 | 3
Contour Global | NICGA | 12
Coolkeeragh | NIC30 | 408
Coolkeeragh | NICGT8 | 53 | [17 empty] | S
Empower | NIEMP | 3
Endeco Technologies | NIECA | 13
Energy Trading | NIETB | 9
Energy Trading | NIETD | 5
Energy Trading | NIETR | 19
iPower | NIAGU | 74
Kilroot | NIK1 | 256 | [30 empty] | S | S | S | S | S | S | S | S | S
Kilroot | NIK2 | 258 | [18 empty] | S | S | S | S | S | S | S | S
Kilroot | NIKGT1 | 29
Kilroot | NIKGT2 | 29 | [9 empty] | S | S | S | S | S | S
Kilroot | NIKGT3 | 42 | [38 empty] | S | S | S
Kilroot | NIKGT4 | 42 | [38 empty] | S | S | S
Lisahally | NILPS | 18
Moyle | MOYLE | 450
Powerhouse Generation | NIPH1 | 34

## SONI Outages
Upcoming Outages including STMOs and Annual Outages
Station | Unit | NPR | Start Date | End Date | Value | Duration
Ballylumford | NIB31 | 249 | 2022-02-16 19:00 | 2022-02-19 19:30 | S | 3
Kilroot | NIKGT2 | 29 | 2022-03-01 | 2022-04-12 | S | 42
Coolkeeragh | NIC30 | 408 | 2022-03-27 | 2022-03-28 | S | 1
Moyle | MOYLE | 450 | 2022-04-02 | 2022-04-03 | S | 1
Moyle | MOYLE | 450 | 2022-04-03 | 2022-06-03 | 250 | 61
Coolkeeragh | NICGT8 | 53 | 2022-04-25 | 2022-04-30 | S | 5
Kilroot | NIK2 | 258 | 2022-04-29 | 2022-06-28 | S | 60
Ballylumford | NIBGT1 | 58 | 2022-05-01 | 2022-06-12 | S | 42
Moyle | MOYLE | 450 | 2022-06-03 | 2022-06-11 | S | 8
Moyle | MOYLE | 450 | 2022-06-11 | 2022-07-22 | 250 | 41
Moyle | MOYLE | 450 | 2022-07-22 | 2022-08-05 | 450 | 14
Kilroot | NIK1 | 256 | 2022-07-25 | 2022-09-23 | S | 60
Moyle | MOYLE | 450 | 2022-08-05 | 2022-08-27 | 450 | 22
Ballylumford | NIBGT2 | 58 | 2022-09-05 | 2022-09-12 | S | 7
Coolkeeragh | NIC30 | 408 | 2022-09-18 | 2022-09-19 | S | 1
Kilroot | NIKGT4 | 42 | 2022-09-19 | 2022-10-10 | S | 21
Kilroot | NIKGT3 | 42 | 2022-09-19 | 2022-10-10 | S | 21
Kilroot | NIKGT1 | 29 | 2022-09-24 | 2022-09-25 23:30 | S | 1.96
Ballylumford | NIB31 | 249 | 2022-09-24 | 2022-10-08 | 161 | 14
Ballylumford | NIB32 | 249 | 2022-09-24 | 2022-10-08 | 161 | 14
Kilroot | NIKGT2 | 29 | 2022-09-24 | 2022-09-26 | S | 2
Coolkeeragh | NIC30 | 408 | 2022-10-15 | 2022-10-17 | S | 2
|  |  | Scheduled Outage | S
|  |  | Forced Outage | F
|  |  | Unit partially available | 10

## Outage Plan All Island
2022 GENERATION OUTAGE PLAN (All Island)
|  | Month | Jan '2022 | [5 empty] | Feb '2022 |  |  |  | Mar '2022 |  |  |  | Apr '2022 |  |  |  | May '2022 |  |  |  |  | Jun '2022 |  |  |  | Jul '2022 |  |  |  | Aug '2022 |  |  |  |  | Sep '2022 |  |  |  | Oct '2022 |  |  |  |  | Nov '2022 |  |  |  | Dec '2022
|  | Week | 52 '2021 | 1 '2022 | 2 '2022 | 3 '2022 | 4 '2022 | 5 '2022 | 6 '2022 | 7 '2022 | 8 '2022 | 9 '2022 | 10 '2022 | 11 '2022 | 12 '2022 | 13 '2022 | 14 '2022 | 15 '2022 | 16 '2022 | 17 '2022 | 18 '2022 | 19 '2022 | 20 '2022 | 21 '2022 | 22 '2022 | 23 '2022 | 24 '2022 | 25 '2022 | 26 '2022 | 27 '2022 | 28 '2022 | 29 '2022 | 30 '2022 | 31 '2022 | 32 '2022 | 33 '2022 | 34 '2022 | 35 '2022 | 36 '2022 | 37 '2022 | 38 '2022 | 39 '2022 | 40 '2022 | 41 '2022 | 42 '2022 | 43 '2022 | 44 '2022 | 45 '2022 | 46 '2022 | 47 '2022 | 48 '2022 | 49 '2022 | 50 '2022 | 51 '2022 | 52 '2022
Station | Unit | NPR
AC Automation | NIACA | 8
Activation Energy | NIAEA | 9
Aghada | AD2 | 449 | [20 empty] | S | S | S | S | [20 empty] | S
Aghada | AT1 | 90
Aghada | AT2 | 90
Aghada | AT4 | 90
Ardnacrusha | AA1 | 21 | [17 empty] | S
Ardnacrusha | AA2 | 22 | [24 empty] | S
Ardnacrusha | AA3 | 19 | [36 empty] | S
Ardnacrusha | AA4 | 24 | [14 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Ballylumford | NIB10 | 94
Ballylumford | NIB31 | 249
Ballylumford | NIB32 | 249
Ballylumford | NIBGT1 | 58 | [18 empty] | S | S | S | S | S | S
Ballylumford | NIBGT2 | 58 | [36 empty] | S
Beenanaspuck Tobertoreen | XT2 | 11
Contour Global | NICG2 | 3
Contour Global | NICGA | 12
Coolkeeragh | NIC30 | 408
Coolkeeragh | NICGT8 | 53 | [17 empty] | S
DAE Virtual Power Plant | DP1 | 19
DAE Virtual Power Plant | DP2 | 26
Dublin Bay | DB1 | 405 | [26 empty] | S | S
Dublin Waste To Energy | DW1 | 62 | [19 empty] | S
Edenderry | ED1 | 118 | S | [26 empty] | S | S | S | S | S | S | S | S | [17 empty] | S
Edenderry | ED3 | 58
Edenderry | ED5 | 58
Electric Ireland | EI1 | 20
Empower | NIEMP | 3
Endeco Technologies | EC1 | 47
Endeco Technologies | EC2 | 11
Endeco Technologies | EC5 | 15
Endeco Technologies | NIECA | 13
Energy Trading | ET1 | 13
Energy Trading | NIETB | 9
Energy Trading | NIETD | 5
Energy Trading | NIETR | 19
Enernoc | AE1 | 95
Enernoc | AE2 | 12
Enernoc | AE3 | 14
Enernoc | AE4 | 15
Enernoc | AE5 | 15
Enernoc | EN1 | 15
Enernoc | EN2 | 16
Enernoc | EN3 | 16
Enernoc | EN4 | 16
Enernoc | EN5 | 6
Enernoc | EN6 | 11
Enernoc | EN8 | 21
Enernoc | EN9 | 16
Erne | ER1 | 10 | [14 empty] | S
Erne | ER2 | 10 | [19 empty] | S
Erne | ER3 | 22 | [24 empty] | S
Erne | ER4 | 22 | [36 empty] | S
EWIC | EW1 | 500 | [11 empty] | S | S | S | S | S | S | S
Gardnershill | GP1 | 8
Great Island | GI4 | 461 | [25 empty] | S | S | S | S | S | S | S
Huntstown | HN2 | 400
Huntstown | HNC | 342 | [9 empty] | S | S
Indaver | IW1 | 17 | [12 empty] | S | S | S
iPower | NIAGU | 74
Kelwin | KZ4 | 27
Kilroot | NIK1 | 256 | [30 empty] | S | S | S | S | S | S | S | S | S
Kilroot | NIK2 | 258 | [18 empty] | S | S | S | S | S | S | S | S
Kilroot | NIKGT1 | 29
Kilroot | NIKGT2 | 29 | [9 empty] | S | S | S | S | S | S
Kilroot | NIKGT3 | 42 | [38 empty] | S | S | S
Kilroot | NIKGT4 | 42 | [38 empty] | S | S | S
Knockacummer | KC1 | 100
Lee | LE1 | 15 | [18 empty] | S | S
Lee | LE2 | 4 | [13 empty] | S | S | S |  |  |  | S
Lee | LE3 | 8 | [21 empty] | S | S
Liffey | LI1 | 15 | [24 empty] | S
Liffey | LI2 | 15 | [24 empty] | S
Liffey | LI4 | 4 | [26 empty] | S
Liffey | LI5 | 4 | [28 empty] | S
Lisahally | NILPS | 18
Lumcloon | LU1 | 50
Lumcloon | LU2 | 50
Moneypoint | MP1 | 285 | [22 empty] | S | S
Moneypoint | MP2 | 285 | [9 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Moneypoint | MP3 | 285 | [39 empty] | S | S | S
Moyle | MOYLE | 450
Poolbeg | PB4 | 154 | [42 empty] | S
Poolbeg | PB5 | 146 | [21 empty] | S | S | S
Poolbeg | PB6 | 168 | [21 empty] | S | S | S
Powerhouse Generation | NIPH1 | 34
Powerhouse Generation | PG1 | 10
Rhode | RP1 | 52
Rhode | RP2 | 52
Seal Rock | SK3 | 85
Seal Rock | SK4 | 85
Seecon | SO1 | 105
Shannonbridge | SI1 | 50
Shannonbridge | SI2 | 50
Tarbert | TB1 | 54
Tarbert | TB2 | 54
Tarbert | TB3 | 241
Tarbert | TB4 | 243
Tawnaghmore | TP1 | 52 | [33 empty] | S | S | S | S | S | S | S | S | S | S
Tawnaghmore | TP3 | 52 | [33 empty] | S | S | S | S | S | S | S | S | S | S
Turlough Hill | TH1 | 73 | [18 empty] | S | S | S | S
Turlough Hill | TH2 | 73 | [18 empty] | S | S | S | S
Turlough Hill | TH3 | 73 | [18 empty] | S | S | S | S
Turlough Hill | TH4 | 73 | [18 empty] | S | S | S | S
Tynagh | TYC | 384 | [33 empty] | S
VIOTAS | EE1 | 47
VIOTAS | EE2 | 20
VIOTAS | EE3 | 8
VIOTAS | EE4 | 9
VIOTAS | EE5 | 7
VIOTAS | EE6 | 14
VIOTAS | EE7 | 9
Viridian Energy | VE1 | 20
Viridian Energy DSU | VE2 | 13
Whitegate | WG1 | 444 | [36 empty] | S

## All Island Outages
Upcoming Outages including STMOs and Annual Outages
Station | Unit | NPR | Start Date | End Date | Value | Duration
Edenderry | ED1 | 118 | 2021-12-26 13:00 | 2022-01-02 08:00 | S | 6.75
Ardnacrusha | AA4 | 24 | 2022-01-18 08:00 | 2022-01-19 20:00 | S | 1.5
Seal Rock | SK3 | 85 | 2022-01-31 06:00 | 2022-02-02 18:00 | S | 2.5
Ballylumford | NIB31 | 249 | 2022-02-16 19:00 | 2022-02-19 19:30 | S | 3
Moneypoint | MP2 | 285 | 2022-02-28 22:00 | 2022-09-04 22:00 | S | 188
Huntstown | HNC | 342 | 2022-03-01 | 2022-03-12 | S | 11
Kilroot | NIKGT2 | 29 | 2022-03-01 | 2022-04-12 | S | 42
EWIC | EW1 | 500 | 2022-03-14 09:00 | 2022-03-14 17:00 | S | 0.33
EWIC | EW1 | 500 | 2022-03-14 17:00 | 2022-05-03 23:00 | S | 50.25
Indaver | IW1 | 17 | 2022-03-20 | 2022-04-14 | S | 25
Seal Rock | SK4 | 85 | 2022-03-21 06:00 | 2022-03-23 18:00 | S | 2.5
Lee | LE2 | 4 | 2022-03-26 08:00 | 2022-04-15 20:00 | S | 20.5
Coolkeeragh | NIC30 | 408 | 2022-03-27 | 2022-03-28 | S | 1
Aghada | AD2 | 449 | 2022-03-31 01:00 | 2022-04-05 20:00 | S | 5.75
Moyle | MOYLE | 450 | 2022-04-02 | 2022-04-03 | S | 1
Moyle | MOYLE | 450 | 2022-04-03 | 2022-06-03 | 250 | 61
Ardnacrusha | AA4 | 24 | 2022-04-04 08:00 | 2022-11-18 20:00 | S | 228.5
Erne | ER1 | 10 | 2022-04-04 08:00 | 2022-04-08 20:00 | S | 4.5
Edenderry | ED1 | 118 | 2022-04-14 18:00 | 2022-04-20 08:00 | S | 5.58
Coolkeeragh | NICGT8 | 53 | 2022-04-25 | 2022-04-30 | S | 5
Ardnacrusha | AA1 | 21 | 2022-04-25 08:00 | 2022-04-29 20:00 | S | 4.5
Kilroot | NIK2 | 258 | 2022-04-29 | 2022-06-28 | S | 60
Dublin Waste To Energy | DW1 | 61.5 | 2022-05-01 | 2022-05-06 | 26 | 5
Ballylumford | NIBGT1 | 58 | 2022-05-01 | 2022-06-12 | S | 42
Turlough Hill | TH3 | 73 | 2022-05-01 06:00 | 2022-05-28 21:00 | S | 27.58
Turlough Hill | TH1 | 73 | 2022-05-01 06:00 | 2022-05-28 21:00 | S | 27.58
Turlough Hill | TH2 | 73 | 2022-05-01 06:00 | 2022-05-28 21:00 | S | 27.58
Turlough Hill | TH4 | 73 | 2022-05-01 06:00 | 2022-05-28 21:00 | S | 27.58
Lee | LE1 | 15 | 2022-05-03 08:00 | 2022-05-13 20:00 | S | 10.5
Dublin Waste To Energy | DW1 | 61.5 | 2022-05-06 | 2022-05-16 | S | 10
Erne | ER2 | 10 | 2022-05-09 08:00 | 2022-05-13 20:00 | S | 4.5
Lee | LE2 | 4 | 2022-05-09 08:00 | 2022-05-15 20:00 | S | 6.5
Dublin Waste To Energy | DW1 | 61.5 | 2022-05-16 | 2022-05-21 | 26 | 5
Seal Rock | SK3 | 85 | 2022-05-16 18:00 | 2022-05-19 18:00 | S | 3
Seal Rock | SK4 | 85 | 2022-05-17 | 2022-05-19 12:00 | S | 2.5
Aghada | AD2 | 449 | 2022-05-17 01:00 | 2022-06-13 20:00 | S | 27.75
Lee | LE3 | 8 | 2022-05-23 08:00 | 2022-06-03 20:00 | S | 11.5
Poolbeg | PB6 | 168 | 2022-05-23 12:00 | 2022-06-11 20:00 | S | 19.33
Poolbeg | PB5 | 146 | 2022-05-23 12:00 | 2022-06-11 20:00 | S | 19.33
Moneypoint | MP1 | 285 | 2022-05-27 22:00 | 2022-06-15 22:00 | S | 19
Moyle | MOYLE | 450 | 2022-06-03 | 2022-06-11 | S | 8
Seal Rock | SK4 | 85 | 2022-06-06 06:00 | 2022-06-09 18:00 | S | 3.5
Moyle | MOYLE | 450 | 2022-06-11 | 2022-07-22 | 250 | 41
Liffey | LI2 | 15 | 2022-06-12 08:00 | 2022-06-17 17:00 | S | 5.33
Liffey | LI1 | 15 | 2022-06-12 08:00 | 2022-06-17 17:00 | S | 5.33
Ardnacrusha | AA2 | 22 | 2022-06-13 08:00 | 2022-06-20 20:00 | S | 7.5
Erne | ER3 | 22.5 | 2022-06-13 08:00 | 2022-06-17 20:00 | S | 4.5
Great Island | GI4 | 461 | 2022-06-21 | 2022-08-10 | S | 50
Dublin Bay | DB1 | 405 | 2022-06-24 20:00 | 2022-07-12 18:00 | S | 17.92
Tarbert | TB4 | 243 | 2022-06-25 | 2022-07-01 | S | 6
Liffey | LI4 | 4 | 2022-06-26 08:00 | 2022-07-01 17:00 | S | 5.33
Edenderry | ED1 | 118 | 2022-07-01 12:00 | 2022-08-29 08:00 | S | 58.83
Liffey | LI5 | 4 | 2022-07-10 08:00 | 2022-07-15 17:00 | S | 5.33
Aghada | AT2 | 90 | 2022-07-11 | 2022-07-14 | S | 3
Aghada | AT1 | 90 | 2022-07-11 | 2022-07-14 | S | 3
Aghada | AT4 | 90 | 2022-07-18 | 2022-07-21 | S | 3
Moyle | MOYLE | 450 | 2022-07-22 | 2022-08-05 | 450 | 14
Kilroot | NIK1 | 256 | 2022-07-25 | 2022-09-23 | S | 60
Seal Rock | SK3 | 85 | 2022-07-25 06:00 | 2022-07-28 18:00 | S | 3.5
Moyle | MOYLE | 450 | 2022-08-05 | 2022-08-27 | 450 | 22
Tawnaghmore | TP3 | 52 | 2022-08-13 | 2022-10-22 | S | 70
Tawnaghmore | TP1 | 52 | 2022-08-13 | 2022-10-22 | S | 70
Tynagh | TYC | 384 | 2022-08-15 20:00 | 2022-08-20 20:00 | S | 5
EWIC | EW1 | 500 | 2022-08-18 09:00 | 2022-08-18 23:00 | S | 0.58
Whitegate | WG1 | 444 | 2022-09-02 21:00 | 2022-09-14 21:00 | S | 12
Ballylumford | NIBGT2 | 58 | 2022-09-05 | 2022-09-12 | S | 7
Erne | ER4 | 22.5 | 2022-09-05 08:00 | 2022-09-09 20:00 | S | 4.5
Ardnacrusha | AA3 | 19 | 2022-09-05 08:00 | 2022-09-09 20:00 | S | 4.5
Coolkeeragh | NIC30 | 408 | 2022-09-18 | 2022-09-19 | S | 1
Kilroot | NIKGT4 | 42 | 2022-09-19 | 2022-10-10 | S | 21
Kilroot | NIKGT3 | 42 | 2022-09-19 | 2022-10-10 | S | 21
Moneypoint | MP3 | 285 | 2022-09-23 22:00 | 2022-10-13 22:00 | S | 20
Kilroot | NIKGT1 | 29 | 2022-09-24 | 2022-09-25 23:30 | S | 1.96
Ballylumford | NIB31 | 249 | 2022-09-24 | 2022-10-08 | 161 | 14
Ballylumford | NIB32 | 249 | 2022-09-24 | 2022-10-08 | 161 | 14
Kilroot | NIKGT2 | 29 | 2022-09-24 | 2022-09-26 | S | 2
Dublin Waste To Energy | DW1 | 61.5 | 2022-10-01 | 2022-10-05 | 26 | 4
Dublin Waste To Energy | DW1 | 61.5 | 2022-10-05 | 2022-10-07 | S | 2
Dublin Waste To Energy | DW1 | 61.5 | 2022-10-07 | 2022-10-11 | 26 | 4
Coolkeeragh | NIC30 | 408 | 2022-10-15 | 2022-10-17 | S | 2
Poolbeg | PB6 | 168 | 2022-10-17 12:00 | 2022-10-22 20:00 | 84 | 5.33
Poolbeg | PB4 | 154 | 2022-10-17 12:00 | 2022-10-22 20:00 | S | 5.33
Seal Rock | SK4 | 85 | 2022-10-24 06:00 | 2022-10-26 18:00 | S | 2.5
Edenderry | ED5 | 58 | 2022-10-24 08:00 | 2022-10-24 18:00 | S | 0.42
Edenderry | ED3 | 58 | 2022-10-24 08:00 | 2022-10-24 18:00 | S | 0.42
Aghada | AD2 | 449 | 2022-10-31 01:00 | 2022-11-05 20:00 | S | 5.75
Seal Rock | SK3 | 85 | 2022-11-28 06:00 | 2022-11-30 18:00 | S | 2.5
Edenderry | ED1 | 118 | 2022-12-26 12:00 | 2023-01-01 08:00 | S | 5.83
|  |  | Scheduled Outage | S
|  |  | Forced Outage | F
|  |  | Unit partially available | 10