## Outage Plan EirGrid
2022 GENERATION OUTAGE PLAN (EIRGRID)
|  | Month | Jan '2022 | [5 empty] | Feb '2022 |  |  |  | Mar '2022 |  |  |  | Apr '2022 |  |  |  | May '2022 |  |  |  |  | Jun '2022 |  |  |  | Jul '2022 |  |  |  | Aug '2022 |  |  |  |  | Sep '2022 |  |  |  | Oct '2022 |  |  |  |  | Nov '2022 |  |  |  | Dec '2022
|  | Week | 52 '2021 | 1 '2022 | 2 '2022 | 3 '2022 | 4 '2022 | 5 '2022 | 6 '2022 | 7 '2022 | 8 '2022 | 9 '2022 | 10 '2022 | 11 '2022 | 12 '2022 | 13 '2022 | 14 '2022 | 15 '2022 | 16 '2022 | 17 '2022 | 18 '2022 | 19 '2022 | 20 '2022 | 21 '2022 | 22 '2022 | 23 '2022 | 24 '2022 | 25 '2022 | 26 '2022 | 27 '2022 | 28 '2022 | 29 '2022 | 30 '2022 | 31 '2022 | 32 '2022 | 33 '2022 | 34 '2022 | 35 '2022 | 36 '2022 | 37 '2022 | 38 '2022 | 39 '2022 | 40 '2022 | 41 '2022 | 42 '2022 | 43 '2022 | 44 '2022 | 45 '2022 | 46 '2022 | 47 '2022 | 48 '2022 | 49 '2022 | 50 '2022 | 51 '2022 | 52 '2022
Station | Unit | NPR
Aghada | AD2 | 449 |  | F | [33 empty] | S | S | S | S | [5 empty] | S
Aghada | AT1 | 90
Aghada | AT2 | 90
Aghada | AT4 | 90
Ardnacrusha | AA1 | 21 | [17 empty] | S
Ardnacrusha | AA2 | 22 | [24 empty] | S
Ardnacrusha | AA3 | 19 | [36 empty] | S
Ardnacrusha | AA4 | 24 | [11 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Beenanaspuck Tobertoreen | XT2 | 11
DAE Virtual Power Plant | DP1 | 19
DAE Virtual Power Plant | DP2 | 26
Dublin Bay | DB1 | 405 | [28 empty] | S | S
Dublin Waste To Energy | DW1 | 62 | [22 empty] | S
Edenderry | ED1 | 118 | [27 empty] | S | S | S | S | S | S | [19 empty] | S
Edenderry | ED3 | 58 |  |  |  |  | F
Edenderry | ED5 | 58
Electric Ireland | EI1 | 20
Endeco Technologies | EC1 | 47
Endeco Technologies | EC2 | 11
Endeco Technologies | EC5 | 15
Energy Trading | ET1 | 13
Enernoc | AE1 | 95
Enernoc | AE2 | 12
Enernoc | AE3 | 14
Enernoc | AE4 | 15
Enernoc | AE5 | 15
Enernoc | EN1 | 15
Enernoc | EN2 | 16
Enernoc | EN3 | 16
Enernoc | EN4 | 16
Enernoc | EN5 | 6
Enernoc | EN6 | 11
Enernoc | EN8 | 21
Enernoc | EN9 | 16
Erne | ER1 | 10 | [14 empty] | S
Erne | ER2 | 10 | F | F | F | [16 empty] | S
Erne | ER3 | 22 | [24 empty] | S
Erne | ER4 | 22 | [36 empty] | S
EWIC | EW1 | 500 | [11 empty] | S | S | S | S | S | S | S
Gardnershill | GP1 | 8
Great Island | GI4 | 461 | [25 empty] | S | S | S | S | S | S | S
Huntstown | HN2 | 400
Huntstown | HNC | 342 | [9 empty] | S | S
Indaver | IW1 | 17 | [12 empty] | S | S | S
Kelwin | KZ4 | 27
Knockacummer | KC1 | 100
Lee | LE1 | 15 | [18 empty] | S | S
Lee | LE2 | 4 | [13 empty] | S | S | S |  |  |  | S
Lee | LE3 | 8 | [21 empty] | S | S
Liffey | LI1 | 15 | F | F | F | F | F | F | F | F | F | F | F | F | F | F | [10 empty] | S
Liffey | LI2 | 15 | F | F | F | [21 empty] | S
Liffey | LI4 | 4 | [26 empty] | S
Liffey | LI5 | 4 | [28 empty] | S
Lumcloon | LU1 | 50
Lumcloon | LU2 | 50
Moneypoint | MP1 | 285 | [23 empty] | S | F | F
Moneypoint | MP2 | 285 | [9 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Moneypoint | MP3 | 285 | [39 empty] | S | S | S
Poolbeg | PB4 | 154 | [42 empty] | S
Poolbeg | PB5 | 146 | [21 empty] | S | S | S
Poolbeg | PB6 | 168 | [21 empty] | S | S | S
Powerhouse Generation | PG1 | 10
Rhode | RP1 | 52
Rhode | RP2 | 52
Seal Rock | SK3 | 85
Seal Rock | SK4 | 85
Seecon | SO1 | 105
Shannonbridge | SI1 | 50
Shannonbridge | SI2 | 50
Tarbert | TB1 | 54 | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F
Tarbert | TB2 | 54 | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F
Tarbert | TB3 | 241 | [13 empty] | F | F | F | F | F | F
Tarbert | TB4 | 243 | F | F | F | F | F | F | F | F | F
Tawnaghmore | TP1 | 52 | [33 empty] | S
Tawnaghmore | TP3 | 52 | [34 empty] | S
Turlough Hill | TH1 | 73 | [18 empty] | S | S | S | S | S | S | S
Turlough Hill | TH2 | 73 | [18 empty] | S | S | S | S | S | S | S
Turlough Hill | TH3 | 73 | [18 empty] | S | S | S | S | S | S | S
Turlough Hill | TH4 | 73 | [18 empty] | S | S | S | S | S | S | S
Tynagh | TYC | 384 | [33 empty] | S
VIOTAS | EE1 | 47
VIOTAS | EE2 | 20
VIOTAS | EE3 | 8
VIOTAS | EE4 | 9
VIOTAS | EE5 | 7
VIOTAS | EE6 | 14
VIOTAS | EE7 | 9
Viridian Energy | VE1 | 20
Viridian Energy DSU | VE2 | 13
Whitegate | WG1 | 444 | [41 empty] | S

## EirGrid Outages
Upcoming Outages including STMOs and Annual Outages
Station | Unit | NPR | Start Date | End Date | Value | Duration
Tarbert | TB4 | 243 | 2021-04-13 15:00 | 2022-02-28 17:00 | F | 321.08
Liffey | LI2 | 15 | 2021-05-09 17:00 | 2022-01-15 | F | 250.25
Liffey | LI1 | 15 | 2021-05-09 17:00 | 2022-04-01 | F | 326.25
Tarbert | TB2 | 54 | 2021-09-18 21:30 | 2023-04-01 | F | 559.08
Tarbert | TB1 | 54 | 2021-11-03 17:00 | 2023-04-01 | F | 513.25
Ardnacrusha | AA4 | 24 | 2021-12-08 20:00 | 2022-03-14 08:00 | 12 | 95.5
Erne | ER2 | 10 | 2021-12-09 10:00 | 2022-01-13 18:00 | F | 35.33
Moneypoint | MP1 | 285 | 2021-12-14 20:00 | 2022-05-27 22:00 | 265 | 164.08
Moneypoint | MP3 | 285 | 2021-12-20 17:00 | 2022-09-23 22:00 | 260 | 277.17
Moneypoint | MP2 | 285 | 2021-12-23 07:00 | 2022-01-16 07:00 | 220 | 24
Edenderry | ED1 | 118 | 2021-12-29 22:30 | 2022-01-12 10:00 | 100 | 13.46
Tarbert | TB3 | 241 | 2021-12-31 18:00 | 2022-01-27 20:00 | 220 | 27.08
Tynagh | TYC | 384 | 2022-01-05 09:00 | 2022-01-05 10:30 | 50 | 0.04
Poolbeg | PB5 | 146 | 2022-01-05 09:30 | 2022-01-06 12:00 | F | 1.08
Poolbeg | PB6 | 168 | 2022-01-05 09:30 | 2022-01-06 12:00 | 84 | 1.08
Dublin Waste To Energy | DW1 | 61.5 | 2022-01-05 10:00 | 2022-01-06 02:00 | 50 | 0.67
Tynagh | TYC | 384 | 2022-01-05 10:30 | 2022-01-05 12:30 | 194 | 0.08
Aghada | AD2 | 449 | 2022-01-05 20:00 | 2022-01-12 10:30 | F | 6.58
Dublin Waste To Energy | DW1 | 61.5 | 2022-01-06 02:00 | 2022-01-06 17:00 | 33 | 0.58
Dublin Waste To Energy | DW1 | 61.5 | 2022-01-06 17:00 | 2022-01-06 23:00 | 50 | 0.25
Whitegate | WG1 | 444 | 2022-01-07 02:00 | 2022-01-07 03:00 | F | 0
Huntstown | HN2 | 400 | 2022-01-07 06:00 | 2022-01-07 12:00 | F | 0.25
Dublin Waste To Energy | DW1 | 61.5 | 2022-01-08 11:00 | 2022-01-09 | 45 | 0.5
Dublin Waste To Energy | DW1 | 61.5 | 2022-01-09 | 2022-01-09 09:00 | 28 | 0.33
Dublin Waste To Energy | DW1 | 61.5 | 2022-01-10 10:00 | 2022-01-10 20:00 | 50 | 0.42
Dublin Waste To Energy | DW1 | 61.5 | 2022-01-12 08:00 | 2022-01-18 17:00 | 28 | 6.33
Edenderry | ED1 | 118 | 2022-01-12 10:00 | 2022-01-13 09:30 | 105 | 0.96
Erne | ER1 | 10 | 2022-01-13 08:00 | 2022-01-13 18:00 | F | 0.42
Turlough Hill | TH3 | 73 | 2022-01-13 09:00 | 2022-01-13 16:00 | F | 0.25
Edenderry | ED1 | 118 | 2022-01-13 09:30 | 2022-01-17 23:00 | 108 | 4.54
Huntstown | HNC | 342 | 2022-01-14 05:30 | 2022-01-14 09:00 | 232 | 0.12
Aghada | AD2 | 449 | 2022-01-14 21:00 | 2022-01-15 13:00 | F | 0.67
Moneypoint | MP2 | 285 | 2022-01-16 07:00 | 2022-01-16 10:30 | 99 | 0.12
Moneypoint | MP2 | 285 | 2022-01-16 10:30 | 2022-02-28 22:00 | 220 | 43.46
Huntstown | HNC | 342 | 2022-01-17 06:30 | 2022-01-17 08:00 | F | 0.04
Edenderry | ED1 | 118 | 2022-01-17 23:00 | 2022-01-19 17:00 | 105 | 1.75
Aghada | AD2 | 449 | 2022-01-18 22:00 | 2022-01-19 20:00 | F | 0.92
Edenderry | ED1 | 118 | 2022-01-19 17:00 | 2022-01-20 10:00 | 108 | 0.67
Edenderry | ED1 | 118 | 2022-01-20 10:00 | 2022-01-28 23:00 | 110 | 8.5
Edenderry | ED3 | 58 | 2022-01-24 09:00 | 2022-01-28 16:00 | F | 4.25
Edenderry | ED5 | 58 | 2022-01-25 08:00 | 2022-01-25 12:00 | 30 | 0.17
Edenderry | ED5 | 58 | 2022-01-25 12:00 | 2022-01-25 14:00 | 40 | 0.08
Erne | ER2 | 10 | 2022-01-26 11:00 | 2022-01-26 17:00 | F | 0.25
Turlough Hill | TH1 | 73 | 2022-01-26 12:00 | 2022-01-26 13:00 | F | 0
Turlough Hill | TH2 | 73 | 2022-01-26 13:00 | 2022-01-26 14:00 | F | 0
Tarbert | TB3 | 241 | 2022-01-27 20:00 | 2022-01-30 17:00 | F | 2.83
Turlough Hill | TH4 | 73 | 2022-01-28 09:00 | 2022-01-28 16:00 | F | 0.25
Edenderry | ED1 | 118 | 2022-01-28 23:00 | 2022-01-31 23:00 | 105 | 3
Tarbert | TB3 | 241 | 2022-01-30 17:00 | 2022-03-26 08:00 | 220 | 54.58
Seal Rock | SK3 | 85 | 2022-01-31 06:00 | 2022-02-02 18:00 | S | 2.5
Edenderry | ED1 | 118 | 2022-01-31 23:00 | 2022-02-04 23:00 | 110 | 4
Erne | ER4 | 22.5 | 2022-02-03 09:00 | 2022-02-03 16:30 | F | 0.29
Erne | ER3 | 22.5 | 2022-02-03 09:00 | 2022-02-03 16:30 | F | 0.29
Tynagh | TYC | 384 | 2022-02-03 20:00 | 2022-02-08 20:00 | F | 5
Erne | ER1 | 10 | 2022-02-04 09:00 | 2022-02-04 16:30 | F | 0.29
Erne | ER2 | 10 | 2022-02-04 09:00 | 2022-02-04 16:30 | F | 0.29
Seal Rock | SK4 | 85 | 2022-02-21 06:00 | 2022-02-23 18:00 | S | 2.5
Moneypoint | MP2 | 285 | 2022-02-28 22:00 | 2022-09-04 22:00 | S | 188
Huntstown | HNC | 342 | 2022-03-01 | 2022-03-11 | S | 10
Ardnacrusha | AA4 | 24 | 2022-03-14 08:00 | 2022-12-21 20:00 | S | 282.5
EWIC | EW1 | 500 | 2022-03-14 09:00 | 2022-03-14 17:00 | S | 0.33
EWIC | EW1 | 500 | 2022-03-14 17:00 | 2022-05-03 23:00 | S | 50.25
Indaver | IW1 | 17 | 2022-03-20 | 2022-04-14 | S | 25
Tarbert | TB3 | 241 | 2022-03-26 08:00 | 2022-05-07 17:00 | F | 42.33
Lee | LE2 | 4 | 2022-03-26 08:00 | 2022-04-15 20:00 | S | 20.5
Aghada | AD2 | 449 | 2022-03-31 01:00 | 2022-04-05 20:00 | S | 5.75
Erne | ER1 | 10 | 2022-04-04 08:00 | 2022-04-08 20:00 | S | 4.5
Edenderry | ED1 | 118 | 2022-04-14 18:00 | 2022-04-20 08:00 | S | 5.58
Ardnacrusha | AA1 | 21 | 2022-04-25 08:00 | 2022-04-29 20:00 | S | 4.5
Lee | LE1 | 15 | 2022-05-03 08:00 | 2022-05-13 20:00 | S | 10.5
Turlough Hill | TH4 | 73 | 2022-05-04 06:00 | 2022-06-22 21:00 | S | 49.58
Turlough Hill | TH3 | 73 | 2022-05-04 06:00 | 2022-06-22 21:00 | S | 49.58
Turlough Hill | TH1 | 73 | 2022-05-04 06:00 | 2022-06-22 21:00 | S | 49.58
Turlough Hill | TH2 | 73 | 2022-05-04 06:00 | 2022-06-22 21:00 | S | 49.58
Erne | ER2 | 10 | 2022-05-09 08:00 | 2022-05-13 20:00 | S | 4.5
Lee | LE2 | 4 | 2022-05-09 08:00 | 2022-05-13 20:00 | S | 4.5
Seal Rock | SK3 | 85 | 2022-05-16 18:00 | 2022-05-19 18:00 | S | 3
Seal Rock | SK4 | 85 | 2022-05-17 | 2022-05-19 12:00 | S | 2.5
Dublin Waste To Energy | DW1 | 61.5 | 2022-05-22 | 2022-06-02 | 26 | 11
Lee | LE3 | 8 | 2022-05-23 08:00 | 2022-06-03 20:00 | S | 11.5
Poolbeg | PB6 | 168 | 2022-05-23 12:00 | 2022-06-11 20:00 | S | 19.33
Poolbeg | PB5 | 146 | 2022-05-23 12:00 | 2022-06-11 20:00 | S | 19.33
Dublin Waste To Energy | DW1 | 61.5 | 2022-06-02 | 2022-06-06 | S | 4
Moneypoint | MP1 | 285 | 2022-06-03 22:00 | 2022-06-23 22:00 | S | 20
Dublin Waste To Energy | DW1 | 61.5 | 2022-06-06 | 2022-06-17 | 26 | 11
Seal Rock | SK4 | 85 | 2022-06-06 06:00 | 2022-06-09 18:00 | S | 3.5
Liffey | LI2 | 15 | 2022-06-12 08:00 | 2022-06-17 17:00 | S | 5.33
Liffey | LI1 | 15 | 2022-06-12 08:00 | 2022-06-17 17:00 | S | 5.33
Ardnacrusha | AA2 | 22 | 2022-06-13 08:00 | 2022-06-20 20:00 | S | 7.5
Erne | ER3 | 22.5 | 2022-06-13 08:00 | 2022-06-17 20:00 | S | 4.5
Moneypoint | MP1 | 285 | 2022-06-15 22:00 | 2023-01-01 | 265 | 199.08
Great Island | GI4 | 461 | 2022-06-21 | 2022-08-10 | S | 50
Liffey | LI4 | 4 | 2022-06-26 08:00 | 2022-07-01 17:00 | S | 5.33
Edenderry | ED1 | 118 | 2022-07-01 12:00 | 2022-08-13 08:00 | S | 42.83
Dublin Bay | DB1 | 405 | 2022-07-08 20:00 | 2022-07-26 18:00 | S | 17.92
Liffey | LI5 | 4 | 2022-07-10 08:00 | 2022-07-15 17:00 | S | 5.33
Aghada | AT2 | 90 | 2022-07-11 | 2022-07-14 | S | 3
Aghada | AT1 | 90 | 2022-07-11 | 2022-07-14 | S | 3
Aghada | AT4 | 90 | 2022-07-18 | 2022-07-21 | S | 3
Seal Rock | SK3 | 85 | 2022-07-25 06:00 | 2022-07-28 18:00 | S | 3.5
Tawnaghmore | TP1 | 52 | 2022-08-13 | 2022-08-21 | S | 8
Tynagh | TYC | 384 | 2022-08-15 20:00 | 2022-08-20 20:00 | S | 5
EWIC | EW1 | 500 | 2022-08-18 09:00 | 2022-08-18 23:00 | S | 0.58
Tawnaghmore | TP3 | 52 | 2022-08-20 | 2022-08-28 | S | 8
Aghada | AD2 | 449 | 2022-08-27 22:00 | 2022-09-24 06:00 | S | 27.33
Moneypoint | MP2 | 285 | 2022-09-04 22:00 | 2023-01-01 | 220 | 118.08
Erne | ER4 | 22.5 | 2022-09-05 08:00 | 2022-09-09 20:00 | S | 4.5
Ardnacrusha | AA3 | 19 | 2022-09-05 08:00 | 2022-09-09 20:00 | S | 4.5
Moneypoint | MP3 | 285 | 2022-09-23 22:00 | 2022-10-13 22:00 | S | 20
Dublin Waste To Energy | DW1 | 61.5 | 2022-10-01 | 2022-10-05 | 26 | 4
Dublin Waste To Energy | DW1 | 61.5 | 2022-10-05 | 2022-10-07 | S | 2
Dublin Waste To Energy | DW1 | 61.5 | 2022-10-07 | 2022-10-11 | 26 | 4
Whitegate | WG1 | 444 | 2022-10-07 21:00 | 2022-10-19 21:00 | S | 12
Poolbeg | PB6 | 168 | 2022-10-17 12:00 | 2022-10-22 20:00 | 84 | 5.33
Poolbeg | PB4 | 154 | 2022-10-17 12:00 | 2022-10-22 20:00 | S | 5.33
Moneypoint | MP3 | 285 | 2022-10-23 22:00 | 2023-01-01 | 260 | 69.08
Seal Rock | SK4 | 85 | 2022-10-24 06:00 | 2022-10-26 18:00 | S | 2.5
Edenderry | ED5 | 58 | 2022-10-24 08:00 | 2022-10-24 18:00 | S | 0.42
Edenderry | ED3 | 58 | 2022-10-24 08:00 | 2022-10-24 18:00 | S | 0.42
Aghada | AD2 | 449 | 2022-10-31 01:00 | 2022-11-05 20:00 | S | 5.75
Seal Rock | SK3 | 85 | 2022-11-28 06:00 | 2022-11-30 18:00 | S | 2.5
Edenderry | ED1 | 118 | 2022-12-26 13:00 | 2023-01-02 08:00 | S | 6.75
|  |  | Scheduled Outage | S
|  |  | Forced Outage | F
|  |  | Unit partially available | 10

## Outage Plan SONI
2022 GENERATION OUTAGE PLAN (SONI)
|  | Month | Jan '2022 | [5 empty] | Feb '2022 |  |  |  | Mar '2022 |  |  |  | Apr '2022 |  |  |  | May '2022 |  |  |  |  | Jun '2022 |  |  |  | Jul '2022 |  |  |  | Aug '2022 |  |  |  |  | Sep '2022 |  |  |  | Oct '2022 |  |  |  |  | Nov '2022 |  |  |  | Dec '2022
|  | Week | 52 '2021 | 1 '2022 | 2 '2022 | 3 '2022 | 4 '2022 | 5 '2022 | 6 '2022 | 7 '2022 | 8 '2022 | 9 '2022 | 10 '2022 | 11 '2022 | 12 '2022 | 13 '2022 | 14 '2022 | 15 '2022 | 16 '2022 | 17 '2022 | 18 '2022 | 19 '2022 | 20 '2022 | 21 '2022 | 22 '2022 | 23 '2022 | 24 '2022 | 25 '2022 | 26 '2022 | 27 '2022 | 28 '2022 | 29 '2022 | 30 '2022 | 31 '2022 | 32 '2022 | 33 '2022 | 34 '2022 | 35 '2022 | 36 '2022 | 37 '2022 | 38 '2022 | 39 '2022 | 40 '2022 | 41 '2022 | 42 '2022 | 43 '2022 | 44 '2022 | 45 '2022 | 46 '2022 | 47 '2022 | 48 '2022 | 49 '2022 | 50 '2022 | 51 '2022 | 52 '2022
Station | Unit | NPR
AC Automation | NIACA | 8
Activation Energy | NIAEA | 9
Ballylumford | NIB10 | 94
Ballylumford | NIB31 | 249
Ballylumford | NIB32 | 249
Ballylumford | NIBGT1 | 58 | [18 empty] | S | S | S | S | S | S | S | S
Ballylumford | NIBGT2 | 58 | [36 empty] | S
Contour Global | NICG2 | 3
Contour Global | NICGA | 12
Coolkeeragh | NIC30 | 408 | [39 empty] | S
Coolkeeragh | NICGT8 | 53 | [17 empty] | S
Empower | NIEMP | 3
Endeco Technologies | NIECA | 13
Energy Trading | NIETB | 9
Energy Trading | NIETD | 5
Energy Trading | NIETR | 19
iPower | NIAGU | 74
Kilroot | NIK1 | 256 |  |  | F | F | [26 empty] | S | S | S | S | S | S | S | S | S
Kilroot | NIK2 | 258 |  | F | [16 empty] | S | S | S | S | S | S | S | S
Kilroot | NIKGT1 | 29
Kilroot | NIKGT2 | 29 | [9 empty] | S | S | S | S | S | S
Kilroot | NIKGT3 | 42 | [41 empty] | S | S | S
Kilroot | NIKGT4 | 42 | [41 empty] | S | S | S
Lisahally | NILPS | 18
Moyle | MOYLE | 450
Powerhouse Generation | NIPH1 | 34

## SONI Outages
Upcoming Outages including STMOs and Annual Outages
Station | Unit | NPR | Start Date | End Date | Value | Duration
Kilroot | NIKGT4 | 42 | 2022-01-03 17:00 | 2022-01-05 17:30 | F | 2
Kilroot | NIK2 | 258 | 2022-01-04 10:00 | 2022-01-09 22:30 | F | 5.5
Kilroot | NIK1 | 256 | 2022-01-08 21:00 | 2022-01-25 11:30 | F | 16.58
Kilroot | NIK2 | 258 | 2022-01-10 09:30 | 2022-01-11 18:00 | 140 | 1.33
Coolkeeragh | NIC30 | 408 | 2022-01-10 12:00 | 2022-01-10 15:30 | F | 0.12
Kilroot | NIKGT4 | 42 | 2022-01-12 08:00 | 2022-01-13 11:00 | F | 1.08
Kilroot | NIK2 | 258 | 2022-01-12 17:00 | 2022-01-13 01:30 | 140 | 0.33
Coolkeeragh | NICGT8 | 53 | 2022-01-17 07:30 | 2022-01-17 11:30 | F | 0.17
Ballylumford | NIBGT1 | 58 | 2022-01-19 07:00 | 2022-01-19 13:00 | 29 | 0.25
Coolkeeragh | NICGT8 | 53 | 2022-01-20 10:00 | 2022-01-20 14:30 | 26 | 0.17
Kilroot | NIKGT3 | 42 | 2022-01-26 06:00 | 2022-01-26 19:00 | S | 0.5
Coolkeeragh | NICGT8 | 53 | 2022-01-26 10:00 | 2022-01-26 15:30 | 26 | 0.21
Kilroot | NIKGT3 | 42 | 2022-01-27 | 2022-01-28 | S | 1
Ballylumford | NIB10 | 94 | 2022-01-27 03:00 | 2022-01-27 13:30 | F | 0.42
Kilroot | NIKGT4 | 42 | 2022-01-27 06:00 | 2022-01-27 16:30 | S | 0.42
Ballylumford | NIB32 | 249 | 2022-01-27 10:00 | 2022-01-27 11:30 | F | 0.04
Kilroot | NIKGT4 | 42 | 2022-01-28 | 2022-01-29 | S | 1
Ballylumford | NIB32 | 249 | 2022-01-29 07:00 | 2022-01-29 22:30 | S | 0.62
Kilroot | NIKGT3 | 42 | 2022-01-31 06:00 | 2022-02-02 18:30 | S | 2.5
Kilroot | NIKGT4 | 42 | 2022-02-03 06:00 | 2022-02-05 18:30 | S | 2.5
Kilroot | NIKGT3 | 42 | 2022-02-07 06:00 | 2022-02-08 18:30 | S | 1.5
Kilroot | NIKGT4 | 42 | 2022-02-07 06:00 | 2022-02-08 18:30 | S | 1.5
Ballylumford | NIB31 | 249 | 2022-02-16 19:00 | 2022-02-19 19:30 | S | 3
Kilroot | NIKGT2 | 29 | 2022-03-01 | 2022-04-12 | S | 42
Coolkeeragh | NIC30 | 408 | 2022-03-27 | 2022-03-28 | S | 1
Moyle | MOYLE | 450 | 2022-04-02 | 2022-04-03 | S | 1
Moyle | MOYLE | 450 | 2022-04-03 | 2022-06-03 | 250 | 61
Kilroot | NIKGT2 | 29 | 2022-04-04 05:00 | 2022-04-11 18:30 | S | 7.54
Kilroot | NIKGT1 | 29 | 2022-04-04 05:00 | 2022-04-04 18:30 | S | 0.54
Coolkeeragh | NICGT8 | 53 | 2022-04-25 | 2022-04-30 | S | 5
Kilroot | NIK2 | 258 | 2022-04-29 | 2022-06-28 | S | 60
Ballylumford | NIBGT1 | 58 | 2022-05-01 | 2022-06-30 | S | 60
Moyle | MOYLE | 450 | 2022-06-03 | 2022-06-11 | S | 8
Moyle | MOYLE | 450 | 2022-06-11 | 2022-07-22 | 250 | 41
Coolkeeragh | NIC30 | 408 | 2022-07-02 | 2022-07-04 | S | 2
Moyle | MOYLE | 450 | 2022-07-22 | 2022-08-05 | 450 | 14
Kilroot | NIK1 | 256 | 2022-07-25 | 2022-09-23 | S | 60
Moyle | MOYLE | 450 | 2022-08-05 | 2022-08-27 | 450 | 22
Ballylumford | NIBGT2 | 58 | 2022-09-05 | 2022-09-12 | S | 7
Coolkeeragh | NIC30 | 408 | 2022-09-24 | 2022-10-04 | S | 10
Ballylumford | NIB31 | 249 | 2022-10-08 | 2022-10-22 | 161 | 14
Ballylumford | NIB32 | 249 | 2022-10-08 | 2022-10-22 | 161 | 14
Kilroot | NIKGT4 | 42 | 2022-10-10 | 2022-10-31 | S | 21
Kilroot | NIKGT3 | 42 | 2022-10-10 | 2022-10-31 | S | 21
Kilroot | NIKGT1 | 29 | 2022-10-15 | 2022-10-16 23:30 | S | 1.96
Kilroot | NIKGT2 | 29 | 2022-10-15 | 2022-10-17 | S | 2
Coolkeeragh | NIC30 | 408 | 2022-11-19 | 2022-11-20 | S | 1
|  |  | Scheduled Outage | S
|  |  | Forced Outage | F
|  |  | Unit partially available | 10

## Outage Plan All Island
2022 GENERATION OUTAGE PLAN (All Island)
|  | Month | Jan '2022 | [5 empty] | Feb '2022 |  |  |  | Mar '2022 |  |  |  | Apr '2022 |  |  |  | May '2022 |  |  |  |  | Jun '2022 |  |  |  | Jul '2022 |  |  |  | Aug '2022 |  |  |  |  | Sep '2022 |  |  |  | Oct '2022 |  |  |  |  | Nov '2022 |  |  |  | Dec '2022
|  | Week | 52 '2021 | 1 '2022 | 2 '2022 | 3 '2022 | 4 '2022 | 5 '2022 | 6 '2022 | 7 '2022 | 8 '2022 | 9 '2022 | 10 '2022 | 11 '2022 | 12 '2022 | 13 '2022 | 14 '2022 | 15 '2022 | 16 '2022 | 17 '2022 | 18 '2022 | 19 '2022 | 20 '2022 | 21 '2022 | 22 '2022 | 23 '2022 | 24 '2022 | 25 '2022 | 26 '2022 | 27 '2022 | 28 '2022 | 29 '2022 | 30 '2022 | 31 '2022 | 32 '2022 | 33 '2022 | 34 '2022 | 35 '2022 | 36 '2022 | 37 '2022 | 38 '2022 | 39 '2022 | 40 '2022 | 41 '2022 | 42 '2022 | 43 '2022 | 44 '2022 | 45 '2022 | 46 '2022 | 47 '2022 | 48 '2022 | 49 '2022 | 50 '2022 | 51 '2022 | 52 '2022
Station | Unit | NPR
AC Automation | NIACA | 8
Activation Energy | NIAEA | 9
Aghada | AD2 | 449 |  | F | [33 empty] | S | S | S | S | [5 empty] | S
Aghada | AT1 | 90
Aghada | AT2 | 90
Aghada | AT4 | 90
Ardnacrusha | AA1 | 21 | [17 empty] | S
Ardnacrusha | AA2 | 22 | [24 empty] | S
Ardnacrusha | AA3 | 19 | [36 empty] | S
Ardnacrusha | AA4 | 24 | [11 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Ballylumford | NIB10 | 94
Ballylumford | NIB31 | 249
Ballylumford | NIB32 | 249
Ballylumford | NIBGT1 | 58 | [18 empty] | S | S | S | S | S | S | S | S
Ballylumford | NIBGT2 | 58 | [36 empty] | S
Beenanaspuck Tobertoreen | XT2 | 11
Contour Global | NICG2 | 3
Contour Global | NICGA | 12
Coolkeeragh | NIC30 | 408 | [39 empty] | S
Coolkeeragh | NICGT8 | 53 | [17 empty] | S
DAE Virtual Power Plant | DP1 | 19
DAE Virtual Power Plant | DP2 | 26
Dublin Bay | DB1 | 405 | [28 empty] | S | S
Dublin Waste To Energy | DW1 | 62 | [22 empty] | S
Edenderry | ED1 | 118 | [27 empty] | S | S | S | S | S | S | [19 empty] | S
Edenderry | ED3 | 58 |  |  |  |  | F
Edenderry | ED5 | 58
Electric Ireland | EI1 | 20
Empower | NIEMP | 3
Endeco Technologies | EC1 | 47
Endeco Technologies | EC2 | 11
Endeco Technologies | EC5 | 15
Endeco Technologies | NIECA | 13
Energy Trading | ET1 | 13
Energy Trading | NIETB | 9
Energy Trading | NIETD | 5
Energy Trading | NIETR | 19
Enernoc | AE1 | 95
Enernoc | AE2 | 12
Enernoc | AE3 | 14
Enernoc | AE4 | 15
Enernoc | AE5 | 15
Enernoc | EN1 | 15
Enernoc | EN2 | 16
Enernoc | EN3 | 16
Enernoc | EN4 | 16
Enernoc | EN5 | 6
Enernoc | EN6 | 11
Enernoc | EN8 | 21
Enernoc | EN9 | 16
Erne | ER1 | 10 | [14 empty] | S
Erne | ER2 | 10 | F | F | F | [16 empty] | S
Erne | ER3 | 22 | [24 empty] | S
Erne | ER4 | 22 | [36 empty] | S
EWIC | EW1 | 500 | [11 empty] | S | S | S | S | S | S | S
Gardnershill | GP1 | 8
Great Island | GI4 | 461 | [25 empty] | S | S | S | S | S | S | S
Huntstown | HN2 | 400
Huntstown | HNC | 342 | [9 empty] | S | S
Indaver | IW1 | 17 | [12 empty] | S | S | S
iPower | NIAGU | 74
Kelwin | KZ4 | 27
Kilroot | NIK1 | 256 |  |  | F | F | [26 empty] | S | S | S | S | S | S | S | S | S
Kilroot | NIK2 | 258 |  | F | [16 empty] | S | S | S | S | S | S | S | S
Kilroot | NIKGT1 | 29
Kilroot | NIKGT2 | 29 | [9 empty] | S | S | S | S | S | S
Kilroot | NIKGT3 | 42 | [41 empty] | S | S | S
Kilroot | NIKGT4 | 42 | [41 empty] | S | S | S
Knockacummer | KC1 | 100
Lee | LE1 | 15 | [18 empty] | S | S
Lee | LE2 | 4 | [13 empty] | S | S | S |  |  |  | S
Lee | LE3 | 8 | [21 empty] | S | S
Liffey | LI1 | 15 | F | F | F | F | F | F | F | F | F | F | F | F | F | F | [10 empty] | S
Liffey | LI2 | 15 | F | F | F | [21 empty] | S
Liffey | LI4 | 4 | [26 empty] | S
Liffey | LI5 | 4 | [28 empty] | S
Lisahally | NILPS | 18
Lumcloon | LU1 | 50
Lumcloon | LU2 | 50
Moneypoint | MP1 | 285 | [23 empty] | S | F | F
Moneypoint | MP2 | 285 | [9 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Moneypoint | MP3 | 285 | [39 empty] | S | S | S
Moyle | MOYLE | 450
Poolbeg | PB4 | 154 | [42 empty] | S
Poolbeg | PB5 | 146 | [21 empty] | S | S | S
Poolbeg | PB6 | 168 | [21 empty] | S | S | S
Powerhouse Generation | NIPH1 | 34
Powerhouse Generation | PG1 | 10
Rhode | RP1 | 52
Rhode | RP2 | 52
Seal Rock | SK3 | 85
Seal Rock | SK4 | 85
Seecon | SO1 | 105
Shannonbridge | SI1 | 50
Shannonbridge | SI2 | 50
Tarbert | TB1 | 54 | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F
Tarbert | TB2 | 54 | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F
Tarbert | TB3 | 241 | [13 empty] | F | F | F | F | F | F
Tarbert | TB4 | 243 | F | F | F | F | F | F | F | F | F
Tawnaghmore | TP1 | 52 | [33 empty] | S
Tawnaghmore | TP3 | 52 | [34 empty] | S
Turlough Hill | TH1 | 73 | [18 empty] | S | S | S | S | S | S | S
Turlough Hill | TH2 | 73 | [18 empty] | S | S | S | S | S | S | S
Turlough Hill | TH3 | 73 | [18 empty] | S | S | S | S | S | S | S
Turlough Hill | TH4 | 73 | [18 empty] | S | S | S | S | S | S | S
Tynagh | TYC | 384 | [33 empty] | S
VIOTAS | EE1 | 47
VIOTAS | EE2 | 20
VIOTAS | EE3 | 8
VIOTAS | EE4 | 9
VIOTAS | EE5 | 7
VIOTAS | EE6 | 14
VIOTAS | EE7 | 9
Viridian Energy | VE1 | 20
Viridian Energy DSU | VE2 | 13
Whitegate | WG1 | 444 | [41 empty] | S

## All Island Outages
Upcoming Outages including STMOs and Annual Outages
Station | Unit | NPR | Start Date | End Date | Value | Duration
Tarbert | TB4 | 243 | 2021-04-13 15:00 | 2022-02-28 17:00 | F | 321.08
Liffey | LI2 | 15 | 2021-05-09 17:00 | 2022-01-15 | F | 250.25
Liffey | LI1 | 15 | 2021-05-09 17:00 | 2022-04-01 | F | 326.25
Tarbert | TB2 | 54 | 2021-09-18 21:30 | 2023-04-01 | F | 559.08
Tarbert | TB1 | 54 | 2021-11-03 17:00 | 2023-04-01 | F | 513.25
Ardnacrusha | AA4 | 24 | 2021-12-08 20:00 | 2022-03-14 08:00 | 12 | 95.5
Erne | ER2 | 10 | 2021-12-09 10:00 | 2022-01-13 18:00 | F | 35.33
Moneypoint | MP1 | 285 | 2021-12-14 20:00 | 2022-05-27 22:00 | 265 | 164.08
Moneypoint | MP3 | 285 | 2021-12-20 17:00 | 2022-09-23 22:00 | 260 | 277.17
Moneypoint | MP2 | 285 | 2021-12-23 07:00 | 2022-01-16 07:00 | 220 | 24
Edenderry | ED1 | 118 | 2021-12-29 22:30 | 2022-01-12 10:00 | 100 | 13.46
Tarbert | TB3 | 241 | 2021-12-31 18:00 | 2022-01-27 20:00 | 220 | 27.08
Kilroot | NIKGT4 | 42 | 2022-01-03 17:00 | 2022-01-05 17:30 | F | 2
Kilroot | NIK2 | 258 | 2022-01-04 10:00 | 2022-01-09 22:30 | F | 5.5
Tynagh | TYC | 384 | 2022-01-05 09:00 | 2022-01-05 10:30 | 50 | 0.04
Poolbeg | PB5 | 146 | 2022-01-05 09:30 | 2022-01-06 12:00 | F | 1.08
Poolbeg | PB6 | 168 | 2022-01-05 09:30 | 2022-01-06 12:00 | 84 | 1.08
Dublin Waste To Energy | DW1 | 61.5 | 2022-01-05 10:00 | 2022-01-06 02:00 | 50 | 0.67
Tynagh | TYC | 384 | 2022-01-05 10:30 | 2022-01-05 12:30 | 194 | 0.08
Aghada | AD2 | 449 | 2022-01-05 20:00 | 2022-01-12 10:30 | F | 6.58
Dublin Waste To Energy | DW1 | 61.5 | 2022-01-06 02:00 | 2022-01-06 17:00 | 33 | 0.58
Dublin Waste To Energy | DW1 | 61.5 | 2022-01-06 17:00 | 2022-01-06 23:00 | 50 | 0.25
Whitegate | WG1 | 444 | 2022-01-07 02:00 | 2022-01-07 03:00 | F | 0
Huntstown | HN2 | 400 | 2022-01-07 06:00 | 2022-01-07 12:00 | F | 0.25
Dublin Waste To Energy | DW1 | 61.5 | 2022-01-08 11:00 | 2022-01-09 | 45 | 0.5
Kilroot | NIK1 | 256 | 2022-01-08 21:00 | 2022-01-25 11:30 | F | 16.58
Dublin Waste To Energy | DW1 | 61.5 | 2022-01-09 | 2022-01-09 09:00 | 28 | 0.33
Kilroot | NIK2 | 258 | 2022-01-10 09:30 | 2022-01-11 18:00 | 140 | 1.33
Dublin Waste To Energy | DW1 | 61.5 | 2022-01-10 10:00 | 2022-01-10 20:00 | 50 | 0.42
Coolkeeragh | NIC30 | 408 | 2022-01-10 12:00 | 2022-01-10 15:30 | F | 0.12
Dublin Waste To Energy | DW1 | 61.5 | 2022-01-12 08:00 | 2022-01-18 17:00 | 28 | 6.33
Kilroot | NIKGT4 | 42 | 2022-01-12 08:00 | 2022-01-13 11:00 | F | 1.08
Edenderry | ED1 | 118 | 2022-01-12 10:00 | 2022-01-13 09:30 | 105 | 0.96
Kilroot | NIK2 | 258 | 2022-01-12 17:00 | 2022-01-13 01:30 | 140 | 0.33
Erne | ER1 | 10 | 2022-01-13 08:00 | 2022-01-13 18:00 | F | 0.42
Turlough Hill | TH3 | 73 | 2022-01-13 09:00 | 2022-01-13 16:00 | F | 0.25
Edenderry | ED1 | 118 | 2022-01-13 09:30 | 2022-01-17 23:00 | 108 | 4.54
Huntstown | HNC | 342 | 2022-01-14 05:30 | 2022-01-14 09:00 | 232 | 0.12
Aghada | AD2 | 449 | 2022-01-14 21:00 | 2022-01-15 13:00 | F | 0.67
Moneypoint | MP2 | 285 | 2022-01-16 07:00 | 2022-01-16 10:30 | 99 | 0.12
Moneypoint | MP2 | 285 | 2022-01-16 10:30 | 2022-02-28 22:00 | 220 | 43.46
Huntstown | HNC | 342 | 2022-01-17 06:30 | 2022-01-17 08:00 | F | 0.04
Coolkeeragh | NICGT8 | 53 | 2022-01-17 07:30 | 2022-01-17 11:30 | F | 0.17
Edenderry | ED1 | 118 | 2022-01-17 23:00 | 2022-01-19 17:00 | 105 | 1.75
Aghada | AD2 | 449 | 2022-01-18 22:00 | 2022-01-19 20:00 | F | 0.92
Ballylumford | NIBGT1 | 58 | 2022-01-19 07:00 | 2022-01-19 13:00 | 29 | 0.25
Edenderry | ED1 | 118 | 2022-01-19 17:00 | 2022-01-20 10:00 | 108 | 0.67
Edenderry | ED1 | 118 | 2022-01-20 10:00 | 2022-01-28 23:00 | 110 | 8.5
Coolkeeragh | NICGT8 | 53 | 2022-01-20 10:00 | 2022-01-20 14:30 | 26 | 0.17
Edenderry | ED3 | 58 | 2022-01-24 09:00 | 2022-01-28 16:00 | F | 4.25
Edenderry | ED5 | 58 | 2022-01-25 08:00 | 2022-01-25 12:00 | 30 | 0.17
Edenderry | ED5 | 58 | 2022-01-25 12:00 | 2022-01-25 14:00 | 40 | 0.08
Kilroot | NIKGT3 | 42 | 2022-01-26 06:00 | 2022-01-26 19:00 | S | 0.5
Coolkeeragh | NICGT8 | 53 | 2022-01-26 10:00 | 2022-01-26 15:30 | 26 | 0.21
Erne | ER2 | 10 | 2022-01-26 11:00 | 2022-01-26 17:00 | F | 0.25
Turlough Hill | TH1 | 73 | 2022-01-26 12:00 | 2022-01-26 13:00 | F | 0
Turlough Hill | TH2 | 73 | 2022-01-26 13:00 | 2022-01-26 14:00 | F | 0
Kilroot | NIKGT3 | 42 | 2022-01-27 | 2022-01-28 | S | 1
Ballylumford | NIB10 | 94 | 2022-01-27 03:00 | 2022-01-27 13:30 | F | 0.42
Kilroot | NIKGT4 | 42 | 2022-01-27 06:00 | 2022-01-27 16:30 | S | 0.42
Ballylumford | NIB32 | 249 | 2022-01-27 10:00 | 2022-01-27 11:30 | F | 0.04
Tarbert | TB3 | 241 | 2022-01-27 20:00 | 2022-01-30 17:00 | F | 2.83
Kilroot | NIKGT4 | 42 | 2022-01-28 | 2022-01-29 | S | 1
Turlough Hill | TH4 | 73 | 2022-01-28 09:00 | 2022-01-28 16:00 | F | 0.25
Edenderry | ED1 | 118 | 2022-01-28 23:00 | 2022-01-31 23:00 | 105 | 3
Ballylumford | NIB32 | 249 | 2022-01-29 07:00 | 2022-01-29 22:30 | S | 0.62
Tarbert | TB3 | 241 | 2022-01-30 17:00 | 2022-03-26 08:00 | 220 | 54.58
Seal Rock | SK3 | 85 | 2022-01-31 06:00 | 2022-02-02 18:00 | S | 2.5
Kilroot | NIKGT3 | 42 | 2022-01-31 06:00 | 2022-02-02 18:30 | S | 2.5
Edenderry | ED1 | 118 | 2022-01-31 23:00 | 2022-02-04 23:00 | 110 | 4
Kilroot | NIKGT4 | 42 | 2022-02-03 06:00 | 2022-02-05 18:30 | S | 2.5
Erne | ER4 | 22.5 | 2022-02-03 09:00 | 2022-02-03 16:30 | F | 0.29
Erne | ER3 | 22.5 | 2022-02-03 09:00 | 2022-02-03 16:30 | F | 0.29
Tynagh | TYC | 384 | 2022-02-03 20:00 | 2022-02-08 20:00 | F | 5
Erne | ER1 | 10 | 2022-02-04 09:00 | 2022-02-04 16:30 | F | 0.29
Erne | ER2 | 10 | 2022-02-04 09:00 | 2022-02-04 16:30 | F | 0.29
Kilroot | NIKGT3 | 42 | 2022-02-07 06:00 | 2022-02-08 18:30 | S | 1.5
Kilroot | NIKGT4 | 42 | 2022-02-07 06:00 | 2022-02-08 18:30 | S | 1.5
Ballylumford | NIB31 | 249 | 2022-02-16 19:00 | 2022-02-19 19:30 | S | 3
Seal Rock | SK4 | 85 | 2022-02-21 06:00 | 2022-02-23 18:00 | S | 2.5
Moneypoint | MP2 | 285 | 2022-02-28 22:00 | 2022-09-04 22:00 | S | 188
Huntstown | HNC | 342 | 2022-03-01 | 2022-03-11 | S | 10
Kilroot | NIKGT2 | 29 | 2022-03-01 | 2022-04-12 | S | 42
Ardnacrusha | AA4 | 24 | 2022-03-14 08:00 | 2022-12-21 20:00 | S | 282.5
EWIC | EW1 | 500 | 2022-03-14 09:00 | 2022-03-14 17:00 | S | 0.33
EWIC | EW1 | 500 | 2022-03-14 17:00 | 2022-05-03 23:00 | S | 50.25
Indaver | IW1 | 17 | 2022-03-20 | 2022-04-14 | S | 25
Tarbert | TB3 | 241 | 2022-03-26 08:00 | 2022-05-07 17:00 | F | 42.33
Lee | LE2 | 4 | 2022-03-26 08:00 | 2022-04-15 20:00 | S | 20.5
Coolkeeragh | NIC30 | 408 | 2022-03-27 | 2022-03-28 | S | 1
Aghada | AD2 | 449 | 2022-03-31 01:00 | 2022-04-05 20:00 | S | 5.75
Moyle | MOYLE | 450 | 2022-04-02 | 2022-04-03 | S | 1
Moyle | MOYLE | 450 | 2022-04-03 | 2022-06-03 | 250 | 61
Kilroot | NIKGT2 | 29 | 2022-04-04 05:00 | 2022-04-11 18:30 | S | 7.54
Kilroot | NIKGT1 | 29 | 2022-04-04 05:00 | 2022-04-04 18:30 | S | 0.54
Erne | ER1 | 10 | 2022-04-04 08:00 | 2022-04-08 20:00 | S | 4.5
Edenderry | ED1 | 118 | 2022-04-14 18:00 | 2022-04-20 08:00 | S | 5.58
Coolkeeragh | NICGT8 | 53 | 2022-04-25 | 2022-04-30 | S | 5
Ardnacrusha | AA1 | 21 | 2022-04-25 08:00 | 2022-04-29 20:00 | S | 4.5
Kilroot | NIK2 | 258 | 2022-04-29 | 2022-06-28 | S | 60
Ballylumford | NIBGT1 | 58 | 2022-05-01 | 2022-06-30 | S | 60
Lee | LE1 | 15 | 2022-05-03 08:00 | 2022-05-13 20:00 | S | 10.5
Turlough Hill | TH4 | 73 | 2022-05-04 06:00 | 2022-06-22 21:00 | S | 49.58
Turlough Hill | TH3 | 73 | 2022-05-04 06:00 | 2022-06-22 21:00 | S | 49.58
Turlough Hill | TH1 | 73 | 2022-05-04 06:00 | 2022-06-22 21:00 | S | 49.58
Turlough Hill | TH2 | 73 | 2022-05-04 06:00 | 2022-06-22 21:00 | S | 49.58
Erne | ER2 | 10 | 2022-05-09 08:00 | 2022-05-13 20:00 | S | 4.5
Lee | LE2 | 4 | 2022-05-09 08:00 | 2022-05-13 20:00 | S | 4.5
Seal Rock | SK3 | 85 | 2022-05-16 18:00 | 2022-05-19 18:00 | S | 3
Seal Rock | SK4 | 85 | 2022-05-17 | 2022-05-19 12:00 | S | 2.5
Dublin Waste To Energy | DW1 | 61.5 | 2022-05-22 | 2022-06-02 | 26 | 11
Lee | LE3 | 8 | 2022-05-23 08:00 | 2022-06-03 20:00 | S | 11.5
Poolbeg | PB6 | 168 | 2022-05-23 12:00 | 2022-06-11 20:00 | S | 19.33
Poolbeg | PB5 | 146 | 2022-05-23 12:00 | 2022-06-11 20:00 | S | 19.33
Dublin Waste To Energy | DW1 | 61.5 | 2022-06-02 | 2022-06-06 | S | 4
Moyle | MOYLE | 450 | 2022-06-03 | 2022-06-11 | S | 8
Moneypoint | MP1 | 285 | 2022-06-03 22:00 | 2022-06-23 22:00 | S | 20
Dublin Waste To Energy | DW1 | 61.5 | 2022-06-06 | 2022-06-17 | 26 | 11
Seal Rock | SK4 | 85 | 2022-06-06 06:00 | 2022-06-09 18:00 | S | 3.5
Moyle | MOYLE | 450 | 2022-06-11 | 2022-07-22 | 250 | 41
Liffey | LI2 | 15 | 2022-06-12 08:00 | 2022-06-17 17:00 | S | 5.33
Liffey | LI1 | 15 | 2022-06-12 08:00 | 2022-06-17 17:00 | S | 5.33
Ardnacrusha | AA2 | 22 | 2022-06-13 08:00 | 2022-06-20 20:00 | S | 7.5
Erne | ER3 | 22.5 | 2022-06-13 08:00 | 2022-06-17 20:00 | S | 4.5
Moneypoint | MP1 | 285 | 2022-06-15 22:00 | 2023-01-01 | 265 | 199.08
Great Island | GI4 | 461 | 2022-06-21 | 2022-08-10 | S | 50
Liffey | LI4 | 4 | 2022-06-26 08:00 | 2022-07-01 17:00 | S | 5.33
Edenderry | ED1 | 118 | 2022-07-01 12:00 | 2022-08-13 08:00 | S | 42.83
Coolkeeragh | NIC30 | 408 | 2022-07-02 | 2022-07-04 | S | 2
Dublin Bay | DB1 | 405 | 2022-07-08 20:00 | 2022-07-26 18:00 | S | 17.92
Liffey | LI5 | 4 | 2022-07-10 08:00 | 2022-07-15 17:00 | S | 5.33
Aghada | AT2 | 90 | 2022-07-11 | 2022-07-14 | S | 3
Aghada | AT1 | 90 | 2022-07-11 | 2022-07-14 | S | 3
Aghada | AT4 | 90 | 2022-07-18 | 2022-07-21 | S | 3
Moyle | MOYLE | 450 | 2022-07-22 | 2022-08-05 | 450 | 14
Kilroot | NIK1 | 256 | 2022-07-25 | 2022-09-23 | S | 60
Seal Rock | SK3 | 85 | 2022-07-25 06:00 | 2022-07-28 18:00 | S | 3.5
Moyle | MOYLE | 450 | 2022-08-05 | 2022-08-27 | 450 | 22
Tawnaghmore | TP1 | 52 | 2022-08-13 | 2022-08-21 | S | 8
Tynagh | TYC | 384 | 2022-08-15 20:00 | 2022-08-20 20:00 | S | 5
EWIC | EW1 | 500 | 2022-08-18 09:00 | 2022-08-18 23:00 | S | 0.58
Tawnaghmore | TP3 | 52 | 2022-08-20 | 2022-08-28 | S | 8
Aghada | AD2 | 449 | 2022-08-27 22:00 | 2022-09-24 06:00 | S | 27.33
Moneypoint | MP2 | 285 | 2022-09-04 22:00 | 2023-01-01 | 220 | 118.08
Ballylumford | NIBGT2 | 58 | 2022-09-05 | 2022-09-12 | S | 7
Erne | ER4 | 22.5 | 2022-09-05 08:00 | 2022-09-09 20:00 | S | 4.5
Ardnacrusha | AA3 | 19 | 2022-09-05 08:00 | 2022-09-09 20:00 | S | 4.5
Moneypoint | MP3 | 285 | 2022-09-23 22:00 | 2022-10-13 22:00 | S | 20
Coolkeeragh | NIC30 | 408 | 2022-09-24 | 2022-10-04 | S | 10
Dublin Waste To Energy | DW1 | 61.5 | 2022-10-01 | 2022-10-05 | 26 | 4
Dublin Waste To Energy | DW1 | 61.5 | 2022-10-05 | 2022-10-07 | S | 2
Dublin Waste To Energy | DW1 | 61.5 | 2022-10-07 | 2022-10-11 | 26 | 4
Whitegate | WG1 | 444 | 2022-10-07 21:00 | 2022-10-19 21:00 | S | 12
Ballylumford | NIB31 | 249 | 2022-10-08 | 2022-10-22 | 161 | 14
Ballylumford | NIB32 | 249 | 2022-10-08 | 2022-10-22 | 161 | 14
Kilroot | NIKGT4 | 42 | 2022-10-10 | 2022-10-31 | S | 21
Kilroot | NIKGT3 | 42 | 2022-10-10 | 2022-10-31 | S | 21
Kilroot | NIKGT1 | 29 | 2022-10-15 | 2022-10-16 23:30 | S | 1.96
Kilroot | NIKGT2 | 29 | 2022-10-15 | 2022-10-17 | S | 2
Poolbeg | PB6 | 168 | 2022-10-17 12:00 | 2022-10-22 20:00 | 84 | 5.33
Poolbeg | PB4 | 154 | 2022-10-17 12:00 | 2022-10-22 20:00 | S | 5.33
Moneypoint | MP3 | 285 | 2022-10-23 22:00 | 2023-01-01 | 260 | 69.08
Seal Rock | SK4 | 85 | 2022-10-24 06:00 | 2022-10-26 18:00 | S | 2.5
Edenderry | ED5 | 58 | 2022-10-24 08:00 | 2022-10-24 18:00 | S | 0.42
Edenderry | ED3 | 58 | 2022-10-24 08:00 | 2022-10-24 18:00 | S | 0.42
Aghada | AD2 | 449 | 2022-10-31 01:00 | 2022-11-05 20:00 | S | 5.75
Coolkeeragh | NIC30 | 408 | 2022-11-19 | 2022-11-20 | S | 1
Seal Rock | SK3 | 85 | 2022-11-28 06:00 | 2022-11-30 18:00 | S | 2.5
Edenderry | ED1 | 118 | 2022-12-26 13:00 | 2023-01-02 08:00 | S | 6.75
|  |  | Scheduled Outage | S
|  |  | Forced Outage | F
|  |  | Unit partially available | 10