## Outage Plan EirGrid
2022 GENERATION OUTAGE PLAN (EIRGRID)
|  | Month | Jan '2022 | [5 empty] | Feb '2022 |  |  |  | Mar '2022 |  |  |  | Apr '2022 |  |  |  | May '2022 |  |  |  |  | Jun '2022 |  |  |  | Jul '2022 |  |  |  | Aug '2022 |  |  |  |  | Sep '2022 |  |  |  | Oct '2022 |  |  |  |  | Nov '2022 |  |  |  | Dec '2022
|  | Week | 52 '2021 | 1 '2022 | 2 '2022 | 3 '2022 | 4 '2022 | 5 '2022 | 6 '2022 | 7 '2022 | 8 '2022 | 9 '2022 | 10 '2022 | 11 '2022 | 12 '2022 | 13 '2022 | 14 '2022 | 15 '2022 | 16 '2022 | 17 '2022 | 18 '2022 | 19 '2022 | 20 '2022 | 21 '2022 | 22 '2022 | 23 '2022 | 24 '2022 | 25 '2022 | 26 '2022 | 27 '2022 | 28 '2022 | 29 '2022 | 30 '2022 | 31 '2022 | 32 '2022 | 33 '2022 | 34 '2022 | 35 '2022 | 36 '2022 | 37 '2022 | 38 '2022 | 39 '2022 | 40 '2022 | 41 '2022 | 42 '2022 | 43 '2022 | 44 '2022 | 45 '2022 | 46 '2022 | 47 '2022 | 48 '2022 | 49 '2022 | 50 '2022 | 51 '2022 | 52 '2022
Station | Unit | NPR
Aghada | AD2 | 449 |  | F | [17 empty] | S | [15 empty] | S | S | S | S | [5 empty] | S
Aghada | AT1 | 90
Aghada | AT2 | 90
Aghada | AT4 | 90
Ardnacrusha | AA1 | 21 | [17 empty] | S
Ardnacrusha | AA2 | 22 | [24 empty] | S
Ardnacrusha | AA3 | 19 | [36 empty] | S
Ardnacrusha | AA4 | 24 | [8 empty] | S |  |  |  | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Beenanaspuck Tobertoreen | XT2 | 11
DAE Virtual Power Plant | DP1 | 19
DAE Virtual Power Plant | DP2 | 26
Dublin Bay | DB1 | 405 | [13 empty] | F |  |  | F | F | F | [17 empty] | S | S
Dublin Waste To Energy | DW1 | 62 | [22 empty] | S
Edenderry | ED1 | 118 | [27 empty] | S | S | S | S | S | S | [19 empty] | S
Edenderry | ED3 | 58 |  |  |  |  | F
Edenderry | ED5 | 58
Electric Ireland | EI1 | 20
Endeco Technologies | EC1 | 47
Endeco Technologies | EC2 | 11
Endeco Technologies | EC5 | 15
Energy Trading | ET1 | 13
Enernoc | AE1 | 95
Enernoc | AE2 | 12
Enernoc | AE3 | 14
Enernoc | AE4 | 15
Enernoc | AE5 | 15
Enernoc | EN1 | 15
Enernoc | EN2 | 16
Enernoc | EN3 | 16
Enernoc | EN4 | 16
Enernoc | EN5 | 6
Enernoc | EN6 | 11
Enernoc | EN8 | 21
Enernoc | EN9 | 16
Erne | ER1 | 10 | [14 empty] | S
Erne | ER2 | 10 | F | F | F | [16 empty] | S
Erne | ER3 | 22 | [24 empty] | S
Erne | ER4 | 22 | [36 empty] | S
EWIC | EW1 | 500 | [11 empty] | S | S | S | S | S | S | S
Gardnershill | GP1 | 8
Great Island | GI4 | 461 | [9 empty] | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | S | S | S | S | S | S | S
Huntstown | HN2 | 400
Huntstown | HNC | 342 | [9 empty] | S | S
Indaver | IW1 | 17 | [12 empty] | S | S | S
Kelwin | KZ4 | 27
Knockacummer | KC1 | 100
Lee | LE1 | 15 | [18 empty] | S | S
Lee | LE2 | 4 | [12 empty] | S | S | S | S | F | F | S | S
Lee | LE3 | 8 | [21 empty] | S | S
Liffey | LI1 | 15 | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | [6 empty] | S
Liffey | LI2 | 15 | F | F | F | [21 empty] | S
Liffey | LI4 | 4 | [26 empty] | S
Liffey | LI5 | 4 | [28 empty] | S
Lumcloon | LU1 | 50
Lumcloon | LU2 | 50
Moneypoint | MP1 | 285 | [23 empty] | S | S | F
Moneypoint | MP2 | 285 | [14 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Moneypoint | MP3 | 285 | [39 empty] | S | S | S
Poolbeg | PB4 | 154 | [42 empty] | S
Poolbeg | PB5 | 146
Poolbeg | PB6 | 168 | [21 empty] | S | S
Powerhouse Generation | PG1 | 10
Rhode | RP1 | 52
Rhode | RP2 | 52
Seal Rock | SK3 | 85
Seal Rock | SK4 | 85
Seecon | SO1 | 105
Shannonbridge | SI1 | 50
Shannonbridge | SI2 | 50
Tarbert | TB1 | 54 | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F
Tarbert | TB2 | 54 | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F
Tarbert | TB3 | 241 | F | [21 empty] | F | F | F | F | F | F
Tarbert | TB4 | 243 | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F
Tawnaghmore | TP1 | 52 | [33 empty] | S
Tawnaghmore | TP3 | 52 | [34 empty] | S
Turlough Hill | TH1 | 73 | [19 empty] | S | S | S | S | S | S | S
Turlough Hill | TH2 | 73 | [19 empty] | S | S | S | S | S | S | S
Turlough Hill | TH3 | 73 | [19 empty] | S | S | S | S | S | S | S
Turlough Hill | TH4 | 73 | [19 empty] | S | S | S | S | S | S | S
Tynagh | TYC | 384 | [33 empty] | S
VIOTAS | EE1 | 47
VIOTAS | EE2 | 20
VIOTAS | EE3 | 8
VIOTAS | EE4 | 9
VIOTAS | EE5 | 7
VIOTAS | EE6 | 14
VIOTAS | EE7 | 9
Viridian Energy | VE1 | 20
Viridian Energy DSU | VE2 | 13
Whitegate | WG1 | 444 | [41 empty] | S

## EirGrid Outages
Upcoming Outages including STMOs and Annual Outages
Station | Unit | NPR | Start Date | End Date | Value | Duration
Tarbert | TB4 | 243 | 2021-04-13 15:00 | 2023-04-01 | F | 717.33
Liffey | LI2 | 15 | 2021-05-09 17:00 | 2022-01-15 | F | 250.25
Liffey | LI1 | 15 | 2021-05-09 17:00 | 2022-05-01 | F | 356.25
Tarbert | TB2 | 54 | 2021-09-18 21:30 | 2031-01-01 | F | 3391.08
Tarbert | TB1 | 54 | 2021-11-03 17:00 | 2031-01-01 | F | 3345.25
Ardnacrusha | AA4 | 24 | 2021-12-08 20:00 | 2022-02-21 08:00 | 12 | 74.5
Erne | ER2 | 10 | 2021-12-09 10:00 | 2022-01-13 18:00 | F | 35.33
Moneypoint | MP1 | 285 | 2021-12-14 20:00 | 2022-02-20 13:30 | 265 | 67.71
Moneypoint | MP3 | 285 | 2021-12-20 17:00 | 2022-02-23 15:30 | 260 | 64.92
Moneypoint | MP2 | 285 | 2021-12-23 07:00 | 2022-02-01 11:00 | 220 | 40.17
Tarbert | TB3 | 241 | 2021-12-27 21:00 | 2022-01-05 10:00 | F | 8.5
Edenderry | ED1 | 118 | 2021-12-29 22:30 | 2022-01-12 10:00 | 100 | 13.46
Tynagh | TYC | 384 | 2022-01-05 09:00 | 2022-01-05 10:30 | 50 | 0.04
Poolbeg | PB5 | 146 | 2022-01-05 09:30 | 2022-01-06 12:00 | F | 1.08
Poolbeg | PB6 | 168 | 2022-01-05 09:30 | 2022-01-06 12:00 | 84 | 1.08
Tarbert | TB3 | 241 | 2022-01-05 10:00 | 2022-01-27 20:00 | 220 | 22.42
Dublin Waste To Energy | DW1 | 61.5 | 2022-01-05 10:00 | 2022-01-06 02:00 | 50 | 0.67
Tynagh | TYC | 384 | 2022-01-05 10:30 | 2022-01-05 12:30 | 194 | 0.08
Aghada | AD2 | 449 | 2022-01-05 20:00 | 2022-01-12 10:30 | F | 6.58
Dublin Waste To Energy | DW1 | 61.5 | 2022-01-06 02:00 | 2022-01-06 17:00 | 33 | 0.58
Dublin Waste To Energy | DW1 | 61.5 | 2022-01-06 17:00 | 2022-01-06 23:00 | 50 | 0.25
Lee | LE2 | 4 | 2022-01-07 01:30 | 2022-01-07 03:00 | F | 0.04
Whitegate | WG1 | 444 | 2022-01-07 02:00 | 2022-01-07 03:00 | F | 0
Huntstown | HN2 | 400 | 2022-01-07 06:00 | 2022-01-07 12:00 | F | 0.25
Dublin Waste To Energy | DW1 | 61.5 | 2022-01-08 11:00 | 2022-01-09 | 45 | 0.5
Dublin Waste To Energy | DW1 | 61.5 | 2022-01-09 | 2022-01-09 09:00 | 28 | 0.33
Dublin Waste To Energy | DW1 | 61.5 | 2022-01-10 10:00 | 2022-01-10 20:00 | 50 | 0.42
Edenderry | ED1 | 118 | 2022-01-12 10:00 | 2022-01-13 09:30 | 105 | 0.96
Erne | ER1 | 10 | 2022-01-13 08:00 | 2022-01-13 18:00 | F | 0.42
Turlough Hill | TH3 | 73 | 2022-01-13 09:00 | 2022-01-13 16:00 | F | 0.25
Edenderry | ED1 | 118 | 2022-01-13 09:30 | 2022-01-17 23:00 | 108 | 4.54
Huntstown | HNC | 342 | 2022-01-14 05:30 | 2022-01-14 09:00 | 232 | 0.12
Aghada | AD2 | 449 | 2022-01-14 21:00 | 2022-01-15 13:00 | F | 0.67
Dublin Waste To Energy | DW1 | 61.5 | 2022-01-16 08:00 | 2022-01-19 07:00 | 28 | 2.92
Huntstown | HNC | 342 | 2022-01-17 06:30 | 2022-01-17 08:00 | F | 0.04
Edenderry | ED1 | 118 | 2022-01-17 23:00 | 2022-01-19 17:00 | 105 | 1.75
Aghada | AD2 | 449 | 2022-01-18 22:00 | 2022-01-19 20:00 | F | 0.92
Edenderry | ED1 | 118 | 2022-01-19 17:00 | 2022-01-20 10:00 | 108 | 0.67
Edenderry | ED1 | 118 | 2022-01-20 10:00 | 2022-01-28 23:00 | 110 | 8.5
Edenderry | ED3 | 58 | 2022-01-24 09:00 | 2022-01-28 16:00 | F | 4.25
Edenderry | ED5 | 58 | 2022-01-25 08:00 | 2022-01-25 12:00 | 30 | 0.17
Edenderry | ED5 | 58 | 2022-01-25 12:00 | 2022-01-25 14:00 | 40 | 0.08
Ardnacrusha | AA1 | 21 | 2022-01-25 13:30 | 2022-01-25 15:00 | F | 0.04
Turlough Hill | TH2 | 73 | 2022-01-26 13:00 | 2022-01-26 14:00 | F | 0
Tarbert | TB3 | 241 | 2022-01-27 20:00 | 2022-01-31 02:00 | F | 3.25
Turlough Hill | TH4 | 73 | 2022-01-28 09:00 | 2022-01-28 16:00 | F | 0.25
Aghada | AT2 | 90 | 2022-01-28 23:00 | 2022-01-30 10:30 | F | 1.46
Edenderry | ED1 | 118 | 2022-01-28 23:00 | 2022-01-31 23:00 | 105 | 3
Whitegate | WG1 | 444 | 2022-01-29 14:00 | 2022-01-29 21:30 | F | 0.29
Tarbert | TB3 | 241 | 2022-01-30 17:00 | 2022-03-11 22:00 | 220 | 40.17
Seal Rock | SK3 | 85 | 2022-01-31 06:00 | 2022-02-02 18:00 | S | 2.5
Edenderry | ED1 | 118 | 2022-01-31 23:00 | 2022-02-04 23:00 | 110 | 4
Moneypoint | MP2 | 285 | 2022-02-01 11:00 | 2022-02-07 11:00 | 99 | 6
Aghada | AT2 | 90 | 2022-02-03 08:00 | 2022-02-03 16:00 | F | 0.33
Erne | ER4 | 22.5 | 2022-02-03 09:00 | 2022-02-03 16:30 | F | 0.29
Erne | ER3 | 22.5 | 2022-02-03 09:00 | 2022-02-03 16:30 | F | 0.29
Tynagh | TYC | 384 | 2022-02-03 20:00 | 2022-02-08 06:00 | F | 4.42
Erne | ER1 | 10 | 2022-02-04 09:00 | 2022-02-04 16:30 | F | 0.29
Erne | ER2 | 10 | 2022-02-04 09:00 | 2022-02-04 16:30 | F | 0.29
Edenderry | ED1 | 118 | 2022-02-04 23:00 | 2022-02-14 20:30 | 102 | 9.88
Turlough Hill | TH2 | 73 | 2022-02-07 10:00 | 2022-02-07 15:00 | F | 0.17
Moneypoint | MP2 | 285 | 2022-02-07 11:00 | 2022-02-09 09:00 | F | 1.92
Turlough Hill | TH1 | 73 | 2022-02-08 10:00 | 2022-02-08 15:00 | F | 0.17
Aghada | AD2 | 449 | 2022-02-08 19:00 | 2022-02-08 20:00 | 130 | 0
Moneypoint | MP2 | 285 | 2022-02-09 09:00 | 2022-02-14 11:00 | 99 | 5.08
Turlough Hill | TH1 | 73 | 2022-02-09 23:00 | 2022-02-10 01:00 | F | 0.08
Turlough Hill | TH2 | 73 | 2022-02-09 23:00 | 2022-02-10 01:00 | F | 0.08
Turlough Hill | TH3 | 73 | 2022-02-09 23:00 | 2022-02-10 01:00 | F | 0.08
Turlough Hill | TH4 | 73 | 2022-02-09 23:00 | 2022-02-10 01:00 | F | 0.08
Turlough Hill | TH1 | 73 | 2022-02-10 09:00 | 2022-02-10 15:30 | F | 0.25
Indaver | IW1 | 17 | 2022-02-10 14:00 | 2022-02-13 05:30 | F | 2.62
Tynagh | TYC | 384 | 2022-02-13 20:00 | 2022-02-14 20:00 | F | 1
Moneypoint | MP2 | 285 | 2022-02-14 11:00 | 2022-02-25 14:00 | 200 | 11.08
Edenderry | ED1 | 118 | 2022-02-14 20:30 | 2022-02-22 18:30 | 100 | 7.92
Ardnacrusha | AA2 | 22 | 2022-02-15 17:00 | 2022-02-16 09:30 | F | 0.67
Moneypoint | MP1 | 285 | 2022-02-20 13:30 | 2022-02-20 16:30 | F | 0.08
Moneypoint | MP1 | 285 | 2022-02-20 16:30 | 2022-02-23 15:30 | 265 | 2.92
Ardnacrusha | AA4 | 24 | 2022-02-21 08:00 | 2022-02-25 16:00 | S | 4.33
Tawnaghmore | TP1 | 52 | 2022-02-21 09:00 | 2022-02-23 09:30 | F | 2
Dublin Waste To Energy | DW1 | 61.5 | 2022-02-22 04:00 | 2022-02-24 19:00 | 28 | 2.58
Edenderry | ED1 | 118 | 2022-02-22 18:30 | 2022-02-23 18:00 | F | 0.96
Whitegate | WG1 | 444 | 2022-02-23 07:00 | 2022-02-23 10:30 | F | 0.12
Turlough Hill | TH1 | 73 | 2022-02-23 09:00 | 2022-02-23 12:00 | F | 0.08
Tawnaghmore | TP3 | 52 | 2022-02-23 09:00 | 2022-02-24 17:00 | F | 1.33
Moneypoint | MP3 | 285 | 2022-02-23 15:30 | 2022-02-24 15:30 | 175 | 1
Moneypoint | MP1 | 285 | 2022-02-23 15:30 | 2022-02-24 15:30 | 175 | 1
Edenderry | ED1 | 118 | 2022-02-23 18:00 | 2022-02-23 20:00 | 60 | 0.08
Edenderry | ED1 | 118 | 2022-02-23 20:00 | 2022-02-24 10:30 | 96 | 0.58
Edenderry | ED1 | 118 | 2022-02-24 10:30 | 2022-03-05 22:00 | 94 | 9.46
Moneypoint | MP1 | 285 | 2022-02-24 15:30 | 2022-03-22 09:30 | 250 | 25.75
Moneypoint | MP3 | 285 | 2022-02-24 15:30 | 2022-03-16 | 260 | 19.33
Moneypoint | MP2 | 285 | 2022-02-25 14:00 | 2022-03-03 22:00 | F | 6.33
Ardnacrusha | AA4 | 24 | 2022-02-25 16:00 | 2022-03-15 09:00 | 12 | 17.67
Whitegate | WG1 | 444 | 2022-02-25 16:30 | 2022-03-04 06:00 | F | 6.54
Aghada | AD2 | 449 | 2022-02-26 01:00 | 2022-02-26 12:30 | F | 0.46
Huntstown | HNC | 342 | 2022-03-01 | 2022-03-11 | S | 10
Great Island | GI4 | 461 | 2022-03-01 13:00 | 2022-06-21 | F | 111.42
Moneypoint | MP2 | 285 | 2022-03-03 22:00 | 2022-03-21 12:30 | 200 | 17.58
Edenderry | ED1 | 118 | 2022-03-05 22:00 | 2022-03-05 23:30 | F | 0.04
Edenderry | ED1 | 118 | 2022-03-05 23:30 | 2022-03-09 23:00 | 94 | 3.96
Aghada | AD2 | 449 | 2022-03-06 22:00 | 2022-03-08 16:00 | F | 1.75
Turlough Hill | TH4 | 73 | 2022-03-07 10:00 | 2022-03-07 15:00 | S | 0.17
Turlough Hill | TH2 | 73 | 2022-03-08 10:00 | 2022-03-08 15:00 | S | 0.17
Edenderry | ED1 | 118 | 2022-03-09 23:00 | 2022-03-11 08:00 | F | 1.33
Aghada | AD2 | 449 | 2022-03-10 10:30 | 2022-03-11 16:00 | F | 1.21
Huntstown | HNC | 342 | 2022-03-11 | 2022-03-11 11:30 | F | 0.46
Edenderry | ED1 | 118 | 2022-03-11 08:00 | 2022-04-14 17:00 | 84 | 34.33
Liffey | LI5 | 4 | 2022-03-11 10:00 | 2022-03-11 14:00 | F | 0.17
Tarbert | TB3 | 241 | 2022-03-11 22:00 | 2022-03-12 17:00 | F | 0.75
Tarbert | TB3 | 241 | 2022-03-12 17:00 | 2022-03-25 20:00 | 220 | 13.08
EWIC | EW1 | 500 | 2022-03-14 09:00 | 2022-03-14 17:00 | S | 0.33
EWIC | EW1 | 500 | 2022-03-14 17:00 | 2022-05-03 23:00 | S | 50.25
Aghada | AD2 | 449 | 2022-03-15 00:30 | 2022-03-17 01:30 | F | 2
Ardnacrusha | AA4 | 24 | 2022-03-15 09:00 | 2022-03-15 16:00 | F | 0.25
Turlough Hill | TH2 | 73 | 2022-03-15 11:00 | 2022-03-15 15:00 | F | 0.17
Ardnacrusha | AA4 | 24 | 2022-03-15 16:00 | 2022-03-21 08:00 | 12 | 5.67
Moneypoint | MP3 | 285 | 2022-03-16 | 2022-09-23 22:00 | 210 | 191.92
Turlough Hill | TH3 | 73 | 2022-03-17 15:30 | 2022-03-18 11:00 | F | 0.79
Indaver | IW1 | 17 | 2022-03-20 | 2022-04-14 | S | 25
Seal Rock | SK4 | 85 | 2022-03-21 06:00 | 2022-03-23 18:00 | F | 2.5
Ardnacrusha | AA4 | 24 | 2022-03-21 08:00 | 2022-12-21 20:00 | S | 275.5
Moneypoint | MP2 | 285 | 2022-03-21 12:30 | 2022-03-24 12:30 | F | 3
Moneypoint | MP1 | 285 | 2022-03-22 09:30 | 2022-03-23 10:30 | F | 1
Rhode | RP2 | 52 | 2022-03-23 07:30 | 2022-03-23 12:30 | F | 0.17
Moneypoint | MP1 | 285 | 2022-03-23 10:30 | 2022-04-08 09:00 | 250 | 15.92
Rhode | RP2 | 52 | 2022-03-24 07:00 | 2022-03-24 09:30 | F | 0.08
Lee | LE2 | 4 | 2022-03-24 08:00 | 2022-04-15 20:00 | S | 22.5
Moneypoint | MP2 | 285 | 2022-03-24 12:30 | 2022-04-02 21:00 | 200 | 9.33
Tarbert | TB3 | 241 | 2022-03-25 20:00 | 2022-03-27 22:30 | F | 2.08
Dublin Bay | DB1 | 405 | 2022-03-26 20:00 | 2022-04-02 20:00 | F | 7
Tarbert | TB3 | 241 | 2022-03-27 22:30 | 2022-03-28 21:30 | 220 | 0.92
Tarbert | TB3 | 241 | 2022-03-28 21:30 | 2022-03-29 12:00 | F | 0.58
Tarbert | TB3 | 241 | 2022-03-29 12:00 | 2022-04-08 20:00 | 220 | 10.33
Turlough Hill | TH3 | 73 | 2022-03-31 10:00 | 2022-03-31 15:00 | F | 0.17
Moneypoint | MP2 | 285 | 2022-04-02 21:00 | 2022-09-04 22:00 | S | 155
Erne | ER1 | 10 | 2022-04-04 08:00 | 2022-04-08 20:00 | S | 4.5
Aghada | AT1 | 90 | 2022-04-06 08:30 | 2022-04-06 13:00 | F | 0.17
Moneypoint | MP1 | 285 | 2022-04-08 09:00 | 2022-04-15 23:30 | F | 7.58
Turlough Hill | TH4 | 73 | 2022-04-08 09:30 | 2022-04-08 14:30 | F | 0.17
Tarbert | TB3 | 241 | 2022-04-08 20:00 | 2022-04-11 17:00 | F | 2.83
Tarbert | TB3 | 241 | 2022-04-11 17:00 | 2022-04-12 03:30 | 220 | 0.42
Tarbert | TB3 | 241 | 2022-04-12 03:30 | 2022-04-12 12:30 | F | 0.33
Tynagh | TYC | 384 | 2022-04-12 06:30 | 2022-04-12 11:30 | F | 0.17
Tarbert | TB3 | 241 | 2022-04-12 12:30 | 2022-05-28 07:00 | 220 | 45.75
Edenderry | ED1 | 118 | 2022-04-14 17:00 | 2022-04-20 08:00 | S | 5.58
Lee | LE2 | 4 | 2022-04-15 20:00 | 2022-05-03 08:00 | F | 17.5
Moneypoint | MP1 | 285 | 2022-04-15 23:30 | 2022-04-19 04:30 | 250 | 3.17
Moneypoint | MP1 | 285 | 2022-04-19 04:30 | 2022-04-20 22:00 | F | 1.71
Dublin Bay | DB1 | 405 | 2022-04-20 04:30 | 2022-05-09 15:00 | F | 19.42
Edenderry | ED1 | 118 | 2022-04-20 08:00 | 2022-05-06 | 100 | 15.67
Moneypoint | MP1 | 285 | 2022-04-20 22:00 | 2022-05-04 22:00 | 240 | 14
Turlough Hill | TH4 | 73 | 2022-04-21 09:00 | 2022-04-21 15:00 | F | 0.25
Huntstown | HNC | 342 | 2022-04-21 23:00 | 2022-04-22 16:00 | 220 | 0.67
Ardnacrusha | AA1 | 21 | 2022-04-25 08:00 | 2022-04-29 20:00 | S | 4.5
Lee | LE3 | 8 | 2022-04-25 18:30 | 2022-04-29 15:00 | F | 3.83
Ardnacrusha | AA1 | 21 | 2022-04-29 20:00 | 2022-05-06 20:00 | F | 7
Lee | LE1 | 15 | 2022-05-03 08:00 | 2022-05-13 20:00 | S | 10.5
Lee | LE2 | 4 | 2022-05-03 08:00 | 2022-05-13 20:00 | S | 10.5
Aghada | AT2 | 90 | 2022-05-03 18:00 | 2022-05-05 17:30 | F | 1.96
EWIC | EW1 | 500 | 2022-05-03 23:00 | 2022-05-07 14:30 | F | 3.62
Moneypoint | MP1 | 285 | 2022-05-04 22:00 | 2022-05-07 22:00 | F | 3
Moneypoint | MP1 | 285 | 2022-05-07 22:00 | 2022-06-03 22:00 | 240 | 27
Aghada | AD2 | 449 | 2022-05-08 22:00 | 2022-05-15 22:00 | S | 7
Edenderry | ED1 | 118 | 2022-05-09 | 2022-07-01 12:00 | 94 | 53.5
Turlough Hill | TH1 | 73 | 2022-05-10 07:00 | 2022-06-27 21:00 | S | 49.58
Turlough Hill | TH2 | 73 | 2022-05-10 07:00 | 2022-06-27 21:00 | S | 49.58
Turlough Hill | TH3 | 73 | 2022-05-10 07:00 | 2022-06-27 21:00 | S | 49.58
Turlough Hill | TH4 | 73 | 2022-05-10 07:00 | 2022-06-27 21:00 | S | 49.58
Erne | ER2 | 10 | 2022-05-09 08:00 | 2022-05-13 20:00 | S | 4.5
Moneypoint | MP3 | 285 | 2022-05-09 11:00 | 2022-05-10 09:00 | F | 0.92
Ardnacrusha | AA3 | 19 | 2022-05-11 08:00 | 2022-05-11 16:00 | F | 0.33
Ardnacrusha | AA3 | 19 | 2022-05-18 09:00 | 2022-05-18 17:00 | S | 0.33
Tynagh | TYC | 384 | 2022-05-20 21:00 | 2022-05-22 21:00 | S | 2
Dublin Waste To Energy | DW1 | 61.5 | 2022-05-22 | 2022-06-02 | 26 | 11
Lee | LE3 | 8 | 2022-05-23 08:00 | 2022-06-03 20:00 | S | 11.5
Poolbeg | PB6 | 168 | 2022-05-23 13:00 | 2022-06-03 18:00 | S | 11.17
Tarbert | TB3 | 241 | 2022-05-28 07:00 | 2022-07-10 16:00 | F | 43.33
Dublin Waste To Energy | DW1 | 61.5 | 2022-06-02 | 2022-06-06 | S | 4
Moneypoint | MP1 | 285 | 2022-06-03 22:00 | 2022-06-23 22:00 | S | 20
Dublin Waste To Energy | DW1 | 61.5 | 2022-06-06 | 2022-06-17 | 26 | 11
Seal Rock | SK3 | 85 | 2022-06-06 06:00 | 2022-06-09 18:00 | S | 3.5
Liffey | LI2 | 15 | 2022-06-12 08:00 | 2022-06-17 17:00 | S | 5.33
Liffey | LI1 | 15 | 2022-06-12 08:00 | 2022-06-17 17:00 | S | 5.33
Ardnacrusha | AA2 | 22 | 2022-06-13 08:00 | 2022-06-20 20:00 | S | 7.5
Erne | ER3 | 22.5 | 2022-06-13 08:00 | 2022-06-17 20:00 | S | 4.5
Great Island | GI4 | 461 | 2022-06-21 | 2022-08-10 | S | 50
Moneypoint | MP1 | 285 | 2022-06-23 22:00 | 2023-01-01 | 265 | 191.08
Liffey | LI4 | 4 | 2022-06-26 08:00 | 2022-07-01 17:00 | S | 5.33
Lee | LE1 | 15 | 2022-06-27 09:00 | 2022-06-27 17:00 | S | 0.33
Lee | LE2 | 4 | 2022-06-27 09:00 | 2022-06-27 17:00 | S | 0.33
Edenderry | ED1 | 118 | 2022-07-01 12:00 | 2022-08-13 08:00 | S | 42.83
Liffey | LI5 | 4 | 2022-07-10 08:00 | 2022-07-15 17:00 | S | 5.33
Tarbert | TB3 | 241 | 2022-07-10 16:00 | 2023-01-01 | 220 | 174.33
Aghada | AT2 | 90 | 2022-07-11 | 2022-07-14 | S | 3
Aghada | AT1 | 90 | 2022-07-11 | 2022-07-14 | S | 3
Aghada | AT1 | 90 | 2022-07-14 09:00 | 2022-07-14 17:00 | S | 0.33
Aghada | AT2 | 90 | 2022-07-14 09:00 | 2022-07-14 17:00 | S | 0.33
Aghada | AT4 | 90 | 2022-07-18 | 2022-07-21 | S | 3
Seal Rock | SK4 | 85 | 2022-07-25 06:00 | 2022-07-28 18:00 | S | 3.5
Erne | ER1 | 10 | 2022-08-02 09:00 | 2022-08-02 17:00 | S | 0.33
Erne | ER2 | 10 | 2022-08-02 09:00 | 2022-08-02 17:00 | S | 0.33
Tawnaghmore | TP1 | 52 | 2022-08-13 | 2022-08-21 | S | 8
Edenderry | ED1 | 118 | 2022-08-13 07:30 | 2022-10-31 07:30 | 94 | 79
Tynagh | TYC | 384 | 2022-08-14 20:00 | 2022-08-19 20:00 | S | 5
EWIC | EW1 | 500 | 2022-08-18 09:00 | 2022-08-18 23:00 | S | 0.58
Tawnaghmore | TP3 | 52 | 2022-08-20 | 2022-08-28 | S | 8
Aghada | AD2 | 449 | 2022-08-27 22:00 | 2022-09-24 06:00 | S | 27.33
Dublin Bay | DB1 | 405 | 2022-09-02 08:00 | 2022-09-20 18:00 | S | 18.42
Moneypoint | MP2 | 285 | 2022-09-04 22:00 | 2023-01-01 | 220 | 118.08
Erne | ER4 | 22.5 | 2022-09-05 08:00 | 2022-09-09 20:00 | S | 4.5
Ardnacrusha | AA3 | 19 | 2022-09-05 08:00 | 2022-09-09 20:00 | S | 4.5
Seal Rock | SK3 | 85 | 2022-09-12 18:00 | 2022-09-15 18:00 | S | 3
Seal Rock | SK4 | 85 | 2022-09-13 | 2022-09-15 12:00 | S | 2.5
Liffey | LI1 | 15 | 2022-09-14 09:00 | 2022-09-14 17:00 | S | 0.33
Liffey | LI2 | 15 | 2022-09-14 09:00 | 2022-09-14 17:00 | S | 0.33
Liffey | LI4 | 4 | 2022-09-14 09:00 | 2022-09-14 17:00 | S | 0.33
Moneypoint | MP3 | 285 | 2022-09-23 22:00 | 2022-10-13 22:00 | S | 20
Turlough Hill | TH2 | 73 | 2022-09-29 09:00 | 2022-09-29 17:00 | S | 0.33
Turlough Hill | TH1 | 73 | 2022-09-29 09:00 | 2022-09-29 17:00 | S | 0.33
Dublin Waste To Energy | DW1 | 61.5 | 2022-10-01 | 2022-10-05 | 26 | 4
Dublin Waste To Energy | DW1 | 61.5 | 2022-10-05 | 2022-10-07 | S | 2
Dublin Waste To Energy | DW1 | 61.5 | 2022-10-07 | 2022-10-11 | 26 | 4
Whitegate | WG1 | 444 | 2022-10-07 21:00 | 2022-10-19 21:00 | S | 12
Poolbeg | PB6 | 168 | 2022-10-17 12:00 | 2022-10-22 20:00 | 84 | 5.33
Poolbeg | PB4 | 154 | 2022-10-17 12:00 | 2022-10-22 20:00 | S | 5.33
Moneypoint | MP3 | 285 | 2022-10-23 22:00 | 2023-01-01 | 260 | 69.08
Seal Rock | SK3 | 85 | 2022-10-24 06:00 | 2022-10-26 18:00 | S | 2.5
Edenderry | ED5 | 58 | 2022-10-24 08:00 | 2022-10-24 18:00 | S | 0.42
Edenderry | ED3 | 58 | 2022-10-24 08:00 | 2022-10-24 18:00 | S | 0.42
Aghada | AD2 | 449 | 2022-10-31 01:00 | 2022-11-05 20:00 | S | 5.75
Seal Rock | SK4 | 85 | 2022-11-28 06:00 | 2022-11-30 18:00 | S | 2.5
Edenderry | ED1 | 118 | 2022-12-26 13:00 | 2023-01-02 08:00 | S | 6.75
|  |  | Scheduled Outage | S
|  |  | Forced Outage | F
|  |  | Unit partially available | 10

## Outage Plan SONI
2022 GENERATION OUTAGE PLAN (SONI)
|  | Month | Jan '2022 | [5 empty] | Feb '2022 |  |  |  | Mar '2022 |  |  |  | Apr '2022 |  |  |  | May '2022 |  |  |  |  | Jun '2022 |  |  |  | Jul '2022 |  |  |  | Aug '2022 |  |  |  |  | Sep '2022 |  |  |  | Oct '2022 |  |  |  |  | Nov '2022 |  |  |  | Dec '2022
|  | Week | 52 '2021 | 1 '2022 | 2 '2022 | 3 '2022 | 4 '2022 | 5 '2022 | 6 '2022 | 7 '2022 | 8 '2022 | 9 '2022 | 10 '2022 | 11 '2022 | 12 '2022 | 13 '2022 | 14 '2022 | 15 '2022 | 16 '2022 | 17 '2022 | 18 '2022 | 19 '2022 | 20 '2022 | 21 '2022 | 22 '2022 | 23 '2022 | 24 '2022 | 25 '2022 | 26 '2022 | 27 '2022 | 28 '2022 | 29 '2022 | 30 '2022 | 31 '2022 | 32 '2022 | 33 '2022 | 34 '2022 | 35 '2022 | 36 '2022 | 37 '2022 | 38 '2022 | 39 '2022 | 40 '2022 | 41 '2022 | 42 '2022 | 43 '2022 | 44 '2022 | 45 '2022 | 46 '2022 | 47 '2022 | 48 '2022 | 49 '2022 | 50 '2022 | 51 '2022 | 52 '2022
Station | Unit | NPR
AC Automation | NIACA | 8
Activation Energy | NIAEA | 9
Ballylumford | NIB10 | 94
Ballylumford | NIB31 | 249
Ballylumford | NIB32 | 249
Ballylumford | NIBGT1 | 58 | [18 empty] | S | S | S | S | S | S | S | S
Ballylumford | NIBGT2 | 58 | [36 empty] | S
Contour Global | NICG2 | 3
Contour Global | NICGA | 12
Coolkeeragh | NIC30 | 408 | [39 empty] | S
Coolkeeragh | NICGT8 | 53 | [17 empty] | S
Empower | NIEMP | 3
Endeco Technologies | NIECA | 13
Energy Trading | NIETB | 9
Energy Trading | NIETD | 5
Energy Trading | NIETR | 19
iPower | NIAGU | 74
Kilroot | NIK1 | 256 |  |  | F | F |  |  |  | F | F | F | F | F | F | F | F | F | F | F | F | F | [10 empty] | S | S | S | S | S | S | S | S | S
Kilroot | NIK2 | 258 |  | F | [5 empty] | F | [5 empty] | F | F |  |  |  | S | S | S | S | S | S | S | S
Kilroot | NIKGT1 | 29
Kilroot | NIKGT2 | 29 | [9 empty] | F |  |  |  | S | S
Kilroot | NIKGT3 | 42 | [5 empty] | F |  |  | F | F |  |  | F | [28 empty] | S | S | S
Kilroot | NIKGT4 | 42 | [41 empty] | S | S | S
Lisahally | NILPS | 18 | [12 empty] | S | S
Moyle | MOYLE | 450 | [26 empty] | S | S | S | S | [5 empty] | S | S | S
Powerhouse Generation | NIPH1 | 34

## SONI Outages
Upcoming Outages including STMOs and Annual Outages
Station | Unit | NPR | Start Date | End Date | Value | Duration
Kilroot | NIK1 | 256 | 2021-12-23 13:30 | 2022-01-08 21:00 | 195 | 16.29
Kilroot | NIK2 | 258 | 2021-12-31 22:00 | 2022-01-04 10:00 | 195 | 3.5
Ballylumford | NIB31 | 249 | 2022-01-03 12:30 | 2022-01-04 20:30 | F | 1.33
Kilroot | NIKGT4 | 42 | 2022-01-03 17:00 | 2022-01-05 17:30 | F | 2
Kilroot | NIK2 | 258 | 2022-01-04 10:00 | 2022-01-09 22:30 | F | 5.5
Kilroot | NIK1 | 256 | 2022-01-08 21:00 | 2022-01-25 11:00 | F | 16.58
Kilroot | NIK2 | 258 | 2022-01-09 22:00 | 2022-01-10 09:30 | 195 | 0.46
Kilroot | NIK2 | 258 | 2022-01-10 09:30 | 2022-01-11 18:00 | 140 | 1.33
Coolkeeragh | NIC30 | 408 | 2022-01-10 12:00 | 2022-01-10 15:30 | F | 0.12
Kilroot | NIK2 | 258 | 2022-01-11 18:00 | 2022-01-12 17:00 | 195 | 0.92
Kilroot | NIKGT4 | 42 | 2022-01-12 08:00 | 2022-01-13 11:00 | F | 1.08
Kilroot | NIK2 | 258 | 2022-01-12 17:00 | 2022-01-13 01:30 | 140 | 0.33
Kilroot | NIK2 | 258 | 2022-01-13 01:00 | 2022-02-04 13:00 | 175 | 22.5
Coolkeeragh | NICGT8 | 53 | 2022-01-17 07:30 | 2022-01-17 11:30 | F | 0.17
Ballylumford | NIBGT1 | 58 | 2022-01-19 07:00 | 2022-01-19 13:00 | 29 | 0.25
iPower | NIAGU | 74 | 2022-01-19 14:00 | 2022-02-10 16:00 | 45 | 22.08
Coolkeeragh | NICGT8 | 53 | 2022-01-20 10:00 | 2022-01-20 14:30 | 26 | 0.17
Kilroot | NIK1 | 256 | 2022-01-25 11:00 | 2022-01-31 13:00 | 195 | 6.08
Kilroot | NIKGT3 | 42 | 2022-01-26 06:00 | 2022-01-26 19:00 | S | 0.5
Coolkeeragh | NICGT8 | 53 | 2022-01-26 10:00 | 2022-01-26 15:30 | 26 | 0.21
Ballylumford | NIB10 | 94 | 2022-01-27 03:00 | 2022-01-27 13:30 | F | 0.42
Kilroot | NIKGT4 | 42 | 2022-01-27 06:00 | 2022-01-27 16:30 | S | 0.42
Ballylumford | NIB32 | 249 | 2022-01-27 10:00 | 2022-01-27 11:30 | F | 0.04
Ballylumford | NIB32 | 249 | 2022-01-29 07:00 | 2022-01-29 21:30 | S | 0.58
Kilroot | NIK1 | 256 | 2022-01-31 01:00 | 2022-01-31 11:00 | 140 | 0.42
Ballylumford | NIB32 | 249 | 2022-01-31 03:00 | 2022-01-31 17:30 | F | 0.58
Kilroot | NIKGT3 | 42 | 2022-01-31 06:00 | 2022-02-02 18:30 | S | 2.5
Kilroot | NIK1 | 256 | 2022-01-31 10:00 | 2022-02-09 03:30 | 175 | 8.71
Kilroot | NIKGT3 | 42 | 2022-02-02 18:00 | 2022-02-07 06:00 | F | 4.5
Contour Global | NICGA | 12.08 | 2022-02-02 18:00 | 2022-02-02 20:00 | F | 0.08
Kilroot | NIKGT4 | 42 | 2022-02-03 06:00 | 2022-02-05 13:00 | S | 2.25
Kilroot | NIK2 | 258 | 2022-02-04 13:30 | 2022-02-04 20:30 | 122 | 0.25
Contour Global | NICGA | 12.08 | 2022-02-04 19:30 | 2022-02-04 22:00 | 9 | 0.08
Kilroot | NIK2 | 258 | 2022-02-04 20:00 | 2022-02-13 23:30 | 175 | 9.12
Coolkeeragh | NIC30 | 408 | 2022-02-04 22:00 | 2022-02-05 21:00 | F | 0.92
Kilroot | NIKGT4 | 42 | 2022-02-07 06:00 | 2022-02-08 14:00 | S | 1.33
Kilroot | NIKGT3 | 42 | 2022-02-07 06:00 | 2022-02-08 18:30 | S | 1.5
Kilroot | NIKGT3 | 42 | 2022-02-08 18:00 | 2022-02-10 14:00 | F | 1.83
Kilroot | NIK1 | 256 | 2022-02-09 03:00 | 2022-02-11 18:30 | 122 | 2.62
iPower | NIAGU | 74 | 2022-02-10 16:00 | 2022-02-10 18:00 | 40 | 0.08
iPower | NIAGU | 74 | 2022-02-10 18:00 | 2022-02-14 15:00 | 45 | 3.83
Ballylumford | NIBGT1 | 58 | 2022-02-11 06:00 | 2022-02-13 22:30 | F | 2.67
Ballylumford | NIBGT2 | 58 | 2022-02-11 06:00 | 2022-02-13 22:30 | F | 2.67
Kilroot | NIK1 | 256 | 2022-02-11 20:00 | 2022-02-14 | F | 2.17
Ballylumford | NIB10 | 94 | 2022-02-13 14:00 | 2022-02-15 01:30 | F | 1.46
Kilroot | NIK2 | 258 | 2022-02-13 23:00 | 2022-02-14 04:30 | 93 | 0.21
Kilroot | NIK2 | 258 | 2022-02-14 04:00 | 2022-02-22 09:30 | F | 8.21
Kilroot | NIK1 | 256 | 2022-02-14 08:30 | 2022-05-18 23:00 | F | 93.58
iPower | NIAGU | 74 | 2022-02-14 14:30 | 2022-02-14 18:00 | 48 | 0.12
iPower | NIAGU | 74 | 2022-02-14 18:00 | 2022-02-19 13:00 | 50 | 4.75
Ballylumford | NIB31 | 249 | 2022-02-16 19:00 | 2022-02-19 20:00 | S | 3
Ballylumford | NIB32 | 249 | 2022-02-17 | 2022-02-17 01:00 | 161 | 0
Kilroot | NIK1 | 256 | 2022-02-18 23:00 | 2022-02-19 16:00 | 122 | 0.67
iPower | NIAGU | 74 | 2022-02-19 12:30 | 2022-03-10 18:30 | 48 | 19.25
Kilroot | NIK1 | 256 | 2022-02-19 15:30 | 2022-02-21 16:30 | 175 | 2
Kilroot | NIKGT3 | 42 | 2022-02-20 16:30 | 2022-03-08 18:00 | F | 16.04
Contour Global | NICGA | 12.08 | 2022-02-21 13:00 | 2022-03-10 14:30 | 9 | 17.04
Kilroot | NIK1 | 256 | 2022-02-21 17:00 | 2022-03-01 00:30 | F | 7.29
Kilroot | NIK2 | 258 | 2022-02-22 09:00 | 2022-03-01 00:30 | 175 | 6.62
Kilroot | NIK2 | 258 | 2022-03-01 | 2022-03-05 15:30 | 110 | 4.62
Kilroot | NIKGT2 | 29 | 2022-03-01 09:30 | 2022-03-09 20:30 | F | 8.42
Kilroot | NIKGT1 | 29 | 2022-03-01 09:30 | 2022-03-02 16:30 | F | 1.25
Kilroot | NIK1 | 256 | 2022-03-04 23:30 | 2022-03-05 07:30 | 110 | 0.33
Kilroot | NIK1 | 256 | 2022-03-06 09:00 | 2022-03-06 13:30 | 110 | 0.17
Kilroot | NIK2 | 258 | 2022-03-10 23:00 | 2022-03-11 07:30 | 110 | 0.33
Kilroot | NIK1 | 256 | 2022-03-10 23:00 | 2022-03-11 07:30 | 110 | 0.33
Moyle | MOYLE | 450 | 2022-03-11 10:00 | 2022-03-11 15:30 | S | 0.21
Kilroot | NIK1 | 256 | 2022-03-13 23:00 | 2022-03-14 07:30 | 110 | 0.33
Kilroot | NIK1 | 256 | 2022-03-16 | 2022-03-16 07:30 | 110 | 0.29
Kilroot | NIK1 | 256 | 2022-03-17 23:00 | 2022-03-18 07:00 | 110 | 0.33
Lisahally | NILPS | 17.6 | 2022-03-19 08:00 | 2022-04-04 08:30 | S | 16
Kilroot | NIK1 | 256 | 2022-03-20 21:00 | 2022-03-22 06:00 | F | 1.33
Kilroot | NIK2 | 258 | 2022-03-21 15:00 | 2022-03-24 00:30 | 93 | 2.38
Kilroot | NIK1 | 256 | 2022-03-22 05:30 | 2022-03-23 20:30 | F | 1.58
Ballylumford | NIBGT1 | 58 | 2022-03-23 07:00 | 2022-03-23 17:30 | 29 | 0.42
Kilroot | NIKGT3 | 42 | 2022-03-23 08:30 | 2022-03-29 12:30 | F | 6.17
Kilroot | NIKGT4 | 42 | 2022-03-24 06:00 | 2022-03-24 13:00 | F | 0.25
Kilroot | NIK2 | 258 | 2022-03-30 00:30 | 2022-04-13 18:00 | F | 14.71
Kilroot | NIKGT2 | 29 | 2022-03-30 06:00 | 2022-04-11 20:00 | S | 12.58
Ballylumford | NIB31 | 249 | 2022-03-30 23:00 | 2022-03-31 05:30 | F | 0.25
Kilroot | NIK1 | 256 | 2022-03-30 23:00 | 2022-03-31 07:30 | 110 | 0.33
Kilroot | NIKGT1 | 29 | 2022-04-04 06:00 | 2022-04-04 18:30 | S | 0.5
Kilroot | NIKGT1 | 29 | 2022-04-09 06:00 | 2022-04-09 18:30 | S | 0.5
Kilroot | NIKGT4 | 42 | 2022-04-09 09:30 | 2022-04-12 19:00 | F | 3.38
Kilroot | NIKGT2 | 29 | 2022-04-11 20:00 | 2022-04-13 18:00 | F | 1.92
Ballylumford | NIB31 | 249 | 2022-04-14 22:00 | 2022-04-15 02:00 | F | 0.17
Kilroot | NIKGT3 | 42 | 2022-04-15 10:00 | 2022-04-15 12:00 | S | 0.08
Coolkeeragh | NICGT8 | 53 | 2022-04-20 09:00 | 2022-04-20 16:00 | 26 | 0.25
Coolkeeragh | NICGT8 | 53 | 2022-04-21 09:00 | 2022-04-21 16:00 | 26 | 0.25
Ballylumford | NIB31 | 249 | 2022-04-21 20:00 | 2022-04-24 20:00 | S | 3
Coolkeeragh | NICGT8 | 53 | 2022-04-22 09:00 | 2022-04-22 16:00 | S | 0.25
Coolkeeragh | NICGT8 | 53 | 2022-04-25 | 2022-04-30 22:00 | S | 5.92
Kilroot | NIKGT4 | 42 | 2022-04-28 | 2022-04-28 06:00 | F | 0.25
Kilroot | NIKGT3 | 42 | 2022-04-28 | 2022-04-28 06:00 | F | 0.25
Kilroot | NIK2 | 258 | 2022-04-29 | 2022-06-28 | S | 60
Coolkeeragh | NICGT8 | 53 | 2022-04-30 18:30 | 2022-05-07 | 26 | 6.21
Ballylumford | NIBGT1 | 58 | 2022-05-01 | 2022-06-30 | S | 60
Ballylumford | NIBGT2 | 58 | 2022-05-01 07:00 | 2022-05-01 19:30 | 29 | 0.5
Ballylumford | NIBGT2 | 58 | 2022-05-02 07:00 | 2022-05-02 19:30 | 29 | 0.5
Moyle | MOYLE | 450 | 2022-05-13 22:00 | 2022-05-14 22:00 | S | 1
Moyle | MOYLE | 450 | 2022-05-14 22:00 | 2022-06-30 22:00 | 250 | 47
Moyle | MOYLE | 450 | 2022-06-30 22:00 | 2022-07-22 22:00 | S | 22
Coolkeeragh | NIC30 | 408 | 2022-07-02 | 2022-07-04 | S | 2
Ballylumford | NIB10 | 94 | 2022-07-17 19:00 | 2022-07-20 19:00 | S | 3
Ballylumford | NIB32 | 249 | 2022-07-21 19:00 | 2022-07-24 19:00 | S | 3
Moyle | MOYLE | 450 | 2022-07-22 22:00 | 2022-08-27 22:00 | 250 | 36
Kilroot | NIK1 | 256 | 2022-07-25 | 2022-09-23 | S | 60
Moyle | MOYLE | 450 | 2022-08-27 22:00 | 2022-09-16 22:30 | S | 20
Ballylumford | NIBGT2 | 58 | 2022-09-05 | 2022-09-12 | S | 7
Coolkeeragh | NIC30 | 408 | 2022-09-24 | 2022-10-04 | S | 10
Ballylumford | NIB31 | 249 | 2022-10-08 | 2022-10-22 | 161 | 14
Ballylumford | NIB32 | 249 | 2022-10-08 | 2022-10-22 | 161 | 14
Kilroot | NIKGT4 | 42 | 2022-10-10 | 2022-10-31 | S | 21
Kilroot | NIKGT3 | 42 | 2022-10-10 | 2022-10-31 | S | 21
Kilroot | NIKGT1 | 29 | 2022-10-15 | 2022-10-16 23:30 | S | 1.96
Kilroot | NIKGT2 | 29 | 2022-10-15 | 2022-10-17 | S | 2
Coolkeeragh | NIC30 | 408 | 2022-11-19 | 2022-11-20 | S | 1
|  |  | Scheduled Outage | S
|  |  | Forced Outage | F
|  |  | Unit partially available | 10

## Outage Plan All Island
2022 GENERATION OUTAGE PLAN (All Island)
|  | Month | Jan '2022 | [5 empty] | Feb '2022 |  |  |  | Mar '2022 |  |  |  | Apr '2022 |  |  |  | May '2022 |  |  |  |  | Jun '2022 |  |  |  | Jul '2022 |  |  |  | Aug '2022 |  |  |  |  | Sep '2022 |  |  |  | Oct '2022 |  |  |  |  | Nov '2022 |  |  |  | Dec '2022
|  | Week | 52 '2021 | 1 '2022 | 2 '2022 | 3 '2022 | 4 '2022 | 5 '2022 | 6 '2022 | 7 '2022 | 8 '2022 | 9 '2022 | 10 '2022 | 11 '2022 | 12 '2022 | 13 '2022 | 14 '2022 | 15 '2022 | 16 '2022 | 17 '2022 | 18 '2022 | 19 '2022 | 20 '2022 | 21 '2022 | 22 '2022 | 23 '2022 | 24 '2022 | 25 '2022 | 26 '2022 | 27 '2022 | 28 '2022 | 29 '2022 | 30 '2022 | 31 '2022 | 32 '2022 | 33 '2022 | 34 '2022 | 35 '2022 | 36 '2022 | 37 '2022 | 38 '2022 | 39 '2022 | 40 '2022 | 41 '2022 | 42 '2022 | 43 '2022 | 44 '2022 | 45 '2022 | 46 '2022 | 47 '2022 | 48 '2022 | 49 '2022 | 50 '2022 | 51 '2022 | 52 '2022
Station | Unit | NPR
AC Automation | NIACA | 8
Activation Energy | NIAEA | 9
Aghada | AD2 | 449 |  | F | [17 empty] | S | [15 empty] | S | S | S | S | [5 empty] | S
Aghada | AT1 | 90
Aghada | AT2 | 90
Aghada | AT4 | 90
Ardnacrusha | AA1 | 21 | [17 empty] | S
Ardnacrusha | AA2 | 22 | [24 empty] | S
Ardnacrusha | AA3 | 19 | [36 empty] | S
Ardnacrusha | AA4 | 24 | [8 empty] | S |  |  |  | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Ballylumford | NIB10 | 94
Ballylumford | NIB31 | 249
Ballylumford | NIB32 | 249
Ballylumford | NIBGT1 | 58 | [18 empty] | S | S | S | S | S | S | S | S
Ballylumford | NIBGT2 | 58 | [36 empty] | S
Beenanaspuck Tobertoreen | XT2 | 11
Contour Global | NICG2 | 3
Contour Global | NICGA | 12
Coolkeeragh | NIC30 | 408 | [39 empty] | S
Coolkeeragh | NICGT8 | 53 | [17 empty] | S
DAE Virtual Power Plant | DP1 | 19
DAE Virtual Power Plant | DP2 | 26
Dublin Bay | DB1 | 405 | [13 empty] | F |  |  | F | F | F | [17 empty] | S | S
Dublin Waste To Energy | DW1 | 62 | [22 empty] | S
Edenderry | ED1 | 118 | [27 empty] | S | S | S | S | S | S | [19 empty] | S
Edenderry | ED3 | 58 |  |  |  |  | F
Edenderry | ED5 | 58
Electric Ireland | EI1 | 20
Empower | NIEMP | 3
Endeco Technologies | EC1 | 47
Endeco Technologies | EC2 | 11
Endeco Technologies | EC5 | 15
Endeco Technologies | NIECA | 13
Energy Trading | ET1 | 13
Energy Trading | NIETB | 9
Energy Trading | NIETD | 5
Energy Trading | NIETR | 19
Enernoc | AE1 | 95
Enernoc | AE2 | 12
Enernoc | AE3 | 14
Enernoc | AE4 | 15
Enernoc | AE5 | 15
Enernoc | EN1 | 15
Enernoc | EN2 | 16
Enernoc | EN3 | 16
Enernoc | EN4 | 16
Enernoc | EN5 | 6
Enernoc | EN6 | 11
Enernoc | EN8 | 21
Enernoc | EN9 | 16
Erne | ER1 | 10 | [14 empty] | S
Erne | ER2 | 10 | F | F | F | [16 empty] | S
Erne | ER3 | 22 | [24 empty] | S
Erne | ER4 | 22 | [36 empty] | S
EWIC | EW1 | 500 | [11 empty] | S | S | S | S | S | S | S
Gardnershill | GP1 | 8
Great Island | GI4 | 461 | [9 empty] | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | S | S | S | S | S | S | S
Huntstown | HN2 | 400
Huntstown | HNC | 342 | [9 empty] | S | S
Indaver | IW1 | 17 | [12 empty] | S | S | S
iPower | NIAGU | 74
Kelwin | KZ4 | 27
Kilroot | NIK1 | 256 |  |  | F | F |  |  |  | F | F | F | F | F | F | F | F | F | F | F | F | F | [10 empty] | S | S | S | S | S | S | S | S | S
Kilroot | NIK2 | 258 |  | F | [5 empty] | F | [5 empty] | F | F |  |  |  | S | S | S | S | S | S | S | S
Kilroot | NIKGT1 | 29
Kilroot | NIKGT2 | 29 | [9 empty] | F |  |  |  | S | S
Kilroot | NIKGT3 | 42 | [5 empty] | F |  |  | F | F |  |  | F | [28 empty] | S | S | S
Kilroot | NIKGT4 | 42 | [41 empty] | S | S | S
Knockacummer | KC1 | 100
Lee | LE1 | 15 | [18 empty] | S | S
Lee | LE2 | 4 | [12 empty] | S | S | S | S | F | F | S | S
Lee | LE3 | 8 | [21 empty] | S | S
Liffey | LI1 | 15 | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | [6 empty] | S
Liffey | LI2 | 15 | F | F | F | [21 empty] | S
Liffey | LI4 | 4 | [26 empty] | S
Liffey | LI5 | 4 | [28 empty] | S
Lisahally | NILPS | 18 | [12 empty] | S | S
Lumcloon | LU1 | 50
Lumcloon | LU2 | 50
Moneypoint | MP1 | 285 | [23 empty] | S | S | F
Moneypoint | MP2 | 285 | [14 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Moneypoint | MP3 | 285 | [39 empty] | S | S | S
Moyle | MOYLE | 450 | [26 empty] | S | S | S | S | [5 empty] | S | S | S
Poolbeg | PB4 | 154 | [42 empty] | S
Poolbeg | PB5 | 146
Poolbeg | PB6 | 168 | [21 empty] | S | S
Powerhouse Generation | NIPH1 | 34
Powerhouse Generation | PG1 | 10
Rhode | RP1 | 52
Rhode | RP2 | 52
Seal Rock | SK3 | 85
Seal Rock | SK4 | 85
Seecon | SO1 | 105
Shannonbridge | SI1 | 50
Shannonbridge | SI2 | 50
Tarbert | TB1 | 54 | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F
Tarbert | TB2 | 54 | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F
Tarbert | TB3 | 241 | F | [21 empty] | F | F | F | F | F | F
Tarbert | TB4 | 243 | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F
Tawnaghmore | TP1 | 52 | [33 empty] | S
Tawnaghmore | TP3 | 52 | [34 empty] | S
Turlough Hill | TH1 | 73 | [19 empty] | S | S | S | S | S | S | S
Turlough Hill | TH2 | 73 | [19 empty] | S | S | S | S | S | S | S
Turlough Hill | TH3 | 73 | [19 empty] | S | S | S | S | S | S | S
Turlough Hill | TH4 | 73 | [19 empty] | S | S | S | S | S | S | S
Tynagh | TYC | 384 | [33 empty] | S
VIOTAS | EE1 | 47
VIOTAS | EE2 | 20
VIOTAS | EE3 | 8
VIOTAS | EE4 | 9
VIOTAS | EE5 | 7
VIOTAS | EE6 | 14
VIOTAS | EE7 | 9
Viridian Energy | VE1 | 20
Viridian Energy DSU | VE2 | 13
Whitegate | WG1 | 444 | [41 empty] | S

## All Island Outages
Upcoming Outages including STMOs and Annual Outages
Station | Unit | NPR | Start Date | End Date | Value | Duration
Tarbert | TB4 | 243 | 2021-04-13 15:00 | 2023-04-01 | F | 717.33
Liffey | LI2 | 15 | 2021-05-09 17:00 | 2022-01-15 | F | 250.25
Liffey | LI1 | 15 | 2021-05-09 17:00 | 2022-05-01 | F | 356.25
Tarbert | TB2 | 54 | 2021-09-18 21:30 | 2031-01-01 | F | 3391.08
Tarbert | TB1 | 54 | 2021-11-03 17:00 | 2031-01-01 | F | 3345.25
Ardnacrusha | AA4 | 24 | 2021-12-08 20:00 | 2022-02-21 08:00 | 12 | 74.5
Erne | ER2 | 10 | 2021-12-09 10:00 | 2022-01-13 18:00 | F | 35.33
Moneypoint | MP1 | 285 | 2021-12-14 20:00 | 2022-02-20 13:30 | 265 | 67.71
Moneypoint | MP3 | 285 | 2021-12-20 17:00 | 2022-02-23 15:30 | 260 | 64.92
Moneypoint | MP2 | 285 | 2021-12-23 07:00 | 2022-02-01 11:00 | 220 | 40.17
Kilroot | NIK1 | 256 | 2021-12-23 13:30 | 2022-01-08 21:00 | 195 | 16.29
Tarbert | TB3 | 241 | 2021-12-27 21:00 | 2022-01-05 10:00 | F | 8.5
Edenderry | ED1 | 118 | 2021-12-29 22:30 | 2022-01-12 10:00 | 100 | 13.46
Kilroot | NIK2 | 258 | 2021-12-31 22:00 | 2022-01-04 10:00 | 195 | 3.5
Ballylumford | NIB31 | 249 | 2022-01-03 12:30 | 2022-01-04 20:30 | F | 1.33
Kilroot | NIKGT4 | 42 | 2022-01-03 17:00 | 2022-01-05 17:30 | F | 2
Kilroot | NIK2 | 258 | 2022-01-04 10:00 | 2022-01-09 22:30 | F | 5.5
Tynagh | TYC | 384 | 2022-01-05 09:00 | 2022-01-05 10:30 | 50 | 0.04
Poolbeg | PB5 | 146 | 2022-01-05 09:30 | 2022-01-06 12:00 | F | 1.08
Poolbeg | PB6 | 168 | 2022-01-05 09:30 | 2022-01-06 12:00 | 84 | 1.08
Tarbert | TB3 | 241 | 2022-01-05 10:00 | 2022-01-27 20:00 | 220 | 22.42
Dublin Waste To Energy | DW1 | 61.5 | 2022-01-05 10:00 | 2022-01-06 02:00 | 50 | 0.67
Tynagh | TYC | 384 | 2022-01-05 10:30 | 2022-01-05 12:30 | 194 | 0.08
Aghada | AD2 | 449 | 2022-01-05 20:00 | 2022-01-12 10:30 | F | 6.58
Dublin Waste To Energy | DW1 | 61.5 | 2022-01-06 02:00 | 2022-01-06 17:00 | 33 | 0.58
Dublin Waste To Energy | DW1 | 61.5 | 2022-01-06 17:00 | 2022-01-06 23:00 | 50 | 0.25
Lee | LE2 | 4 | 2022-01-07 01:30 | 2022-01-07 03:00 | F | 0.04
Whitegate | WG1 | 444 | 2022-01-07 02:00 | 2022-01-07 03:00 | F | 0
Huntstown | HN2 | 400 | 2022-01-07 06:00 | 2022-01-07 12:00 | F | 0.25
Dublin Waste To Energy | DW1 | 61.5 | 2022-01-08 11:00 | 2022-01-09 | 45 | 0.5
Kilroot | NIK1 | 256 | 2022-01-08 21:00 | 2022-01-25 11:00 | F | 16.58
Dublin Waste To Energy | DW1 | 61.5 | 2022-01-09 | 2022-01-09 09:00 | 28 | 0.33
Kilroot | NIK2 | 258 | 2022-01-09 22:00 | 2022-01-10 09:30 | 195 | 0.46
Kilroot | NIK2 | 258 | 2022-01-10 09:30 | 2022-01-11 18:00 | 140 | 1.33
Dublin Waste To Energy | DW1 | 61.5 | 2022-01-10 10:00 | 2022-01-10 20:00 | 50 | 0.42
Coolkeeragh | NIC30 | 408 | 2022-01-10 12:00 | 2022-01-10 15:30 | F | 0.12
Kilroot | NIK2 | 258 | 2022-01-11 18:00 | 2022-01-12 17:00 | 195 | 0.92
Kilroot | NIKGT4 | 42 | 2022-01-12 08:00 | 2022-01-13 11:00 | F | 1.08
Edenderry | ED1 | 118 | 2022-01-12 10:00 | 2022-01-13 09:30 | 105 | 0.96
Kilroot | NIK2 | 258 | 2022-01-12 17:00 | 2022-01-13 01:30 | 140 | 0.33
Kilroot | NIK2 | 258 | 2022-01-13 01:00 | 2022-02-04 13:00 | 175 | 22.5
Erne | ER1 | 10 | 2022-01-13 08:00 | 2022-01-13 18:00 | F | 0.42
Turlough Hill | TH3 | 73 | 2022-01-13 09:00 | 2022-01-13 16:00 | F | 0.25
Edenderry | ED1 | 118 | 2022-01-13 09:30 | 2022-01-17 23:00 | 108 | 4.54
Huntstown | HNC | 342 | 2022-01-14 05:30 | 2022-01-14 09:00 | 232 | 0.12
Aghada | AD2 | 449 | 2022-01-14 21:00 | 2022-01-15 13:00 | F | 0.67
Dublin Waste To Energy | DW1 | 61.5 | 2022-01-16 08:00 | 2022-01-19 07:00 | 28 | 2.92
Huntstown | HNC | 342 | 2022-01-17 06:30 | 2022-01-17 08:00 | F | 0.04
Coolkeeragh | NICGT8 | 53 | 2022-01-17 07:30 | 2022-01-17 11:30 | F | 0.17
Edenderry | ED1 | 118 | 2022-01-17 23:00 | 2022-01-19 17:00 | 105 | 1.75
Aghada | AD2 | 449 | 2022-01-18 22:00 | 2022-01-19 20:00 | F | 0.92
Ballylumford | NIBGT1 | 58 | 2022-01-19 07:00 | 2022-01-19 13:00 | 29 | 0.25
iPower | NIAGU | 74 | 2022-01-19 14:00 | 2022-02-10 16:00 | 45 | 22.08
Edenderry | ED1 | 118 | 2022-01-19 17:00 | 2022-01-20 10:00 | 108 | 0.67
Edenderry | ED1 | 118 | 2022-01-20 10:00 | 2022-01-28 23:00 | 110 | 8.5
Coolkeeragh | NICGT8 | 53 | 2022-01-20 10:00 | 2022-01-20 14:30 | 26 | 0.17
Edenderry | ED3 | 58 | 2022-01-24 09:00 | 2022-01-28 16:00 | F | 4.25
Edenderry | ED5 | 58 | 2022-01-25 08:00 | 2022-01-25 12:00 | 30 | 0.17
Kilroot | NIK1 | 256 | 2022-01-25 11:00 | 2022-01-31 13:00 | 195 | 6.08
Edenderry | ED5 | 58 | 2022-01-25 12:00 | 2022-01-25 14:00 | 40 | 0.08
Ardnacrusha | AA1 | 21 | 2022-01-25 13:30 | 2022-01-25 15:00 | F | 0.04
Kilroot | NIKGT3 | 42 | 2022-01-26 06:00 | 2022-01-26 19:00 | S | 0.5
Coolkeeragh | NICGT8 | 53 | 2022-01-26 10:00 | 2022-01-26 15:30 | 26 | 0.21
Turlough Hill | TH2 | 73 | 2022-01-26 13:00 | 2022-01-26 14:00 | F | 0
Ballylumford | NIB10 | 94 | 2022-01-27 03:00 | 2022-01-27 13:30 | F | 0.42
Kilroot | NIKGT4 | 42 | 2022-01-27 06:00 | 2022-01-27 16:30 | S | 0.42
Ballylumford | NIB32 | 249 | 2022-01-27 10:00 | 2022-01-27 11:30 | F | 0.04
Tarbert | TB3 | 241 | 2022-01-27 20:00 | 2022-01-31 02:00 | F | 3.25
Turlough Hill | TH4 | 73 | 2022-01-28 09:00 | 2022-01-28 16:00 | F | 0.25
Aghada | AT2 | 90 | 2022-01-28 23:00 | 2022-01-30 10:30 | F | 1.46
Edenderry | ED1 | 118 | 2022-01-28 23:00 | 2022-01-31 23:00 | 105 | 3
Ballylumford | NIB32 | 249 | 2022-01-29 07:00 | 2022-01-29 21:30 | S | 0.58
Whitegate | WG1 | 444 | 2022-01-29 14:00 | 2022-01-29 21:30 | F | 0.29
Tarbert | TB3 | 241 | 2022-01-30 17:00 | 2022-03-11 22:00 | 220 | 40.17
Kilroot | NIK1 | 256 | 2022-01-31 01:00 | 2022-01-31 11:00 | 140 | 0.42
Ballylumford | NIB32 | 249 | 2022-01-31 03:00 | 2022-01-31 17:30 | F | 0.58
Seal Rock | SK3 | 85 | 2022-01-31 06:00 | 2022-02-02 18:00 | S | 2.5
Kilroot | NIKGT3 | 42 | 2022-01-31 06:00 | 2022-02-02 18:30 | S | 2.5
Kilroot | NIK1 | 256 | 2022-01-31 10:00 | 2022-02-09 03:30 | 175 | 8.71
Edenderry | ED1 | 118 | 2022-01-31 23:00 | 2022-02-04 23:00 | 110 | 4
Moneypoint | MP2 | 285 | 2022-02-01 11:00 | 2022-02-07 11:00 | 99 | 6
Kilroot | NIKGT3 | 42 | 2022-02-02 18:00 | 2022-02-07 06:00 | F | 4.5
Contour Global | NICGA | 12.08 | 2022-02-02 18:00 | 2022-02-02 20:00 | F | 0.08
Kilroot | NIKGT4 | 42 | 2022-02-03 06:00 | 2022-02-05 13:00 | S | 2.25
Aghada | AT2 | 90 | 2022-02-03 08:00 | 2022-02-03 16:00 | F | 0.33
Erne | ER4 | 22.5 | 2022-02-03 09:00 | 2022-02-03 16:30 | F | 0.29
Erne | ER3 | 22.5 | 2022-02-03 09:00 | 2022-02-03 16:30 | F | 0.29
Tynagh | TYC | 384 | 2022-02-03 20:00 | 2022-02-08 06:00 | F | 4.42
Erne | ER1 | 10 | 2022-02-04 09:00 | 2022-02-04 16:30 | F | 0.29
Erne | ER2 | 10 | 2022-02-04 09:00 | 2022-02-04 16:30 | F | 0.29
Kilroot | NIK2 | 258 | 2022-02-04 13:30 | 2022-02-04 20:30 | 122 | 0.25
Contour Global | NICGA | 12.08 | 2022-02-04 19:30 | 2022-02-04 22:00 | 9 | 0.08
Kilroot | NIK2 | 258 | 2022-02-04 20:00 | 2022-02-13 23:30 | 175 | 9.12
Coolkeeragh | NIC30 | 408 | 2022-02-04 22:00 | 2022-02-05 21:00 | F | 0.92
Edenderry | ED1 | 118 | 2022-02-04 23:00 | 2022-02-14 20:30 | 102 | 9.88
Kilroot | NIKGT4 | 42 | 2022-02-07 06:00 | 2022-02-08 14:00 | S | 1.33
Kilroot | NIKGT3 | 42 | 2022-02-07 06:00 | 2022-02-08 18:30 | S | 1.5
Turlough Hill | TH2 | 73 | 2022-02-07 10:00 | 2022-02-07 15:00 | F | 0.17
Moneypoint | MP2 | 285 | 2022-02-07 11:00 | 2022-02-09 09:00 | F | 1.92
Turlough Hill | TH1 | 73 | 2022-02-08 10:00 | 2022-02-08 15:00 | F | 0.17
Kilroot | NIKGT3 | 42 | 2022-02-08 18:00 | 2022-02-10 14:00 | F | 1.83
Aghada | AD2 | 449 | 2022-02-08 19:00 | 2022-02-08 20:00 | 130 | 0
Kilroot | NIK1 | 256 | 2022-02-09 03:00 | 2022-02-11 18:30 | 122 | 2.62
Moneypoint | MP2 | 285 | 2022-02-09 09:00 | 2022-02-14 11:00 | 99 | 5.08
Turlough Hill | TH1 | 73 | 2022-02-09 23:00 | 2022-02-10 01:00 | F | 0.08
Turlough Hill | TH2 | 73 | 2022-02-09 23:00 | 2022-02-10 01:00 | F | 0.08
Turlough Hill | TH3 | 73 | 2022-02-09 23:00 | 2022-02-10 01:00 | F | 0.08
Turlough Hill | TH4 | 73 | 2022-02-09 23:00 | 2022-02-10 01:00 | F | 0.08
Turlough Hill | TH1 | 73 | 2022-02-10 09:00 | 2022-02-10 15:30 | F | 0.25
Indaver | IW1 | 17 | 2022-02-10 14:00 | 2022-02-13 05:30 | F | 2.62
iPower | NIAGU | 74 | 2022-02-10 16:00 | 2022-02-10 18:00 | 40 | 0.08
iPower | NIAGU | 74 | 2022-02-10 18:00 | 2022-02-14 15:00 | 45 | 3.83
Ballylumford | NIBGT1 | 58 | 2022-02-11 06:00 | 2022-02-13 22:30 | F | 2.67
Ballylumford | NIBGT2 | 58 | 2022-02-11 06:00 | 2022-02-13 22:30 | F | 2.67
Kilroot | NIK1 | 256 | 2022-02-11 20:00 | 2022-02-14 | F | 2.17
Ballylumford | NIB10 | 94 | 2022-02-13 14:00 | 2022-02-15 01:30 | F | 1.46
Tynagh | TYC | 384 | 2022-02-13 20:00 | 2022-02-14 20:00 | F | 1
Kilroot | NIK2 | 258 | 2022-02-13 23:00 | 2022-02-14 04:30 | 93 | 0.21
Kilroot | NIK2 | 258 | 2022-02-14 04:00 | 2022-02-22 09:30 | F | 8.21
Kilroot | NIK1 | 256 | 2022-02-14 08:30 | 2022-05-18 23:00 | F | 93.58
Moneypoint | MP2 | 285 | 2022-02-14 11:00 | 2022-02-25 14:00 | 200 | 11.08
iPower | NIAGU | 74 | 2022-02-14 14:30 | 2022-02-14 18:00 | 48 | 0.12
iPower | NIAGU | 74 | 2022-02-14 18:00 | 2022-02-19 13:00 | 50 | 4.75
Edenderry | ED1 | 118 | 2022-02-14 20:30 | 2022-02-22 18:30 | 100 | 7.92
Ardnacrusha | AA2 | 22 | 2022-02-15 17:00 | 2022-02-16 09:30 | F | 0.67
Ballylumford | NIB31 | 249 | 2022-02-16 19:00 | 2022-02-19 20:00 | S | 3
Ballylumford | NIB32 | 249 | 2022-02-17 | 2022-02-17 01:00 | 161 | 0
Kilroot | NIK1 | 256 | 2022-02-18 23:00 | 2022-02-19 16:00 | 122 | 0.67
iPower | NIAGU | 74 | 2022-02-19 12:30 | 2022-03-10 18:30 | 48 | 19.25
Kilroot | NIK1 | 256 | 2022-02-19 15:30 | 2022-02-21 16:30 | 175 | 2
Moneypoint | MP1 | 285 | 2022-02-20 13:30 | 2022-02-20 16:30 | F | 0.08
Moneypoint | MP1 | 285 | 2022-02-20 16:30 | 2022-02-23 15:30 | 265 | 2.92
Kilroot | NIKGT3 | 42 | 2022-02-20 16:30 | 2022-03-08 18:00 | F | 16.04
Ardnacrusha | AA4 | 24 | 2022-02-21 08:00 | 2022-02-25 16:00 | S | 4.33
Tawnaghmore | TP1 | 52 | 2022-02-21 09:00 | 2022-02-23 09:30 | F | 2
Contour Global | NICGA | 12.08 | 2022-02-21 13:00 | 2022-03-10 14:30 | 9 | 17.04
Kilroot | NIK1 | 256 | 2022-02-21 17:00 | 2022-03-01 00:30 | F | 7.29
Dublin Waste To Energy | DW1 | 61.5 | 2022-02-22 04:00 | 2022-02-24 19:00 | 28 | 2.58
Kilroot | NIK2 | 258 | 2022-02-22 09:00 | 2022-03-01 00:30 | 175 | 6.62
Edenderry | ED1 | 118 | 2022-02-22 18:30 | 2022-02-23 18:00 | F | 0.96
Whitegate | WG1 | 444 | 2022-02-23 07:00 | 2022-02-23 10:30 | F | 0.12
Turlough Hill | TH1 | 73 | 2022-02-23 09:00 | 2022-02-23 12:00 | F | 0.08
Tawnaghmore | TP3 | 52 | 2022-02-23 09:00 | 2022-02-24 17:00 | F | 1.33
Moneypoint | MP3 | 285 | 2022-02-23 15:30 | 2022-02-24 15:30 | 175 | 1
Moneypoint | MP1 | 285 | 2022-02-23 15:30 | 2022-02-24 15:30 | 175 | 1
Edenderry | ED1 | 118 | 2022-02-23 18:00 | 2022-02-23 20:00 | 60 | 0.08
Edenderry | ED1 | 118 | 2022-02-23 20:00 | 2022-02-24 10:30 | 96 | 0.58
Edenderry | ED1 | 118 | 2022-02-24 10:30 | 2022-03-05 22:00 | 94 | 9.46
Moneypoint | MP1 | 285 | 2022-02-24 15:30 | 2022-03-22 09:30 | 250 | 25.75
Moneypoint | MP3 | 285 | 2022-02-24 15:30 | 2022-03-16 | 260 | 19.33
Moneypoint | MP2 | 285 | 2022-02-25 14:00 | 2022-03-03 22:00 | F | 6.33
Ardnacrusha | AA4 | 24 | 2022-02-25 16:00 | 2022-03-15 09:00 | 12 | 17.67
Whitegate | WG1 | 444 | 2022-02-25 16:30 | 2022-03-04 06:00 | F | 6.54
Aghada | AD2 | 449 | 2022-02-26 01:00 | 2022-02-26 12:30 | F | 0.46
Huntstown | HNC | 342 | 2022-03-01 | 2022-03-11 | S | 10
Kilroot | NIK2 | 258 | 2022-03-01 | 2022-03-05 15:30 | 110 | 4.62
Kilroot | NIKGT2 | 29 | 2022-03-01 09:30 | 2022-03-09 20:30 | F | 8.42
Kilroot | NIKGT1 | 29 | 2022-03-01 09:30 | 2022-03-02 16:30 | F | 1.25
Great Island | GI4 | 461 | 2022-03-01 13:00 | 2022-06-21 | F | 111.42
Moneypoint | MP2 | 285 | 2022-03-03 22:00 | 2022-03-21 12:30 | 200 | 17.58
Kilroot | NIK1 | 256 | 2022-03-04 23:30 | 2022-03-05 07:30 | 110 | 0.33
Edenderry | ED1 | 118 | 2022-03-05 22:00 | 2022-03-05 23:30 | F | 0.04
Edenderry | ED1 | 118 | 2022-03-05 23:30 | 2022-03-09 23:00 | 94 | 3.96
Kilroot | NIK1 | 256 | 2022-03-06 09:00 | 2022-03-06 13:30 | 110 | 0.17
Aghada | AD2 | 449 | 2022-03-06 22:00 | 2022-03-08 16:00 | F | 1.75
Turlough Hill | TH4 | 73 | 2022-03-07 10:00 | 2022-03-07 15:00 | S | 0.17
Turlough Hill | TH2 | 73 | 2022-03-08 10:00 | 2022-03-08 15:00 | S | 0.17
Edenderry | ED1 | 118 | 2022-03-09 23:00 | 2022-03-11 08:00 | F | 1.33
Aghada | AD2 | 449 | 2022-03-10 10:30 | 2022-03-11 16:00 | F | 1.21
Kilroot | NIK2 | 258 | 2022-03-10 23:00 | 2022-03-11 07:30 | 110 | 0.33
Kilroot | NIK1 | 256 | 2022-03-10 23:00 | 2022-03-11 07:30 | 110 | 0.33
Huntstown | HNC | 342 | 2022-03-11 | 2022-03-11 11:30 | F | 0.46
Edenderry | ED1 | 118 | 2022-03-11 08:00 | 2022-04-14 17:00 | 84 | 34.33
Liffey | LI5 | 4 | 2022-03-11 10:00 | 2022-03-11 14:00 | F | 0.17
Moyle | MOYLE | 450 | 2022-03-11 10:00 | 2022-03-11 15:30 | S | 0.21
Tarbert | TB3 | 241 | 2022-03-11 22:00 | 2022-03-12 17:00 | F | 0.75
Tarbert | TB3 | 241 | 2022-03-12 17:00 | 2022-03-25 20:00 | 220 | 13.08
Kilroot | NIK1 | 256 | 2022-03-13 23:00 | 2022-03-14 07:30 | 110 | 0.33
EWIC | EW1 | 500 | 2022-03-14 09:00 | 2022-03-14 17:00 | S | 0.33
EWIC | EW1 | 500 | 2022-03-14 17:00 | 2022-05-03 23:00 | S | 50.25
Aghada | AD2 | 449 | 2022-03-15 00:30 | 2022-03-17 01:30 | F | 2
Ardnacrusha | AA4 | 24 | 2022-03-15 09:00 | 2022-03-15 16:00 | F | 0.25
Turlough Hill | TH2 | 73 | 2022-03-15 11:00 | 2022-03-15 15:00 | F | 0.17
Ardnacrusha | AA4 | 24 | 2022-03-15 16:00 | 2022-03-21 08:00 | 12 | 5.67
Moneypoint | MP3 | 285 | 2022-03-16 | 2022-09-23 22:00 | 210 | 191.92
Kilroot | NIK1 | 256 | 2022-03-16 | 2022-03-16 07:30 | 110 | 0.29
Turlough Hill | TH3 | 73 | 2022-03-17 15:30 | 2022-03-18 11:00 | F | 0.79
Kilroot | NIK1 | 256 | 2022-03-17 23:00 | 2022-03-18 07:00 | 110 | 0.33
Lisahally | NILPS | 17.6 | 2022-03-19 08:00 | 2022-04-04 08:30 | S | 16
Indaver | IW1 | 17 | 2022-03-20 | 2022-04-14 | S | 25
Kilroot | NIK1 | 256 | 2022-03-20 21:00 | 2022-03-22 06:00 | F | 1.33
Seal Rock | SK4 | 85 | 2022-03-21 06:00 | 2022-03-23 18:00 | F | 2.5
Ardnacrusha | AA4 | 24 | 2022-03-21 08:00 | 2022-12-21 20:00 | S | 275.5
Moneypoint | MP2 | 285 | 2022-03-21 12:30 | 2022-03-24 12:30 | F | 3
Kilroot | NIK2 | 258 | 2022-03-21 15:00 | 2022-03-24 00:30 | 93 | 2.38
Kilroot | NIK1 | 256 | 2022-03-22 05:30 | 2022-03-23 20:30 | F | 1.58
Moneypoint | MP1 | 285 | 2022-03-22 09:30 | 2022-03-23 10:30 | F | 1
Ballylumford | NIBGT1 | 58 | 2022-03-23 07:00 | 2022-03-23 17:30 | 29 | 0.42
Rhode | RP2 | 52 | 2022-03-23 07:30 | 2022-03-23 12:30 | F | 0.17
Kilroot | NIKGT3 | 42 | 2022-03-23 08:30 | 2022-03-29 12:30 | F | 6.17
Moneypoint | MP1 | 285 | 2022-03-23 10:30 | 2022-04-08 09:00 | 250 | 15.92
Kilroot | NIKGT4 | 42 | 2022-03-24 06:00 | 2022-03-24 13:00 | F | 0.25
Rhode | RP2 | 52 | 2022-03-24 07:00 | 2022-03-24 09:30 | F | 0.08
Lee | LE2 | 4 | 2022-03-24 08:00 | 2022-04-15 20:00 | S | 22.5
Moneypoint | MP2 | 285 | 2022-03-24 12:30 | 2022-04-02 21:00 | 200 | 9.33
Tarbert | TB3 | 241 | 2022-03-25 20:00 | 2022-03-27 22:30 | F | 2.08
Dublin Bay | DB1 | 405 | 2022-03-26 20:00 | 2022-04-02 20:00 | F | 7
Tarbert | TB3 | 241 | 2022-03-27 22:30 | 2022-03-28 21:30 | 220 | 0.92
Tarbert | TB3 | 241 | 2022-03-28 21:30 | 2022-03-29 12:00 | F | 0.58
Tarbert | TB3 | 241 | 2022-03-29 12:00 | 2022-04-08 20:00 | 220 | 10.33
Kilroot | NIK2 | 258 | 2022-03-30 00:30 | 2022-04-13 18:00 | F | 14.71
Kilroot | NIKGT2 | 29 | 2022-03-30 06:00 | 2022-04-11 20:00 | S | 12.58
Ballylumford | NIB31 | 249 | 2022-03-30 23:00 | 2022-03-31 05:30 | F | 0.25
Kilroot | NIK1 | 256 | 2022-03-30 23:00 | 2022-03-31 07:30 | 110 | 0.33
Turlough Hill | TH3 | 73 | 2022-03-31 10:00 | 2022-03-31 15:00 | F | 0.17
Moneypoint | MP2 | 285 | 2022-04-02 21:00 | 2022-09-04 22:00 | S | 155
Kilroot | NIKGT1 | 29 | 2022-04-04 06:00 | 2022-04-04 18:30 | S | 0.5
Erne | ER1 | 10 | 2022-04-04 08:00 | 2022-04-08 20:00 | S | 4.5
Aghada | AT1 | 90 | 2022-04-06 08:30 | 2022-04-06 13:00 | F | 0.17
Moneypoint | MP1 | 285 | 2022-04-08 09:00 | 2022-04-15 23:30 | F | 7.58
Turlough Hill | TH4 | 73 | 2022-04-08 09:30 | 2022-04-08 14:30 | F | 0.17
Tarbert | TB3 | 241 | 2022-04-08 20:00 | 2022-04-11 17:00 | F | 2.83
Kilroot | NIKGT1 | 29 | 2022-04-09 06:00 | 2022-04-09 18:30 | S | 0.5
Kilroot | NIKGT4 | 42 | 2022-04-09 09:30 | 2022-04-12 19:00 | F | 3.38
Tarbert | TB3 | 241 | 2022-04-11 17:00 | 2022-04-12 03:30 | 220 | 0.42
Kilroot | NIKGT2 | 29 | 2022-04-11 20:00 | 2022-04-13 18:00 | F | 1.92
Tarbert | TB3 | 241 | 2022-04-12 03:30 | 2022-04-12 12:30 | F | 0.33
Tynagh | TYC | 384 | 2022-04-12 06:30 | 2022-04-12 11:30 | F | 0.17
Tarbert | TB3 | 241 | 2022-04-12 12:30 | 2022-05-28 07:00 | 220 | 45.75
Edenderry | ED1 | 118 | 2022-04-14 17:00 | 2022-04-20 08:00 | S | 5.58
Ballylumford | NIB31 | 249 | 2022-04-14 22:00 | 2022-04-15 02:00 | F | 0.17
Kilroot | NIKGT3 | 42 | 2022-04-15 10:00 | 2022-04-15 12:00 | S | 0.08
Lee | LE2 | 4 | 2022-04-15 20:00 | 2022-05-03 08:00 | F | 17.5
Moneypoint | MP1 | 285 | 2022-04-15 23:30 | 2022-04-19 04:30 | 250 | 3.17
Moneypoint | MP1 | 285 | 2022-04-19 04:30 | 2022-04-20 22:00 | F | 1.71
Dublin Bay | DB1 | 405 | 2022-04-20 04:30 | 2022-05-09 15:00 | F | 19.42
Edenderry | ED1 | 118 | 2022-04-20 08:00 | 2022-05-06 | 100 | 15.67
Coolkeeragh | NICGT8 | 53 | 2022-04-20 09:00 | 2022-04-20 16:00 | 26 | 0.25
Moneypoint | MP1 | 285 | 2022-04-20 22:00 | 2022-05-04 22:00 | 240 | 14
Turlough Hill | TH4 | 73 | 2022-04-21 09:00 | 2022-04-21 15:00 | F | 0.25
Coolkeeragh | NICGT8 | 53 | 2022-04-21 09:00 | 2022-04-21 16:00 | 26 | 0.25
Ballylumford | NIB31 | 249 | 2022-04-21 20:00 | 2022-04-24 20:00 | S | 3
Huntstown | HNC | 342 | 2022-04-21 23:00 | 2022-04-22 16:00 | 220 | 0.67
Coolkeeragh | NICGT8 | 53 | 2022-04-22 09:00 | 2022-04-22 16:00 | S | 0.25
Coolkeeragh | NICGT8 | 53 | 2022-04-25 | 2022-04-30 22:00 | S | 5.92
Ardnacrusha | AA1 | 21 | 2022-04-25 08:00 | 2022-04-29 20:00 | S | 4.5
Lee | LE3 | 8 | 2022-04-25 18:30 | 2022-04-29 15:00 | F | 3.83
Kilroot | NIKGT4 | 42 | 2022-04-28 | 2022-04-28 06:00 | F | 0.25
Kilroot | NIKGT3 | 42 | 2022-04-28 | 2022-04-28 06:00 | F | 0.25
Kilroot | NIK2 | 258 | 2022-04-29 | 2022-06-28 | S | 60
Ardnacrusha | AA1 | 21 | 2022-04-29 20:00 | 2022-05-06 20:00 | F | 7
Coolkeeragh | NICGT8 | 53 | 2022-04-30 18:30 | 2022-05-07 | 26 | 6.21
Ballylumford | NIBGT1 | 58 | 2022-05-01 | 2022-06-30 | S | 60
Ballylumford | NIBGT2 | 58 | 2022-05-01 07:00 | 2022-05-01 19:30 | 29 | 0.5
Ballylumford | NIBGT2 | 58 | 2022-05-02 07:00 | 2022-05-02 19:30 | 29 | 0.5
Lee | LE1 | 15 | 2022-05-03 08:00 | 2022-05-13 20:00 | S | 10.5
Lee | LE2 | 4 | 2022-05-03 08:00 | 2022-05-13 20:00 | S | 10.5
Aghada | AT2 | 90 | 2022-05-03 18:00 | 2022-05-05 17:30 | F | 1.96
EWIC | EW1 | 500 | 2022-05-03 23:00 | 2022-05-07 14:30 | F | 3.62
Moneypoint | MP1 | 285 | 2022-05-04 22:00 | 2022-05-07 22:00 | F | 3
Moneypoint | MP1 | 285 | 2022-05-07 22:00 | 2022-06-03 22:00 | 240 | 27
Aghada | AD2 | 449 | 2022-05-08 22:00 | 2022-05-15 22:00 | S | 7
Edenderry | ED1 | 118 | 2022-05-09 | 2022-07-01 12:00 | 94 | 53.5
Turlough Hill | TH1 | 73 | 2022-05-10 07:00 | 2022-06-27 21:00 | S | 49.58
Turlough Hill | TH2 | 73 | 2022-05-10 07:00 | 2022-06-27 21:00 | S | 49.58
Turlough Hill | TH3 | 73 | 2022-05-10 07:00 | 2022-06-27 21:00 | S | 49.58
Turlough Hill | TH4 | 73 | 2022-05-10 07:00 | 2022-06-27 21:00 | S | 49.58
Erne | ER2 | 10 | 2022-05-09 08:00 | 2022-05-13 20:00 | S | 4.5
Moneypoint | MP3 | 285 | 2022-05-09 11:00 | 2022-05-10 09:00 | F | 0.92
Ardnacrusha | AA3 | 19 | 2022-05-11 08:00 | 2022-05-11 16:00 | F | 0.33
Moyle | MOYLE | 450 | 2022-05-13 22:00 | 2022-05-14 22:00 | S | 1
Moyle | MOYLE | 450 | 2022-05-14 22:00 | 2022-06-30 22:00 | 250 | 47
Ardnacrusha | AA3 | 19 | 2022-05-18 09:00 | 2022-05-18 17:00 | S | 0.33
Tynagh | TYC | 384 | 2022-05-20 21:00 | 2022-05-22 21:00 | S | 2
Dublin Waste To Energy | DW1 | 61.5 | 2022-05-22 | 2022-06-02 | 26 | 11
Lee | LE3 | 8 | 2022-05-23 08:00 | 2022-06-03 20:00 | S | 11.5
Poolbeg | PB6 | 168 | 2022-05-23 13:00 | 2022-06-03 18:00 | S | 11.17
Tarbert | TB3 | 241 | 2022-05-28 07:00 | 2022-07-10 16:00 | F | 43.33
Dublin Waste To Energy | DW1 | 61.5 | 2022-06-02 | 2022-06-06 | S | 4
Moneypoint | MP1 | 285 | 2022-06-03 22:00 | 2022-06-23 22:00 | S | 20
Dublin Waste To Energy | DW1 | 61.5 | 2022-06-06 | 2022-06-17 | 26 | 11
Seal Rock | SK3 | 85 | 2022-06-06 06:00 | 2022-06-09 18:00 | S | 3.5
Liffey | LI2 | 15 | 2022-06-12 08:00 | 2022-06-17 17:00 | S | 5.33
Liffey | LI1 | 15 | 2022-06-12 08:00 | 2022-06-17 17:00 | S | 5.33
Ardnacrusha | AA2 | 22 | 2022-06-13 08:00 | 2022-06-20 20:00 | S | 7.5
Erne | ER3 | 22.5 | 2022-06-13 08:00 | 2022-06-17 20:00 | S | 4.5
Great Island | GI4 | 461 | 2022-06-21 | 2022-08-10 | S | 50
Moneypoint | MP1 | 285 | 2022-06-23 22:00 | 2023-01-01 | 265 | 191.08
Liffey | LI4 | 4 | 2022-06-26 08:00 | 2022-07-01 17:00 | S | 5.33
Lee | LE1 | 15 | 2022-06-27 09:00 | 2022-06-27 17:00 | S | 0.33
Lee | LE2 | 4 | 2022-06-27 09:00 | 2022-06-27 17:00 | S | 0.33
Moyle | MOYLE | 450 | 2022-06-30 22:00 | 2022-07-22 22:00 | S | 22
Edenderry | ED1 | 118 | 2022-07-01 12:00 | 2022-08-13 08:00 | S | 42.83
Coolkeeragh | NIC30 | 408 | 2022-07-02 | 2022-07-04 | S | 2
Liffey | LI5 | 4 | 2022-07-10 08:00 | 2022-07-15 17:00 | S | 5.33
Tarbert | TB3 | 241 | 2022-07-10 16:00 | 2023-01-01 | 220 | 174.33
Aghada | AT2 | 90 | 2022-07-11 | 2022-07-14 | S | 3
Aghada | AT1 | 90 | 2022-07-11 | 2022-07-14 | S | 3
Aghada | AT1 | 90 | 2022-07-14 09:00 | 2022-07-14 17:00 | S | 0.33
Aghada | AT2 | 90 | 2022-07-14 09:00 | 2022-07-14 17:00 | S | 0.33
Ballylumford | NIB10 | 94 | 2022-07-17 19:00 | 2022-07-20 19:00 | S | 3
Aghada | AT4 | 90 | 2022-07-18 | 2022-07-21 | S | 3
Ballylumford | NIB32 | 249 | 2022-07-21 19:00 | 2022-07-24 19:00 | S | 3
Moyle | MOYLE | 450 | 2022-07-22 22:00 | 2022-08-27 22:00 | 250 | 36
Kilroot | NIK1 | 256 | 2022-07-25 | 2022-09-23 | S | 60
Seal Rock | SK4 | 85 | 2022-07-25 06:00 | 2022-07-28 18:00 | S | 3.5
Erne | ER1 | 10 | 2022-08-02 09:00 | 2022-08-02 17:00 | S | 0.33
Erne | ER2 | 10 | 2022-08-02 09:00 | 2022-08-02 17:00 | S | 0.33
Tawnaghmore | TP1 | 52 | 2022-08-13 | 2022-08-21 | S | 8
Edenderry | ED1 | 118 | 2022-08-13 07:30 | 2022-10-31 07:30 | 94 | 79
Tynagh | TYC | 384 | 2022-08-14 20:00 | 2022-08-19 20:00 | S | 5
EWIC | EW1 | 500 | 2022-08-18 09:00 | 2022-08-18 23:00 | S | 0.58
Tawnaghmore | TP3 | 52 | 2022-08-20 | 2022-08-28 | S | 8
Aghada | AD2 | 449 | 2022-08-27 22:00 | 2022-09-24 06:00 | S | 27.33
Moyle | MOYLE | 450 | 2022-08-27 22:00 | 2022-09-16 22:30 | S | 20
Dublin Bay | DB1 | 405 | 2022-09-02 08:00 | 2022-09-20 18:00 | S | 18.42
Moneypoint | MP2 | 285 | 2022-09-04 22:00 | 2023-01-01 | 220 | 118.08
Ballylumford | NIBGT2 | 58 | 2022-09-05 | 2022-09-12 | S | 7
Erne | ER4 | 22.5 | 2022-09-05 08:00 | 2022-09-09 20:00 | S | 4.5
Ardnacrusha | AA3 | 19 | 2022-09-05 08:00 | 2022-09-09 20:00 | S | 4.5
Seal Rock | SK3 | 85 | 2022-09-12 18:00 | 2022-09-15 18:00 | S | 3
Seal Rock | SK4 | 85 | 2022-09-13 | 2022-09-15 12:00 | S | 2.5
Liffey | LI1 | 15 | 2022-09-14 09:00 | 2022-09-14 17:00 | S | 0.33
Liffey | LI2 | 15 | 2022-09-14 09:00 | 2022-09-14 17:00 | S | 0.33
Liffey | LI4 | 4 | 2022-09-14 09:00 | 2022-09-14 17:00 | S | 0.33
Moneypoint | MP3 | 285 | 2022-09-23 22:00 | 2022-10-13 22:00 | S | 20
Coolkeeragh | NIC30 | 408 | 2022-09-24 | 2022-10-04 | S | 10
Turlough Hill | TH2 | 73 | 2022-09-29 09:00 | 2022-09-29 17:00 | S | 0.33
Turlough Hill | TH1 | 73 | 2022-09-29 09:00 | 2022-09-29 17:00 | S | 0.33
Dublin Waste To Energy | DW1 | 61.5 | 2022-10-01 | 2022-10-05 | 26 | 4
Dublin Waste To Energy | DW1 | 61.5 | 2022-10-05 | 2022-10-07 | S | 2
Dublin Waste To Energy | DW1 | 61.5 | 2022-10-07 | 2022-10-11 | 26 | 4
Whitegate | WG1 | 444 | 2022-10-07 21:00 | 2022-10-19 21:00 | S | 12
Ballylumford | NIB31 | 249 | 2022-10-08 | 2022-10-22 | 161 | 14
Ballylumford | NIB32 | 249 | 2022-10-08 | 2022-10-22 | 161 | 14
Kilroot | NIKGT4 | 42 | 2022-10-10 | 2022-10-31 | S | 21
Kilroot | NIKGT3 | 42 | 2022-10-10 | 2022-10-31 | S | 21
Kilroot | NIKGT1 | 29 | 2022-10-15 | 2022-10-16 23:30 | S | 1.96
Kilroot | NIKGT2 | 29 | 2022-10-15 | 2022-10-17 | S | 2
Poolbeg | PB6 | 168 | 2022-10-17 12:00 | 2022-10-22 20:00 | 84 | 5.33
Poolbeg | PB4 | 154 | 2022-10-17 12:00 | 2022-10-22 20:00 | S | 5.33
Moneypoint | MP3 | 285 | 2022-10-23 22:00 | 2023-01-01 | 260 | 69.08
Seal Rock | SK3 | 85 | 2022-10-24 06:00 | 2022-10-26 18:00 | S | 2.5
Edenderry | ED5 | 58 | 2022-10-24 08:00 | 2022-10-24 18:00 | S | 0.42
Edenderry | ED3 | 58 | 2022-10-24 08:00 | 2022-10-24 18:00 | S | 0.42
Aghada | AD2 | 449 | 2022-10-31 01:00 | 2022-11-05 20:00 | S | 5.75
Coolkeeragh | NIC30 | 408 | 2022-11-19 | 2022-11-20 | S | 1
Seal Rock | SK4 | 85 | 2022-11-28 06:00 | 2022-11-30 18:00 | S | 2.5
Edenderry | ED1 | 118 | 2022-12-26 13:00 | 2023-01-02 08:00 | S | 6.75
|  |  | Scheduled Outage | S
|  |  | Forced Outage | F
|  |  | Unit partially available | 10