## Outage Plan EirGrid
2018 GENERATION OUTAGE PLAN (EIRGRID)
|  | Month | Nov '2018 |  |  |  |  | Dec '2018
|  | Week | 44 '2018 | 45 '2018 | 46 '2018 | 47 '2018 | 48 '2018 | 49 '2018 | 50 '2018 | 51 '2018 | 52 '2018 | 1 '2019
Station | Unit | NPR
Activation Energy | AE1 | 77
Activation Energy | AE2 | 8
Activation Energy | AE3 | 14
Activation Energy | AE4 | 11
Activation Energy | AE5 | 15
Activation Energy | EN6 | 9
Aghada | AD1 | 258 | F | F | F | F | F | F | F | F | F | F
Aghada | AD2 | 431
Aghada | AT1 | 90
Aghada | AT2 | 90
Aghada | AT4 | 90
Ardnacrusha | AA1 | 21
Ardnacrusha | AA2 | 22
Ardnacrusha | AA3 | 19
Ardnacrusha | AA4 | 24
DAE Virtual Power Plant | DP1 | 19
DAE Virtual Power Plant | DP2 | 20
Dublin Bay | DB1 | 405
Dublin Waste To Energy | DW1 | 62
Edenderry | ED1 | 118 | [8 empty] | S
Edenderry | ED3 | 58
Edenderry | ED5 | 58
Electric Ireland | EI1 | 20
Electricity Exchange DSU | EE1 | 39
Electricity Exchange DSU | EE2 | 17
Electricity Exchange DSU | EE3 | 7
Electricity Exchange DSU | EE4 | 9
Electricity Exchange DSU | EE5 | 7
Endeco Technologies | EC1 | 37
Endeco Technologies | EC2 | 10
Endeco Technologies | EC5 | 16
Energy Trading | ET1 | 13
Erne | ER1 | 10
Erne | ER2 | 10
Erne | ER3 | 22
Erne | ER4 | 22
EWIC | EW1 | 500
Great Island | GI4 | 461 | F | F | F | F | F | F
Huntstown | HN2 | 400
Huntstown | HNC | 342
Indaver | IW1 | 17
Lanesboro | LR4 | 91
Lee | LE1 | 15
Lee | LE2 | 4
Lee | LE3 | 8
Liffey | LI1 | 15
Liffey | LI2 | 15
Liffey | LI4 | 4
Liffey | LI5 | 4
Marina | MRC | 95 | F | F | F | F | F | F | F | F | F | F
Moneypoint | MP1 | 285 | F | F | F | F | F | F | F
Moneypoint | MP2 | 285 | F | F | F | F | F | F
Moneypoint | MP3 | 285 | F | F | F | F | F | F | F
North Wall | NW5 | 104
Poolbeg | PB4 | 154
Poolbeg | PB5 | 146
Poolbeg | PB6 | 168
Powerhouse Generation | PG1 | 11
Rhode | RP1 | 52
Rhode | RP2 | 52
Seal Rock | SK3 | 85
Seal Rock | SK4 | 85
Tarbert | TB1 | 54
Tarbert | TB2 | 54
Tarbert | TB3 | 241
Tarbert | TB4 | 243
Tawnaghmore | TP1 | 52
Tawnaghmore | TP3 | 52
Turlough Hill | TH1 | 73
Turlough Hill | TH2 | 73
Turlough Hill | TH3 | 73
Turlough Hill | TH4 | 73
Tynagh | TYC | 384
Viridian Energy | VE1 | 19
Viridian Energy DSU | VE2 | 6
West Offaly | WO4 | 137
Whitegate | WG1 | 444

## EirGrid Outages
Upcoming Outages including STMOs and Annual Outages
Station | Unit | NPR | Start Date | End Date | Value | Duration
Moneypoint | MP3 | 285 | 2018-06-11 | 2018-12-16 | F | 188
Marina | MRC | 95 | 2018-09-10 08:00 | 2023-01-01 | F | 1573.67
Moneypoint | MP2 | 285 | 2018-09-26 23:00 | 2018-12-12 22:30 | F | 76.96
Aghada | AD1 | 258 | 2018-09-30 23:00 | 2023-01-01 | F | 1553
Moneypoint | MP1 | 285 | 2018-10-01 | 2018-12-17 | F | 77
Great Island | GI4 | 461 | 2018-10-25 | 2018-12-10 | F | 46
EWIC | EW1 | 500 | 2018-11-03 19:00 | 2018-11-04 16:00 | S | 0.83
Seal Rock | SK4 | 85 | 2018-11-04 07:00 | 2018-11-06 17:00 | S | 2.42
Edenderry | ED1 | 118 | 2018-12-26 12:00 | 2019-01-02 08:00 | S | 6.83
|  |  | Scheduled Outage | S
|  |  | Forced Outage | F
|  |  | Unit partially available | 10

## Outage Plan SONI
2018 GENERATION OUTAGE PLAN (SONI)
|  | Month | Nov '2018 |  |  |  |  | Dec '2018
|  | Week | 44 '2018 | 45 '2018 | 46 '2018 | 47 '2018 | 48 '2018 | 49 '2018 | 50 '2018 | 51 '2018 | 52 '2018 | 1 '2019
Station | Unit | NPR
Ballylumford | NIB10 | 94
Ballylumford | NIB31 | 249 | F | F | F | F | F
Ballylumford | NIB32 | 249
Ballylumford | NIB4 | 144
Ballylumford | NIB5 | 147
Ballylumford | NIBGT1 | 58
Ballylumford | NIBGT2 | 58
Contour Global | NICG2 | 3
Contour Global | NICGA | 12
Coolkeeragh | NIC30 | 408
Coolkeeragh | NICGT8 | 53
Empower | NIEMP | 3
iPower | NIAGU | 74
Kilroot | NIK1 | 256
Kilroot | NIK2 | 258
Kilroot | NIKGT1 | 29
Kilroot | NIKGT2 | 29
Kilroot | NIKGT3 | 42
Kilroot | NIKGT4 | 42
Lisahally | NILPS | 18
Moyle | MOYLE | 450
Powerhouse Generation | NIPH1 | 18

## SONI Outages
Upcoming Outages including STMOs and Annual Outages
Station | Unit | NPR | Start Date | End Date | Value | Duration
Ballylumford | NIB31 | 249 | 2018-06-22 05:30 | 2018-12-01 | F | 161.75
|  |  | Scheduled Outage | S
|  |  | Forced Outage | F
|  |  | Unit partially available | 10

## Outage Plan All Island
2018 GENERATION OUTAGE PLAN (All Island)
|  | Month | Nov '2018 |  |  |  |  | Dec '2018
|  | Week | 44 '2018 | 45 '2018 | 46 '2018 | 47 '2018 | 48 '2018 | 49 '2018 | 50 '2018 | 51 '2018 | 52 '2018 | 1 '2019
Station | Unit | NPR
Activation Energy | AE1 | 77
Activation Energy | AE2 | 8
Activation Energy | AE3 | 14
Activation Energy | AE4 | 11
Activation Energy | AE5 | 15
Activation Energy | EN6 | 9
Aghada | AD1 | 258 | F | F | F | F | F | F | F | F | F | F
Aghada | AD2 | 431
Aghada | AT1 | 90
Aghada | AT2 | 90
Aghada | AT4 | 90
Ardnacrusha | AA1 | 21
Ardnacrusha | AA2 | 22
Ardnacrusha | AA3 | 19
Ardnacrusha | AA4 | 24
Ballylumford | NIB10 | 94
Ballylumford | NIB31 | 249 | F | F | F | F | F
Ballylumford | NIB32 | 249
Ballylumford | NIB4 | 144
Ballylumford | NIB5 | 147
Ballylumford | NIBGT1 | 58
Ballylumford | NIBGT2 | 58
Contour Global | NICG2 | 3
Contour Global | NICGA | 12
Coolkeeragh | NIC30 | 408
Coolkeeragh | NICGT8 | 53
DAE Virtual Power Plant | DP1 | 19
DAE Virtual Power Plant | DP2 | 20
Dublin Bay | DB1 | 405
Dublin Waste To Energy | DW1 | 62
Edenderry | ED1 | 118 | [8 empty] | S
Edenderry | ED3 | 58
Edenderry | ED5 | 58
Electric Ireland | EI1 | 20
Electricity Exchange DSU | EE1 | 39
Electricity Exchange DSU | EE2 | 17
Electricity Exchange DSU | EE3 | 7
Electricity Exchange DSU | EE4 | 9
Electricity Exchange DSU | EE5 | 7
Empower | NIEMP | 3
Endeco Technologies | EC1 | 37
Endeco Technologies | EC2 | 10
Endeco Technologies | EC5 | 16
Energy Trading | ET1 | 13
Erne | ER1 | 10
Erne | ER2 | 10
Erne | ER3 | 22
Erne | ER4 | 22
EWIC | EW1 | 500
Great Island | GI4 | 461 | F | F | F | F | F | F
Huntstown | HN2 | 400
Huntstown | HNC | 342
Indaver | IW1 | 17
iPower | NIAGU | 74
Kilroot | NIK1 | 256
Kilroot | NIK2 | 258
Kilroot | NIKGT1 | 29
Kilroot | NIKGT2 | 29
Kilroot | NIKGT3 | 42
Kilroot | NIKGT4 | 42
Lanesboro | LR4 | 91
Lee | LE1 | 15
Lee | LE2 | 4
Lee | LE3 | 8
Liffey | LI1 | 15
Liffey | LI2 | 15
Liffey | LI4 | 4
Liffey | LI5 | 4
Lisahally | NILPS | 18
Marina | MRC | 95 | F | F | F | F | F | F | F | F | F | F
Moneypoint | MP1 | 285 | F | F | F | F | F | F | F
Moneypoint | MP2 | 285 | F | F | F | F | F | F
Moneypoint | MP3 | 285 | F | F | F | F | F | F | F
Moyle | MOYLE | 450
North Wall | NW5 | 104
Poolbeg | PB4 | 154
Poolbeg | PB5 | 146
Poolbeg | PB6 | 168
Powerhouse Generation | NIPH1 | 18
Powerhouse Generation | PG1 | 11
Rhode | RP1 | 52
Rhode | RP2 | 52
Seal Rock | SK3 | 85
Seal Rock | SK4 | 85
Tarbert | TB1 | 54
Tarbert | TB2 | 54
Tarbert | TB3 | 241
Tarbert | TB4 | 243
Tawnaghmore | TP1 | 52
Tawnaghmore | TP3 | 52
Turlough Hill | TH1 | 73
Turlough Hill | TH2 | 73
Turlough Hill | TH3 | 73
Turlough Hill | TH4 | 73
Tynagh | TYC | 384
Viridian Energy | VE1 | 19
Viridian Energy DSU | VE2 | 6
West Offaly | WO4 | 137
Whitegate | WG1 | 444

## All Island Outages
Upcoming Outages including STMOs and Annual Outages
Station | Unit | NPR | Start Date | End Date | Value | Duration
Moneypoint | MP3 | 285 | 2018-06-11 | 2018-12-16 | F | 188
Ballylumford | NIB31 | 249 | 2018-06-22 05:30 | 2018-12-01 | F | 161.75
Marina | MRC | 95 | 2018-09-10 08:00 | 2023-01-01 | F | 1573.67
Moneypoint | MP2 | 285 | 2018-09-26 23:00 | 2018-12-12 22:30 | F | 76.96
Aghada | AD1 | 258 | 2018-09-30 23:00 | 2023-01-01 | F | 1553
Moneypoint | MP1 | 285 | 2018-10-01 | 2018-12-17 | F | 77
Great Island | GI4 | 461 | 2018-10-25 | 2018-12-10 | F | 46
EWIC | EW1 | 500 | 2018-11-03 19:00 | 2018-11-04 16:00 | S | 0.83
Seal Rock | SK4 | 85 | 2018-11-04 07:00 | 2018-11-06 17:00 | S | 2.42
Edenderry | ED1 | 118 | 2018-12-26 12:00 | 2019-01-02 08:00 | S | 6.83
|  |  | Scheduled Outage | S
|  |  | Forced Outage | F
|  |  | Unit partially available | 10