## Outage Plan EirGrid
2021 GENERATION OUTAGE PLAN (EIRGRID)
|  | Month | Feb '2021 |  |  |  | Mar '2021
|  | Week | 5 '2021 | 6 '2021 | 7 '2021 | 8 '2021 | 9 '2021 | 10 '2021 | 11 '2021 | 12 '2021 | 13 '2021
Station | Unit | NPR
Activation Energy | AE1 | 95
Activation Energy | AE2 | 12
Activation Energy | AE3 | 14
Activation Energy | AE4 | 15
Activation Energy | AE5 | 15
Activation Energy | EN1 | 15
Activation Energy | EN2 | 16
Activation Energy | EN3 | 16
Activation Energy | EN4 | 16
Activation Energy | EN5 | 6
Activation Energy | EN6 | 11
Aghada | AD2 | 449
Aghada | AT1 | 90
Aghada | AT2 | 90
Aghada | AT4 | 90
Ardnacrusha | AA1 | 21
Ardnacrusha | AA2 | 22
Ardnacrusha | AA3 | 19
Ardnacrusha | AA4 | 24
DAE Virtual Power Plant | DP1 | 19
DAE Virtual Power Plant | DP2 | 26
Dublin Bay | DB1 | 405
Dublin Waste To Energy | DW1 | 62
Edenderry | ED1 | 118
Edenderry | ED3 | 58
Edenderry | ED5 | 58
Electric Ireland | EI1 | 20
Electricity Exchange DSU | EE1 | 47
Electricity Exchange DSU | EE2 | 20
Electricity Exchange DSU | EE3 | 8
Electricity Exchange DSU | EE4 | 9
Electricity Exchange DSU | EE5 | 7
Electricity Exchange DSU | EE6 | 14
Endeco Technologies | EC1 | 47
Endeco Technologies | EC2 | 11
Endeco Technologies | EC5 | 15
Energy Trading | ET1 | 13
Erne | ER1 | 10
Erne | ER2 | 10
Erne | ER3 | 22
Erne | ER4 | 22
EWIC | EW1 | 500
Great Island | GI4 | 461
Huntstown | HN2 | 400 | F | F |  |  | S | S | S | S | S
Huntstown | HNC | 342
Indaver | IW1 | 17
Knockacummer | KC1 | 100
Lee | LE1 | 15
Lee | LE2 | 4
Lee | LE3 | 8
Liffey | LI1 | 15
Liffey | LI2 | 15
Liffey | LI4 | 4
Liffey | LI5 | 4
Moneypoint | MP1 | 285
Moneypoint | MP2 | 285
Moneypoint | MP3 | 285
North Wall | NW5 | 104 | S | S | S | S | S | S | S | S | S
Poolbeg | PB4 | 154
Poolbeg | PB5 | 146
Poolbeg | PB6 | 168
Powerhouse Generation | PG1 | 10
Rhode | RP1 | 52
Rhode | RP2 | 52
Seal Rock | SK3 | 85
Seal Rock | SK4 | 85
Seecon | SO1 | 105
Tarbert | TB1 | 54
Tarbert | TB2 | 54
Tarbert | TB3 | 241
Tarbert | TB4 | 243
Tawnaghmore | TP1 | 52
Tawnaghmore | TP3 | 52
Turlough Hill | TH1 | 73 | [7 empty] | S
Turlough Hill | TH2 | 73 | [7 empty] | S
Turlough Hill | TH3 | 73 | [7 empty] | S
Turlough Hill | TH4 | 73 | [7 empty] | S
Tynagh | TYC | 384
Viridian Energy | VE1 | 20
Viridian Energy DSU | VE2 | 13
Whitegate | WG1 | 444 | F | F | F | F | F | F | F | F | F

## EirGrid Outages
Upcoming Outages including STMOs and Annual Outages
Station | Unit | NPR | Start Date | End Date | Value | Duration
North Wall | NW5 | 104 | 2019-10-01 | 2022-10-01 | S | 1096
Whitegate | WG1 | 444 | 2020-12-02 08:00 | 2021-06-30 23:00 | F | 210.58
Tarbert | TB3 | 241 | 2020-12-08 14:30 | 2021-04-30 | 226 | 142.38
Poolbeg | PB6 | 168 | 2021-01-18 17:30 | 2021-02-02 17:00 | 84 | 14.96
Poolbeg | PB4 | 154 | 2021-01-19 12:00 | 2021-02-02 17:00 | F | 14.17
Moneypoint | MP2 | 285 | 2021-01-19 22:00 | 2021-02-03 13:00 | 120 | 14.58
Moneypoint | MP3 | 285 | 2021-01-21 09:00 | 2021-02-04 03:00 | 260 | 13.75
Tarbert | TB4 | 243 | 2021-01-26 13:00 | 2021-02-04 17:00 | 217 | 9.17
Huntstown | HN2 | 400 | 2021-01-30 09:00 | 2021-02-10 23:00 | F | 29.58
Moneypoint | MP1 | 285 | 2021-01-31 13:00 | 2021-02-02 15:00 | 200 | 2.08
Dublin Waste To Energy | DW1 | 61.5 | 2021-02-01 04:30 | 2021-02-01 09:00 | 45 | 0.17
Tarbert | TB1 | 54 | 2021-02-01 09:00 | 2021-02-01 12:00 | F | 0.08
Turlough Hill | TH1 | 73 | 2021-02-02 10:00 | 2021-02-02 12:30 | S | 0.08
Moneypoint | MP1 | 285 | 2021-02-02 15:00 | 2021-03-07 23:00 | 220 | 33.33
Poolbeg | PB4 | 154 | 2021-02-03 11:30 | 2021-02-03 17:00 | F | 0.21
Moneypoint | MP2 | 285 | 2021-02-03 13:00 | 2021-02-12 23:00 | 99 | 9.42
Moneypoint | MP3 | 285 | 2021-02-04 03:00 | 2021-02-04 15:30 | 190 | 0.5
Tarbert | TB3 | 241 | 2021-02-04 08:00 | 2021-02-10 16:00 | F | 6.33
Seecon | SO1 | 105 | 2021-02-04 10:00 | 2021-02-04 17:00 | S | 0.25
Moneypoint | MP3 | 285 | 2021-02-04 15:30 | 2021-03-07 23:00 | 260 | 31.29
Tynagh | TYC | 384 | 2021-02-12 20:00 | 2021-02-15 | S | 2.17
Moneypoint | MP2 | 285 | 2021-02-12 23:00 | 2021-03-08 | 120 | 23
Aghada | AD2 | 449 | 2021-02-25 01:00 | 2021-03-02 05:00 | F | 5.17
EWIC | EW1 | 500 | 2021-02-25 09:00 | 2021-02-26 23:00 | S | 1.58
Huntstown | HN2 | 400 | 2021-03-01 | 2021-04-15 | S | 45
Seal Rock | SK3 | 85 | 2021-03-01 06:00 | 2021-03-03 18:00 | S | 2.5
Aghada | AT4 | 90 | 2021-03-08 | 2021-03-11 20:00 | S | 3.83
Turlough Hill | TH3 | 73 | 2021-03-20 06:00 | 2021-03-28 21:00 | S | 8.58
Turlough Hill | TH4 | 73 | 2021-03-20 06:00 | 2021-03-28 21:00 | S | 8.58
Turlough Hill | TH2 | 73 | 2021-03-20 06:00 | 2021-03-28 21:00 | S | 8.58
Turlough Hill | TH1 | 73 | 2021-03-20 06:00 | 2021-03-28 21:00 | S | 8.58
|  |  | Scheduled Outage | S
|  |  | Forced Outage | F
|  |  | Unit partially available | 10

## Outage Plan SONI
2021 GENERATION OUTAGE PLAN (SONI)
|  | Month | Feb '2021 |  |  |  | Mar '2021
|  | Week | 5 '2021 | 6 '2021 | 7 '2021 | 8 '2021 | 9 '2021 | 10 '2021 | 11 '2021 | 12 '2021 | 13 '2021
Station | Unit | NPR
AC Automation | NIACA | 8
Activation Energy | NIAEA | 9
Ballylumford | NIB10 | 94
Ballylumford | NIB31 | 249
Ballylumford | NIB32 | 249 |  |  |  |  | S | S | S | S | S
Ballylumford | NIBGT1 | 58
Ballylumford | NIBGT2 | 58
Contour Global | NICG2 | 3
Contour Global | NICGA | 12
Coolkeeragh | NIC30 | 408 |  |  | S
Coolkeeragh | NICGT8 | 53
Empower | NIEMP | 3
Endeco Technologies | NIECA | 13
Energy Trading | NIETB | 9
Energy Trading | NIETD | 5
Energy Trading | NIETR | 19
iPower | NIAGU | 74
Kilroot | NIK1 | 256
Kilroot | NIK2 | 258
Kilroot | NIKGT1 | 29
Kilroot | NIKGT2 | 29
Kilroot | NIKGT3 | 42
Kilroot | NIKGT4 | 42
Lisahally | NILPS | 18 |  |  |  |  | S | S
Moyle | MOYLE | 450
Powerhouse Generation | NIPH1 | 34

## SONI Outages
Upcoming Outages including STMOs and Annual Outages
Station | Unit | NPR | Start Date | End Date | Value | Duration
Kilroot | NIK2 | 258 | 2021-02-01 18:30 | 2021-02-01 21:30 | 148 | 0.08
Kilroot | NIK2 | 258 | 2021-02-03 12:30 | 2021-02-04 20:30 | 169 | 1.33
Ballylumford | NIB32 | 249 | 2021-02-16 22:00 | 2021-02-17 04:30 | S | 0.25
Coolkeeragh | NIC30 | 408 | 2021-02-17 20:00 | 2021-02-21 22:30 | S | 4.08
Kilroot | NIKGT3 | 42 | 2021-02-28 | 2021-03-01 | S | 1
Kilroot | NIKGT4 | 42 | 2021-02-28 | 2021-03-01 | S | 1
Kilroot | NIKGT2 | 29 | 2021-02-28 | 2021-03-01 | S | 1
Ballylumford | NIB32 | 249 | 2021-02-28 20:00 | 2021-04-29 20:30 | S | 60
Lisahally | NILPS | 17.6 | 2021-03-04 18:00 | 2021-03-14 18:30 | S | 10
|  |  | Scheduled Outage | S
|  |  | Forced Outage | F
|  |  | Unit partially available | 10

## Outage Plan All Island
2021 GENERATION OUTAGE PLAN (All Island)
|  | Month | Feb '2021 |  |  |  | Mar '2021
|  | Week | 5 '2021 | 6 '2021 | 7 '2021 | 8 '2021 | 9 '2021 | 10 '2021 | 11 '2021 | 12 '2021 | 13 '2021
Station | Unit | NPR
AC Automation | NIACA | 8
Activation Energy | AE1 | 95
Activation Energy | AE2 | 12
Activation Energy | AE3 | 14
Activation Energy | AE4 | 15
Activation Energy | AE5 | 15
Activation Energy | EN1 | 15
Activation Energy | EN2 | 16
Activation Energy | EN3 | 16
Activation Energy | EN4 | 16
Activation Energy | EN5 | 6
Activation Energy | EN6 | 11
Activation Energy | NIAEA | 9
Aghada | AD2 | 449
Aghada | AT1 | 90
Aghada | AT2 | 90
Aghada | AT4 | 90
Ardnacrusha | AA1 | 21
Ardnacrusha | AA2 | 22
Ardnacrusha | AA3 | 19
Ardnacrusha | AA4 | 24
Ballylumford | NIB10 | 94
Ballylumford | NIB31 | 249
Ballylumford | NIB32 | 249 |  |  |  |  | S | S | S | S | S
Ballylumford | NIBGT1 | 58
Ballylumford | NIBGT2 | 58
Contour Global | NICG2 | 3
Contour Global | NICGA | 12
Coolkeeragh | NIC30 | 408 |  |  | S
Coolkeeragh | NICGT8 | 53
DAE Virtual Power Plant | DP1 | 19
DAE Virtual Power Plant | DP2 | 26
Dublin Bay | DB1 | 405
Dublin Waste To Energy | DW1 | 62
Edenderry | ED1 | 118
Edenderry | ED3 | 58
Edenderry | ED5 | 58
Electric Ireland | EI1 | 20
Electricity Exchange DSU | EE1 | 47
Electricity Exchange DSU | EE2 | 20
Electricity Exchange DSU | EE3 | 8
Electricity Exchange DSU | EE4 | 9
Electricity Exchange DSU | EE5 | 7
Electricity Exchange DSU | EE6 | 14
Empower | NIEMP | 3
Endeco Technologies | EC1 | 47
Endeco Technologies | EC2 | 11
Endeco Technologies | EC5 | 15
Endeco Technologies | NIECA | 13
Energy Trading | ET1 | 13
Energy Trading | NIETB | 9
Energy Trading | NIETD | 5
Energy Trading | NIETR | 19
Erne | ER1 | 10
Erne | ER2 | 10
Erne | ER3 | 22
Erne | ER4 | 22
EWIC | EW1 | 500
Great Island | GI4 | 461
Huntstown | HN2 | 400 | F | F |  |  | S | S | S | S | S
Huntstown | HNC | 342
Indaver | IW1 | 17
iPower | NIAGU | 74
Kilroot | NIK1 | 256
Kilroot | NIK2 | 258
Kilroot | NIKGT1 | 29
Kilroot | NIKGT2 | 29
Kilroot | NIKGT3 | 42
Kilroot | NIKGT4 | 42
Knockacummer | KC1 | 100
Lee | LE1 | 15
Lee | LE2 | 4
Lee | LE3 | 8
Liffey | LI1 | 15
Liffey | LI2 | 15
Liffey | LI4 | 4
Liffey | LI5 | 4
Lisahally | NILPS | 18 |  |  |  |  | S | S
Moneypoint | MP1 | 285
Moneypoint | MP2 | 285
Moneypoint | MP3 | 285
Moyle | MOYLE | 450
North Wall | NW5 | 104 | S | S | S | S | S | S | S | S | S
Poolbeg | PB4 | 154
Poolbeg | PB5 | 146
Poolbeg | PB6 | 168
Powerhouse Generation | NIPH1 | 34
Powerhouse Generation | PG1 | 10
Rhode | RP1 | 52
Rhode | RP2 | 52
Seal Rock | SK3 | 85
Seal Rock | SK4 | 85
Seecon | SO1 | 105
Tarbert | TB1 | 54
Tarbert | TB2 | 54
Tarbert | TB3 | 241
Tarbert | TB4 | 243
Tawnaghmore | TP1 | 52
Tawnaghmore | TP3 | 52
Turlough Hill | TH1 | 73 | [7 empty] | S
Turlough Hill | TH2 | 73 | [7 empty] | S
Turlough Hill | TH3 | 73 | [7 empty] | S
Turlough Hill | TH4 | 73 | [7 empty] | S
Tynagh | TYC | 384
Viridian Energy | VE1 | 20
Viridian Energy DSU | VE2 | 13
Whitegate | WG1 | 444 | F | F | F | F | F | F | F | F | F

## All Island Outages
Upcoming Outages including STMOs and Annual Outages
Station | Unit | NPR | Start Date | End Date | Value | Duration
North Wall | NW5 | 104 | 2019-10-01 | 2022-10-01 | S | 1096
Whitegate | WG1 | 444 | 2020-12-02 08:00 | 2021-06-30 23:00 | F | 210.58
Tarbert | TB3 | 241 | 2020-12-08 14:30 | 2021-04-30 | 226 | 142.38
Poolbeg | PB6 | 168 | 2021-01-18 17:30 | 2021-02-02 17:00 | 84 | 14.96
Poolbeg | PB4 | 154 | 2021-01-19 12:00 | 2021-02-02 17:00 | F | 14.17
Moneypoint | MP2 | 285 | 2021-01-19 22:00 | 2021-02-03 13:00 | 120 | 14.58
Moneypoint | MP3 | 285 | 2021-01-21 09:00 | 2021-02-04 03:00 | 260 | 13.75
Tarbert | TB4 | 243 | 2021-01-26 13:00 | 2021-02-04 17:00 | 217 | 9.17
Huntstown | HN2 | 400 | 2021-01-30 09:00 | 2021-02-10 23:00 | F | 29.58
Moneypoint | MP1 | 285 | 2021-01-31 13:00 | 2021-02-02 15:00 | 200 | 2.08
Dublin Waste To Energy | DW1 | 61.5 | 2021-02-01 04:30 | 2021-02-01 09:00 | 45 | 0.17
Tarbert | TB1 | 54 | 2021-02-01 09:00 | 2021-02-01 12:00 | F | 0.08
Kilroot | NIK2 | 258 | 2021-02-01 18:30 | 2021-02-01 21:30 | 148 | 0.08
Turlough Hill | TH1 | 73 | 2021-02-02 10:00 | 2021-02-02 12:30 | S | 0.08
Moneypoint | MP1 | 285 | 2021-02-02 15:00 | 2021-03-07 23:00 | 220 | 33.33
Poolbeg | PB4 | 154 | 2021-02-03 11:30 | 2021-02-03 17:00 | F | 0.21
Kilroot | NIK2 | 258 | 2021-02-03 12:30 | 2021-02-04 20:30 | 169 | 1.33
Moneypoint | MP2 | 285 | 2021-02-03 13:00 | 2021-02-12 23:00 | 99 | 9.42
Moneypoint | MP3 | 285 | 2021-02-04 03:00 | 2021-02-04 15:30 | 190 | 0.5
Tarbert | TB3 | 241 | 2021-02-04 08:00 | 2021-02-10 16:00 | F | 6.33
Seecon | SO1 | 105 | 2021-02-04 10:00 | 2021-02-04 17:00 | S | 0.25
Moneypoint | MP3 | 285 | 2021-02-04 15:30 | 2021-03-07 23:00 | 260 | 31.29
Tynagh | TYC | 384 | 2021-02-12 20:00 | 2021-02-15 | S | 2.17
Moneypoint | MP2 | 285 | 2021-02-12 23:00 | 2021-03-08 | 120 | 23
Ballylumford | NIB32 | 249 | 2021-02-16 22:00 | 2021-02-17 04:30 | S | 0.25
Coolkeeragh | NIC30 | 408 | 2021-02-17 20:00 | 2021-02-21 22:30 | S | 4.08
Aghada | AD2 | 449 | 2021-02-25 01:00 | 2021-03-02 05:00 | F | 5.17
EWIC | EW1 | 500 | 2021-02-25 09:00 | 2021-02-26 23:00 | S | 1.58
Kilroot | NIKGT3 | 42 | 2021-02-28 | 2021-03-01 | S | 1
Kilroot | NIKGT4 | 42 | 2021-02-28 | 2021-03-01 | S | 1
Kilroot | NIKGT2 | 29 | 2021-02-28 | 2021-03-01 | S | 1
Ballylumford | NIB32 | 249 | 2021-02-28 20:00 | 2021-04-29 20:30 | S | 60
Huntstown | HN2 | 400 | 2021-03-01 | 2021-04-15 | S | 45
Seal Rock | SK3 | 85 | 2021-03-01 06:00 | 2021-03-03 18:00 | S | 2.5
Lisahally | NILPS | 17.6 | 2021-03-04 18:00 | 2021-03-14 18:30 | S | 10
Aghada | AT4 | 90 | 2021-03-08 | 2021-03-11 20:00 | S | 3.83
Turlough Hill | TH3 | 73 | 2021-03-20 06:00 | 2021-03-28 21:00 | S | 8.58
Turlough Hill | TH4 | 73 | 2021-03-20 06:00 | 2021-03-28 21:00 | S | 8.58
Turlough Hill | TH2 | 73 | 2021-03-20 06:00 | 2021-03-28 21:00 | S | 8.58
Turlough Hill | TH1 | 73 | 2021-03-20 06:00 | 2021-03-28 21:00 | S | 8.58
|  |  | Scheduled Outage | S
|  |  | Forced Outage | F
|  |  | Unit partially available | 10