## Outage Plan EirGrid
2019 GENERATION OUTAGE PLAN (EIRGRID)
|  | Month | Jan '2019 |  |  |  |  | Feb '2019 |  |  |  | Mar '2019 |  |  |  | Apr '2019 |  |  |  |  | May '2019 |  |  |  | Jun '2019 |  |  |  | Jul '2019 |  |  |  |  | Aug '2019 |  |  |  | Sep '2019 |  |  |  |  | Oct '2019 |  |  |  | Nov '2019 |  |  |  | Dec '2019
|  | Week | 1 '2019 | 2 '2019 | 3 '2019 | 4 '2019 | 5 '2019 | 6 '2019 | 7 '2019 | 8 '2019 | 9 '2019 | 10 '2019 | 11 '2019 | 12 '2019 | 13 '2019 | 14 '2019 | 15 '2019 | 16 '2019 | 17 '2019 | 18 '2019 | 19 '2019 | 20 '2019 | 21 '2019 | 22 '2019 | 23 '2019 | 24 '2019 | 25 '2019 | 26 '2019 | 27 '2019 | 28 '2019 | 29 '2019 | 30 '2019 | 31 '2019 | 32 '2019 | 33 '2019 | 34 '2019 | 35 '2019 | 36 '2019 | 37 '2019 | 38 '2019 | 39 '2019 | 40 '2019 | 41 '2019 | 42 '2019 | 43 '2019 | 44 '2019 | 45 '2019 | 46 '2019 | 47 '2019 | 48 '2019 | 49 '2019 | 50 '2019 | 51 '2019 | 52 '2019 | 1 '2020
Station | Unit | NPR
Activation Energy | AE1 | 95
Activation Energy | AE2 | 8
Activation Energy | AE3 | 14
Activation Energy | AE4 | 15
Activation Energy | AE5 | 15
Activation Energy | EN5 | 6
Activation Energy | EN6 | 11
Aghada | AD2 | 431 | [34 empty] | S | S | S | S | S | S | S | S | S | F | F
Aghada | AT1 | 90
Aghada | AT2 | 90
Aghada | AT4 | 90
Ardnacrusha | AA1 | 21 | [14 empty] | S
Ardnacrusha | AA2 | 22 | [34 empty] | S | S | S
Ardnacrusha | AA3 | 19 | [20 empty] | S
Ardnacrusha | AA4 | 24 | [36 empty] | F | F | S
DAE Virtual Power Plant | DP1 | 19
DAE Virtual Power Plant | DP2 | 26
Dublin Bay | DB1 | 405 | [12 empty] | S | S | S | F
Dublin Waste To Energy | DW1 | 62 | [9 empty] | S
Edenderry | ED1 | 118 | [23 empty] | S | S | S | S | S | S | S | S | S | [19 empty] | S | S
Edenderry | ED3 | 58
Edenderry | ED5 | 58
Electric Ireland | EI1 | 20
Electricity Exchange DSU | EE1 | 51
Electricity Exchange DSU | EE2 | 28
Electricity Exchange DSU | EE3 | 8
Electricity Exchange DSU | EE4 | 9
Electricity Exchange DSU | EE5 | 6
Endeco Technologies | EC1 | 42
Endeco Technologies | EC2 | 11
Endeco Technologies | EC5 | 15
Energy Trading | ET1 | 13
Erne | ER1 | 10 | F | F | [25 empty] | S | [7 empty] | S
Erne | ER2 | 10 |  | F | [32 empty] | F | S
Erne | ER3 | 22 | [19 empty] | S
Erne | ER4 | 22 | [23 empty] | S | S | S
EWIC | EW1 | 500 | [18 empty] | S
Great Island | GI4 | 461 | F | F | F | F | F | F | [14 empty] | F
Huntstown | HN2 | 400 | [11 empty] | F | F | F | F | F | F
Huntstown | HNC | 342 | [32 empty] | S | S | F | F | F | F | F
Indaver | IW1 | 17 | [13 empty] | S | S
Knockacummer | KC1 | 100
Lanesboro | LR4 | 91 | [24 empty] | S | S | S | F | F | F | F | F | F | F | F | F | F | F
Lee | LE1 | 15 |  | F | [16 empty] | S | S | S
Lee | LE2 | 4 | [13 empty] | S | [5 empty] | S | S
Lee | LE3 | 8 | [22 empty] | S | S | S
Liffey | LI1 | 15 | [18 empty] | F | F
Liffey | LI2 | 15 | [18 empty] | F | F
Liffey | LI4 | 4
Liffey | LI5 | 4
Moneypoint | MP1 | 285 | F | F | [37 empty] | F | F | F
Moneypoint | MP2 | 285 | F | F | F | F | F | F | F | F | F | F | F | F | [14 empty] | F |  |  |  | S | S | S | S | S | F | F | F
Moneypoint | MP3 | 285 | F | [9 empty] | F | [27 empty] | F | F | F | F | F | F | F | F | F | F | F | F
North Wall | NW5 | 104 | [39 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Poolbeg | PB4 | 154 | [7 empty] | S | [22 empty] | S |  |  |  |  | S | S | S | S | S | S
Poolbeg | PB5 | 146 | [30 empty] | S |  |  |  |  | S |  |  |  | S
Poolbeg | PB6 | 168 | [10 empty] | F | [19 empty] | S |  |  |  |  | S | S |  |  | S
Powerhouse Generation | PG1 | 11
Rhode | RP1 | 52 | [29 empty] | F | F | F | S
Rhode | RP2 | 52 | [29 empty] | F | F | F | S
Seal Rock | SK3 | 85 | [31 empty] | F | [6 empty] | S
Seal Rock | SK4 | 85 | [26 empty] | S | S | S
Seecon | SO1 | 105
Tarbert | TB1 | 54 | [19 empty] | S
Tarbert | TB2 | 54 | [19 empty] | S
Tarbert | TB3 | 241 | [23 empty] | S | F | F | F | F | F | F | F | F | F
Tarbert | TB4 | 243 |  | F | [25 empty] | F
Tawnaghmore | TP1 | 52
Tawnaghmore | TP3 | 52
Turlough Hill | TH1 | 73 | [20 empty] | S | S | S | S
Turlough Hill | TH2 | 73 | [20 empty] | S | S | S | S
Turlough Hill | TH3 | 73 | [16 empty] | F | F |  |  | S | S | S | S
Turlough Hill | TH4 | 73 | [20 empty] | S | S | S | S
Tynagh | TYC | 384 | [22 empty] | F | F
Viridian Energy | VE1 | 20
Viridian Energy DSU | VE2 | 13
West Offaly | WO4 | 137 | [18 empty] | S | S | S | F
Whitegate | WG1 | 444 | F | [28 empty] | S | S | S

## EirGrid Outages
Upcoming Outages including STMOs and Annual Outages
Station | Unit | NPR | Start Date | End Date | Value | Duration
Moneypoint | MP2 | 285 | 2018-09-26 23:00 | 2019-03-27 12:00 | F | 181.5
Moneypoint | MP1 | 285 | 2018-10-01 | 2019-01-16 12:00 | F | 107.5
Great Island | GI4 | 461 | 2018-10-25 | 2019-01-21 18:30 | F | 88.75
Erne | ER1 | 10 | 2018-12-13 14:30 | 2019-01-15 18:00 | F | 33.12
Moneypoint | MP3 | 285 | 2018-12-24 | 2019-01-07 16:30 | F | 14.67
Whitegate | WG1 | 444 | 2018-12-24 | 2019-01-05 23:00 | F | 12.92
Edenderry | ED1 | 118 | 2018-12-26 12:00 | 2019-01-02 08:00 | S | 6.83
Rhode | RP1 | 52 | 2019-01-03 13:00 | 2019-01-03 18:30 | F | 0.21
EWIC | EW1 | 500 | 2019-01-04 09:00 | 2019-01-05 23:00 | F | 1.58
Tarbert | TB4 | 243 | 2019-01-06 19:30 | 2019-01-14 17:00 | F | 7.88
Moneypoint | MP3 | 285 | 2019-01-07 20:30 | 2019-01-08 16:00 | F | 0.79
Lee | LE1 | 15 | 2019-01-09 08:30 | 2019-01-16 | F | 6.62
Erne | ER2 | 10 | 2019-01-09 08:30 | 2019-01-14 | F | 4.62
Moneypoint | MP3 | 285 | 2019-01-10 05:30 | 2019-01-11 18:00 | 180 | 1.5
Turlough Hill | TH4 | 73 | 2019-01-11 11:00 | 2019-01-11 12:30 | S | 0.04
Moneypoint | MP3 | 285 | 2019-01-12 16:30 | 2019-01-16 18:00 | 160 | 4.04
Turlough Hill | TH3 | 73 | 2019-01-15 08:00 | 2019-01-15 18:00 | S | 0.42
Moneypoint | MP3 | 285 | 2019-01-16 18:00 | 2019-01-20 18:00 | 210 | 4
Moneypoint | MP1 | 285 | 2019-01-17 | 2019-01-20 23:00 | 150 | 3.92
Lee | LE1 | 15 | 2019-01-17 06:00 | 2019-01-20 18:00 | F | 3.5
Ardnacrusha | AA4 | 24 | 2019-01-17 08:00 | 2019-01-17 17:00 | S | 0.33
North Wall | NW5 | 104 | 2019-01-17 17:30 | 2019-01-18 10:00 | F | 0.67
Moneypoint | MP3 | 285 | 2019-01-19 07:30 | 2019-01-21 16:30 | 200 | 2.33
Moneypoint | MP1 | 285 | 2019-01-19 09:00 | 2019-01-21 16:30 | 200 | 2.29
Dublin Bay | DB1 | 405 | 2019-01-19 22:00 | 2019-01-22 | F | 2.08
Great Island | GI4 | 461 | 2019-01-21 18:30 | 2019-02-12 23:00 | F | 22.17
Moneypoint | MP3 | 285 | 2019-01-22 06:00 | 2019-01-22 18:00 | 170 | 0.5
Moneypoint | MP1 | 285 | 2019-01-22 07:30 | 2019-01-22 18:00 | 140 | 0.42
North Wall | NW5 | 104 | 2019-01-25 07:00 | 2019-01-27 17:00 | S | 2.42
Whitegate | WG1 | 444 | 2019-01-26 11:30 | 2019-01-28 21:00 | F | 2.38
Erne | ER4 | 22.5 | 2019-01-26 20:00 | 2019-01-31 13:00 | F | 4.67
Tawnaghmore | TP3 | 52 | 2019-01-30 20:00 | 2019-01-31 12:00 | F | 0.67
Turlough Hill | TH2 | 73 | 2019-01-31 08:00 | 2019-01-31 13:00 | S | 0.17
Liffey | LI2 | 15 | 2019-01-31 18:00 | 2019-02-01 10:00 | F | 0.67
Turlough Hill | TH3 | 73 | 2019-02-07 00:30 | 2019-02-07 09:00 | F | 0.33
Turlough Hill | TH4 | 73 | 2019-02-14 08:00 | 2019-02-14 13:00 | S | 0.17
EWIC | EW1 | 500 | 2019-02-16 09:00 | 2019-02-17 23:00 | S | 1.58
Seal Rock | SK3 | 85 | 2019-02-17 07:00 | 2019-02-20 17:00 | S | 3.42
Poolbeg | PB4 | 154 | 2019-02-19 | 2019-02-24 | S | 5
Poolbeg | PB6 | 168 | 2019-02-19 | 2019-02-24 | 84 | 5
Seal Rock | SK3 | 85 | 2019-02-20 17:00 | 2019-02-21 14:00 | F | 0.83
Turlough Hill | TH1 | 73 | 2019-02-21 08:00 | 2019-02-21 13:00 | S | 0.17
Great Island | GI4 | 461 | 2019-02-22 16:30 | 2019-02-25 08:00 | F | 2.62
Tarbert | TB3 | 241 | 2019-02-27 08:00 | 2019-03-01 17:00 | S | 2.33
Great Island | GI4 | 461 | 2019-03-01 23:00 | 2019-03-03 23:00 | F | 2
Dublin Waste To Energy | DW1 | 61.5 | 2019-03-03 | 2019-03-07 | 26 | 4
Seal Rock | SK4 | 85 | 2019-03-03 07:00 | 2019-03-05 17:00 | S | 2.42
Dublin Waste To Energy | DW1 | 61.5 | 2019-03-07 | 2019-03-12 | S | 5
Great Island | GI4 | 461 | 2019-03-08 23:30 | 2019-03-10 23:00 | F | 1.96
Moneypoint | MP3 | 285 | 2019-03-09 20:00 | 2019-03-16 22:00 | F | 7.08
Poolbeg | PB6 | 168 | 2019-03-10 23:00 | 2019-03-20 23:00 | F | 10
Dublin Waste To Energy | DW1 | 61.5 | 2019-03-12 | 2019-03-14 | F | 2
Moneypoint | MP1 | 285 | 2019-03-14 | 2019-03-15 | 200 | 1
Great Island | GI4 | 461 | 2019-03-15 16:30 | 2019-03-21 23:30 | 400 | 6.25
Great Island | GI4 | 461 | 2019-03-15 22:30 | 2019-03-16 19:00 | F | 0.83
Indaver | IW1 | 17 | 2019-03-18 09:00 | 2019-03-19 22:00 | F | 1.5
Moneypoint | MP1 | 285 | 2019-03-19 08:00 | 2019-04-08 | 200 | 19.67
Dublin Bay | DB1 | 405 | 2019-03-19 22:00 | 2019-03-22 13:00 | F | 2.58
Huntstown | HN2 | 400 | 2019-03-20 | 2019-04-29 | F | 40
Liffey | LI4 | 4 | 2019-03-20 07:30 | 2019-03-21 | F | 0.67
Aghada | AT1 | 90 | 2019-03-21 08:00 | 2019-03-21 15:00 | S | 0.25
Turlough Hill | TH3 | 73 | 2019-03-22 08:00 | 2019-03-22 13:00 | F | 0.17
Dublin Bay | DB1 | 405 | 2019-03-22 13:00 | 2019-04-14 13:00 | S | 23
Turlough Hill | TH2 | 73 | 2019-03-26 08:00 | 2019-03-26 19:00 | F | 0.42
Turlough Hill | TH3 | 73 | 2019-03-28 11:00 | 2019-03-28 13:00 | F | 0.08
Indaver | IW1 | 17 | 2019-04-01 05:00 | 2019-04-17 11:00 | S | 16.25
Lee | LE2 | 4 | 2019-04-01 08:00 | 2019-04-05 20:00 | S | 4.5
Liffey | LI1 | 15 | 2019-04-02 08:00 | 2019-04-04 17:00 | S | 2.33
Liffey | LI2 | 15 | 2019-04-02 08:00 | 2019-04-04 17:00 | S | 2.33
Lee | LE2 | 4 | 2019-04-05 20:00 | 2019-04-12 08:00 | F | 6.5
Ardnacrusha | AA1 | 21 | 2019-04-08 08:00 | 2019-04-12 20:00 | S | 4.5
Liffey | LI4 | 4 | 2019-04-09 08:00 | 2019-04-11 17:00 | S | 2.33
Ardnacrusha | AA2 | 22 | 2019-04-10 08:00 | 2019-04-10 17:00 | S | 0.33
Huntstown | HNC | 342 | 2019-04-12 22:00 | 2019-04-14 04:00 | 220 | 1.25
Moneypoint | MP1 | 285 | 2019-04-14 11:00 | 2019-04-18 23:30 | F | 4.5
Dublin Bay | DB1 | 405 | 2019-04-14 13:00 | 2019-04-24 16:00 | F | 10.08
Moneypoint | MP2 | 285 | 2019-04-15 15:00 | 2019-05-07 17:30 | 99 | 22.08
Lee | LE2 | 4 | 2019-04-16 08:00 | 2019-04-16 17:00 | S | 0.33
Turlough Hill | TH2 | 73 | 2019-04-18 08:00 | 2019-04-18 13:00 | S | 0.17
Turlough Hill | TH1 | 73 | 2019-04-18 14:00 | 2019-04-18 15:00 | F | 0
Edenderry | ED1 | 118 | 2019-04-18 18:00 | 2019-04-19 23:00 | F | 1.17
Moneypoint | MP1 | 285 | 2019-04-18 23:30 | 2019-05-24 16:00 | 200 | 35.67
Tarbert | TB3 | 241 | 2019-04-19 23:00 | 2019-04-26 17:00 | 121 | 6.75
Whitegate | WG1 | 444 | 2019-04-22 13:00 | 2019-04-25 16:00 | F | 3.08
Turlough Hill | TH3 | 73 | 2019-04-23 06:00 | 2019-05-05 12:00 | F | 12.25
Ardnacrusha | AA2 | 22 | 2019-04-23 08:00 | 2019-04-23 15:00 | S | 0.25
Great Island | GI4 | 461 | 2019-04-28 23:00 | 2019-05-02 23:00 | S | 4
Aghada | AT1 | 90 | 2019-05-01 09:00 | 2019-05-01 13:00 | S | 0.17
Great Island | GI4 | 461 | 2019-05-02 23:00 | 2019-05-03 11:00 | F | 0.5
Liffey | LI2 | 15 | 2019-05-07 | 2019-05-17 18:00 | F | 10.75
Liffey | LI1 | 15 | 2019-05-07 | 2019-05-17 18:00 | F | 10.75
Lee | LE1 | 15 | 2019-05-07 08:00 | 2019-05-27 20:00 | S | 20.5
EWIC | EW1 | 500 | 2019-05-07 14:00 | 2019-05-13 23:00 | S | 6.33
Moneypoint | MP2 | 285 | 2019-05-07 17:30 | 2019-06-30 23:00 | 200 | 54.21
Whitegate | WG1 | 444 | 2019-05-08 10:00 | 2019-05-09 23:00 | F | 1.5
West Offaly | WO4 | 137 | 2019-05-09 16:00 | 2019-05-27 16:00 | S | 18
Erne | ER3 | 22.5 | 2019-05-13 08:00 | 2019-05-17 20:00 | S | 4.5
Tarbert | TB1 | 54 | 2019-05-13 09:00 | 2019-05-17 17:00 | S | 4.33
Tarbert | TB2 | 54 | 2019-05-13 09:00 | 2019-05-20 09:00 | S | 7
Huntstown | HNC | 342 | 2019-05-13 10:30 | 2019-05-13 14:00 | 220 | 0.12
Seal Rock | SK3 | 85 | 2019-05-13 13:00 | 2019-05-16 19:00 | S | 3.25
Seal Rock | SK4 | 85 | 2019-05-13 18:00 | 2019-05-16 23:00 | S | 3.17
Lee | LE2 | 4 | 2019-05-14 08:00 | 2019-05-24 16:00 | S | 10.33
Huntstown | HNC | 342 | 2019-05-16 00:30 | 2019-05-16 12:00 | 229 | 0.46
Edenderry | ED5 | 58 | 2019-05-17 08:00 | 2019-05-17 18:00 | S | 0.42
Edenderry | ED3 | 58 | 2019-05-17 08:00 | 2019-05-17 18:00 | S | 0.42
Turlough Hill | TH3 | 73 | 2019-05-17 23:30 | 2019-06-14 17:00 | S | 27.71
Turlough Hill | TH2 | 73 | 2019-05-17 23:30 | 2019-06-14 17:00 | S | 27.71
Turlough Hill | TH1 | 73 | 2019-05-17 23:30 | 2019-06-14 17:00 | S | 27.71
Huntstown | HN2 | 400 | 2019-05-18 06:00 | 2019-05-18 20:00 | S | 0.58
Turlough Hill | TH4 | 73 | 2019-05-18 11:30 | 2019-06-14 17:00 | S | 27.21
Ardnacrusha | AA3 | 19 | 2019-05-20 08:00 | 2019-05-24 20:00 | S | 4.5
Great Island | GI4 | 461 | 2019-05-20 15:30 | 2019-05-26 23:00 | F | 6.29
Moneypoint | MP1 | 285 | 2019-05-24 15:30 | 2019-05-28 17:00 | F | 4.04
Aghada | AD2 | 431 | 2019-05-24 20:00 | 2019-05-26 | S | 1.17
West Offaly | WO4 | 137 | 2019-05-27 16:00 | 2019-05-31 16:00 | F | 4
Dublin Bay | DB1 | 405 | 2019-05-27 20:00 | 2019-05-28 02:00 | S | 0.25
Moneypoint | MP1 | 285 | 2019-05-29 07:00 | 2019-06-30 23:00 | 230 | 32.67
Dublin Bay | DB1 | 405 | 2019-05-29 10:30 | 2019-05-29 12:00 | F | 0.04
Tarbert | TB2 | 54 | 2019-05-29 17:00 | 2019-05-30 17:00 | F | 1
Tarbert | TB3 | 241 | 2019-05-30 18:30 | 2019-06-04 | 124 | 4.21
Tynagh | TYC | 384 | 2019-05-31 23:00 | 2019-06-02 06:00 | S | 1.25
Tynagh | TYC | 384 | 2019-06-02 06:00 | 2019-06-10 23:00 | F | 8.67
Lee | LE3 | 8 | 2019-06-04 08:00 | 2019-06-24 20:00 | S | 20.5
Edenderry | ED1 | 118 | 2019-06-07 11:00 | 2019-08-10 12:00 | S | 64
Tarbert | TB3 | 241 | 2019-06-10 08:00 | 2019-06-17 08:00 | S | 7
Erne | ER4 | 22.5 | 2019-06-10 08:00 | 2019-06-30 20:00 | S | 20.5
Tynagh | TYC | 384 | 2019-06-11 19:30 | 2019-06-18 23:00 | F | 7.12
Turlough Hill | TH1 | 73 | 2019-06-14 17:00 | 2019-06-21 17:00 | F | 7
Turlough Hill | TH3 | 73 | 2019-06-16 15:00 | 2019-06-17 12:00 | F | 0.83
Tarbert | TB3 | 241 | 2019-06-17 08:00 | 2019-08-15 17:00 | F | 59.33
Lanesboro | LR4 | 91 | 2019-06-19 16:00 | 2019-07-07 16:00 | S | 18
Erne | ER3 | 22.5 | 2019-06-26 09:00 | 2019-06-27 18:00 | S | 1.33
Seal Rock | SK4 | 85 | 2019-06-30 07:00 | 2019-07-18 07:00 | S | 18
Aghada | AT1 | 90 | 2019-07-01 07:00 | 2019-07-04 16:00 | S | 3.33
Poolbeg | PB6 | 168 | 2019-07-01 08:00 | 2019-07-04 16:00 | S | 3.33
Moneypoint | MP2 | 285 | 2019-07-02 10:00 | 2019-07-06 11:00 | F | 4
Turlough Hill | TH3 | 73 | 2019-07-06 09:00 | 2019-07-06 14:00 | S | 0.17
Lanesboro | LR4 | 91 | 2019-07-07 16:00 | 2019-09-23 18:00 | F | 78.08
Erne | ER1 | 10 | 2019-07-08 09:00 | 2019-07-13 18:00 | S | 5.33
Tarbert | TB4 | 243 | 2019-07-10 09:00 | 2019-07-14 17:00 | F | 4.33
Turlough Hill | TH2 | 73 | 2019-07-13 08:00 | 2019-07-13 20:00 | S | 0.5
Turlough Hill | TH2 | 73 | 2019-07-14 08:00 | 2019-07-14 20:00 | S | 0.5
Aghada | AT4 | 90 | 2019-07-16 11:30 | 2019-07-16 17:30 | S | 0.25
Turlough Hill | TH4 | 73 | 2019-07-18 10:30 | 2019-07-18 13:00 | S | 0.08
Turlough Hill | TH1 | 73 | 2019-07-18 10:30 | 2019-07-18 13:00 | S | 0.08
Turlough Hill | TH3 | 73 | 2019-07-18 10:30 | 2019-07-18 13:00 | S | 0.08
Turlough Hill | TH2 | 73 | 2019-07-18 10:30 | 2019-07-18 13:00 | S | 0.08
Ardnacrusha | AA4 | 24 | 2019-07-23 08:00 | 2019-07-25 20:00 | S | 2.5
Rhode | RP2 | 52 | 2019-07-23 13:30 | 2019-07-26 17:00 | F | 3.12
Rhode | RP2 | 52 | 2019-07-24 16:00 | 2019-08-09 17:00 | F | 16
Rhode | RP1 | 52 | 2019-07-24 16:00 | 2019-08-09 17:00 | F | 16
Rhode | RP1 | 52 | 2019-07-24 16:00 | 2019-07-26 17:00 | F | 2
Whitegate | WG1 | 444 | 2019-07-24 21:00 | 2019-08-09 21:00 | S | 16
Moneypoint | MP2 | 285 | 2019-07-26 22:00 | 2019-08-30 22:30 | S | 35
Poolbeg | PB5 | 146 | 2019-07-29 | 2019-08-03 | S | 5
Poolbeg | PB4 | 154 | 2019-07-29 | 2019-08-03 | S | 5
Poolbeg | PB6 | 168 | 2019-07-29 | 2019-08-03 | S | 5
West Offaly | WO4 | 137 | 2019-08-02 17:00 | 2019-08-14 17:00 | 48 | 12
Seal Rock | SK3 | 85 | 2019-08-05 22:00 | 2019-08-09 22:00 | F | 4
Turlough Hill | TH1 | 73 | 2019-08-06 09:00 | 2019-08-06 13:00 | S | 0.17
Turlough Hill | TH3 | 73 | 2019-08-07 09:00 | 2019-08-07 13:00 | S | 0.17
Turlough Hill | TH4 | 73 | 2019-08-07 13:00 | 2019-08-07 17:00 | S | 0.17
Huntstown | HNC | 342 | 2019-08-12 | 2019-08-28 22:00 | S | 16.92
Rhode | RP1 | 52 | 2019-08-12 09:00 | 2019-08-19 17:00 | S | 7.33
Rhode | RP2 | 52 | 2019-08-12 09:00 | 2019-08-19 17:00 | S | 7.33
Turlough Hill | TH2 | 73 | 2019-08-13 09:00 | 2019-08-13 13:00 | S | 0.17
Whitegate | WG1 | 444 | 2019-08-15 11:00 | 2019-08-16 23:00 | F | 1.5
Turlough Hill | TH1 | 73 | 2019-08-17 08:00 | 2019-08-17 20:00 | S | 0.5
Turlough Hill | TH1 | 73 | 2019-08-18 08:00 | 2019-08-18 20:00 | S | 0.5
EWIC | EW1 | 500 | 2019-08-19 08:00 | 2019-08-20 23:00 | S | 1.58
Aghada | AD2 | 431 | 2019-08-23 20:00 | 2019-10-29 20:00 | S | 67
Ardnacrusha | AA2 | 22 | 2019-08-26 08:00 | 2019-09-13 20:00 | S | 18.5
Erne | ER2 | 10 | 2019-08-26 19:00 | 2019-09-02 | F | 6.17
Huntstown | HNC | 342 | 2019-08-28 22:00 | 2019-09-27 20:00 | F | 29.92
Moneypoint | MP2 | 285 | 2019-08-30 22:00 | 2019-09-20 08:00 | F | 20.42
Poolbeg | PB6 | 168 | 2019-09-01 | 2019-09-15 | S | 14
Poolbeg | PB4 | 154 | 2019-09-01 | 2019-10-12 | S | 41
Dublin Waste To Energy | DW1 | 61.5 | 2019-09-01 | 2019-09-06 | 26 | 5
Poolbeg | PB5 | 146 | 2019-09-02 | 2019-09-06 20:00 | S | 4.83
Erne | ER2 | 10 | 2019-09-02 08:00 | 2019-09-06 16:00 | S | 4.33
Erne | ER1 | 10 | 2019-09-02 08:00 | 2019-09-06 16:00 | S | 4.33
Dublin Waste To Energy | DW1 | 61.5 | 2019-09-06 | 2019-09-08 | S | 2
Dublin Waste To Energy | DW1 | 61.5 | 2019-09-08 | 2019-09-10 05:00 | F | 2.17
Liffey | LI5 | 4 | 2019-09-10 08:00 | 2019-09-12 17:00 | S | 2.33
Moneypoint | MP1 | 285 | 2019-09-11 04:30 | 2019-09-13 18:00 | F | 2.54
Ardnacrusha | AA4 | 24 | 2019-09-12 05:00 | 2019-09-23 | F | 10.75
Poolbeg | PB6 | 168 | 2019-09-15 | 2019-09-30 | 84 | 15
Tynagh | TYC | 384 | 2019-09-15 23:00 | 2019-09-19 23:00 | S | 4
North Wall | NW5 | 104 | 2019-09-18 20:00 | 2019-09-20 13:00 | F | 1.67
Tynagh | TYC | 384 | 2019-09-20 | 2019-09-23 23:00 | F | 3.92
Seal Rock | SK3 | 85 | 2019-09-23 07:00 | 2019-09-27 17:00 | S | 4.42
Ardnacrusha | AA4 | 24 | 2019-09-23 08:00 | 2019-09-27 20:00 | S | 4.5
Moneypoint | MP3 | 285 | 2019-09-23 12:00 | 2019-12-13 23:00 | F | 81.42
Poolbeg | PB5 | 146 | 2019-09-30 | 2019-10-04 | S | 4
Poolbeg | PB6 | 168 | 2019-09-30 | 2019-10-04 | S | 4
Turlough Hill | TH4 | 73 | 2019-09-30 00:30 | 2019-09-30 12:00 | F | 0.46
North Wall | NW5 | 104 | 2019-10-01 | 2022-10-01 | S | 1096
Moneypoint | MP1 | 285 | 2019-10-02 21:00 | 2019-10-19 18:00 | F | 16.83
Poolbeg | PB6 | 168 | 2019-10-04 | 2019-10-12 | 84 | 8
Dublin Bay | DB1 | 405 | 2019-10-07 09:00 | 2019-10-08 13:00 | F | 1.17
Turlough Hill | TH2 | 73 | 2019-10-08 21:00 | 2019-10-11 13:00 | F | 2.67
Great Island | GI4 | 461 | 2019-10-09 06:00 | 2019-10-10 12:00 | F | 1.25
Great Island | GI4 | 461 | 2019-10-11 23:00 | 2019-10-18 16:00 | F | 6.67
Poolbeg | PB6 | 168 | 2019-10-12 | 2019-10-14 22:00 | 84 | 2.92
Poolbeg | PB4 | 154 | 2019-10-12 | 2019-10-14 22:00 | F | 2.92
Turlough Hill | TH3 | 73 | 2019-10-14 09:00 | 2019-10-14 13:00 | S | 0.17
Lanesboro | LR4 | 91 | 2019-10-15 10:00 | 2019-10-15 14:00 | F | 0.17
Turlough Hill | TH4 | 73 | 2019-10-23 09:00 | 2019-10-23 17:00 | S | 0.33
Turlough Hill | TH3 | 73 | 2019-10-23 09:00 | 2019-10-23 17:00 | S | 0.33
Turlough Hill | TH2 | 73 | 2019-10-23 09:00 | 2019-10-23 17:00 | S | 0.33
Turlough Hill | TH1 | 73 | 2019-10-23 09:00 | 2019-10-23 17:00 | S | 0.33
Dublin Bay | DB1 | 405 | 2019-10-25 01:00 | 2019-10-29 | S | 3.92
Aghada | AD2 | 431 | 2019-10-30 | 2019-11-07 12:00 | F | 8.5
Tynagh | TYC | 384 | 2019-10-31 01:00 | 2019-10-31 15:30 | F | 0.58
Huntstown | HNC | 342 | 2019-10-31 02:00 | 2019-11-01 18:00 | F | 1.67
Poolbeg | PB6 | 168 | 2019-10-31 05:00 | 2019-11-05 23:00 | F | 5.75
EWIC | EW1 | 500 | 2019-10-31 09:00 | 2019-11-01 23:00 | S | 1.58
Edenderry | ED1 | 118 | 2019-11-02 08:00 | 2019-11-02 20:00 | 52 | 0.5
Huntstown | HN2 | 400 | 2019-11-05 23:00 | 2019-11-07 19:00 | F | 1.83
Dublin Waste To Energy | DW1 | 61.5 | 2019-11-06 05:00 | 2019-11-07 01:00 | F | 0.83
Moneypoint | MP1 | 285 | 2019-11-06 10:00 | 2019-11-09 23:00 | F | 3.5
Great Island | GI4 | 461 | 2019-11-11 15:00 | 2019-11-13 12:00 | F | 1.83
Tynagh | TYC | 384 | 2019-11-12 23:00 | 2019-11-14 18:00 | F | 1.75
Great Island | GI4 | 461 | 2019-11-14 10:30 | 2019-11-14 17:00 | F | 0.25
Tynagh | TYC | 384 | 2019-11-15 06:30 | 2019-11-16 23:00 | F | 1.67
Turlough Hill | TH4 | 73 | 2019-11-18 11:00 | 2019-11-18 13:00 | F | 0.08
Whitegate | WG1 | 444 | 2019-11-18 23:00 | 2019-11-19 06:00 | F | 0.25
Aghada | AD2 | 431 | 2019-11-20 15:00 | 2019-11-20 16:00 | F | 0
Aghada | AD2 | 431 | 2019-11-20 19:00 | 2019-11-21 17:00 | F | 0.92
Poolbeg | PB6 | 168 | 2019-11-20 22:00 | 2019-11-20 23:30 | 84 | 0.04
Moneypoint | MP1 | 285 | 2019-11-21 03:30 | 2019-11-21 06:30 | F | 0.08
Dublin Bay | DB1 | 405 | 2019-11-25 21:00 | 2019-11-26 00:30 | F | 0.12
Tarbert | TB4 | 243 | 2019-11-26 18:30 | 2019-11-29 17:00 | F | 2.92
Huntstown | HN2 | 400 | 2019-11-26 23:00 | 2019-11-28 23:00 | F | 2
Huntstown | HNC | 342 | 2019-12-02 23:00 | 2019-12-04 23:00 | F | 2
Seal Rock | SK4 | 85 | 2019-12-08 08:00 | 2019-12-10 17:00 | S | 2.33
Edenderry | ED1 | 118 | 2019-12-26 13:00 | 2020-01-02 08:00 | S | 6.75
|  |  | Scheduled Outage | S
|  |  | Forced Outage | F
|  |  | Unit partially available | 10

## Outage Plan SONI
2019 GENERATION OUTAGE PLAN (SONI)
|  | Month | Jan '2019 |  |  |  |  | Feb '2019 |  |  |  | Mar '2019 |  |  |  | Apr '2019 |  |  |  |  | May '2019 |  |  |  | Jun '2019 |  |  |  | Jul '2019 |  |  |  |  | Aug '2019 |  |  |  | Sep '2019 |  |  |  |  | Oct '2019 |  |  |  | Nov '2019 |  |  |  | Dec '2019
|  | Week | 1 '2019 | 2 '2019 | 3 '2019 | 4 '2019 | 5 '2019 | 6 '2019 | 7 '2019 | 8 '2019 | 9 '2019 | 10 '2019 | 11 '2019 | 12 '2019 | 13 '2019 | 14 '2019 | 15 '2019 | 16 '2019 | 17 '2019 | 18 '2019 | 19 '2019 | 20 '2019 | 21 '2019 | 22 '2019 | 23 '2019 | 24 '2019 | 25 '2019 | 26 '2019 | 27 '2019 | 28 '2019 | 29 '2019 | 30 '2019 | 31 '2019 | 32 '2019 | 33 '2019 | 34 '2019 | 35 '2019 | 36 '2019 | 37 '2019 | 38 '2019 | 39 '2019 | 40 '2019 | 41 '2019 | 42 '2019 | 43 '2019 | 44 '2019 | 45 '2019 | 46 '2019 | 47 '2019 | 48 '2019 | 49 '2019 | 50 '2019 | 51 '2019 | 52 '2019 | 1 '2020
Station | Unit | NPR
AC Automation | NIACA | 8
Activation Energy | NIAEA | 9
Ballylumford | NIB10 | 94 |  |  | S | [25 empty] | F | F | F
Ballylumford | NIB31 | 249
Ballylumford | NIB32 | 249 | [36 empty] | S |  |  | S
Ballylumford | NIB4 | 144 | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F
Ballylumford | NIB5 | 147 | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F
Ballylumford | NIBGT1 | 58 | [42 empty] | S
Ballylumford | NIBGT2 | 58 | [47 empty] | S
Contour Global | NICG2 | 3
Contour Global | NICGA | 12
Coolkeeragh | NIC30 | 408 | [33 empty] | S | S
Coolkeeragh | NICGT8 | 53 | [21 empty] | S | [17 empty] | S | S | S | S
Empower | NIEMP | 3
Endeco Technologies | NIECA | 13
Energy Trading | NIETB | 9
Energy Trading | NIETD | 5
Energy Trading | NIETR | 19
iPower | NIAGU | 74
Kilroot | NIK1 | 256 | [15 empty] | S | S | S | S | S | S | S | S | S | S | [16 empty] | S
Kilroot | NIK2 | 258 |  |  |  |  | S | S | S | S | S | S | S | S | S | F | F
Kilroot | NIKGT1 | 29 | [22 empty] | S | S | S
Kilroot | NIKGT2 | 29
Kilroot | NIKGT3 | 42 | [41 empty] | S
Kilroot | NIKGT4 | 42 | [41 empty] | S
Lisahally | NILPS | 18 | [11 empty] | S | S | S | S
Moyle | MOYLE | 450 | [23 empty] | S | S
Powerhouse Generation | NIPH1 | 34

## SONI Outages
Upcoming Outages including STMOs and Annual Outages
Station | Unit | NPR | Start Date | End Date | Value | Duration
Ballylumford | NIB4 | 144 | 2018-11-14 | 2101-01-01 | F | 29998
Ballylumford | NIB5 | 147 | 2019-01-01 | 2101-01-01 | F | 29950
Ballylumford | NIB32 | 249 | 2019-01-11 19:00 | 2019-01-14 19:00 | S | 3
Ballylumford | NIB10 | 94 | 2019-01-14 19:00 | 2019-01-21 19:00 | S | 7
Coolkeeragh | NICGT8 | 53 | 2019-01-15 06:00 | 2019-01-16 02:00 | 26 | 0.83
Coolkeeragh | NICGT8 | 53 | 2019-01-16 02:00 | 2019-01-17 20:00 | S | 1.75
Kilroot | NIK2 | 258 | 2019-01-17 21:00 | 2019-01-21 | F | 3.08
Kilroot | NIK1 | 256 | 2019-01-18 | 2019-01-21 | F | 3
Coolkeeragh | NIC30 | 408 | 2019-01-23 04:30 | 2019-01-24 22:00 | F | 1.71
Kilroot | NIK2 | 258 | 2019-01-25 12:30 | 2019-01-30 20:30 | F | 5.33
Kilroot | NIK2 | 258 | 2019-01-30 20:00 | 2019-03-29 20:00 | S | 58
Kilroot | NIK1 | 256 | 2019-02-01 20:00 | 2019-02-04 06:00 | S | 2.42
Contour Global | NICGA | 12.08 | 2019-02-02 06:00 | 2019-02-06 20:00 | S | 4.58
Kilroot | NIK1 | 256 | 2019-02-14 13:30 | 2019-02-16 13:30 | F | 2
Coolkeeragh | NICGT8 | 53 | 2019-02-21 06:00 | 2019-02-21 16:30 | S | 0.42
Ballylumford | NIBGT2 | 58 | 2019-03-05 08:00 | 2019-03-05 16:00 | S | 0.33
Ballylumford | NIBGT1 | 58 | 2019-03-05 08:00 | 2019-03-05 16:00 | S | 0.33
Ballylumford | NIB10 | 94 | 2019-03-11 19:00 | 2019-03-13 02:00 | S | 1.25
Coolkeeragh | NICGT8 | 53 | 2019-03-14 06:00 | 2019-03-14 18:00 | S | 0.5
Lisahally | NILPS | 17.6 | 2019-03-19 20:00 | 2019-04-17 23:30 | S | 29.12
Kilroot | NIK2 | 258 | 2019-03-29 20:00 | 2019-04-16 06:30 | F | 17.42
Ballylumford | NIBGT1 | 58 | 2019-04-03 08:30 | 2019-04-03 11:30 | S | 0.08
Ballylumford | NIBGT2 | 58 | 2019-04-03 11:30 | 2019-04-03 15:30 | S | 0.17
Kilroot | NIKGT2 | 29 | 2019-04-05 09:00 | 2019-04-10 20:30 | S | 5.46
Coolkeeragh | NIC30 | 408 | 2019-04-07 21:30 | 2019-04-09 18:30 | F | 1.83
Kilroot | NIK1 | 256 | 2019-04-10 17:00 | 2019-04-11 17:30 | F | 1
Kilroot | NIKGT2 | 29 | 2019-04-10 20:00 | 2019-04-13 12:00 | F | 2.67
Kilroot | NIK1 | 256 | 2019-04-16 12:00 | 2019-06-26 16:30 | S | 71.17
Kilroot | NIK2 | 258 | 2019-04-17 08:30 | 2019-04-19 08:00 | F | 1.96
Kilroot | NIK2 | 258 | 2019-04-22 11:00 | 2019-04-26 01:30 | F | 3.58
Kilroot | NIK2 | 258 | 2019-05-05 04:00 | 2019-05-06 04:00 | S | 1
Kilroot | NIK2 | 258 | 2019-05-08 20:00 | 2019-05-09 22:00 | S | 1.08
Coolkeeragh | NIC30 | 408 | 2019-05-10 16:00 | 2019-05-14 16:00 | S | 4
Kilroot | NIKGT3 | 42 | 2019-05-15 08:00 | 2019-05-15 12:00 | S | 0.17
Kilroot | NIK2 | 258 | 2019-05-15 22:00 | 2019-05-16 06:00 | S | 0.33
Kilroot | NIKGT4 | 42 | 2019-05-17 07:30 | 2019-05-17 12:30 | S | 0.17
Ballylumford | NIB10 | 94 | 2019-05-17 19:00 | 2019-05-19 01:00 | S | 1.25
Coolkeeragh | NICGT8 | 53 | 2019-05-28 06:00 | 2019-06-01 18:00 | S | 4.5
Ballylumford | NIB31 | 249 | 2019-05-31 15:00 | 2019-06-04 | 160 | 3.33
Ballylumford | NIB32 | 249 | 2019-05-31 15:00 | 2019-06-04 | 160 | 3.33
Kilroot | NIK2 | 258 | 2019-05-31 15:30 | 2019-06-01 00:30 | F | 0.33
Kilroot | NIKGT1 | 29 | 2019-06-03 08:00 | 2019-06-26 16:00 | S | 23.33
Ballylumford | NIB32 | 249 | 2019-06-04 | 2019-06-08 12:30 | 161 | 4.5
Ballylumford | NIB31 | 249 | 2019-06-04 | 2019-06-08 12:30 | 161 | 4.5
Kilroot | NIK2 | 258 | 2019-06-05 14:00 | 2019-06-06 00:30 | F | 0.42
Moyle | MOYLE | 450 | 2019-06-11 23:00 | 2019-06-20 23:00 | S | 9
Kilroot | NIK2 | 258 | 2019-06-24 23:00 | 2019-06-26 03:30 | F | 1.17
Ballylumford | NIB31 | 249 | 2019-06-26 06:00 | 2019-06-29 06:30 | S | 3
Ballylumford | NIB32 | 249 | 2019-06-27 19:00 | 2019-06-30 19:00 | S | 3
Ballylumford | NIB31 | 249 | 2019-06-28 19:00 | 2019-07-05 19:00 | 161 | 7
Ballylumford | NIB32 | 249 | 2019-06-30 19:00 | 2019-07-05 19:00 | 161 | 5
Ballylumford | NIB32 | 249 | 2019-07-05 19:00 | 2019-07-12 19:00 | S | 7
Ballylumford | NIB31 | 249 | 2019-07-05 19:00 | 2019-07-12 19:00 | S | 7
Ballylumford | NIB10 | 94 | 2019-07-05 19:00 | 2019-07-12 19:00 | S | 7
Ballylumford | NIB31 | 249 | 2019-07-12 19:00 | 2019-07-29 19:00 | 161 | 17
Ballylumford | NIB32 | 249 | 2019-07-12 19:00 | 2019-08-08 19:00 | 161 | 27
Ballylumford | NIB10 | 94 | 2019-07-16 22:00 | 2019-08-07 22:00 | F | 22
Kilroot | NIKGT1 | 29 | 2019-07-17 06:00 | 2019-07-17 16:00 | S | 0.42
Kilroot | NIKGT4 | 42 | 2019-07-18 06:00 | 2019-07-18 13:00 | S | 0.25
Ballylumford | NIB31 | 249 | 2019-07-29 19:00 | 2019-08-11 19:00 | 161 | 13
Ballylumford | NIB32 | 249 | 2019-08-08 19:00 | 2019-08-11 19:00 | 161 | 3
Ballylumford | NIB31 | 249 | 2019-08-11 18:30 | 2019-09-14 | 161 | 33.21
Ballylumford | NIB32 | 249 | 2019-08-11 18:30 | 2019-08-29 06:00 | 161 | 17.46
Ballylumford | NIB31 | 249 | 2019-08-16 | 2019-08-19 | S | 3
Coolkeeragh | NIC30 | 408 | 2019-08-21 22:00 | 2019-08-31 22:00 | S | 10
Ballylumford | NIB32 | 249 | 2019-08-23 | 2019-08-26 | S | 3
Ballylumford | NIB32 | 249 | 2019-09-08 14:00 | 2019-09-14 | S | 5.42
Kilroot | NIK1 | 256 | 2019-09-12 00:30 | 2019-09-16 | F | 3.96
Coolkeeragh | NIC30 | 408 | 2019-09-15 09:30 | 2019-09-17 13:00 | F | 2.12
Kilroot | NIK2 | 258 | 2019-09-16 03:30 | 2019-09-19 09:30 | F | 3.25
Ballylumford | NIB10 | 94 | 2019-09-24 21:00 | 2019-09-25 07:30 | F | 0.42
Coolkeeragh | NICGT8 | 53 | 2019-09-27 08:00 | 2019-09-27 17:30 | S | 0.38
Coolkeeragh | NICGT8 | 53 | 2019-09-30 08:00 | 2019-10-27 17:30 | S | 27.38
Ballylumford | NIB32 | 249 | 2019-10-01 20:00 | 2019-10-07 20:00 | S | 6
Ballylumford | NIB31 | 249 | 2019-10-01 20:00 | 2019-10-07 21:00 | 161 | 6
Kilroot | NIKGT3 | 42 | 2019-10-14 08:00 | 2019-10-18 18:30 | S | 4.42
Kilroot | NIKGT4 | 42 | 2019-10-14 08:00 | 2019-10-18 18:30 | S | 4.42
Kilroot | NIK1 | 256 | 2019-10-15 20:00 | 2019-10-20 20:00 | S | 5
Ballylumford | NIBGT1 | 58 | 2019-10-16 10:00 | 2019-10-16 13:00 | 29 | 0.08
Ballylumford | NIBGT1 | 58 | 2019-10-21 06:00 | 2019-10-26 18:00 | S | 5.5
Kilroot | NIKGT3 | 42 | 2019-11-01 06:00 | 2019-11-01 14:30 | S | 0.33
Kilroot | NIKGT4 | 42 | 2019-11-04 08:00 | 2019-11-04 14:30 | S | 0.25
Kilroot | NIKGT3 | 42 | 2019-11-05 06:00 | 2019-11-08 06:00 | S | 3
Kilroot | NIKGT4 | 42 | 2019-11-06 08:00 | 2019-11-06 16:30 | S | 0.33
Kilroot | NIKGT4 | 42 | 2019-11-08 06:00 | 2019-11-11 06:00 | S | 3
Kilroot | NIK2 | 258 | 2019-11-11 22:00 | 2019-11-12 23:00 | S | 1
Coolkeeragh | NICGT8 | 53 | 2019-11-13 10:00 | 2019-11-13 16:30 | S | 0.25
Ballylumford | NIBGT2 | 58 | 2019-11-20 10:00 | 2019-11-20 13:00 | 29 | 0.08
Coolkeeragh | NIC30 | 408 | 2019-11-23 | 2019-11-25 | S | 2
Ballylumford | NIBGT2 | 58 | 2019-11-24 06:00 | 2019-11-29 18:00 | S | 5.5
Kilroot | NIKGT1 | 29 | 2019-11-28 10:30 | 2019-11-28 15:00 | S | 0.17
Kilroot | NIKGT2 | 29 | 2019-11-29 10:30 | 2019-11-29 15:00 | S | 0.17
Kilroot | NIKGT1 | 29 | 2019-12-03 06:00 | 2019-12-06 06:00 | S | 3
Kilroot | NIKGT2 | 29 | 2019-12-10 06:00 | 2019-12-13 06:00 | S | 3
|  |  | Scheduled Outage | S
|  |  | Forced Outage | F
|  |  | Unit partially available | 10

## Outage Plan All Island
2019 GENERATION OUTAGE PLAN (All Island)
|  | Month | Jan '2019 |  |  |  |  | Feb '2019 |  |  |  | Mar '2019 |  |  |  | Apr '2019 |  |  |  |  | May '2019 |  |  |  | Jun '2019 |  |  |  | Jul '2019 |  |  |  |  | Aug '2019 |  |  |  | Sep '2019 |  |  |  |  | Oct '2019 |  |  |  | Nov '2019 |  |  |  | Dec '2019
|  | Week | 1 '2019 | 2 '2019 | 3 '2019 | 4 '2019 | 5 '2019 | 6 '2019 | 7 '2019 | 8 '2019 | 9 '2019 | 10 '2019 | 11 '2019 | 12 '2019 | 13 '2019 | 14 '2019 | 15 '2019 | 16 '2019 | 17 '2019 | 18 '2019 | 19 '2019 | 20 '2019 | 21 '2019 | 22 '2019 | 23 '2019 | 24 '2019 | 25 '2019 | 26 '2019 | 27 '2019 | 28 '2019 | 29 '2019 | 30 '2019 | 31 '2019 | 32 '2019 | 33 '2019 | 34 '2019 | 35 '2019 | 36 '2019 | 37 '2019 | 38 '2019 | 39 '2019 | 40 '2019 | 41 '2019 | 42 '2019 | 43 '2019 | 44 '2019 | 45 '2019 | 46 '2019 | 47 '2019 | 48 '2019 | 49 '2019 | 50 '2019 | 51 '2019 | 52 '2019 | 1 '2020
Station | Unit | NPR
AC Automation | NIACA | 8
Activation Energy | AE1 | 95
Activation Energy | AE2 | 8
Activation Energy | AE3 | 14
Activation Energy | AE4 | 15
Activation Energy | AE5 | 15
Activation Energy | EN5 | 6
Activation Energy | EN6 | 11
Activation Energy | NIAEA | 9
Aghada | AD2 | 431 | [34 empty] | S | S | S | S | S | S | S | S | S | F | F
Aghada | AT1 | 90
Aghada | AT2 | 90
Aghada | AT4 | 90
Ardnacrusha | AA1 | 21 | [14 empty] | S
Ardnacrusha | AA2 | 22 | [34 empty] | S | S | S
Ardnacrusha | AA3 | 19 | [20 empty] | S
Ardnacrusha | AA4 | 24 | [36 empty] | F | F | S
Ballylumford | NIB10 | 94 |  |  | S | [25 empty] | F | F | F
Ballylumford | NIB31 | 249
Ballylumford | NIB32 | 249 | [36 empty] | S |  |  | S
Ballylumford | NIB4 | 144 | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F
Ballylumford | NIB5 | 147 | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F
Ballylumford | NIBGT1 | 58 | [42 empty] | S
Ballylumford | NIBGT2 | 58 | [47 empty] | S
Contour Global | NICG2 | 3
Contour Global | NICGA | 12
Coolkeeragh | NIC30 | 408 | [33 empty] | S | S
Coolkeeragh | NICGT8 | 53 | [21 empty] | S | [17 empty] | S | S | S | S
DAE Virtual Power Plant | DP1 | 19
DAE Virtual Power Plant | DP2 | 26
Dublin Bay | DB1 | 405 | [12 empty] | S | S | S | F
Dublin Waste To Energy | DW1 | 62 | [9 empty] | S
Edenderry | ED1 | 118 | [23 empty] | S | S | S | S | S | S | S | S | S | [19 empty] | S | S
Edenderry | ED3 | 58
Edenderry | ED5 | 58
Electric Ireland | EI1 | 20
Electricity Exchange DSU | EE1 | 51
Electricity Exchange DSU | EE2 | 28
Electricity Exchange DSU | EE3 | 8
Electricity Exchange DSU | EE4 | 9
Electricity Exchange DSU | EE5 | 6
Empower | NIEMP | 3
Endeco Technologies | EC1 | 42
Endeco Technologies | EC2 | 11
Endeco Technologies | EC5 | 15
Endeco Technologies | NIECA | 13
Energy Trading | ET1 | 13
Energy Trading | NIETB | 9
Energy Trading | NIETD | 5
Energy Trading | NIETR | 19
Erne | ER1 | 10 | F | F | [25 empty] | S | [7 empty] | S
Erne | ER2 | 10 |  | F | [32 empty] | F | S
Erne | ER3 | 22 | [19 empty] | S
Erne | ER4 | 22 | [23 empty] | S | S | S
EWIC | EW1 | 500 | [18 empty] | S
Great Island | GI4 | 461 | F | F | F | F | F | F | [14 empty] | F
Huntstown | HN2 | 400 | [11 empty] | F | F | F | F | F | F
Huntstown | HNC | 342 | [32 empty] | S | S | F | F | F | F | F
Indaver | IW1 | 17 | [13 empty] | S | S
iPower | NIAGU | 74
Kilroot | NIK1 | 256 | [15 empty] | S | S | S | S | S | S | S | S | S | S | [16 empty] | S
Kilroot | NIK2 | 258 |  |  |  |  | S | S | S | S | S | S | S | S | S | F | F
Kilroot | NIKGT1 | 29 | [22 empty] | S | S | S
Kilroot | NIKGT2 | 29
Kilroot | NIKGT3 | 42 | [41 empty] | S
Kilroot | NIKGT4 | 42 | [41 empty] | S
Knockacummer | KC1 | 100
Lanesboro | LR4 | 91 | [24 empty] | S | S | S | F | F | F | F | F | F | F | F | F | F | F
Lee | LE1 | 15 |  | F | [16 empty] | S | S | S
Lee | LE2 | 4 | [13 empty] | S | [5 empty] | S | S
Lee | LE3 | 8 | [22 empty] | S | S | S
Liffey | LI1 | 15 | [18 empty] | F | F
Liffey | LI2 | 15 | [18 empty] | F | F
Liffey | LI4 | 4
Liffey | LI5 | 4
Lisahally | NILPS | 18 | [11 empty] | S | S | S | S
Moneypoint | MP1 | 285 | F | F | [37 empty] | F | F | F
Moneypoint | MP2 | 285 | F | F | F | F | F | F | F | F | F | F | F | F | [14 empty] | F |  |  |  | S | S | S | S | S | F | F | F
Moneypoint | MP3 | 285 | F | [9 empty] | F | [27 empty] | F | F | F | F | F | F | F | F | F | F | F | F
Moyle | MOYLE | 450 | [23 empty] | S | S
North Wall | NW5 | 104 | [39 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Poolbeg | PB4 | 154 | [7 empty] | S | [22 empty] | S |  |  |  |  | S | S | S | S | S | S
Poolbeg | PB5 | 146 | [30 empty] | S |  |  |  |  | S |  |  |  | S
Poolbeg | PB6 | 168 | [10 empty] | F | [19 empty] | S |  |  |  |  | S | S |  |  | S
Powerhouse Generation | NIPH1 | 34
Powerhouse Generation | PG1 | 11
Rhode | RP1 | 52 | [29 empty] | F | F | F | S
Rhode | RP2 | 52 | [29 empty] | F | F | F | S
Seal Rock | SK3 | 85 | [31 empty] | F | [6 empty] | S
Seal Rock | SK4 | 85 | [26 empty] | S | S | S
Seecon | SO1 | 105
Tarbert | TB1 | 54 | [19 empty] | S
Tarbert | TB2 | 54 | [19 empty] | S
Tarbert | TB3 | 241 | [23 empty] | S | F | F | F | F | F | F | F | F | F
Tarbert | TB4 | 243 |  | F | [25 empty] | F
Tawnaghmore | TP1 | 52
Tawnaghmore | TP3 | 52
Turlough Hill | TH1 | 73 | [20 empty] | S | S | S | S
Turlough Hill | TH2 | 73 | [20 empty] | S | S | S | S
Turlough Hill | TH3 | 73 | [16 empty] | F | F |  |  | S | S | S | S
Turlough Hill | TH4 | 73 | [20 empty] | S | S | S | S
Tynagh | TYC | 384 | [22 empty] | F | F
Viridian Energy | VE1 | 20
Viridian Energy DSU | VE2 | 13
West Offaly | WO4 | 137 | [18 empty] | S | S | S | F
Whitegate | WG1 | 444 | F | [28 empty] | S | S | S

## All Island Outages
Upcoming Outages including STMOs and Annual Outages
Station | Unit | NPR | Start Date | End Date | Value | Duration
Moneypoint | MP2 | 285 | 2018-09-26 23:00 | 2019-03-27 12:00 | F | 181.5
Moneypoint | MP1 | 285 | 2018-10-01 | 2019-01-16 12:00 | F | 107.5
Great Island | GI4 | 461 | 2018-10-25 | 2019-01-21 18:30 | F | 88.75
Ballylumford | NIB4 | 144 | 2018-11-14 | 2101-01-01 | F | 29998
Erne | ER1 | 10 | 2018-12-13 14:30 | 2019-01-15 18:00 | F | 33.12
Moneypoint | MP3 | 285 | 2018-12-24 | 2019-01-07 16:30 | F | 14.67
Whitegate | WG1 | 444 | 2018-12-24 | 2019-01-05 23:00 | F | 12.92
Edenderry | ED1 | 118 | 2018-12-26 12:00 | 2019-01-02 08:00 | S | 6.83
Ballylumford | NIB5 | 147 | 2019-01-01 | 2101-01-01 | F | 29950
Rhode | RP1 | 52 | 2019-01-03 13:00 | 2019-01-03 18:30 | F | 0.21
EWIC | EW1 | 500 | 2019-01-04 09:00 | 2019-01-05 23:00 | F | 1.58
Tarbert | TB4 | 243 | 2019-01-06 19:30 | 2019-01-14 17:00 | F | 7.88
Moneypoint | MP3 | 285 | 2019-01-07 20:30 | 2019-01-08 16:00 | F | 0.79
Lee | LE1 | 15 | 2019-01-09 08:30 | 2019-01-16 | F | 6.62
Erne | ER2 | 10 | 2019-01-09 08:30 | 2019-01-14 | F | 4.62
Moneypoint | MP3 | 285 | 2019-01-10 05:30 | 2019-01-11 18:00 | 180 | 1.5
Turlough Hill | TH4 | 73 | 2019-01-11 11:00 | 2019-01-11 12:30 | S | 0.04
Ballylumford | NIB32 | 249 | 2019-01-11 19:00 | 2019-01-14 19:00 | S | 3
Moneypoint | MP3 | 285 | 2019-01-12 16:30 | 2019-01-16 18:00 | 160 | 4.04
Ballylumford | NIB10 | 94 | 2019-01-14 19:00 | 2019-01-21 19:00 | S | 7
Coolkeeragh | NICGT8 | 53 | 2019-01-15 06:00 | 2019-01-16 02:00 | 26 | 0.83
Turlough Hill | TH3 | 73 | 2019-01-15 08:00 | 2019-01-15 18:00 | S | 0.42
Coolkeeragh | NICGT8 | 53 | 2019-01-16 02:00 | 2019-01-17 20:00 | S | 1.75
Moneypoint | MP3 | 285 | 2019-01-16 18:00 | 2019-01-20 18:00 | 210 | 4
Moneypoint | MP1 | 285 | 2019-01-17 | 2019-01-20 23:00 | 150 | 3.92
Lee | LE1 | 15 | 2019-01-17 06:00 | 2019-01-20 18:00 | F | 3.5
Ardnacrusha | AA4 | 24 | 2019-01-17 08:00 | 2019-01-17 17:00 | S | 0.33
North Wall | NW5 | 104 | 2019-01-17 17:30 | 2019-01-18 10:00 | F | 0.67
Kilroot | NIK2 | 258 | 2019-01-17 21:00 | 2019-01-21 | F | 3.08
Kilroot | NIK1 | 256 | 2019-01-18 | 2019-01-21 | F | 3
Moneypoint | MP3 | 285 | 2019-01-19 07:30 | 2019-01-21 16:30 | 200 | 2.33
Moneypoint | MP1 | 285 | 2019-01-19 09:00 | 2019-01-21 16:30 | 200 | 2.29
Dublin Bay | DB1 | 405 | 2019-01-19 22:00 | 2019-01-22 | F | 2.08
Great Island | GI4 | 461 | 2019-01-21 18:30 | 2019-02-12 23:00 | F | 22.17
Moneypoint | MP3 | 285 | 2019-01-22 06:00 | 2019-01-22 18:00 | 170 | 0.5
Moneypoint | MP1 | 285 | 2019-01-22 07:30 | 2019-01-22 18:00 | 140 | 0.42
Coolkeeragh | NIC30 | 408 | 2019-01-23 04:30 | 2019-01-24 22:00 | F | 1.71
North Wall | NW5 | 104 | 2019-01-25 07:00 | 2019-01-27 17:00 | S | 2.42
Kilroot | NIK2 | 258 | 2019-01-25 12:30 | 2019-01-30 20:30 | F | 5.33
Whitegate | WG1 | 444 | 2019-01-26 11:30 | 2019-01-28 21:00 | F | 2.38
Erne | ER4 | 22.5 | 2019-01-26 20:00 | 2019-01-31 13:00 | F | 4.67
Tawnaghmore | TP3 | 52 | 2019-01-30 20:00 | 2019-01-31 12:00 | F | 0.67
Kilroot | NIK2 | 258 | 2019-01-30 20:00 | 2019-03-29 20:00 | S | 58
Turlough Hill | TH2 | 73 | 2019-01-31 08:00 | 2019-01-31 13:00 | S | 0.17
Liffey | LI2 | 15 | 2019-01-31 18:00 | 2019-02-01 10:00 | F | 0.67
Kilroot | NIK1 | 256 | 2019-02-01 20:00 | 2019-02-04 06:00 | S | 2.42
Contour Global | NICGA | 12.08 | 2019-02-02 06:00 | 2019-02-06 20:00 | S | 4.58
Turlough Hill | TH3 | 73 | 2019-02-07 00:30 | 2019-02-07 09:00 | F | 0.33
Turlough Hill | TH4 | 73 | 2019-02-14 08:00 | 2019-02-14 13:00 | S | 0.17
Kilroot | NIK1 | 256 | 2019-02-14 13:30 | 2019-02-16 13:30 | F | 2
EWIC | EW1 | 500 | 2019-02-16 09:00 | 2019-02-17 23:00 | S | 1.58
Seal Rock | SK3 | 85 | 2019-02-17 07:00 | 2019-02-20 17:00 | S | 3.42
Poolbeg | PB4 | 154 | 2019-02-19 | 2019-02-24 | S | 5
Poolbeg | PB6 | 168 | 2019-02-19 | 2019-02-24 | 84 | 5
Seal Rock | SK3 | 85 | 2019-02-20 17:00 | 2019-02-21 14:00 | F | 0.83
Coolkeeragh | NICGT8 | 53 | 2019-02-21 06:00 | 2019-02-21 16:30 | S | 0.42
Turlough Hill | TH1 | 73 | 2019-02-21 08:00 | 2019-02-21 13:00 | S | 0.17
Great Island | GI4 | 461 | 2019-02-22 16:30 | 2019-02-25 08:00 | F | 2.62
Tarbert | TB3 | 241 | 2019-02-27 08:00 | 2019-03-01 17:00 | S | 2.33
Great Island | GI4 | 461 | 2019-03-01 23:00 | 2019-03-03 23:00 | F | 2
Dublin Waste To Energy | DW1 | 61.5 | 2019-03-03 | 2019-03-07 | 26 | 4
Seal Rock | SK4 | 85 | 2019-03-03 07:00 | 2019-03-05 17:00 | S | 2.42
Ballylumford | NIBGT2 | 58 | 2019-03-05 08:00 | 2019-03-05 16:00 | S | 0.33
Ballylumford | NIBGT1 | 58 | 2019-03-05 08:00 | 2019-03-05 16:00 | S | 0.33
Dublin Waste To Energy | DW1 | 61.5 | 2019-03-07 | 2019-03-12 | S | 5
Great Island | GI4 | 461 | 2019-03-08 23:30 | 2019-03-10 23:00 | F | 1.96
Moneypoint | MP3 | 285 | 2019-03-09 20:00 | 2019-03-16 22:00 | F | 7.08
Poolbeg | PB6 | 168 | 2019-03-10 23:00 | 2019-03-20 23:00 | F | 10
Ballylumford | NIB10 | 94 | 2019-03-11 19:00 | 2019-03-13 02:00 | S | 1.25
Dublin Waste To Energy | DW1 | 61.5 | 2019-03-12 | 2019-03-14 | F | 2
Moneypoint | MP1 | 285 | 2019-03-14 | 2019-03-15 | 200 | 1
Coolkeeragh | NICGT8 | 53 | 2019-03-14 06:00 | 2019-03-14 18:00 | S | 0.5
Great Island | GI4 | 461 | 2019-03-15 16:30 | 2019-03-21 23:30 | 400 | 6.25
Great Island | GI4 | 461 | 2019-03-15 22:30 | 2019-03-16 19:00 | F | 0.83
Indaver | IW1 | 17 | 2019-03-18 09:00 | 2019-03-19 22:00 | F | 1.5
Moneypoint | MP1 | 285 | 2019-03-19 08:00 | 2019-04-08 | 200 | 19.67
Lisahally | NILPS | 17.6 | 2019-03-19 20:00 | 2019-04-17 23:30 | S | 29.12
Dublin Bay | DB1 | 405 | 2019-03-19 22:00 | 2019-03-22 13:00 | F | 2.58
Huntstown | HN2 | 400 | 2019-03-20 | 2019-04-29 | F | 40
Liffey | LI4 | 4 | 2019-03-20 07:30 | 2019-03-21 | F | 0.67
Aghada | AT1 | 90 | 2019-03-21 08:00 | 2019-03-21 15:00 | S | 0.25
Turlough Hill | TH3 | 73 | 2019-03-22 08:00 | 2019-03-22 13:00 | F | 0.17
Dublin Bay | DB1 | 405 | 2019-03-22 13:00 | 2019-04-14 13:00 | S | 23
Turlough Hill | TH2 | 73 | 2019-03-26 08:00 | 2019-03-26 19:00 | F | 0.42
Turlough Hill | TH3 | 73 | 2019-03-28 11:00 | 2019-03-28 13:00 | F | 0.08
Kilroot | NIK2 | 258 | 2019-03-29 20:00 | 2019-04-16 06:30 | F | 17.42
Indaver | IW1 | 17 | 2019-04-01 05:00 | 2019-04-17 11:00 | S | 16.25
Lee | LE2 | 4 | 2019-04-01 08:00 | 2019-04-05 20:00 | S | 4.5
Liffey | LI1 | 15 | 2019-04-02 08:00 | 2019-04-04 17:00 | S | 2.33
Liffey | LI2 | 15 | 2019-04-02 08:00 | 2019-04-04 17:00 | S | 2.33
Ballylumford | NIBGT1 | 58 | 2019-04-03 08:30 | 2019-04-03 11:30 | S | 0.08
Ballylumford | NIBGT2 | 58 | 2019-04-03 11:30 | 2019-04-03 15:30 | S | 0.17
Kilroot | NIKGT2 | 29 | 2019-04-05 09:00 | 2019-04-10 20:30 | S | 5.46
Lee | LE2 | 4 | 2019-04-05 20:00 | 2019-04-12 08:00 | F | 6.5
Coolkeeragh | NIC30 | 408 | 2019-04-07 21:30 | 2019-04-09 18:30 | F | 1.83
Ardnacrusha | AA1 | 21 | 2019-04-08 08:00 | 2019-04-12 20:00 | S | 4.5
Liffey | LI4 | 4 | 2019-04-09 08:00 | 2019-04-11 17:00 | S | 2.33
Ardnacrusha | AA2 | 22 | 2019-04-10 08:00 | 2019-04-10 17:00 | S | 0.33
Kilroot | NIK1 | 256 | 2019-04-10 17:00 | 2019-04-11 17:30 | F | 1
Kilroot | NIKGT2 | 29 | 2019-04-10 20:00 | 2019-04-13 12:00 | F | 2.67
Huntstown | HNC | 342 | 2019-04-12 22:00 | 2019-04-14 04:00 | 220 | 1.25
Moneypoint | MP1 | 285 | 2019-04-14 11:00 | 2019-04-18 23:30 | F | 4.5
Dublin Bay | DB1 | 405 | 2019-04-14 13:00 | 2019-04-24 16:00 | F | 10.08
Moneypoint | MP2 | 285 | 2019-04-15 15:00 | 2019-05-07 17:30 | 99 | 22.08
Lee | LE2 | 4 | 2019-04-16 08:00 | 2019-04-16 17:00 | S | 0.33
Kilroot | NIK1 | 256 | 2019-04-16 12:00 | 2019-06-26 16:30 | S | 71.17
Kilroot | NIK2 | 258 | 2019-04-17 08:30 | 2019-04-19 08:00 | F | 1.96
Turlough Hill | TH2 | 73 | 2019-04-18 08:00 | 2019-04-18 13:00 | S | 0.17
Turlough Hill | TH1 | 73 | 2019-04-18 14:00 | 2019-04-18 15:00 | F | 0
Edenderry | ED1 | 118 | 2019-04-18 18:00 | 2019-04-19 23:00 | F | 1.17
Moneypoint | MP1 | 285 | 2019-04-18 23:30 | 2019-05-24 16:00 | 200 | 35.67
Tarbert | TB3 | 241 | 2019-04-19 23:00 | 2019-04-26 17:00 | 121 | 6.75
Kilroot | NIK2 | 258 | 2019-04-22 11:00 | 2019-04-26 01:30 | F | 3.58
Whitegate | WG1 | 444 | 2019-04-22 13:00 | 2019-04-25 16:00 | F | 3.08
Turlough Hill | TH3 | 73 | 2019-04-23 06:00 | 2019-05-05 12:00 | F | 12.25
Ardnacrusha | AA2 | 22 | 2019-04-23 08:00 | 2019-04-23 15:00 | S | 0.25
Great Island | GI4 | 461 | 2019-04-28 23:00 | 2019-05-02 23:00 | S | 4
Aghada | AT1 | 90 | 2019-05-01 09:00 | 2019-05-01 13:00 | S | 0.17
Great Island | GI4 | 461 | 2019-05-02 23:00 | 2019-05-03 11:00 | F | 0.5
Kilroot | NIK2 | 258 | 2019-05-05 04:00 | 2019-05-06 04:00 | S | 1
Liffey | LI2 | 15 | 2019-05-07 | 2019-05-17 18:00 | F | 10.75
Liffey | LI1 | 15 | 2019-05-07 | 2019-05-17 18:00 | F | 10.75
Lee | LE1 | 15 | 2019-05-07 08:00 | 2019-05-27 20:00 | S | 20.5
EWIC | EW1 | 500 | 2019-05-07 14:00 | 2019-05-13 23:00 | S | 6.33
Moneypoint | MP2 | 285 | 2019-05-07 17:30 | 2019-06-30 23:00 | 200 | 54.21
Whitegate | WG1 | 444 | 2019-05-08 10:00 | 2019-05-09 23:00 | F | 1.5
Kilroot | NIK2 | 258 | 2019-05-08 20:00 | 2019-05-09 22:00 | S | 1.08
West Offaly | WO4 | 137 | 2019-05-09 16:00 | 2019-05-27 16:00 | S | 18
Coolkeeragh | NIC30 | 408 | 2019-05-10 16:00 | 2019-05-14 16:00 | S | 4
Erne | ER3 | 22.5 | 2019-05-13 08:00 | 2019-05-17 20:00 | S | 4.5
Tarbert | TB1 | 54 | 2019-05-13 09:00 | 2019-05-17 17:00 | S | 4.33
Tarbert | TB2 | 54 | 2019-05-13 09:00 | 2019-05-20 09:00 | S | 7
Huntstown | HNC | 342 | 2019-05-13 10:30 | 2019-05-13 14:00 | 220 | 0.12
Seal Rock | SK3 | 85 | 2019-05-13 13:00 | 2019-05-16 19:00 | S | 3.25
Seal Rock | SK4 | 85 | 2019-05-13 18:00 | 2019-05-16 23:00 | S | 3.17
Lee | LE2 | 4 | 2019-05-14 08:00 | 2019-05-24 16:00 | S | 10.33
Kilroot | NIKGT3 | 42 | 2019-05-15 08:00 | 2019-05-15 12:00 | S | 0.17
Kilroot | NIK2 | 258 | 2019-05-15 22:00 | 2019-05-16 06:00 | S | 0.33
Huntstown | HNC | 342 | 2019-05-16 00:30 | 2019-05-16 12:00 | 229 | 0.46
Kilroot | NIKGT4 | 42 | 2019-05-17 07:30 | 2019-05-17 12:30 | S | 0.17
Edenderry | ED5 | 58 | 2019-05-17 08:00 | 2019-05-17 18:00 | S | 0.42
Edenderry | ED3 | 58 | 2019-05-17 08:00 | 2019-05-17 18:00 | S | 0.42
Ballylumford | NIB10 | 94 | 2019-05-17 19:00 | 2019-05-19 01:00 | S | 1.25
Turlough Hill | TH3 | 73 | 2019-05-17 23:30 | 2019-06-14 17:00 | S | 27.71
Turlough Hill | TH2 | 73 | 2019-05-17 23:30 | 2019-06-14 17:00 | S | 27.71
Turlough Hill | TH1 | 73 | 2019-05-17 23:30 | 2019-06-14 17:00 | S | 27.71
Huntstown | HN2 | 400 | 2019-05-18 06:00 | 2019-05-18 20:00 | S | 0.58
Turlough Hill | TH4 | 73 | 2019-05-18 11:30 | 2019-06-14 17:00 | S | 27.21
Ardnacrusha | AA3 | 19 | 2019-05-20 08:00 | 2019-05-24 20:00 | S | 4.5
Great Island | GI4 | 461 | 2019-05-20 15:30 | 2019-05-26 23:00 | F | 6.29
Moneypoint | MP1 | 285 | 2019-05-24 15:30 | 2019-05-28 17:00 | F | 4.04
Aghada | AD2 | 431 | 2019-05-24 20:00 | 2019-05-26 | S | 1.17
West Offaly | WO4 | 137 | 2019-05-27 16:00 | 2019-05-31 16:00 | F | 4
Dublin Bay | DB1 | 405 | 2019-05-27 20:00 | 2019-05-28 02:00 | S | 0.25
Coolkeeragh | NICGT8 | 53 | 2019-05-28 06:00 | 2019-06-01 18:00 | S | 4.5
Moneypoint | MP1 | 285 | 2019-05-29 07:00 | 2019-06-30 23:00 | 230 | 32.67
Dublin Bay | DB1 | 405 | 2019-05-29 10:30 | 2019-05-29 12:00 | F | 0.04
Tarbert | TB2 | 54 | 2019-05-29 17:00 | 2019-05-30 17:00 | F | 1
Tarbert | TB3 | 241 | 2019-05-30 18:30 | 2019-06-04 | 124 | 4.21
Ballylumford | NIB31 | 249 | 2019-05-31 15:00 | 2019-06-04 | 160 | 3.33
Ballylumford | NIB32 | 249 | 2019-05-31 15:00 | 2019-06-04 | 160 | 3.33
Kilroot | NIK2 | 258 | 2019-05-31 15:30 | 2019-06-01 00:30 | F | 0.33
Tynagh | TYC | 384 | 2019-05-31 23:00 | 2019-06-02 06:00 | S | 1.25
Tynagh | TYC | 384 | 2019-06-02 06:00 | 2019-06-10 23:00 | F | 8.67
Kilroot | NIKGT1 | 29 | 2019-06-03 08:00 | 2019-06-26 16:00 | S | 23.33
Ballylumford | NIB32 | 249 | 2019-06-04 | 2019-06-08 12:30 | 161 | 4.5
Ballylumford | NIB31 | 249 | 2019-06-04 | 2019-06-08 12:30 | 161 | 4.5
Lee | LE3 | 8 | 2019-06-04 08:00 | 2019-06-24 20:00 | S | 20.5
Kilroot | NIK2 | 258 | 2019-06-05 14:00 | 2019-06-06 00:30 | F | 0.42
Edenderry | ED1 | 118 | 2019-06-07 11:00 | 2019-08-10 12:00 | S | 64
Tarbert | TB3 | 241 | 2019-06-10 08:00 | 2019-06-17 08:00 | S | 7
Erne | ER4 | 22.5 | 2019-06-10 08:00 | 2019-06-30 20:00 | S | 20.5
Tynagh | TYC | 384 | 2019-06-11 19:30 | 2019-06-18 23:00 | F | 7.12
Moyle | MOYLE | 450 | 2019-06-11 23:00 | 2019-06-20 23:00 | S | 9
Turlough Hill | TH1 | 73 | 2019-06-14 17:00 | 2019-06-21 17:00 | F | 7
Turlough Hill | TH3 | 73 | 2019-06-16 15:00 | 2019-06-17 12:00 | F | 0.83
Tarbert | TB3 | 241 | 2019-06-17 08:00 | 2019-08-15 17:00 | F | 59.33
Lanesboro | LR4 | 91 | 2019-06-19 16:00 | 2019-07-07 16:00 | S | 18
Kilroot | NIK2 | 258 | 2019-06-24 23:00 | 2019-06-26 03:30 | F | 1.17
Ballylumford | NIB31 | 249 | 2019-06-26 06:00 | 2019-06-29 06:30 | S | 3
Erne | ER3 | 22.5 | 2019-06-26 09:00 | 2019-06-27 18:00 | S | 1.33
Ballylumford | NIB32 | 249 | 2019-06-27 19:00 | 2019-06-30 19:00 | S | 3
Ballylumford | NIB31 | 249 | 2019-06-28 19:00 | 2019-07-05 19:00 | 161 | 7
Seal Rock | SK4 | 85 | 2019-06-30 07:00 | 2019-07-18 07:00 | S | 18
Ballylumford | NIB32 | 249 | 2019-06-30 19:00 | 2019-07-05 19:00 | 161 | 5
Aghada | AT1 | 90 | 2019-07-01 07:00 | 2019-07-04 16:00 | S | 3.33
Poolbeg | PB6 | 168 | 2019-07-01 08:00 | 2019-07-04 16:00 | S | 3.33
Moneypoint | MP2 | 285 | 2019-07-02 10:00 | 2019-07-06 11:00 | F | 4
Ballylumford | NIB32 | 249 | 2019-07-05 19:00 | 2019-07-12 19:00 | S | 7
Ballylumford | NIB31 | 249 | 2019-07-05 19:00 | 2019-07-12 19:00 | S | 7
Ballylumford | NIB10 | 94 | 2019-07-05 19:00 | 2019-07-12 19:00 | S | 7
Turlough Hill | TH3 | 73 | 2019-07-06 09:00 | 2019-07-06 14:00 | S | 0.17
Lanesboro | LR4 | 91 | 2019-07-07 16:00 | 2019-09-23 18:00 | F | 78.08
Erne | ER1 | 10 | 2019-07-08 09:00 | 2019-07-13 18:00 | S | 5.33
Tarbert | TB4 | 243 | 2019-07-10 09:00 | 2019-07-14 17:00 | F | 4.33
Ballylumford | NIB31 | 249 | 2019-07-12 19:00 | 2019-07-29 19:00 | 161 | 17
Ballylumford | NIB32 | 249 | 2019-07-12 19:00 | 2019-08-08 19:00 | 161 | 27
Turlough Hill | TH2 | 73 | 2019-07-13 08:00 | 2019-07-13 20:00 | S | 0.5
Turlough Hill | TH2 | 73 | 2019-07-14 08:00 | 2019-07-14 20:00 | S | 0.5
Aghada | AT4 | 90 | 2019-07-16 11:30 | 2019-07-16 17:30 | S | 0.25
Ballylumford | NIB10 | 94 | 2019-07-16 22:00 | 2019-08-07 22:00 | F | 22
Kilroot | NIKGT1 | 29 | 2019-07-17 06:00 | 2019-07-17 16:00 | S | 0.42
Kilroot | NIKGT4 | 42 | 2019-07-18 06:00 | 2019-07-18 13:00 | S | 0.25
Turlough Hill | TH4 | 73 | 2019-07-18 10:30 | 2019-07-18 13:00 | S | 0.08
Turlough Hill | TH1 | 73 | 2019-07-18 10:30 | 2019-07-18 13:00 | S | 0.08
Turlough Hill | TH3 | 73 | 2019-07-18 10:30 | 2019-07-18 13:00 | S | 0.08
Turlough Hill | TH2 | 73 | 2019-07-18 10:30 | 2019-07-18 13:00 | S | 0.08
Ardnacrusha | AA4 | 24 | 2019-07-23 08:00 | 2019-07-25 20:00 | S | 2.5
Rhode | RP2 | 52 | 2019-07-23 13:30 | 2019-07-26 17:00 | F | 3.12
Rhode | RP2 | 52 | 2019-07-24 16:00 | 2019-08-09 17:00 | F | 16
Rhode | RP1 | 52 | 2019-07-24 16:00 | 2019-08-09 17:00 | F | 16
Rhode | RP1 | 52 | 2019-07-24 16:00 | 2019-07-26 17:00 | F | 2
Whitegate | WG1 | 444 | 2019-07-24 21:00 | 2019-08-09 21:00 | S | 16
Moneypoint | MP2 | 285 | 2019-07-26 22:00 | 2019-08-30 22:30 | S | 35
Poolbeg | PB5 | 146 | 2019-07-29 | 2019-08-03 | S | 5
Poolbeg | PB4 | 154 | 2019-07-29 | 2019-08-03 | S | 5
Poolbeg | PB6 | 168 | 2019-07-29 | 2019-08-03 | S | 5
Ballylumford | NIB31 | 249 | 2019-07-29 19:00 | 2019-08-11 19:00 | 161 | 13
West Offaly | WO4 | 137 | 2019-08-02 17:00 | 2019-08-14 17:00 | 48 | 12
Seal Rock | SK3 | 85 | 2019-08-05 22:00 | 2019-08-09 22:00 | F | 4
Turlough Hill | TH1 | 73 | 2019-08-06 09:00 | 2019-08-06 13:00 | S | 0.17
Turlough Hill | TH3 | 73 | 2019-08-07 09:00 | 2019-08-07 13:00 | S | 0.17
Turlough Hill | TH4 | 73 | 2019-08-07 13:00 | 2019-08-07 17:00 | S | 0.17
Ballylumford | NIB32 | 249 | 2019-08-08 19:00 | 2019-08-11 19:00 | 161 | 3
Ballylumford | NIB31 | 249 | 2019-08-11 18:30 | 2019-09-14 | 161 | 33.21
Ballylumford | NIB32 | 249 | 2019-08-11 18:30 | 2019-08-29 06:00 | 161 | 17.46
Huntstown | HNC | 342 | 2019-08-12 | 2019-08-28 22:00 | S | 16.92
Rhode | RP1 | 52 | 2019-08-12 09:00 | 2019-08-19 17:00 | S | 7.33
Rhode | RP2 | 52 | 2019-08-12 09:00 | 2019-08-19 17:00 | S | 7.33
Turlough Hill | TH2 | 73 | 2019-08-13 09:00 | 2019-08-13 13:00 | S | 0.17
Whitegate | WG1 | 444 | 2019-08-15 11:00 | 2019-08-16 23:00 | F | 1.5
Ballylumford | NIB31 | 249 | 2019-08-16 | 2019-08-19 | S | 3
Turlough Hill | TH1 | 73 | 2019-08-17 08:00 | 2019-08-17 20:00 | S | 0.5
Turlough Hill | TH1 | 73 | 2019-08-18 08:00 | 2019-08-18 20:00 | S | 0.5
EWIC | EW1 | 500 | 2019-08-19 08:00 | 2019-08-20 23:00 | S | 1.58
Coolkeeragh | NIC30 | 408 | 2019-08-21 22:00 | 2019-08-31 22:00 | S | 10
Ballylumford | NIB32 | 249 | 2019-08-23 | 2019-08-26 | S | 3
Aghada | AD2 | 431 | 2019-08-23 20:00 | 2019-10-29 20:00 | S | 67
Ardnacrusha | AA2 | 22 | 2019-08-26 08:00 | 2019-09-13 20:00 | S | 18.5
Erne | ER2 | 10 | 2019-08-26 19:00 | 2019-09-02 | F | 6.17
Huntstown | HNC | 342 | 2019-08-28 22:00 | 2019-09-27 20:00 | F | 29.92
Moneypoint | MP2 | 285 | 2019-08-30 22:00 | 2019-09-20 08:00 | F | 20.42
Poolbeg | PB6 | 168 | 2019-09-01 | 2019-09-15 | S | 14
Poolbeg | PB4 | 154 | 2019-09-01 | 2019-10-12 | S | 41
Dublin Waste To Energy | DW1 | 61.5 | 2019-09-01 | 2019-09-06 | 26 | 5
Poolbeg | PB5 | 146 | 2019-09-02 | 2019-09-06 20:00 | S | 4.83
Erne | ER2 | 10 | 2019-09-02 08:00 | 2019-09-06 16:00 | S | 4.33
Erne | ER1 | 10 | 2019-09-02 08:00 | 2019-09-06 16:00 | S | 4.33
Dublin Waste To Energy | DW1 | 61.5 | 2019-09-06 | 2019-09-08 | S | 2
Dublin Waste To Energy | DW1 | 61.5 | 2019-09-08 | 2019-09-10 05:00 | F | 2.17
Ballylumford | NIB32 | 249 | 2019-09-08 14:00 | 2019-09-14 | S | 5.42
Liffey | LI5 | 4 | 2019-09-10 08:00 | 2019-09-12 17:00 | S | 2.33
Moneypoint | MP1 | 285 | 2019-09-11 04:30 | 2019-09-13 18:00 | F | 2.54
Kilroot | NIK1 | 256 | 2019-09-12 00:30 | 2019-09-16 | F | 3.96
Ardnacrusha | AA4 | 24 | 2019-09-12 05:00 | 2019-09-23 | F | 10.75
Poolbeg | PB6 | 168 | 2019-09-15 | 2019-09-30 | 84 | 15
Coolkeeragh | NIC30 | 408 | 2019-09-15 09:30 | 2019-09-17 13:00 | F | 2.12
Tynagh | TYC | 384 | 2019-09-15 23:00 | 2019-09-19 23:00 | S | 4
Kilroot | NIK2 | 258 | 2019-09-16 03:30 | 2019-09-19 09:30 | F | 3.25
North Wall | NW5 | 104 | 2019-09-18 20:00 | 2019-09-20 13:00 | F | 1.67
Tynagh | TYC | 384 | 2019-09-20 | 2019-09-23 23:00 | F | 3.92
Seal Rock | SK3 | 85 | 2019-09-23 07:00 | 2019-09-27 17:00 | S | 4.42
Ardnacrusha | AA4 | 24 | 2019-09-23 08:00 | 2019-09-27 20:00 | S | 4.5
Moneypoint | MP3 | 285 | 2019-09-23 12:00 | 2019-12-13 23:00 | F | 81.42
Ballylumford | NIB10 | 94 | 2019-09-24 21:00 | 2019-09-25 07:30 | F | 0.42
Coolkeeragh | NICGT8 | 53 | 2019-09-27 08:00 | 2019-09-27 17:30 | S | 0.38
Poolbeg | PB5 | 146 | 2019-09-30 | 2019-10-04 | S | 4
Poolbeg | PB6 | 168 | 2019-09-30 | 2019-10-04 | S | 4
Turlough Hill | TH4 | 73 | 2019-09-30 00:30 | 2019-09-30 12:00 | F | 0.46
Coolkeeragh | NICGT8 | 53 | 2019-09-30 08:00 | 2019-10-27 17:30 | S | 27.38
North Wall | NW5 | 104 | 2019-10-01 | 2022-10-01 | S | 1096
Ballylumford | NIB32 | 249 | 2019-10-01 20:00 | 2019-10-07 20:00 | S | 6
Ballylumford | NIB31 | 249 | 2019-10-01 20:00 | 2019-10-07 21:00 | 161 | 6
Moneypoint | MP1 | 285 | 2019-10-02 21:00 | 2019-10-19 18:00 | F | 16.83
Poolbeg | PB6 | 168 | 2019-10-04 | 2019-10-12 | 84 | 8
Dublin Bay | DB1 | 405 | 2019-10-07 09:00 | 2019-10-08 13:00 | F | 1.17
Turlough Hill | TH2 | 73 | 2019-10-08 21:00 | 2019-10-11 13:00 | F | 2.67
Great Island | GI4 | 461 | 2019-10-09 06:00 | 2019-10-10 12:00 | F | 1.25
Great Island | GI4 | 461 | 2019-10-11 23:00 | 2019-10-18 16:00 | F | 6.67
Poolbeg | PB6 | 168 | 2019-10-12 | 2019-10-14 22:00 | 84 | 2.92
Poolbeg | PB4 | 154 | 2019-10-12 | 2019-10-14 22:00 | F | 2.92
Kilroot | NIKGT3 | 42 | 2019-10-14 08:00 | 2019-10-18 18:30 | S | 4.42
Kilroot | NIKGT4 | 42 | 2019-10-14 08:00 | 2019-10-18 18:30 | S | 4.42
Turlough Hill | TH3 | 73 | 2019-10-14 09:00 | 2019-10-14 13:00 | S | 0.17
Lanesboro | LR4 | 91 | 2019-10-15 10:00 | 2019-10-15 14:00 | F | 0.17
Kilroot | NIK1 | 256 | 2019-10-15 20:00 | 2019-10-20 20:00 | S | 5
Ballylumford | NIBGT1 | 58 | 2019-10-16 10:00 | 2019-10-16 13:00 | 29 | 0.08
Ballylumford | NIBGT1 | 58 | 2019-10-21 06:00 | 2019-10-26 18:00 | S | 5.5
Turlough Hill | TH4 | 73 | 2019-10-23 09:00 | 2019-10-23 17:00 | S | 0.33
Turlough Hill | TH3 | 73 | 2019-10-23 09:00 | 2019-10-23 17:00 | S | 0.33
Turlough Hill | TH2 | 73 | 2019-10-23 09:00 | 2019-10-23 17:00 | S | 0.33
Turlough Hill | TH1 | 73 | 2019-10-23 09:00 | 2019-10-23 17:00 | S | 0.33
Dublin Bay | DB1 | 405 | 2019-10-25 01:00 | 2019-10-29 | S | 3.92
Aghada | AD2 | 431 | 2019-10-30 | 2019-11-07 12:00 | F | 8.5
Tynagh | TYC | 384 | 2019-10-31 01:00 | 2019-10-31 15:30 | F | 0.58
Huntstown | HNC | 342 | 2019-10-31 02:00 | 2019-11-01 18:00 | F | 1.67
Poolbeg | PB6 | 168 | 2019-10-31 05:00 | 2019-11-05 23:00 | F | 5.75
EWIC | EW1 | 500 | 2019-10-31 09:00 | 2019-11-01 23:00 | S | 1.58
Kilroot | NIKGT3 | 42 | 2019-11-01 06:00 | 2019-11-01 14:30 | S | 0.33
Edenderry | ED1 | 118 | 2019-11-02 08:00 | 2019-11-02 20:00 | 52 | 0.5
Kilroot | NIKGT4 | 42 | 2019-11-04 08:00 | 2019-11-04 14:30 | S | 0.25
Kilroot | NIKGT3 | 42 | 2019-11-05 06:00 | 2019-11-08 06:00 | S | 3
Huntstown | HN2 | 400 | 2019-11-05 23:00 | 2019-11-07 19:00 | F | 1.83
Dublin Waste To Energy | DW1 | 61.5 | 2019-11-06 05:00 | 2019-11-07 01:00 | F | 0.83
Kilroot | NIKGT4 | 42 | 2019-11-06 08:00 | 2019-11-06 16:30 | S | 0.33
Moneypoint | MP1 | 285 | 2019-11-06 10:00 | 2019-11-09 23:00 | F | 3.5
Kilroot | NIKGT4 | 42 | 2019-11-08 06:00 | 2019-11-11 06:00 | S | 3
Great Island | GI4 | 461 | 2019-11-11 15:00 | 2019-11-13 12:00 | F | 1.83
Kilroot | NIK2 | 258 | 2019-11-11 22:00 | 2019-11-12 23:00 | S | 1
Tynagh | TYC | 384 | 2019-11-12 23:00 | 2019-11-14 18:00 | F | 1.75
Coolkeeragh | NICGT8 | 53 | 2019-11-13 10:00 | 2019-11-13 16:30 | S | 0.25
Great Island | GI4 | 461 | 2019-11-14 10:30 | 2019-11-14 17:00 | F | 0.25
Tynagh | TYC | 384 | 2019-11-15 06:30 | 2019-11-16 23:00 | F | 1.67
Turlough Hill | TH4 | 73 | 2019-11-18 11:00 | 2019-11-18 13:00 | F | 0.08
Whitegate | WG1 | 444 | 2019-11-18 23:00 | 2019-11-19 06:00 | F | 0.25
Ballylumford | NIBGT2 | 58 | 2019-11-20 10:00 | 2019-11-20 13:00 | 29 | 0.08
Aghada | AD2 | 431 | 2019-11-20 15:00 | 2019-11-20 16:00 | F | 0
Aghada | AD2 | 431 | 2019-11-20 19:00 | 2019-11-21 17:00 | F | 0.92
Poolbeg | PB6 | 168 | 2019-11-20 22:00 | 2019-11-20 23:30 | 84 | 0.04
Moneypoint | MP1 | 285 | 2019-11-21 03:30 | 2019-11-21 06:30 | F | 0.08
Coolkeeragh | NIC30 | 408 | 2019-11-23 | 2019-11-25 | S | 2
Ballylumford | NIBGT2 | 58 | 2019-11-24 06:00 | 2019-11-29 18:00 | S | 5.5
Dublin Bay | DB1 | 405 | 2019-11-25 21:00 | 2019-11-26 00:30 | F | 0.12
Tarbert | TB4 | 243 | 2019-11-26 18:30 | 2019-11-29 17:00 | F | 2.92
Huntstown | HN2 | 400 | 2019-11-26 23:00 | 2019-11-28 23:00 | F | 2
Kilroot | NIKGT1 | 29 | 2019-11-28 10:30 | 2019-11-28 15:00 | S | 0.17
Kilroot | NIKGT2 | 29 | 2019-11-29 10:30 | 2019-11-29 15:00 | S | 0.17
Huntstown | HNC | 342 | 2019-12-02 23:00 | 2019-12-04 23:00 | F | 2
Kilroot | NIKGT1 | 29 | 2019-12-03 06:00 | 2019-12-06 06:00 | S | 3
Seal Rock | SK4 | 85 | 2019-12-08 08:00 | 2019-12-10 17:00 | S | 2.33
Kilroot | NIKGT2 | 29 | 2019-12-10 06:00 | 2019-12-13 06:00 | S | 3
Edenderry | ED1 | 118 | 2019-12-26 13:00 | 2020-01-02 08:00 | S | 6.75
|  |  | Scheduled Outage | S
|  |  | Forced Outage | F
|  |  | Unit partially available | 10