## Outage Plan EirGrid
2019 GENERATION OUTAGE PLAN (EIRGRID)
|  | Month | Jan '2019 |  |  |  |  | Feb '2019
|  | Week | 1 '2019 | 2 '2019 | 3 '2019 | 4 '2019 | 5 '2019 | 6 '2019 | 7 '2019 | 8 '2019 | 9 '2019
Station | Unit | NPR
Activation Energy | AE1 | 77
Activation Energy | AE2 | 8
Activation Energy | AE3 | 14
Activation Energy | AE4 | 11
Activation Energy | AE5 | 15
Activation Energy | EN5 | 6
Activation Energy | EN6 | 10
Aghada | AD2 | 431
Aghada | AT1 | 90
Aghada | AT2 | 90
Aghada | AT4 | 90
Ardnacrusha | AA1 | 21
Ardnacrusha | AA2 | 22
Ardnacrusha | AA3 | 19
Ardnacrusha | AA4 | 24
DAE Virtual Power Plant | DP1 | 19
DAE Virtual Power Plant | DP2 | 20
Dublin Bay | DB1 | 405
Dublin Waste To Energy | DW1 | 62
Edenderry | ED1 | 118
Edenderry | ED3 | 58
Edenderry | ED5 | 58
Electric Ireland | EI1 | 20
Electricity Exchange DSU | EE1 | 39
Electricity Exchange DSU | EE2 | 17
Electricity Exchange DSU | EE3 | 7
Electricity Exchange DSU | EE4 | 9
Electricity Exchange DSU | EE5 | 7
Endeco Technologies | EC1 | 37
Endeco Technologies | EC2 | 10
Endeco Technologies | EC5 | 16
Energy Trading | ET1 | 13
Erne | ER1 | 10
Erne | ER2 | 10
Erne | ER3 | 22
Erne | ER4 | 22
EWIC | EW1 | 500
Great Island | GI4 | 461
Huntstown | HN2 | 400
Huntstown | HNC | 342
Indaver | IW1 | 17
Lanesboro | LR4 | 91
Lee | LE1 | 15
Lee | LE2 | 4
Lee | LE3 | 8
Liffey | LI1 | 15
Liffey | LI2 | 15
Liffey | LI4 | 4
Liffey | LI5 | 4
Moneypoint | MP1 | 285
Moneypoint | MP2 | 285 | F | F | F | F | F | F | F | F | F
Moneypoint | MP3 | 285
North Wall | NW5 | 104
Poolbeg | PB4 | 154
Poolbeg | PB5 | 146
Poolbeg | PB6 | 168
Powerhouse Generation | PG1 | 11
Rhode | RP1 | 52
Rhode | RP2 | 52
Seal Rock | SK3 | 85
Seal Rock | SK4 | 85
Tarbert | TB1 | 54
Tarbert | TB2 | 54
Tarbert | TB3 | 241
Tarbert | TB4 | 243
Tawnaghmore | TP1 | 52
Tawnaghmore | TP3 | 52
Turlough Hill | TH1 | 73
Turlough Hill | TH2 | 73
Turlough Hill | TH3 | 73
Turlough Hill | TH4 | 73
Tynagh | TYC | 384
Viridian Energy | VE1 | 19
Viridian Energy DSU | VE2 | 6
West Offaly | WO4 | 137
Whitegate | WG1 | 444

## EirGrid Outages
Upcoming Outages including STMOs and Annual Outages
Station | Unit | NPR | Start Date | End Date | Value | Duration
Moneypoint | MP2 | 285 | 2018-09-26 23:00 | 2019-04-05 18:00 | F | 190.75
Edenderry | ED1 | 118 | 2018-12-26 12:00 | 2019-01-02 08:00 | S | 6.83
Seal Rock | SK3 | 85 | 2019-01-13 07:00 | 2019-01-15 17:00 | S | 2.42
EWIC | EW1 | 500 | 2019-02-16 12:00 | 2019-02-17 23:00 | S | 1.42
|  |  | Scheduled Outage | S
|  |  | Forced Outage | F
|  |  | Unit partially available | 10

## Outage Plan SONI
2019 GENERATION OUTAGE PLAN (SONI)
|  | Month | Jan '2019 |  |  |  |  | Feb '2019
|  | Week | 1 '2019 | 2 '2019 | 3 '2019 | 4 '2019 | 5 '2019 | 6 '2019 | 7 '2019 | 8 '2019 | 9 '2019
Station | Unit | NPR
AC Automation | NIACA | 8
Activation Energy | NIAEA | 9
Ballylumford | NIB10 | 94 |  |  | S
Ballylumford | NIB31 | 249
Ballylumford | NIB32 | 249
Ballylumford | NIB4 | 144 | F | F | F | F | F | F | F | F | F
Ballylumford | NIB5 | 147 | F | F | F | F | F | F | F | F | F
Ballylumford | NIBGT1 | 58 | [6 empty] | S
Ballylumford | NIBGT2 | 58 | [5 empty] | S
Contour Global | NICG2 | 3
Contour Global | NICGA | 12
Coolkeeragh | NIC30 | 408
Coolkeeragh | NICGT8 | 53
Empower | NIEMP | 3
Endeco Technologies | NIECA | 11
Energy Trading | NIETB | 9
Energy Trading | NIETD | 5
Energy Trading | NIETR | 19
iPower | NIAGU | 74
Kilroot | NIK1 | 256
Kilroot | NIK2 | 258 |  |  |  |  | S | S | S | S | S
Kilroot | NIKGT1 | 29
Kilroot | NIKGT2 | 29
Kilroot | NIKGT3 | 42
Kilroot | NIKGT4 | 42
Lisahally | NILPS | 18
Moyle | MOYLE | 450
Powerhouse Generation | NIPH1 | 31

## SONI Outages
Upcoming Outages including STMOs and Annual Outages
Station | Unit | NPR | Start Date | End Date | Value | Duration
Ballylumford | NIB4 | 144 | 2018-11-14 | 2020-01-01 | F | 413
Ballylumford | NIB5 | 147 | 2019-01-01 | 2101-01-01 | F | 29950
Ballylumford | NIB32 | 249 | 2019-01-07 19:00 | 2019-01-10 19:00 | S | 3
Ballylumford | NIB32 | 249 | 2019-01-07 19:00 | 2019-01-10 19:00 | S | 3
Ballylumford | NIB10 | 94 | 2019-01-14 19:00 | 2019-01-21 19:00 | S | 7
Ballylumford | NIB10 | 94 | 2019-01-14 19:00 | 2019-01-20 19:00 | S | 6
Coolkeeragh | NIC30 | 408 | 2019-01-26 | 2019-01-28 | S | 2
Kilroot | NIK2 | 258 | 2019-01-30 20:00 | 2019-03-29 15:00 | S | 57.75
Ballylumford | NIBGT2 | 58 | 2019-02-04 | 2019-02-11 | S | 7
Ballylumford | NIBGT1 | 58 | 2019-02-11 | 2019-02-18 | S | 7
|  |  | Scheduled Outage | S
|  |  | Forced Outage | F
|  |  | Unit partially available | 10

## Outage Plan All Island
2019 GENERATION OUTAGE PLAN (All Island)
|  | Month | Jan '2019 |  |  |  |  | Feb '2019
|  | Week | 1 '2019 | 2 '2019 | 3 '2019 | 4 '2019 | 5 '2019 | 6 '2019 | 7 '2019 | 8 '2019 | 9 '2019
Station | Unit | NPR
AC Automation | NIACA | 8
Activation Energy | AE1 | 77
Activation Energy | AE2 | 8
Activation Energy | AE3 | 14
Activation Energy | AE4 | 11
Activation Energy | AE5 | 15
Activation Energy | EN5 | 6
Activation Energy | EN6 | 10
Activation Energy | NIAEA | 9
Aghada | AD2 | 431
Aghada | AT1 | 90
Aghada | AT2 | 90
Aghada | AT4 | 90
Ardnacrusha | AA1 | 21
Ardnacrusha | AA2 | 22
Ardnacrusha | AA3 | 19
Ardnacrusha | AA4 | 24
Ballylumford | NIB10 | 94 |  |  | S
Ballylumford | NIB31 | 249
Ballylumford | NIB32 | 249
Ballylumford | NIB4 | 144 | F | F | F | F | F | F | F | F | F
Ballylumford | NIB5 | 147 | F | F | F | F | F | F | F | F | F
Ballylumford | NIBGT1 | 58 | [6 empty] | S
Ballylumford | NIBGT2 | 58 | [5 empty] | S
Contour Global | NICG2 | 3
Contour Global | NICGA | 12
Coolkeeragh | NIC30 | 408
Coolkeeragh | NICGT8 | 53
DAE Virtual Power Plant | DP1 | 19
DAE Virtual Power Plant | DP2 | 20
Dublin Bay | DB1 | 405
Dublin Waste To Energy | DW1 | 62
Edenderry | ED1 | 118
Edenderry | ED3 | 58
Edenderry | ED5 | 58
Electric Ireland | EI1 | 20
Electricity Exchange DSU | EE1 | 39
Electricity Exchange DSU | EE2 | 17
Electricity Exchange DSU | EE3 | 7
Electricity Exchange DSU | EE4 | 9
Electricity Exchange DSU | EE5 | 7
Empower | NIEMP | 3
Endeco Technologies | EC1 | 37
Endeco Technologies | EC2 | 10
Endeco Technologies | EC5 | 16
Endeco Technologies | NIECA | 11
Energy Trading | ET1 | 13
Energy Trading | NIETB | 9
Energy Trading | NIETD | 5
Energy Trading | NIETR | 19
Erne | ER1 | 10
Erne | ER2 | 10
Erne | ER3 | 22
Erne | ER4 | 22
EWIC | EW1 | 500
Great Island | GI4 | 461
Huntstown | HN2 | 400
Huntstown | HNC | 342
Indaver | IW1 | 17
iPower | NIAGU | 74
Kilroot | NIK1 | 256
Kilroot | NIK2 | 258 |  |  |  |  | S | S | S | S | S
Kilroot | NIKGT1 | 29
Kilroot | NIKGT2 | 29
Kilroot | NIKGT3 | 42
Kilroot | NIKGT4 | 42
Lanesboro | LR4 | 91
Lee | LE1 | 15
Lee | LE2 | 4
Lee | LE3 | 8
Liffey | LI1 | 15
Liffey | LI2 | 15
Liffey | LI4 | 4
Liffey | LI5 | 4
Lisahally | NILPS | 18
Moneypoint | MP1 | 285
Moneypoint | MP2 | 285 | F | F | F | F | F | F | F | F | F
Moneypoint | MP3 | 285
Moyle | MOYLE | 450
North Wall | NW5 | 104
Poolbeg | PB4 | 154
Poolbeg | PB5 | 146
Poolbeg | PB6 | 168
Powerhouse Generation | NIPH1 | 31
Powerhouse Generation | PG1 | 11
Rhode | RP1 | 52
Rhode | RP2 | 52
Seal Rock | SK3 | 85
Seal Rock | SK4 | 85
Tarbert | TB1 | 54
Tarbert | TB2 | 54
Tarbert | TB3 | 241
Tarbert | TB4 | 243
Tawnaghmore | TP1 | 52
Tawnaghmore | TP3 | 52
Turlough Hill | TH1 | 73
Turlough Hill | TH2 | 73
Turlough Hill | TH3 | 73
Turlough Hill | TH4 | 73
Tynagh | TYC | 384
Viridian Energy | VE1 | 19
Viridian Energy DSU | VE2 | 6
West Offaly | WO4 | 137
Whitegate | WG1 | 444

## All Island Outages
Upcoming Outages including STMOs and Annual Outages
Station | Unit | NPR | Start Date | End Date | Value | Duration
Moneypoint | MP2 | 285 | 2018-09-26 23:00 | 2019-04-05 18:00 | F | 190.75
Ballylumford | NIB4 | 144 | 2018-11-14 | 2020-01-01 | F | 413
Edenderry | ED1 | 118 | 2018-12-26 12:00 | 2019-01-02 08:00 | S | 6.83
Ballylumford | NIB5 | 147 | 2019-01-01 | 2101-01-01 | F | 29950
Ballylumford | NIB32 | 249 | 2019-01-07 19:00 | 2019-01-10 19:00 | S | 3
Ballylumford | NIB32 | 249 | 2019-01-07 19:00 | 2019-01-10 19:00 | S | 3
Seal Rock | SK3 | 85 | 2019-01-13 07:00 | 2019-01-15 17:00 | S | 2.42
Ballylumford | NIB10 | 94 | 2019-01-14 19:00 | 2019-01-21 19:00 | S | 7
Ballylumford | NIB10 | 94 | 2019-01-14 19:00 | 2019-01-20 19:00 | S | 6
Coolkeeragh | NIC30 | 408 | 2019-01-26 | 2019-01-28 | S | 2
Kilroot | NIK2 | 258 | 2019-01-30 20:00 | 2019-03-29 15:00 | S | 57.75
Ballylumford | NIBGT2 | 58 | 2019-02-04 | 2019-02-11 | S | 7
Ballylumford | NIBGT1 | 58 | 2019-02-11 | 2019-02-18 | S | 7
EWIC | EW1 | 500 | 2019-02-16 12:00 | 2019-02-17 23:00 | S | 1.42
|  |  | Scheduled Outage | S
|  |  | Forced Outage | F
|  |  | Unit partially available | 10