## Outage Plan EirGrid
2024 GENERATION OUTAGE PLAN (EIRGRID)
|  | Month | Jan '2024 |  |  |  |  | Feb '2024 |  |  |  | Mar '2024 |  |  |  | Apr '2024 |  |  |  |  | May '2024 |  |  |  | Jun '2024 |  |  |  | Jul '2024 |  |  |  |  | Aug '2024 |  |  |  | Sep '2024 |  |  |  |  | Oct '2024 |  |  |  | Nov '2024 |  |  |  | Dec '2024
|  | Week | 1 '2024 | 2 '2024 | 3 '2024 | 4 '2024 | 5 '2024 | 6 '2024 | 7 '2024 | 8 '2024 | 9 '2024 | 10 '2024 | 11 '2024 | 12 '2024 | 13 '2024 | 14 '2024 | 15 '2024 | 16 '2024 | 17 '2024 | 18 '2024 | 19 '2024 | 20 '2024 | 21 '2024 | 22 '2024 | 23 '2024 | 24 '2024 | 25 '2024 | 26 '2024 | 27 '2024 | 28 '2024 | 29 '2024 | 30 '2024 | 31 '2024 | 32 '2024 | 33 '2024 | 34 '2024 | 35 '2024 | 36 '2024 | 37 '2024 | 38 '2024 | 39 '2024 | 40 '2024 | 41 '2024 | 42 '2024 | 43 '2024 | 44 '2024 | 45 '2024 | 46 '2024 | 47 '2024 | 48 '2024 | 49 '2024 | 50 '2024 | 51 '2024 | 52 '2024 | 53 '2024
Station | Unit | NPR
Activation Energy | AE1 | 95
Activation Energy | AE2 | 12
Activation Energy | AE3 | 14
Activation Energy | AE4 | 15
Activation Energy | AE5 | 15
Activation Energy | EN1 | 15
Activation Energy | EN2 | 16
Activation Energy | EN3 | 16
Activation Energy | EN4 | 16
Activation Energy | EN5 | 6
Activation Energy | EN6 | 11
Aghada | AD2 | 449
Aghada | AT1 | 90 | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Aghada | AT2 | 90
Aghada | AT4 | 90
Ardnacrusha | AA1 | 21 | [34 empty] | S
Ardnacrusha | AA2 | 22 | [37 empty] | S
Ardnacrusha | AA3 | 19 | [18 empty] | S | S | S | S | S | S | S | S
Ardnacrusha | AA4 | 24 | [14 empty] | S
DAE Virtual Power Plant | DP1 | 19
DAE Virtual Power Plant | DP2 | 26
Dublin Bay | DB1 | 405 | [9 empty] | S
Dublin Waste To Energy | DW1 | 62 | [17 empty] | S | S
Edenderry | ED1 | 118
Edenderry | ED3 | 58
Edenderry | ED5 | 58
Electric Ireland | EI1 | 20
Electricity Exchange DSU | EE1 | 47
Electricity Exchange DSU | EE2 | 20
Electricity Exchange DSU | EE3 | 8
Electricity Exchange DSU | EE4 | 9
Electricity Exchange DSU | EE5 | 7
Electricity Exchange DSU | EE6 | 14
Endeco Technologies | EC1 | 47
Endeco Technologies | EC2 | 11
Endeco Technologies | EC5 | 15
Energy Trading | ET1 | 13
Erne | ER1 | 10 | [25 empty] | S
Erne | ER2 | 10 | [33 empty] | S
Erne | ER3 | 22 | [36 empty] | S
Erne | ER4 | 22 | [15 empty] | S | S | S | S | S | S | S | S
EWIC | EW1 | 500
Great Island | GI4 | 461 | [11 empty] | S | S | S
Huntstown | HN2 | 400 | [29 empty] | S | S | S | S
Huntstown | HNC | 342 | [24 empty] | S | S | S
Indaver | IW1 | 17 | [15 empty] | S | S
Knockacummer | KC1 | 100
Lee | LE1 | 15 | [23 empty] | S | S
Lee | LE2 | 4 | [11 empty] | S | S
Lee | LE3 | 8 | [14 empty] | S | S
Liffey | LI1 | 15 | [19 empty] | S
Liffey | LI2 | 15 | [19 empty] | S
Liffey | LI4 | 4
Liffey | LI5 | 4
Moneypoint | MP1 | 285 | [18 empty] | S
Moneypoint | MP2 | 285 | [18 empty] | S | S
Moneypoint | MP3 | 285 | [15 empty] | S
Poolbeg | PB4 | 154 | [38 empty] | S
Poolbeg | PB5 | 146 | [39 empty] | S
Poolbeg | PB6 | 168 | [35 empty] | S | S | S |  | S | S | S
Powerhouse Generation | PG1 | 10
Rhode | RP1 | 52
Rhode | RP2 | 52
Seal Rock | SK3 | 85
Seal Rock | SK4 | 85
Seecon | SO1 | 105
Tarbert | TB1 | 54 | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F
Tarbert | TB2 | 54 | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F
Tarbert | TB3 | 241 | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F
Tarbert | TB4 | 243 | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F
Tawnaghmore | TP1 | 52
Tawnaghmore | TP3 | 52
Turlough Hill | TH1 | 73 | [12 empty] | S
Turlough Hill | TH2 | 73 | [12 empty] | S
Turlough Hill | TH3 | 73 | [12 empty] | S
Turlough Hill | TH4 | 73 | [12 empty] | S
Tynagh | TYC | 384 | [32 empty] | S | S | S | S | S | S | S | S
Viridian Energy | VE1 | 20
Viridian Energy DSU | VE2 | 13
Whitegate | WG1 | 444

## EirGrid Outages
Upcoming Outages including STMOs and Annual Outages
Station | Unit | NPR | Start Date | End Date | Value | Duration
Tarbert | TB4 | 243 | 2023-09-30 | 2030-12-31 00:30 | F | 2649
Tarbert | TB2 | 54 | 2023-09-30 | 2030-12-31 00:30 | F | 2649
Tarbert | TB3 | 241 | 2023-09-30 | 2030-12-31 00:30 | F | 2649
Tarbert | TB1 | 54 | 2023-09-30 | 2030-12-31 00:30 | F | 2649
Edenderry | ED1 | 118 | 2023-12-26 13:00 | 2024-01-02 08:00 | S | 6.75
Aghada | AT1 | 90 | 2024-01-01 | 2024-12-31 00:30 | S | 365
Seal Rock | SK4 | 85 | 2024-01-08 06:00 | 2024-01-10 18:00 | S | 2.5
Aghada | AD2 | 449 | 2024-02-23 | 2024-03-01 00:30 | S | 7
Seal Rock | SK3 | 85 | 2024-02-26 06:00 | 2024-02-28 18:00 | S | 2.5
Dublin Bay | DB1 | 405 | 2024-03-01 | 2024-03-13 00:30 | S | 12
Great Island | GI4 | 461 | 2024-03-18 | 2024-04-08 00:30 | S | 21
Lee | LE2 | 4 | 2024-03-19 08:00 | 2024-03-29 20:00 | S | 10.5
Turlough Hill | TH1 | 73 | 2024-03-23 07:00 | 2024-03-31 17:00 | S | 8.42
Turlough Hill | TH2 | 73 | 2024-03-23 07:00 | 2024-03-31 17:00 | S | 8.42
Turlough Hill | TH3 | 73 | 2024-03-23 07:00 | 2024-03-31 17:00 | S | 8.42
Turlough Hill | TH4 | 73 | 2024-03-23 07:00 | 2024-03-31 17:00 | S | 8.42
Ardnacrusha | AA4 | 24 | 2024-04-08 08:00 | 2024-04-12 20:00 | S | 4.5
Lee | LE3 | 8 | 2024-04-08 08:00 | 2024-04-19 20:00 | S | 11.5
Moneypoint | MP3 | 285 | 2024-04-12 22:00 | 2024-04-24 22:00 | S | 12
Indaver | IW1 | 17 | 2024-04-14 | 2024-05-01 | S | 17
Erne | ER4 | 22.5 | 2024-04-15 08:00 | 2024-06-09 20:00 | S | 55.5
Seal Rock | SK4 | 85 | 2024-04-22 06:00 | 2024-04-24 18:00 | S | 2.5
Dublin Waste To Energy | DW1 | 61.5 | 2024-05-01 | 2024-05-06 | S | 5
Moneypoint | MP1 | 285 | 2024-05-03 22:00 | 2024-05-15 22:00 | S | 12
Dublin Waste To Energy | DW1 | 61.5 | 2024-05-06 | 2024-05-16 | S | 10
Ardnacrusha | AA3 | 19 | 2024-05-07 08:00 | 2024-06-28 20:00 | S | 52.5
Moneypoint | MP2 | 285 | 2024-05-07 22:00 | 2024-05-19 22:00 | S | 12
Liffey | LI1 | 15 | 2024-05-12 08:00 | 2024-05-17 17:00 | S | 5.33
Liffey | LI2 | 15 | 2024-05-12 08:00 | 2024-05-17 17:00 | S | 5.33
Seal Rock | SK3 | 85 | 2024-05-13 18:00 | 2024-05-16 18:00 | S | 3
Seal Rock | SK4 | 85 | 2024-05-14 | 2024-05-16 12:00 | S | 2.5
Dublin Waste To Energy | DW1 | 61.5 | 2024-05-16 | 2024-05-22 | 26 | 6
Liffey | LI4 | 4 | 2024-05-24 08:00 | 2024-05-25 17:00 | S | 1.33
Lee | LE1 | 15 | 2024-06-10 08:00 | 2024-06-21 20:00 | S | 11.5
Huntstown | HNC | 342 | 2024-06-17 | 2024-07-07 | S | 20
Liffey | LI5 | 4 | 2024-06-17 08:00 | 2024-06-19 17:00 | S | 2.33
Erne | ER1 | 10 | 2024-06-24 08:00 | 2024-06-28 20:00 | S | 4.5
Aghada | AT4 | 90 | 2024-06-27 | 2024-06-30 00:30 | S | 3
Seal Rock | SK3 | 85 | 2024-07-01 06:00 | 2024-07-04 18:00 | S | 3.5
Aghada | AT2 | 90 | 2024-07-04 | 2024-07-07 00:30 | S | 3
Huntstown | HN2 | 400 | 2024-07-25 | 2024-08-21 | S | 27
Tynagh | TYC | 384 | 2024-08-11 | 2024-10-06 | S | 56
Erne | ER2 | 10 | 2024-08-19 08:00 | 2024-08-23 20:00 | S | 4.5
Ardnacrusha | AA1 | 21 | 2024-08-26 08:00 | 2024-08-30 20:00 | S | 4.5
Poolbeg | PB6 | 168 | 2024-09-01 12:00 | 2024-09-22 20:00 | S | 21.33
Seal Rock | SK4 | 85 | 2024-09-02 06:00 | 2024-09-05 18:00 | S | 3.5
Edenderry | ED5 | 58 | 2024-09-06 08:00 | 2024-09-06 18:00 | S | 0.42
Edenderry | ED3 | 58 | 2024-09-06 08:00 | 2024-09-06 18:00 | S | 0.42
Whitegate | WG1 | 444 | 2024-09-06 21:00 | 2024-09-13 21:00 | S | 7
Erne | ER3 | 22.5 | 2024-09-09 08:00 | 2024-09-13 20:00 | S | 4.5
Ardnacrusha | AA2 | 22 | 2024-09-16 08:00 | 2024-09-20 20:00 | S | 4.5
Poolbeg | PB4 | 154 | 2024-09-22 12:00 | 2024-09-27 20:00 | S | 5.33
Poolbeg | PB6 | 168 | 2024-09-27 20:00 | 2024-10-18 20:00 | S | 21
Poolbeg | PB5 | 146 | 2024-09-29 12:00 | 2024-10-04 20:00 | S | 5.33
Dublin Waste To Energy | DW1 | 61.5 | 2024-10-07 | 2024-10-11 | 26 | 4
Dublin Waste To Energy | DW1 | 61.5 | 2024-10-14 | 2024-10-18 | 26 | 4
Aghada | AD2 | 449 | 2024-11-01 | 2024-11-06 00:30 | S | 5
Seal Rock | SK3 | 85 | 2024-11-04 06:00 | 2024-11-06 18:00 | S | 2.5
|  |  | Scheduled Outage | S
|  |  | Forced Outage | F
|  |  | Unit partially available | 10

## Outage Plan SONI
2024 GENERATION OUTAGE PLAN (SONI)
|  | Month | Jan '2024 |  |  |  |  | Feb '2024 |  |  |  | Mar '2024 |  |  |  | Apr '2024 |  |  |  |  | May '2024 |  |  |  | Jun '2024 |  |  |  | Jul '2024 |  |  |  |  | Aug '2024 |  |  |  | Sep '2024 |  |  |  |  | Oct '2024 |  |  |  | Nov '2024 |  |  |  | Dec '2024
|  | Week | 1 '2024 | 2 '2024 | 3 '2024 | 4 '2024 | 5 '2024 | 6 '2024 | 7 '2024 | 8 '2024 | 9 '2024 | 10 '2024 | 11 '2024 | 12 '2024 | 13 '2024 | 14 '2024 | 15 '2024 | 16 '2024 | 17 '2024 | 18 '2024 | 19 '2024 | 20 '2024 | 21 '2024 | 22 '2024 | 23 '2024 | 24 '2024 | 25 '2024 | 26 '2024 | 27 '2024 | 28 '2024 | 29 '2024 | 30 '2024 | 31 '2024 | 32 '2024 | 33 '2024 | 34 '2024 | 35 '2024 | 36 '2024 | 37 '2024 | 38 '2024 | 39 '2024 | 40 '2024 | 41 '2024 | 42 '2024 | 43 '2024 | 44 '2024 | 45 '2024 | 46 '2024 | 47 '2024 | 48 '2024 | 49 '2024 | 50 '2024 | 51 '2024 | 52 '2024 | 53 '2024
Station | Unit | NPR
AC Automation | NIACA | 8
Activation Energy | NIAEA | 9
Ballylumford | NIB10 | 94 | [17 empty] | S | S | S | S | S | S | S | S | S
Ballylumford | NIB31 | 249
Ballylumford | NIB32 | 249
Ballylumford | NIBGT1 | 58 | [15 empty] | S
Ballylumford | NIBGT2 | 58 | [14 empty] | S
Contour Global | NICG2 | 3
Contour Global | NICGA | 12
Coolkeeragh | NIC30 | 408 | [28 empty] | S | S
Coolkeeragh | NICGT8 | 53 | [19 empty] | S
Empower | NIEMP | 3
Endeco Technologies | NIECA | 13
Energy Trading | NIETB | 9
Energy Trading | NIETD | 5
Energy Trading | NIETR | 19
iPower | NIAGU | 74
Kilroot | NIK1 | 256
Kilroot | NIK2 | 258
Kilroot | NIKGT1 | 29 | [39 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Kilroot | NIKGT2 | 29 | [39 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Kilroot | NIKGT3 | 42 | [39 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Kilroot | NIKGT4 | 42 | [39 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Lisahally | NILPS | 18
Moyle | MOYLE | 450
Powerhouse Generation | NIPH1 | 34

## SONI Outages
Upcoming Outages including STMOs and Annual Outages
Station | Unit | NPR | Start Date | End Date | Value | Duration
Coolkeeragh | NIC30 | 408 | 2024-03-10 | 2024-03-11 | S | 1
Ballylumford | NIBGT2 | 58 | 2024-04-08 | 2024-04-15 | S | 7
Ballylumford | NIBGT1 | 58 | 2024-04-15 | 2024-04-22 | S | 7
Ballylumford | NIB10 | 94 | 2024-05-02 | 2024-06-30 | S | 59
Coolkeeragh | NICGT8 | 53 | 2024-05-13 | 2024-05-17 | S | 4
Coolkeeragh | NIC30 | 408 | 2024-07-15 | 2024-07-29 | S | 14
Coolkeeragh | NIC30 | 408 | 2024-08-25 | 2024-08-26 | S | 1
Ballylumford | NIB31 | 249 | 2024-09-09 | 2024-09-22 | 161 | 13
Ballylumford | NIB32 | 249 | 2024-09-09 | 2024-09-22 | 161 | 13
Coolkeeragh | NIC30 | 408 | 2024-09-28 | 2024-09-30 | S | 2
Kilroot | NIKGT2 | 29 | 2024-10-01 | 2025-10-01 | S | 365
Kilroot | NIKGT1 | 29 | 2024-10-01 | 2025-10-01 | S | 365
Kilroot | NIKGT3 | 42 | 2024-10-01 | 2025-10-01 | S | 365
Kilroot | NIKGT4 | 42 | 2024-10-01 | 2025-10-01 | S | 365
|  |  | Scheduled Outage | S
|  |  | Forced Outage | F
|  |  | Unit partially available | 10

## Outage Plan All Island
2024 GENERATION OUTAGE PLAN (All Island)
|  | Month | Jan '2024 |  |  |  |  | Feb '2024 |  |  |  | Mar '2024 |  |  |  | Apr '2024 |  |  |  |  | May '2024 |  |  |  | Jun '2024 |  |  |  | Jul '2024 |  |  |  |  | Aug '2024 |  |  |  | Sep '2024 |  |  |  |  | Oct '2024 |  |  |  | Nov '2024 |  |  |  | Dec '2024
|  | Week | 1 '2024 | 2 '2024 | 3 '2024 | 4 '2024 | 5 '2024 | 6 '2024 | 7 '2024 | 8 '2024 | 9 '2024 | 10 '2024 | 11 '2024 | 12 '2024 | 13 '2024 | 14 '2024 | 15 '2024 | 16 '2024 | 17 '2024 | 18 '2024 | 19 '2024 | 20 '2024 | 21 '2024 | 22 '2024 | 23 '2024 | 24 '2024 | 25 '2024 | 26 '2024 | 27 '2024 | 28 '2024 | 29 '2024 | 30 '2024 | 31 '2024 | 32 '2024 | 33 '2024 | 34 '2024 | 35 '2024 | 36 '2024 | 37 '2024 | 38 '2024 | 39 '2024 | 40 '2024 | 41 '2024 | 42 '2024 | 43 '2024 | 44 '2024 | 45 '2024 | 46 '2024 | 47 '2024 | 48 '2024 | 49 '2024 | 50 '2024 | 51 '2024 | 52 '2024 | 53 '2024
Station | Unit | NPR
AC Automation | NIACA | 8
Activation Energy | AE1 | 95
Activation Energy | AE2 | 12
Activation Energy | AE3 | 14
Activation Energy | AE4 | 15
Activation Energy | AE5 | 15
Activation Energy | EN1 | 15
Activation Energy | EN2 | 16
Activation Energy | EN3 | 16
Activation Energy | EN4 | 16
Activation Energy | EN5 | 6
Activation Energy | EN6 | 11
Activation Energy | NIAEA | 9
Aghada | AD2 | 449
Aghada | AT1 | 90 | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Aghada | AT2 | 90
Aghada | AT4 | 90
Ardnacrusha | AA1 | 21 | [34 empty] | S
Ardnacrusha | AA2 | 22 | [37 empty] | S
Ardnacrusha | AA3 | 19 | [18 empty] | S | S | S | S | S | S | S | S
Ardnacrusha | AA4 | 24 | [14 empty] | S
Ballylumford | NIB10 | 94 | [17 empty] | S | S | S | S | S | S | S | S | S
Ballylumford | NIB31 | 249
Ballylumford | NIB32 | 249
Ballylumford | NIBGT1 | 58 | [15 empty] | S
Ballylumford | NIBGT2 | 58 | [14 empty] | S
Contour Global | NICG2 | 3
Contour Global | NICGA | 12
Coolkeeragh | NIC30 | 408 | [28 empty] | S | S
Coolkeeragh | NICGT8 | 53 | [19 empty] | S
DAE Virtual Power Plant | DP1 | 19
DAE Virtual Power Plant | DP2 | 26
Dublin Bay | DB1 | 405 | [9 empty] | S
Dublin Waste To Energy | DW1 | 62 | [17 empty] | S | S
Edenderry | ED1 | 118
Edenderry | ED3 | 58
Edenderry | ED5 | 58
Electric Ireland | EI1 | 20
Electricity Exchange DSU | EE1 | 47
Electricity Exchange DSU | EE2 | 20
Electricity Exchange DSU | EE3 | 8
Electricity Exchange DSU | EE4 | 9
Electricity Exchange DSU | EE5 | 7
Electricity Exchange DSU | EE6 | 14
Empower | NIEMP | 3
Endeco Technologies | EC1 | 47
Endeco Technologies | EC2 | 11
Endeco Technologies | EC5 | 15
Endeco Technologies | NIECA | 13
Energy Trading | ET1 | 13
Energy Trading | NIETB | 9
Energy Trading | NIETD | 5
Energy Trading | NIETR | 19
Erne | ER1 | 10 | [25 empty] | S
Erne | ER2 | 10 | [33 empty] | S
Erne | ER3 | 22 | [36 empty] | S
Erne | ER4 | 22 | [15 empty] | S | S | S | S | S | S | S | S
EWIC | EW1 | 500
Great Island | GI4 | 461 | [11 empty] | S | S | S
Huntstown | HN2 | 400 | [29 empty] | S | S | S | S
Huntstown | HNC | 342 | [24 empty] | S | S | S
Indaver | IW1 | 17 | [15 empty] | S | S
iPower | NIAGU | 74
Kilroot | NIK1 | 256
Kilroot | NIK2 | 258
Kilroot | NIKGT1 | 29 | [39 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Kilroot | NIKGT2 | 29 | [39 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Kilroot | NIKGT3 | 42 | [39 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Kilroot | NIKGT4 | 42 | [39 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Knockacummer | KC1 | 100
Lee | LE1 | 15 | [23 empty] | S | S
Lee | LE2 | 4 | [11 empty] | S | S
Lee | LE3 | 8 | [14 empty] | S | S
Liffey | LI1 | 15 | [19 empty] | S
Liffey | LI2 | 15 | [19 empty] | S
Liffey | LI4 | 4
Liffey | LI5 | 4
Lisahally | NILPS | 18
Moneypoint | MP1 | 285 | [18 empty] | S
Moneypoint | MP2 | 285 | [18 empty] | S | S
Moneypoint | MP3 | 285 | [15 empty] | S
Moyle | MOYLE | 450
Poolbeg | PB4 | 154 | [38 empty] | S
Poolbeg | PB5 | 146 | [39 empty] | S
Poolbeg | PB6 | 168 | [35 empty] | S | S | S |  | S | S | S
Powerhouse Generation | NIPH1 | 34
Powerhouse Generation | PG1 | 10
Rhode | RP1 | 52
Rhode | RP2 | 52
Seal Rock | SK3 | 85
Seal Rock | SK4 | 85
Seecon | SO1 | 105
Tarbert | TB1 | 54 | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F
Tarbert | TB2 | 54 | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F
Tarbert | TB3 | 241 | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F
Tarbert | TB4 | 243 | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F
Tawnaghmore | TP1 | 52
Tawnaghmore | TP3 | 52
Turlough Hill | TH1 | 73 | [12 empty] | S
Turlough Hill | TH2 | 73 | [12 empty] | S
Turlough Hill | TH3 | 73 | [12 empty] | S
Turlough Hill | TH4 | 73 | [12 empty] | S
Tynagh | TYC | 384 | [32 empty] | S | S | S | S | S | S | S | S
Viridian Energy | VE1 | 20
Viridian Energy DSU | VE2 | 13
Whitegate | WG1 | 444

## All Island Outages
Upcoming Outages including STMOs and Annual Outages
Station | Unit | NPR | Start Date | End Date | Value | Duration
Tarbert | TB4 | 243 | 2023-09-30 | 2030-12-31 00:30 | F | 2649
Tarbert | TB2 | 54 | 2023-09-30 | 2030-12-31 00:30 | F | 2649
Tarbert | TB3 | 241 | 2023-09-30 | 2030-12-31 00:30 | F | 2649
Tarbert | TB1 | 54 | 2023-09-30 | 2030-12-31 00:30 | F | 2649
Edenderry | ED1 | 118 | 2023-12-26 13:00 | 2024-01-02 08:00 | S | 6.75
Aghada | AT1 | 90 | 2024-01-01 | 2024-12-31 00:30 | S | 365
Seal Rock | SK4 | 85 | 2024-01-08 06:00 | 2024-01-10 18:00 | S | 2.5
Aghada | AD2 | 449 | 2024-02-23 | 2024-03-01 00:30 | S | 7
Seal Rock | SK3 | 85 | 2024-02-26 06:00 | 2024-02-28 18:00 | S | 2.5
Dublin Bay | DB1 | 405 | 2024-03-01 | 2024-03-13 00:30 | S | 12
Coolkeeragh | NIC30 | 408 | 2024-03-10 | 2024-03-11 | S | 1
Great Island | GI4 | 461 | 2024-03-18 | 2024-04-08 00:30 | S | 21
Lee | LE2 | 4 | 2024-03-19 08:00 | 2024-03-29 20:00 | S | 10.5
Turlough Hill | TH1 | 73 | 2024-03-23 07:00 | 2024-03-31 17:00 | S | 8.42
Turlough Hill | TH2 | 73 | 2024-03-23 07:00 | 2024-03-31 17:00 | S | 8.42
Turlough Hill | TH3 | 73 | 2024-03-23 07:00 | 2024-03-31 17:00 | S | 8.42
Turlough Hill | TH4 | 73 | 2024-03-23 07:00 | 2024-03-31 17:00 | S | 8.42
Ballylumford | NIBGT2 | 58 | 2024-04-08 | 2024-04-15 | S | 7
Ardnacrusha | AA4 | 24 | 2024-04-08 08:00 | 2024-04-12 20:00 | S | 4.5
Lee | LE3 | 8 | 2024-04-08 08:00 | 2024-04-19 20:00 | S | 11.5
Moneypoint | MP3 | 285 | 2024-04-12 22:00 | 2024-04-24 22:00 | S | 12
Indaver | IW1 | 17 | 2024-04-14 | 2024-05-01 | S | 17
Ballylumford | NIBGT1 | 58 | 2024-04-15 | 2024-04-22 | S | 7
Erne | ER4 | 22.5 | 2024-04-15 08:00 | 2024-06-09 20:00 | S | 55.5
Seal Rock | SK4 | 85 | 2024-04-22 06:00 | 2024-04-24 18:00 | S | 2.5
Dublin Waste To Energy | DW1 | 61.5 | 2024-05-01 | 2024-05-06 | S | 5
Ballylumford | NIB10 | 94 | 2024-05-02 | 2024-06-30 | S | 59
Moneypoint | MP1 | 285 | 2024-05-03 22:00 | 2024-05-15 22:00 | S | 12
Dublin Waste To Energy | DW1 | 61.5 | 2024-05-06 | 2024-05-16 | S | 10
Ardnacrusha | AA3 | 19 | 2024-05-07 08:00 | 2024-06-28 20:00 | S | 52.5
Moneypoint | MP2 | 285 | 2024-05-07 22:00 | 2024-05-19 22:00 | S | 12
Liffey | LI1 | 15 | 2024-05-12 08:00 | 2024-05-17 17:00 | S | 5.33
Liffey | LI2 | 15 | 2024-05-12 08:00 | 2024-05-17 17:00 | S | 5.33
Coolkeeragh | NICGT8 | 53 | 2024-05-13 | 2024-05-17 | S | 4
Seal Rock | SK3 | 85 | 2024-05-13 18:00 | 2024-05-16 18:00 | S | 3
Seal Rock | SK4 | 85 | 2024-05-14 | 2024-05-16 12:00 | S | 2.5
Dublin Waste To Energy | DW1 | 61.5 | 2024-05-16 | 2024-05-22 | 26 | 6
Liffey | LI4 | 4 | 2024-05-24 08:00 | 2024-05-25 17:00 | S | 1.33
Lee | LE1 | 15 | 2024-06-10 08:00 | 2024-06-21 20:00 | S | 11.5
Huntstown | HNC | 342 | 2024-06-17 | 2024-07-07 | S | 20
Liffey | LI5 | 4 | 2024-06-17 08:00 | 2024-06-19 17:00 | S | 2.33
Erne | ER1 | 10 | 2024-06-24 08:00 | 2024-06-28 20:00 | S | 4.5
Aghada | AT4 | 90 | 2024-06-27 | 2024-06-30 00:30 | S | 3
Seal Rock | SK3 | 85 | 2024-07-01 06:00 | 2024-07-04 18:00 | S | 3.5
Aghada | AT2 | 90 | 2024-07-04 | 2024-07-07 00:30 | S | 3
Coolkeeragh | NIC30 | 408 | 2024-07-15 | 2024-07-29 | S | 14
Huntstown | HN2 | 400 | 2024-07-25 | 2024-08-21 | S | 27
Tynagh | TYC | 384 | 2024-08-11 | 2024-10-06 | S | 56
Erne | ER2 | 10 | 2024-08-19 08:00 | 2024-08-23 20:00 | S | 4.5
Coolkeeragh | NIC30 | 408 | 2024-08-25 | 2024-08-26 | S | 1
Ardnacrusha | AA1 | 21 | 2024-08-26 08:00 | 2024-08-30 20:00 | S | 4.5
Poolbeg | PB6 | 168 | 2024-09-01 12:00 | 2024-09-22 20:00 | S | 21.33
Seal Rock | SK4 | 85 | 2024-09-02 06:00 | 2024-09-05 18:00 | S | 3.5
Edenderry | ED5 | 58 | 2024-09-06 08:00 | 2024-09-06 18:00 | S | 0.42
Edenderry | ED3 | 58 | 2024-09-06 08:00 | 2024-09-06 18:00 | S | 0.42
Whitegate | WG1 | 444 | 2024-09-06 21:00 | 2024-09-13 21:00 | S | 7
Ballylumford | NIB31 | 249 | 2024-09-09 | 2024-09-22 | 161 | 13
Ballylumford | NIB32 | 249 | 2024-09-09 | 2024-09-22 | 161 | 13
Erne | ER3 | 22.5 | 2024-09-09 08:00 | 2024-09-13 20:00 | S | 4.5
Ardnacrusha | AA2 | 22 | 2024-09-16 08:00 | 2024-09-20 20:00 | S | 4.5
Poolbeg | PB4 | 154 | 2024-09-22 12:00 | 2024-09-27 20:00 | S | 5.33
Poolbeg | PB6 | 168 | 2024-09-27 20:00 | 2024-10-18 20:00 | S | 21
Coolkeeragh | NIC30 | 408 | 2024-09-28 | 2024-09-30 | S | 2
Poolbeg | PB5 | 146 | 2024-09-29 12:00 | 2024-10-04 20:00 | S | 5.33
Kilroot | NIKGT2 | 29 | 2024-10-01 | 2025-10-01 | S | 365
Kilroot | NIKGT1 | 29 | 2024-10-01 | 2025-10-01 | S | 365
Kilroot | NIKGT3 | 42 | 2024-10-01 | 2025-10-01 | S | 365
Kilroot | NIKGT4 | 42 | 2024-10-01 | 2025-10-01 | S | 365
Dublin Waste To Energy | DW1 | 61.5 | 2024-10-07 | 2024-10-11 | 26 | 4
Dublin Waste To Energy | DW1 | 61.5 | 2024-10-14 | 2024-10-18 | 26 | 4
Aghada | AD2 | 449 | 2024-11-01 | 2024-11-06 00:30 | S | 5
Seal Rock | SK3 | 85 | 2024-11-04 06:00 | 2024-11-06 18:00 | S | 2.5
|  |  | Scheduled Outage | S
|  |  | Forced Outage | F
|  |  | Unit partially available | 10