## Outage Plan EirGrid
2025 GENERATION OUTAGE PLAN (EIRGRID)
|  | Month | Jan '2025 |  |  |  |  | Feb '2025 |  |  |  | Mar '2025 |  |  |  |  | Apr '2025 |  |  |  | May '2025 |  |  |  | Jun '2025 |  |  |  |  | Jul '2025 |  |  |  | Aug '2025 |  |  |  | Sep '2025 |  |  |  |  | Oct '2025 |  |  |  | Nov '2025 |  |  |  | Dec '2025
|  | Week | 1 '2025 | 2 '2025 | 3 '2025 | 4 '2025 | 5 '2025 | 6 '2025 | 7 '2025 | 8 '2025 | 9 '2025 | 10 '2025 | 11 '2025 | 12 '2025 | 13 '2025 | 14 '2025 | 15 '2025 | 16 '2025 | 17 '2025 | 18 '2025 | 19 '2025 | 20 '2025 | 21 '2025 | 22 '2025 | 23 '2025 | 24 '2025 | 25 '2025 | 26 '2025 | 27 '2025 | 28 '2025 | 29 '2025 | 30 '2025 | 31 '2025 | 32 '2025 | 33 '2025 | 34 '2025 | 35 '2025 | 36 '2025 | 37 '2025 | 38 '2025 | 39 '2025 | 40 '2025 | 41 '2025 | 42 '2025 | 43 '2025 | 44 '2025 | 45 '2025 | 46 '2025 | 47 '2025 | 48 '2025 | 49 '2025 | 50 '2025 | 51 '2025 | 52 '2025 | 53 '2025
Station | Unit | NPR
Aghada | AD2 | 449 | [19 empty] | S | S | S | S | S | S | [17 empty] | S
Aghada | AD3 | 19 | [13 empty] | S | [26 empty] | S
Aghada | AD4 | 75
Aghada | AD5 | 75
Aghada | AT1 | 90
Aghada | AT2 | 90
Aghada | AT4 | 90
Ardnacrusha | AA1 | 21 | [37 empty] | S
Ardnacrusha | AA2 | 22 | [38 empty] | S
Ardnacrusha | AA3 | 19 | [22 empty] | S | S | S | S | S | S | S | S | S
Ardnacrusha | AA4 | 24 | [13 empty] | S | S | S | S | S | S | S | S | S
Aughinish Alumina | EB1 | 25
Banoge | OD1 | 9
Cloniffeen | SI1 | 50
Cloniffeen | SI2 | 50
Coolnanoonagh | KZ3 | 2
Coolnanoonagh | KZ4 | 27
Corduff | FG2 | 64
Crane | AV1 | 16
Derrycarney | LU1 | 50
Derrycarney | LU2 | 50
Drybridge | IW1 | 17 | [12 empty] | S | S
Dublin Bay | DB1 | 415 | [10 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Dunsoghly | DG1 | 50
Edenderry | ED1 | 118 | [27 empty] | S | S | S | S | S | S | S | S
Edenderry | ED3 | 58 | [37 empty] | S
Edenderry | ED5 | 58 | [37 empty] | S
Electric Ireland | EI1 | 17
Endeco Technologies | EC1 | 52
Endeco Technologies | EC2 | 12
Endeco Technologies | EC3 | 5
Endeco Technologies | EC4 | 5
Endeco Technologies | EC5 | 21
Enel X | AE1 | 87
Enel X | AE2 | 13
Enel X | AE3 | 14
Enel X | AE4 | 16
Enel X | AE5 | 16
Enel X | EN1 | 16
Enel X | EN2 | 17
Enel X | EN3 | 17
Enel X | EN4 | 16
Enel X | EN5 | 6
Enel X | EN6 | 11
Enel X | EN8 | 24
Enel X | EN9 | 16
Enel X | EX1 | 21
Energy Trading Ireland | ET1 | 5
Erne | ER1 | 10 | [16 empty] | S | S | S
Erne | ER2 | 10 | [14 empty] | S
Erne | ER3 | 23 | [26 empty] | S | S | S | S | S | S | S | S | S
Erne | ER4 | 23 | [13 empty] | S | S | S | S | S | S | S | S | S
EWIC | EW1 | 500 | [15 empty] | S
Gardnershill | GP1 | 8
Golagh | GO2 | 3
Gorman | GF1 | 50
Great Island | GI4 | 464 | [10 empty] | S | [33 empty] | S | S | S | S
Huntstown | HN2 | 402
Huntstown | HNC | 342 | [13 empty] | S | S | S | S | S
Inchicore | IH1 | 30 | [14 empty] | S | [26 empty] | S
Irishtown | IS2 | 30
Irishtown | IS3 | 64
Kilteel | PN1 | 30
Knockacummer | KC1 | 100
Lee | LE1 | 15 | [22 empty] | S | S
Lee | LE2 | 4 | [12 empty] | S | S
Lee | LE3 | 8 | [16 empty] | S | S | S | S
Liffey | LI1 | 15 | [23 empty] | S | S
Liffey | LI2 | 15 | [23 empty] | S | S
Liffey | LI4 | 4
Liffey | LI5 | 4
Lisdrum | LF1 | 60
Moneypoint | MP1 | 285 | [18 empty] | S | S | S | S | S | S | S | S
Moneypoint | MP2 | 285 | [35 empty] | S | S | S | S | S | S | S | S | S
Moneypoint | MP3 | 285 | [23 empty] | S | S
Moneypoint | MP5 | 1
Northwall | NW8 | 191
Poolbeg | PB4 | 148 | [15 empty] | S | S
Poolbeg | PB5 | 148 | [19 empty] | S
Poolbeg | PB6 | 168
Poolbeg | PB7 | 64
Poolbeg | PB8 | 75
Powerhouse Generation | PG1 | 10
Rhode | RP1 | 52
Rhode | RP2 | 52
Seal Rock | SK3 | 83 | [12 empty] | S | S | S | S
Seal Rock | SK4 | 83 | [24 empty] | S
Shannonbridge | SQ1 | 262
Tarbert | TB5 | 160
Tawnaghmore | KF2 | 11
Tawnaghmore | TP1 | 52
Tawnaghmore | TP3 | 52
Tobertoreen | XT2 | 11
Turlough Hill | TH1 | 73 | [9 empty] | S | S
Turlough Hill | TH2 | 73 | [9 empty] | S | S
Turlough Hill | TH3 | 73 | [9 empty] | S | S
Turlough Hill | TH4 | 73 | [9 empty] | S | S
Tynagh | TYC | 404 | [39 empty] | S
Uggool | SO1 | 105
Veolia Alternative Energy | DP1 | 5
Veolia Alternative Energy | DP2 | 30
Veolia Alternative Energy | DP3 | 9
VIOTAS | EE1 | 65
VIOTAS | EE2 | 30
VIOTAS | EE3 | 11
VIOTAS | EE4 | 13
VIOTAS | EE5 | 17
VIOTAS | EE6 | 14
VIOTAS | EE7 | 7
VIOTAS | EE8 | 12
VIOTAS | EE9 | 11
Whitebank | DW1 | 62 | [14 empty] | S
Whitegate | WG1 | 444 | [36 empty] | S

## EirGrid Outages
Upcoming Outages including STMOs and Annual Outages
Station | Unit | NPR | Start Date | End Date | Value | Duration
Edenderry | ED1 | 118 | 2024-12-26 12:00 | 2025-01-01 08:00 | S | 5.83
Huntstown | HNC | 342 | 2025-01-10 21:00 | 2025-01-13 21:00 | S | 3
Seal Rock | SK4 | 83 | 2025-01-27 06:00 | 2025-01-29 18:00 | S | 2.5
Turlough Hill | TH1 | 73 | 2025-03-02 06:00 | 2025-03-14 18:00 | S | 12.5
Turlough Hill | TH2 | 73 | 2025-03-02 06:00 | 2025-03-14 18:00 | S | 12.5
Turlough Hill | TH3 | 73 | 2025-03-02 06:00 | 2025-03-14 18:00 | S | 12.5
Turlough Hill | TH4 | 73 | 2025-03-02 06:00 | 2025-03-14 18:00 | S | 12.5
Dublin Bay | DB1 | 415 | 2025-03-07 08:00 | 2025-07-18 20:00 | S | 133.5
Great Island | GI4 | 464 | 2025-03-08 | 2025-03-16 | S | 8
Seal Rock | SK3 | 83 | 2025-03-23 06:00 | 2025-04-22 18:00 | S | 30.5
Lee | LE2 | 4 | 2025-03-24 | 2025-04-04 20:00 | S | 11.83
Drybridge | IW1 | 17 | 2025-03-26 | 2025-04-06 | S | 11
Whitebank | DW1 | 61.5 | 2025-03-31 | 2025-04-06 | 26 | 6
Ardnacrusha | AA4 | 24 | 2025-03-31 08:00 | 2025-05-30 20:00 | S | 60.5
Erne | ER4 | 23 | 2025-03-31 08:00 | 2025-05-30 20:00 | S | 60.5
Aghada | AD3 | 19 | 2025-04-01 | 2025-04-07 | S | 6
Moneypoint | MP5 | 1 | 2025-04-01 | 2025-04-04 | S | 3
Huntstown | HNC | 342 | 2025-04-01 21:00 | 2025-05-07 21:00 | S | 36
Whitebank | DW1 | 61.5 | 2025-04-05 | 2025-04-16 | S | 11
Erne | ER2 | 10 | 2025-04-07 08:00 | 2025-04-11 20:00 | S | 4.5
Inchicore | IH1 | 30 | 2025-04-08 | 2025-04-14 | S | 6
Edenderry | ED1 | 118 | 2025-04-10 17:00 | 2025-04-16 08:00 | S | 5.58
Poolbeg | PB6 | 168 | 2025-04-13 | 2025-04-26 20:00 | 84 | 13.83
Poolbeg | PB4 | 148 | 2025-04-13 | 2025-04-26 20:00 | S | 13.83
EWIC | EW1 | 500 | 2025-04-14 09:00 | 2025-04-14 21:00 | S | 0.5
EWIC | EW1 | 500 | 2025-04-14 21:00 | 2025-04-18 23:00 | S | 4.08
Whitebank | DW1 | 61.5 | 2025-04-15 | 2025-04-21 | 26 | 6
Lee | LE3 | 8 | 2025-04-22 | 2025-05-16 20:00 | S | 24.83
Erne | ER1 | 10 | 2025-04-22 08:00 | 2025-05-13 20:00 | S | 21.5
Moneypoint | MP1 | 285 | 2025-05-02 22:00 | 2025-06-27 22:00 | S | 56
Aghada | AD2 | 449 | 2025-05-10 | 2025-06-21 23:00 | S | 42.92
Poolbeg | PB6 | 168 | 2025-05-12 | 2025-05-17 20:00 | 84 | 5.83
Poolbeg | PB5 | 148 | 2025-05-12 | 2025-05-18 | S | 6
Seal Rock | SK3 | 83 | 2025-05-12 18:00 | 2025-05-15 18:00 | S | 3
Seal Rock | SK4 | 83 | 2025-05-13 | 2025-05-15 12:00 | S | 2.5
Lee | LE1 | 15 | 2025-06-03 08:00 | 2025-06-13 20:00 | S | 10.5
Ardnacrusha | AA3 | 19 | 2025-06-03 08:00 | 2025-08-01 20:00 | S | 59.5
Moneypoint | MP3 | 285 | 2025-06-06 22:00 | 2025-06-22 22:00 | S | 16
Liffey | LI1 | 15 | 2025-06-08 08:00 | 2025-06-21 20:00 | S | 13.5
Liffey | LI2 | 15 | 2025-06-08 08:00 | 2025-06-21 20:00 | S | 13.5
Aghada | AT2 | 90 | 2025-06-13 | 2025-06-17 | S | 4
Seal Rock | SK4 | 83 | 2025-06-16 06:00 | 2025-06-20 18:00 | S | 4.5
Aghada | AT4 | 90 | 2025-06-27 | 2025-07-01 | S | 4
Erne | ER3 | 23 | 2025-06-30 08:00 | 2025-08-29 20:00 | S | 60.5
Edenderry | ED1 | 118 | 2025-07-04 12:00 | 2025-09-01 08:00 | S | 58.83
Cloniffeen | SI1 | 50 | 2025-07-07 08:00 | 2025-07-08 17:00 | S | 1.33
Cloniffeen | SI2 | 50 | 2025-07-07 08:00 | 2025-07-08 17:00 | S | 1.33
Derrycarney | LU1 | 50 | 2025-07-21 08:00 | 2025-07-22 17:00 | S | 1.33
Derrycarney | LU2 | 50 | 2025-07-21 08:00 | 2025-07-22 17:00 | S | 1.33
EWIC | EW1 | 500 | 2025-08-15 11:00 | 2025-08-15 23:00 | S | 0.5
Moneypoint | MP2 | 285 | 2025-08-29 22:00 | 2025-10-31 22:00 | S | 63
Whitegate | WG1 | 444 | 2025-09-05 21:00 | 2025-09-15 21:00 | S | 10
Seal Rock | SK3 | 83 | 2025-09-08 06:00 | 2025-09-10 18:00 | S | 2.5
Edenderry | ED3 | 58 | 2025-09-15 08:00 | 2025-09-24 18:00 | S | 9.42
Edenderry | ED5 | 58 | 2025-09-15 08:00 | 2025-09-24 18:00 | S | 9.42
Ardnacrusha | AA1 | 21 | 2025-09-15 08:00 | 2025-09-19 20:00 | S | 4.5
Ardnacrusha | AA2 | 22 | 2025-09-22 08:00 | 2025-09-26 20:00 | S | 4.5
Tynagh | TYC | 404 | 2025-09-28 20:00 | 2025-10-03 20:00 | S | 5
Whitebank | DW1 | 61.5 | 2025-10-05 | 2025-10-09 | 26 | 4
Aghada | AD3 | 19 | 2025-10-07 | 2025-10-11 | S | 4
Whitebank | DW1 | 61.5 | 2025-10-12 | 2025-10-16 | 26 | 4
Inchicore | IH1 | 30 | 2025-10-14 | 2025-10-18 | S | 4
Aghada | AD2 | 449 | 2025-10-23 | 2025-10-28 23:00 | S | 5.92
Great Island | GI4 | 464 | 2025-11-01 | 2025-11-30 | S | 29
Seal Rock | SK4 | 83 | 2025-11-03 06:00 | 2025-11-05 18:00 | S | 2.5
Edenderry | ED1 | 118 | 2025-12-26 12:00 | 2026-01-01 08:00 | S | 5.83
|  |  | Scheduled Outage | S
|  |  | Forced Outage | F
|  |  | Unit partially available | 10

## Outage Plan SONI
2025 GENERATION OUTAGE PLAN (SONI)
|  | Month | Jan '2025 |  |  |  |  | Feb '2025 |  |  |  | Mar '2025 |  |  |  |  | Apr '2025 |  |  |  | May '2025 |  |  |  | Jun '2025 |  |  |  |  | Jul '2025 |  |  |  | Aug '2025 |  |  |  | Sep '2025 |  |  |  |  | Oct '2025 |  |  |  | Nov '2025 |  |  |  | Dec '2025
|  | Week | 1 '2025 | 2 '2025 | 3 '2025 | 4 '2025 | 5 '2025 | 6 '2025 | 7 '2025 | 8 '2025 | 9 '2025 | 10 '2025 | 11 '2025 | 12 '2025 | 13 '2025 | 14 '2025 | 15 '2025 | 16 '2025 | 17 '2025 | 18 '2025 | 19 '2025 | 20 '2025 | 21 '2025 | 22 '2025 | 23 '2025 | 24 '2025 | 25 '2025 | 26 '2025 | 27 '2025 | 28 '2025 | 29 '2025 | 30 '2025 | 31 '2025 | 32 '2025 | 33 '2025 | 34 '2025 | 35 '2025 | 36 '2025 | 37 '2025 | 38 '2025 | 39 '2025 | 40 '2025 | 41 '2025 | 42 '2025 | 43 '2025 | 44 '2025 | 45 '2025 | 46 '2025 | 47 '2025 | 48 '2025 | 49 '2025 | 50 '2025 | 51 '2025 | 52 '2025 | 53 '2025
Station | Unit | NPR
AC Automation | NIACA | 8
Activation Energy | NIAEA | 9
Ballylumford | NIB10 | 94
Ballylumford | NIB31 | 249
Ballylumford | NIB32 | 249
Ballylumford | NIBGT1 | 58 | [39 empty] | S
Ballylumford | NIBGT2 | 58 | [5 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S | [22 empty] | S
Contour Global | NICG2 | 3
Contour Global | NICGA | 12
Coolkeeragh | NIC30 | 408 | [35 empty] | S | S
Coolkeeragh | NICGT8 | 53 | [20 empty] | S
Empower | NIEMP | 3
Endeco Technologies | NIECA | 13
Energy Trading | NIETB | 9
Energy Trading | NIETD | 5
Energy Trading | NIETR | 19
iPower | NIAGU | 74
Kilroot | NIKGT1 | 29
Kilroot | NIKGT2 | 29 | [29 empty] | S | S | S | S | S | S
Kilroot | NIKGT3 | 42 | [17 empty] | S | S | S | S | S
Kilroot | NIKGT4 | 42 | [17 empty] | S | S | S | S | S
Kilroot | NIKGT6 | 350
Kilroot | NIKGT7 | 350
Lisahally | NILPS | 18
Moyle | MOYLE | 450
Powerhouse Generation | NIPH1 | 34

## SONI Outages
Upcoming Outages including STMOs and Annual Outages
Station | Unit | NPR | Start Date | End Date | Value | Duration
Coolkeeragh | NIC30 | 408 | 2025-01-04 | 2025-01-06 | S | 2
Ballylumford | NIBGT2 | 58 | 2025-02-01 | 2025-05-02 | S | 90
Kilroot | NIKGT3 | 42 | 2025-02-10 | 2025-02-13 | S | 3
Kilroot | NIKGT4 | 42 | 2025-02-13 | 2025-02-16 | S | 3
Ballylumford | NIB31 | 249 | 2025-04-04 | 2025-04-07 | S | 3
Ballylumford | NIB32 | 249 | 2025-04-11 | 2025-04-14 | S | 3
Ballylumford | NIB10 | 94 | 2025-04-25 | 2025-04-28 | S | 3
Kilroot | NIKGT3 | 42 | 2025-05-01 | 2025-06-01 | S | 31
Kilroot | NIKGT4 | 42 | 2025-05-01 | 2025-06-01 | S | 31
Coolkeeragh | NIC30 | 408 | 2025-05-10 | 2025-05-12 | S | 2
Coolkeeragh | NICGT8 | 53 | 2025-05-19 | 2025-05-24 | S | 5
Moyle | MOYLE | 450 | 2025-06-02 | 2025-06-14 | 250 | 12
Moyle | MOYLE | 450 | 2025-06-16 | 2025-06-28 | 250 | 12
Kilroot | NIKGT2 | 29 | 2025-07-18 | 2025-09-01 | S | 45
Coolkeeragh | NIC30 | 408 | 2025-08-31 | 2025-09-12 | S | 12
Ballylumford | NIB31 | 249 | 2025-09-12 | 2025-09-16 | S | 4
Ballylumford | NIB32 | 249 | 2025-09-12 | 2025-09-19 | 161 | 7
Ballylumford | NIB31 | 249 | 2025-09-16 | 2025-09-26 | 161 | 10
Ballylumford | NIB32 | 249 | 2025-09-19 | 2025-09-23 | S | 4
Ballylumford | NIB32 | 249 | 2025-09-23 | 2025-09-26 | 161 | 3
Ballylumford | NIBGT1 | 58 | 2025-10-01 | 2025-10-07 | S | 6
Ballylumford | NIBGT2 | 58 | 2025-10-07 | 2025-10-13 | S | 6
Ballylumford | NIB10 | 94 | 2025-10-17 | 2025-10-22 | S | 5
|  |  | Scheduled Outage | S
|  |  | Forced Outage | F
|  |  | Unit partially available | 10

## Outage Plan All Island
2025 GENERATION OUTAGE PLAN (All Island)
|  | Month | Jan '2025 |  |  |  |  | Feb '2025 |  |  |  | Mar '2025 |  |  |  |  | Apr '2025 |  |  |  | May '2025 |  |  |  | Jun '2025 |  |  |  |  | Jul '2025 |  |  |  | Aug '2025 |  |  |  | Sep '2025 |  |  |  |  | Oct '2025 |  |  |  | Nov '2025 |  |  |  | Dec '2025
|  | Week | 1 '2025 | 2 '2025 | 3 '2025 | 4 '2025 | 5 '2025 | 6 '2025 | 7 '2025 | 8 '2025 | 9 '2025 | 10 '2025 | 11 '2025 | 12 '2025 | 13 '2025 | 14 '2025 | 15 '2025 | 16 '2025 | 17 '2025 | 18 '2025 | 19 '2025 | 20 '2025 | 21 '2025 | 22 '2025 | 23 '2025 | 24 '2025 | 25 '2025 | 26 '2025 | 27 '2025 | 28 '2025 | 29 '2025 | 30 '2025 | 31 '2025 | 32 '2025 | 33 '2025 | 34 '2025 | 35 '2025 | 36 '2025 | 37 '2025 | 38 '2025 | 39 '2025 | 40 '2025 | 41 '2025 | 42 '2025 | 43 '2025 | 44 '2025 | 45 '2025 | 46 '2025 | 47 '2025 | 48 '2025 | 49 '2025 | 50 '2025 | 51 '2025 | 52 '2025 | 53 '2025
Station | Unit | NPR
AC Automation | NIACA | 8
Activation Energy | NIAEA | 9
Aghada | AD2 | 449 | [19 empty] | S | S | S | S | S | S | [17 empty] | S
Aghada | AD3 | 19 | [13 empty] | S | [26 empty] | S
Aghada | AD4 | 75
Aghada | AD5 | 75
Aghada | AT1 | 90
Aghada | AT2 | 90
Aghada | AT4 | 90
Ardnacrusha | AA1 | 21 | [37 empty] | S
Ardnacrusha | AA2 | 22 | [38 empty] | S
Ardnacrusha | AA3 | 19 | [22 empty] | S | S | S | S | S | S | S | S | S
Ardnacrusha | AA4 | 24 | [13 empty] | S | S | S | S | S | S | S | S | S
Aughinish Alumina | EB1 | 25
Ballylumford | NIB10 | 94
Ballylumford | NIB31 | 249
Ballylumford | NIB32 | 249
Ballylumford | NIBGT1 | 58 | [39 empty] | S
Ballylumford | NIBGT2 | 58 | [5 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S | [22 empty] | S
Banoge | OD1 | 9
Cloniffeen | SI1 | 50
Cloniffeen | SI2 | 50
Contour Global | NICG2 | 3
Contour Global | NICGA | 12
Coolkeeragh | NIC30 | 408 | [35 empty] | S | S
Coolkeeragh | NICGT8 | 53 | [20 empty] | S
Coolnanoonagh | KZ3 | 2
Coolnanoonagh | KZ4 | 27
Corduff | FG2 | 64
Crane | AV1 | 16
Derrycarney | LU1 | 50
Derrycarney | LU2 | 50
Drybridge | IW1 | 17 | [12 empty] | S | S
Dublin Bay | DB1 | 415 | [10 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Dunsoghly | DG1 | 50
Edenderry | ED1 | 118 | [27 empty] | S | S | S | S | S | S | S | S
Edenderry | ED3 | 58 | [37 empty] | S
Edenderry | ED5 | 58 | [37 empty] | S
Electric Ireland | EI1 | 17
Empower | NIEMP | 3
Endeco Technologies | EC1 | 52
Endeco Technologies | EC2 | 12
Endeco Technologies | EC3 | 5
Endeco Technologies | EC4 | 5
Endeco Technologies | EC5 | 21
Endeco Technologies | NIECA | 13
Enel X | AE1 | 87
Enel X | AE2 | 13
Enel X | AE3 | 14
Enel X | AE4 | 16
Enel X | AE5 | 16
Enel X | EN1 | 16
Enel X | EN2 | 17
Enel X | EN3 | 17
Enel X | EN4 | 16
Enel X | EN5 | 6
Enel X | EN6 | 11
Enel X | EN8 | 24
Enel X | EN9 | 16
Enel X | EX1 | 21
Energy Trading | NIETB | 9
Energy Trading | NIETD | 5
Energy Trading | NIETR | 19
Energy Trading Ireland | ET1 | 5
Erne | ER1 | 10 | [16 empty] | S | S | S
Erne | ER2 | 10 | [14 empty] | S
Erne | ER3 | 23 | [26 empty] | S | S | S | S | S | S | S | S | S
Erne | ER4 | 23 | [13 empty] | S | S | S | S | S | S | S | S | S
EWIC | EW1 | 500 | [15 empty] | S
Gardnershill | GP1 | 8
Golagh | GO2 | 3
Gorman | GF1 | 50
Great Island | GI4 | 464 | [10 empty] | S | [33 empty] | S | S | S | S
Huntstown | HN2 | 402
Huntstown | HNC | 342 | [13 empty] | S | S | S | S | S
Inchicore | IH1 | 30 | [14 empty] | S | [26 empty] | S
iPower | NIAGU | 74
Irishtown | IS2 | 30
Irishtown | IS3 | 64
Kilroot | NIKGT1 | 29
Kilroot | NIKGT2 | 29 | [29 empty] | S | S | S | S | S | S
Kilroot | NIKGT3 | 42 | [17 empty] | S | S | S | S | S
Kilroot | NIKGT4 | 42 | [17 empty] | S | S | S | S | S
Kilroot | NIKGT6 | 350
Kilroot | NIKGT7 | 350
Kilteel | PN1 | 30
Knockacummer | KC1 | 100
Lee | LE1 | 15 | [22 empty] | S | S
Lee | LE2 | 4 | [12 empty] | S | S
Lee | LE3 | 8 | [16 empty] | S | S | S | S
Liffey | LI1 | 15 | [23 empty] | S | S
Liffey | LI2 | 15 | [23 empty] | S | S
Liffey | LI4 | 4
Liffey | LI5 | 4
Lisahally | NILPS | 18
Lisdrum | LF1 | 60
Moneypoint | MP1 | 285 | [18 empty] | S | S | S | S | S | S | S | S
Moneypoint | MP2 | 285 | [35 empty] | S | S | S | S | S | S | S | S | S
Moneypoint | MP3 | 285 | [23 empty] | S | S
Moneypoint | MP5 | 1
Moyle | MOYLE | 450
Northwall | NW8 | 191
Poolbeg | PB4 | 148 | [15 empty] | S | S
Poolbeg | PB5 | 148 | [19 empty] | S
Poolbeg | PB6 | 168
Poolbeg | PB7 | 64
Poolbeg | PB8 | 75
Powerhouse Generation | NIPH1 | 34
Powerhouse Generation | PG1 | 10
Rhode | RP1 | 52
Rhode | RP2 | 52
Seal Rock | SK3 | 83 | [12 empty] | S | S | S | S
Seal Rock | SK4 | 83 | [24 empty] | S
Shannonbridge | SQ1 | 262
Tarbert | TB5 | 160
Tawnaghmore | KF2 | 11
Tawnaghmore | TP1 | 52
Tawnaghmore | TP3 | 52
Tobertoreen | XT2 | 11
Turlough Hill | TH1 | 73 | [9 empty] | S | S
Turlough Hill | TH2 | 73 | [9 empty] | S | S
Turlough Hill | TH3 | 73 | [9 empty] | S | S
Turlough Hill | TH4 | 73 | [9 empty] | S | S
Tynagh | TYC | 404 | [39 empty] | S
Uggool | SO1 | 105
Veolia Alternative Energy | DP1 | 5
Veolia Alternative Energy | DP2 | 30
Veolia Alternative Energy | DP3 | 9
VIOTAS | EE1 | 65
VIOTAS | EE2 | 30
VIOTAS | EE3 | 11
VIOTAS | EE4 | 13
VIOTAS | EE5 | 17
VIOTAS | EE6 | 14
VIOTAS | EE7 | 7
VIOTAS | EE8 | 12
VIOTAS | EE9 | 11
Whitebank | DW1 | 62 | [14 empty] | S
Whitegate | WG1 | 444 | [36 empty] | S

## All Island Outages
Upcoming Outages including STMOs and Annual Outages
Station | Unit | NPR | Start Date | End Date | Value | Duration
Edenderry | ED1 | 118 | 2024-12-26 12:00 | 2025-01-01 08:00 | S | 5.83
Coolkeeragh | NIC30 | 408 | 2025-01-04 | 2025-01-06 | S | 2
Huntstown | HNC | 342 | 2025-01-10 21:00 | 2025-01-13 21:00 | S | 3
Seal Rock | SK4 | 83 | 2025-01-27 06:00 | 2025-01-29 18:00 | S | 2.5
Ballylumford | NIBGT2 | 58 | 2025-02-01 | 2025-05-02 | S | 90
Kilroot | NIKGT3 | 42 | 2025-02-10 | 2025-02-13 | S | 3
Kilroot | NIKGT4 | 42 | 2025-02-13 | 2025-02-16 | S | 3
Turlough Hill | TH1 | 73 | 2025-03-02 06:00 | 2025-03-14 18:00 | S | 12.5
Turlough Hill | TH2 | 73 | 2025-03-02 06:00 | 2025-03-14 18:00 | S | 12.5
Turlough Hill | TH3 | 73 | 2025-03-02 06:00 | 2025-03-14 18:00 | S | 12.5
Turlough Hill | TH4 | 73 | 2025-03-02 06:00 | 2025-03-14 18:00 | S | 12.5
Dublin Bay | DB1 | 415 | 2025-03-07 08:00 | 2025-07-18 20:00 | S | 133.5
Great Island | GI4 | 464 | 2025-03-08 | 2025-03-16 | S | 8
Seal Rock | SK3 | 83 | 2025-03-23 06:00 | 2025-04-22 18:00 | S | 30.5
Lee | LE2 | 4 | 2025-03-24 | 2025-04-04 20:00 | S | 11.83
Drybridge | IW1 | 17 | 2025-03-26 | 2025-04-06 | S | 11
Whitebank | DW1 | 61.5 | 2025-03-31 | 2025-04-06 | 26 | 6
Ardnacrusha | AA4 | 24 | 2025-03-31 08:00 | 2025-05-30 20:00 | S | 60.5
Erne | ER4 | 23 | 2025-03-31 08:00 | 2025-05-30 20:00 | S | 60.5
Aghada | AD3 | 19 | 2025-04-01 | 2025-04-07 | S | 6
Moneypoint | MP5 | 1 | 2025-04-01 | 2025-04-04 | S | 3
Huntstown | HNC | 342 | 2025-04-01 21:00 | 2025-05-07 21:00 | S | 36
Ballylumford | NIB31 | 249 | 2025-04-04 | 2025-04-07 | S | 3
Whitebank | DW1 | 61.5 | 2025-04-05 | 2025-04-16 | S | 11
Erne | ER2 | 10 | 2025-04-07 08:00 | 2025-04-11 20:00 | S | 4.5
Inchicore | IH1 | 30 | 2025-04-08 | 2025-04-14 | S | 6
Edenderry | ED1 | 118 | 2025-04-10 17:00 | 2025-04-16 08:00 | S | 5.58
Ballylumford | NIB32 | 249 | 2025-04-11 | 2025-04-14 | S | 3
Poolbeg | PB6 | 168 | 2025-04-13 | 2025-04-26 20:00 | 84 | 13.83
Poolbeg | PB4 | 148 | 2025-04-13 | 2025-04-26 20:00 | S | 13.83
EWIC | EW1 | 500 | 2025-04-14 09:00 | 2025-04-14 21:00 | S | 0.5
EWIC | EW1 | 500 | 2025-04-14 21:00 | 2025-04-18 23:00 | S | 4.08
Whitebank | DW1 | 61.5 | 2025-04-15 | 2025-04-21 | 26 | 6
Lee | LE3 | 8 | 2025-04-22 | 2025-05-16 20:00 | S | 24.83
Erne | ER1 | 10 | 2025-04-22 08:00 | 2025-05-13 20:00 | S | 21.5
Ballylumford | NIB10 | 94 | 2025-04-25 | 2025-04-28 | S | 3
Kilroot | NIKGT3 | 42 | 2025-05-01 | 2025-06-01 | S | 31
Kilroot | NIKGT4 | 42 | 2025-05-01 | 2025-06-01 | S | 31
Moneypoint | MP1 | 285 | 2025-05-02 22:00 | 2025-06-27 22:00 | S | 56
Aghada | AD2 | 449 | 2025-05-10 | 2025-06-21 23:00 | S | 42.92
Coolkeeragh | NIC30 | 408 | 2025-05-10 | 2025-05-12 | S | 2
Poolbeg | PB6 | 168 | 2025-05-12 | 2025-05-17 20:00 | 84 | 5.83
Poolbeg | PB5 | 148 | 2025-05-12 | 2025-05-18 | S | 6
Seal Rock | SK3 | 83 | 2025-05-12 18:00 | 2025-05-15 18:00 | S | 3
Seal Rock | SK4 | 83 | 2025-05-13 | 2025-05-15 12:00 | S | 2.5
Coolkeeragh | NICGT8 | 53 | 2025-05-19 | 2025-05-24 | S | 5
Moyle | MOYLE | 450 | 2025-06-02 | 2025-06-14 | 250 | 12
Lee | LE1 | 15 | 2025-06-03 08:00 | 2025-06-13 20:00 | S | 10.5
Ardnacrusha | AA3 | 19 | 2025-06-03 08:00 | 2025-08-01 20:00 | S | 59.5
Moneypoint | MP3 | 285 | 2025-06-06 22:00 | 2025-06-22 22:00 | S | 16
Liffey | LI1 | 15 | 2025-06-08 08:00 | 2025-06-21 20:00 | S | 13.5
Liffey | LI2 | 15 | 2025-06-08 08:00 | 2025-06-21 20:00 | S | 13.5
Aghada | AT2 | 90 | 2025-06-13 | 2025-06-17 | S | 4
Moyle | MOYLE | 450 | 2025-06-16 | 2025-06-28 | 250 | 12
Seal Rock | SK4 | 83 | 2025-06-16 06:00 | 2025-06-20 18:00 | S | 4.5
Aghada | AT4 | 90 | 2025-06-27 | 2025-07-01 | S | 4
Erne | ER3 | 23 | 2025-06-30 08:00 | 2025-08-29 20:00 | S | 60.5
Edenderry | ED1 | 118 | 2025-07-04 12:00 | 2025-09-01 08:00 | S | 58.83
Cloniffeen | SI1 | 50 | 2025-07-07 08:00 | 2025-07-08 17:00 | S | 1.33
Cloniffeen | SI2 | 50 | 2025-07-07 08:00 | 2025-07-08 17:00 | S | 1.33
Kilroot | NIKGT2 | 29 | 2025-07-18 | 2025-09-01 | S | 45
Derrycarney | LU1 | 50 | 2025-07-21 08:00 | 2025-07-22 17:00 | S | 1.33
Derrycarney | LU2 | 50 | 2025-07-21 08:00 | 2025-07-22 17:00 | S | 1.33
EWIC | EW1 | 500 | 2025-08-15 11:00 | 2025-08-15 23:00 | S | 0.5
Moneypoint | MP2 | 285 | 2025-08-29 22:00 | 2025-10-31 22:00 | S | 63
Coolkeeragh | NIC30 | 408 | 2025-08-31 | 2025-09-12 | S | 12
Whitegate | WG1 | 444 | 2025-09-05 21:00 | 2025-09-15 21:00 | S | 10
Seal Rock | SK3 | 83 | 2025-09-08 06:00 | 2025-09-10 18:00 | S | 2.5
Ballylumford | NIB31 | 249 | 2025-09-12 | 2025-09-16 | S | 4
Ballylumford | NIB32 | 249 | 2025-09-12 | 2025-09-19 | 161 | 7
Edenderry | ED3 | 58 | 2025-09-15 08:00 | 2025-09-24 18:00 | S | 9.42
Edenderry | ED5 | 58 | 2025-09-15 08:00 | 2025-09-24 18:00 | S | 9.42
Ardnacrusha | AA1 | 21 | 2025-09-15 08:00 | 2025-09-19 20:00 | S | 4.5
Ballylumford | NIB31 | 249 | 2025-09-16 | 2025-09-26 | 161 | 10
Ballylumford | NIB32 | 249 | 2025-09-19 | 2025-09-23 | S | 4
Ardnacrusha | AA2 | 22 | 2025-09-22 08:00 | 2025-09-26 20:00 | S | 4.5
Ballylumford | NIB32 | 249 | 2025-09-23 | 2025-09-26 | 161 | 3
Tynagh | TYC | 404 | 2025-09-28 20:00 | 2025-10-03 20:00 | S | 5
Ballylumford | NIBGT1 | 58 | 2025-10-01 | 2025-10-07 | S | 6
Whitebank | DW1 | 61.5 | 2025-10-05 | 2025-10-09 | 26 | 4
Aghada | AD3 | 19 | 2025-10-07 | 2025-10-11 | S | 4
Ballylumford | NIBGT2 | 58 | 2025-10-07 | 2025-10-13 | S | 6
Whitebank | DW1 | 61.5 | 2025-10-12 | 2025-10-16 | 26 | 4
Inchicore | IH1 | 30 | 2025-10-14 | 2025-10-18 | S | 4
Ballylumford | NIB10 | 94 | 2025-10-17 | 2025-10-22 | S | 5
Aghada | AD2 | 449 | 2025-10-23 | 2025-10-28 23:00 | S | 5.92
Great Island | GI4 | 464 | 2025-11-01 | 2025-11-30 | S | 29
Seal Rock | SK4 | 83 | 2025-11-03 06:00 | 2025-11-05 18:00 | S | 2.5
Edenderry | ED1 | 118 | 2025-12-26 12:00 | 2026-01-01 08:00 | S | 5.83
|  |  | Scheduled Outage | S
|  |  | Forced Outage | F
|  |  | Unit partially available | 10