## Outage Plan EirGrid
2021 GENERATION OUTAGE PLAN (EIRGRID)
|  | Month | Jan '2021 |  |  |  |  | Feb '2021 |  |  |  | Mar '2021 |  |  |  |  | Apr '2021 |  |  |  | May '2021 |  |  |  |  | Jun '2021 |  |  |  | Jul '2021 |  |  |  | Aug '2021 |  |  |  |  | Sep '2021 |  |  |  | Oct '2021 |  |  |  | Nov '2021 |  |  |  |  | Dec '2021
|  | Week | 53 '2021 | 1 '2021 | 2 '2021 | 3 '2021 | 4 '2021 | 5 '2021 | 6 '2021 | 7 '2021 | 8 '2021 | 9 '2021 | 10 '2021 | 11 '2021 | 12 '2021 | 13 '2021 | 14 '2021 | 15 '2021 | 16 '2021 | 17 '2021 | 18 '2021 | 19 '2021 | 20 '2021 | 21 '2021 | 22 '2021 | 23 '2021 | 24 '2021 | 25 '2021 | 26 '2021 | 27 '2021 | 28 '2021 | 29 '2021 | 30 '2021 | 31 '2021 | 32 '2021 | 33 '2021 | 34 '2021 | 35 '2021 | 36 '2021 | 37 '2021 | 38 '2021 | 39 '2021 | 40 '2021 | 41 '2021 | 42 '2021 | 43 '2021 | 44 '2021 | 45 '2021 | 46 '2021 | 47 '2021 | 48 '2021 | 49 '2021 | 50 '2021 | 51 '2021 | 52 '2021
Station | Unit | NPR
Activation Energy | AE1 | 95
Activation Energy | AE2 | 8
Activation Energy | AE3 | 14
Activation Energy | AE4 | 15
Activation Energy | AE5 | 15
Activation Energy | EN5 | 6
Activation Energy | EN6 | 11
Aghada | AD2 | 431
Aghada | AT1 | 90
Aghada | AT2 | 90
Aghada | AT4 | 90 | [36 empty] | S | S
Ardnacrusha | AA1 | 21 | [15 empty] | S
Ardnacrusha | AA2 | 22 | [19 empty] | S
Ardnacrusha | AA3 | 19 | [30 empty] | S | S | S | S | S | S | S | S
Ardnacrusha | AA4 | 24 | [24 empty] | S
DAE Virtual Power Plant | DP1 | 19
DAE Virtual Power Plant | DP2 | 26
Dublin Bay | DB1 | 405
Dublin Waste To Energy | DW1 | 62
Edenderry | ED1 | 118 | [24 empty] | S | S | S | [25 empty] | S
Edenderry | ED3 | 58
Edenderry | ED5 | 58
Electric Ireland | EI1 | 20
Electricity Exchange DSU | EE1 | 51
Electricity Exchange DSU | EE2 | 28
Electricity Exchange DSU | EE3 | 8
Electricity Exchange DSU | EE4 | 9
Electricity Exchange DSU | EE5 | 6
Endeco Technologies | EC1 | 42
Endeco Technologies | EC2 | 11
Endeco Technologies | EC5 | 15
Energy Trading | ET1 | 13
Erne | ER1 | 10 | [15 empty] | S
Erne | ER2 | 10 | [19 empty] | S
Erne | ER3 | 22 | [24 empty] | S | S | S
Erne | ER4 | 22 | [36 empty] | S
EWIC | EW1 | 500
Great Island | GI4 | 461
Huntstown | HN2 | 400 | [15 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Huntstown | HNC | 342 | [40 empty] | S
Indaver | IW1 | 17 | [15 empty] | S | S
Knockacummer | KC1 | 100
Lanesboro | LR4 | 91 |  | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F
Lee | LE1 | 15 | [19 empty] | S
Lee | LE2 | 4 | [15 empty] | S
Lee | LE3 | 8 | [24 empty] | S
Liffey | LI1 | 15 | [15 empty] | S | S | S | S
Liffey | LI2 | 15 | [15 empty] | S | S | S | S
Liffey | LI4 | 4
Liffey | LI5 | 4 | [20 empty] | S | S | S | S
Moneypoint | MP1 | 285 | [31 empty] | S
Moneypoint | MP2 | 285 | [31 empty] | S
Moneypoint | MP3 | 285 | [34 empty] | S
North Wall | NW5 | 104 | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Poolbeg | PB4 | 154 | [12 empty] | S
Poolbeg | PB5 | 146 | [14 empty] | S
Poolbeg | PB6 | 168 | [14 empty] | S | S | S | S | S
Powerhouse Generation | PG1 | 11
Rhode | RP1 | 52 | [33 empty] | S
Rhode | RP2 | 52 | [33 empty] | S
Seal Rock | SK3 | 85
Seal Rock | SK4 | 85 | [27 empty] | S
Seecon | SO1 | 105
Tarbert | TB1 | 54 | [21 empty] | S
Tarbert | TB2 | 54 | [21 empty] | S
Tarbert | TB3 | 241
Tarbert | TB4 | 243
Tawnaghmore | TP1 | 52
Tawnaghmore | TP3 | 52
Turlough Hill | TH1 | 73 | [28 empty] | S
Turlough Hill | TH2 | 73 | [28 empty] | S
Turlough Hill | TH3 | 73 | [26 empty] | S
Turlough Hill | TH4 | 73 | [26 empty] | S
Tynagh | TYC | 384 | [13 empty] | S
Viridian Energy | VE1 | 20
Viridian Energy DSU | VE2 | 13
West Offaly | WO4 | 137 |  | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F
Whitegate | WG1 | 444

## EirGrid Outages
Upcoming Outages including STMOs and Annual Outages
Station | Unit | NPR | Start Date | End Date | Value | Duration
North Wall | NW5 | 104 | 2019-10-01 | 2022-10-01 | S | 1096
Edenderry | ED1 | 118 | 2020-12-26 13:00 | 2021-01-02 08:00 | S | 6.75
West Offaly | WO4 | 137 | 2021-01-01 | 2023-01-01 | F | 730
Lanesboro | LR4 | 91 | 2021-01-01 | 2023-01-01 | F | 730
Seal Rock | SK3 | 85 | 2021-01-17 07:00 | 2021-01-19 17:00 | S | 2.42
Aghada | AD2 | 431 | 2021-01-22 | 2021-01-27 | S | 5
Seal Rock | SK4 | 85 | 2021-03-07 07:00 | 2021-03-09 17:00 | S | 2.42
Edenderry | ED1 | 118 | 2021-03-12 18:00 | 2021-03-18 08:00 | S | 5.58
Poolbeg | PB6 | 168 | 2021-03-23 | 2021-03-27 | 84 | 4
Poolbeg | PB4 | 154 | 2021-03-23 | 2021-03-27 | S | 4
Tynagh | TYC | 384 | 2021-03-28 22:00 | 2021-04-02 22:00 | S | 5
Poolbeg | PB6 | 168 | 2021-04-06 | 2021-05-11 | S | 35
Poolbeg | PB5 | 146 | 2021-04-06 | 2021-04-10 | S | 4
Indaver | IW1 | 17 | 2021-04-12 | 2021-04-27 | S | 15
Lee | LE2 | 4 | 2021-04-12 08:00 | 2021-04-16 20:00 | S | 4.5
Erne | ER1 | 10 | 2021-04-12 08:00 | 2021-04-16 20:00 | S | 4.5
Liffey | LI2 | 15 | 2021-04-12 08:00 | 2021-05-09 17:00 | S | 27.33
Liffey | LI1 | 15 | 2021-04-12 08:00 | 2021-05-09 17:00 | S | 27.33
Ardnacrusha | AA1 | 21 | 2021-04-12 08:00 | 2021-04-16 20:00 | S | 4.5
Huntstown | HN2 | 400 | 2021-04-15 23:00 | 2021-07-24 23:00 | S | 100
Whitegate | WG1 | 444 | 2021-05-07 | 2021-05-14 | S | 7
Lee | LE1 | 15 | 2021-05-10 08:00 | 2021-05-14 20:00 | S | 4.5
Erne | ER2 | 10 | 2021-05-10 08:00 | 2021-05-14 20:00 | S | 4.5
Ardnacrusha | AA2 | 22 | 2021-05-10 08:00 | 2021-05-14 20:00 | S | 4.5
Seal Rock | SK3 | 85 | 2021-05-10 21:00 | 2021-05-12 12:00 | S | 1.58
Seal Rock | SK4 | 85 | 2021-05-10 23:00 | 2021-05-11 21:00 | S | 0.92
Edenderry | ED3 | 58 | 2021-05-15 08:00 | 2021-05-15 18:00 | S | 0.42
Edenderry | ED5 | 58 | 2021-05-15 08:00 | 2021-05-15 18:00 | S | 0.42
Liffey | LI5 | 4 | 2021-05-17 08:00 | 2021-06-13 17:00 | S | 27.33
Tarbert | TB2 | 54 | 2021-05-24 | 2021-05-31 | S | 7
Tarbert | TB1 | 54 | 2021-05-24 | 2021-05-31 | S | 7
EWIC | EW1 | 500 | 2021-06-01 | 2021-06-03 21:00 | S | 2.83
Tarbert | TB3 | 241 | 2021-06-04 | 2021-06-11 | S | 7
Edenderry | ED1 | 118 | 2021-06-11 12:00 | 2021-07-06 08:00 | S | 24.83
Lee | LE3 | 8 | 2021-06-14 08:00 | 2021-06-18 20:00 | S | 4.5
Erne | ER3 | 22.5 | 2021-06-14 08:00 | 2021-07-04 20:00 | S | 20.5
Ardnacrusha | AA4 | 24 | 2021-06-14 08:00 | 2021-06-18 20:00 | S | 4.5
Turlough Hill | TH4 | 73 | 2021-06-27 08:00 | 2021-07-03 17:00 | S | 6.33
Turlough Hill | TH3 | 73 | 2021-06-27 08:00 | 2021-07-03 17:00 | S | 6.33
Seal Rock | SK4 | 85 | 2021-07-05 07:00 | 2021-07-09 17:00 | S | 4.42
Aghada | AT1 | 90 | 2021-07-05 08:00 | 2021-07-08 | S | 2.67
Turlough Hill | TH2 | 73 | 2021-07-11 08:00 | 2021-07-17 17:00 | S | 6.33
Turlough Hill | TH1 | 73 | 2021-07-11 08:00 | 2021-07-17 17:00 | S | 6.33
Aghada | AT2 | 90 | 2021-07-12 | 2021-07-15 | S | 3
Ardnacrusha | AA3 | 19 | 2021-07-27 08:00 | 2021-09-21 20:00 | S | 56.5
Moneypoint | MP2 | 285 | 2021-07-30 22:00 | 2021-08-11 22:00 | S | 12
Moneypoint | MP1 | 285 | 2021-08-01 22:00 | 2021-08-10 22:00 | S | 9
Rhode | RP2 | 52 | 2021-08-14 | 2021-08-22 | S | 8
Rhode | RP1 | 52 | 2021-08-14 | 2021-08-22 | S | 8
Moneypoint | MP3 | 285 | 2021-08-20 22:00 | 2021-08-29 22:00 | S | 9
Liffey | LI4 | 4 | 2021-09-01 08:00 | 2021-09-03 17:00 | S | 2.33
Aghada | AT4 | 90 | 2021-09-06 | 2021-09-20 | S | 14
Seal Rock | SK3 | 85 | 2021-09-06 07:00 | 2021-09-09 07:00 | S | 3
Erne | ER4 | 22.5 | 2021-09-06 08:00 | 2021-09-10 20:00 | S | 4.5
Great Island | GI4 | 461 | 2021-09-18 | 2021-09-25 | S | 7
Huntstown | HNC | 342 | 2021-10-01 | 2021-10-12 | S | 11
Dublin Bay | DB1 | 405 | 2021-10-15 13:00 | 2021-10-19 06:00 | S | 3.67
Seal Rock | SK4 | 85 | 2021-11-07 07:00 | 2021-11-09 17:00 | S | 2.42
Turlough Hill | TH1 | 73 | 2021-11-16 08:00 | 2021-11-18 17:00 | S | 2.33
Turlough Hill | TH2 | 73 | 2021-11-16 08:00 | 2021-11-18 17:00 | S | 2.33
Edenderry | ED1 | 118 | 2021-12-26 13:00 | 2022-01-02 08:00 | S | 6.75
|  |  | Scheduled Outage | S
|  |  | Forced Outage | F
|  |  | Unit partially available | 10

## Outage Plan SONI
2021 GENERATION OUTAGE PLAN (SONI)
|  | Month | Jan '2021 |  |  |  |  | Feb '2021 |  |  |  | Mar '2021 |  |  |  |  | Apr '2021 |  |  |  | May '2021 |  |  |  |  | Jun '2021 |  |  |  | Jul '2021 |  |  |  | Aug '2021 |  |  |  |  | Sep '2021 |  |  |  | Oct '2021 |  |  |  | Nov '2021 |  |  |  |  | Dec '2021
|  | Week | 53 '2021 | 1 '2021 | 2 '2021 | 3 '2021 | 4 '2021 | 5 '2021 | 6 '2021 | 7 '2021 | 8 '2021 | 9 '2021 | 10 '2021 | 11 '2021 | 12 '2021 | 13 '2021 | 14 '2021 | 15 '2021 | 16 '2021 | 17 '2021 | 18 '2021 | 19 '2021 | 20 '2021 | 21 '2021 | 22 '2021 | 23 '2021 | 24 '2021 | 25 '2021 | 26 '2021 | 27 '2021 | 28 '2021 | 29 '2021 | 30 '2021 | 31 '2021 | 32 '2021 | 33 '2021 | 34 '2021 | 35 '2021 | 36 '2021 | 37 '2021 | 38 '2021 | 39 '2021 | 40 '2021 | 41 '2021 | 42 '2021 | 43 '2021 | 44 '2021 | 45 '2021 | 46 '2021 | 47 '2021 | 48 '2021 | 49 '2021 | 50 '2021 | 51 '2021 | 52 '2021
Station | Unit | NPR
AC Automation | NIACA | 8
Activation Energy | NIAEA | 9
Ballylumford | NIB10 | 94
Ballylumford | NIB31 | 249
Ballylumford | NIB32 | 249 | [5 empty] | S | S | S | S | S | S | S | S | S
Ballylumford | NIBGT1 | 58 | [20 empty] | S | S | S | S | S | S
Ballylumford | NIBGT2 | 58 | [16 empty] | S
Contour Global | NICG2 | 3
Contour Global | NICGA | 12
Coolkeeragh | NIC30 | 408 | [15 empty] | S | S | S
Coolkeeragh | NICGT8 | 53 | [19 empty] | S
Empower | NIEMP | 3
Endeco Technologies | NIECA | 13
Energy Trading | NIETB | 9
Energy Trading | NIETD | 5
Energy Trading | NIETR | 19
iPower | NIAGU | 74
Kilroot | NIK1 | 256 | [35 empty] | S | S | S | S | S | S | S | S
Kilroot | NIK2 | 258 | [19 empty] | S | S | S | S | S | S | S | S
Kilroot | NIKGT1 | 29
Kilroot | NIKGT2 | 29
Kilroot | NIKGT3 | 42 | [40 empty] | S
Kilroot | NIKGT4 | 42 | [41 empty] | S
Lisahally | NILPS | 18
Moyle | MOYLE | 450
Powerhouse Generation | NIPH1 | 34

## SONI Outages
Upcoming Outages including STMOs and Annual Outages
Station | Unit | NPR | Start Date | End Date | Value | Duration
Ballylumford | NIB32 | 249 | 2021-02-01 | 2021-04-02 | S | 60
Coolkeeragh | NIC30 | 408 | 2021-04-10 | 2021-05-04 | S | 24
Ballylumford | NIBGT2 | 58 | 2021-04-19 | 2021-04-26 | S | 7
Kilroot | NIK2 | 258 | 2021-05-10 | 2021-07-05 | S | 56
Coolkeeragh | NICGT8 | 53 | 2021-05-10 | 2021-05-17 | S | 7
Ballylumford | NIBGT1 | 58 | 2021-05-20 | 2021-07-01 | S | 42
Moyle | MOYLE | 450 | 2021-06-16 | 2021-06-18 | 250 | 2
Coolkeeragh | NIC30 | 408 | 2021-07-17 | 2021-07-19 | S | 2
Ballylumford | NIB32 | 249 | 2021-08-02 | 2021-08-16 | 161 | 14
Ballylumford | NIB31 | 249 | 2021-08-02 | 2021-08-16 | 161 | 14
Coolkeeragh | NIC30 | 408 | 2021-08-21 | 2021-08-23 | S | 2
Kilroot | NIK1 | 256 | 2021-08-28 | 2021-10-23 | S | 56
Kilroot | NIKGT3 | 42 | 2021-10-04 | 2021-10-09 | S | 5
Kilroot | NIKGT4 | 42 | 2021-10-11 | 2021-10-16 | S | 5
Coolkeeragh | NICGT8 | 53 | 2021-10-30 | 2021-11-01 | S | 2
Coolkeeragh | NIC30 | 408 | 2021-11-06 | 2021-11-08 | S | 2
|  |  | Scheduled Outage | S
|  |  | Forced Outage | F
|  |  | Unit partially available | 10

## Outage Plan All Island
2021 GENERATION OUTAGE PLAN (All Island)
|  | Month | Jan '2021 |  |  |  |  | Feb '2021 |  |  |  | Mar '2021 |  |  |  |  | Apr '2021 |  |  |  | May '2021 |  |  |  |  | Jun '2021 |  |  |  | Jul '2021 |  |  |  | Aug '2021 |  |  |  |  | Sep '2021 |  |  |  | Oct '2021 |  |  |  | Nov '2021 |  |  |  |  | Dec '2021
|  | Week | 53 '2021 | 1 '2021 | 2 '2021 | 3 '2021 | 4 '2021 | 5 '2021 | 6 '2021 | 7 '2021 | 8 '2021 | 9 '2021 | 10 '2021 | 11 '2021 | 12 '2021 | 13 '2021 | 14 '2021 | 15 '2021 | 16 '2021 | 17 '2021 | 18 '2021 | 19 '2021 | 20 '2021 | 21 '2021 | 22 '2021 | 23 '2021 | 24 '2021 | 25 '2021 | 26 '2021 | 27 '2021 | 28 '2021 | 29 '2021 | 30 '2021 | 31 '2021 | 32 '2021 | 33 '2021 | 34 '2021 | 35 '2021 | 36 '2021 | 37 '2021 | 38 '2021 | 39 '2021 | 40 '2021 | 41 '2021 | 42 '2021 | 43 '2021 | 44 '2021 | 45 '2021 | 46 '2021 | 47 '2021 | 48 '2021 | 49 '2021 | 50 '2021 | 51 '2021 | 52 '2021
Station | Unit | NPR
AC Automation | NIACA | 8
Activation Energy | AE1 | 95
Activation Energy | AE2 | 8
Activation Energy | AE3 | 14
Activation Energy | AE4 | 15
Activation Energy | AE5 | 15
Activation Energy | EN5 | 6
Activation Energy | EN6 | 11
Activation Energy | NIAEA | 9
Aghada | AD2 | 431
Aghada | AT1 | 90
Aghada | AT2 | 90
Aghada | AT4 | 90 | [36 empty] | S | S
Ardnacrusha | AA1 | 21 | [15 empty] | S
Ardnacrusha | AA2 | 22 | [19 empty] | S
Ardnacrusha | AA3 | 19 | [30 empty] | S | S | S | S | S | S | S | S
Ardnacrusha | AA4 | 24 | [24 empty] | S
Ballylumford | NIB10 | 94
Ballylumford | NIB31 | 249
Ballylumford | NIB32 | 249 | [5 empty] | S | S | S | S | S | S | S | S | S
Ballylumford | NIBGT1 | 58 | [20 empty] | S | S | S | S | S | S
Ballylumford | NIBGT2 | 58 | [16 empty] | S
Contour Global | NICG2 | 3
Contour Global | NICGA | 12
Coolkeeragh | NIC30 | 408 | [15 empty] | S | S | S
Coolkeeragh | NICGT8 | 53 | [19 empty] | S
DAE Virtual Power Plant | DP1 | 19
DAE Virtual Power Plant | DP2 | 26
Dublin Bay | DB1 | 405
Dublin Waste To Energy | DW1 | 62
Edenderry | ED1 | 118 | [24 empty] | S | S | S | [25 empty] | S
Edenderry | ED3 | 58
Edenderry | ED5 | 58
Electric Ireland | EI1 | 20
Electricity Exchange DSU | EE1 | 51
Electricity Exchange DSU | EE2 | 28
Electricity Exchange DSU | EE3 | 8
Electricity Exchange DSU | EE4 | 9
Electricity Exchange DSU | EE5 | 6
Empower | NIEMP | 3
Endeco Technologies | EC1 | 42
Endeco Technologies | EC2 | 11
Endeco Technologies | EC5 | 15
Endeco Technologies | NIECA | 13
Energy Trading | ET1 | 13
Energy Trading | NIETB | 9
Energy Trading | NIETD | 5
Energy Trading | NIETR | 19
Erne | ER1 | 10 | [15 empty] | S
Erne | ER2 | 10 | [19 empty] | S
Erne | ER3 | 22 | [24 empty] | S | S | S
Erne | ER4 | 22 | [36 empty] | S
EWIC | EW1 | 500
Great Island | GI4 | 461
Huntstown | HN2 | 400 | [15 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Huntstown | HNC | 342 | [40 empty] | S
Indaver | IW1 | 17 | [15 empty] | S | S
iPower | NIAGU | 74
Kilroot | NIK1 | 256 | [35 empty] | S | S | S | S | S | S | S | S
Kilroot | NIK2 | 258 | [19 empty] | S | S | S | S | S | S | S | S
Kilroot | NIKGT1 | 29
Kilroot | NIKGT2 | 29
Kilroot | NIKGT3 | 42 | [40 empty] | S
Kilroot | NIKGT4 | 42 | [41 empty] | S
Knockacummer | KC1 | 100
Lanesboro | LR4 | 91 |  | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F
Lee | LE1 | 15 | [19 empty] | S
Lee | LE2 | 4 | [15 empty] | S
Lee | LE3 | 8 | [24 empty] | S
Liffey | LI1 | 15 | [15 empty] | S | S | S | S
Liffey | LI2 | 15 | [15 empty] | S | S | S | S
Liffey | LI4 | 4
Liffey | LI5 | 4 | [20 empty] | S | S | S | S
Lisahally | NILPS | 18
Moneypoint | MP1 | 285 | [31 empty] | S
Moneypoint | MP2 | 285 | [31 empty] | S
Moneypoint | MP3 | 285 | [34 empty] | S
Moyle | MOYLE | 450
North Wall | NW5 | 104 | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Poolbeg | PB4 | 154 | [12 empty] | S
Poolbeg | PB5 | 146 | [14 empty] | S
Poolbeg | PB6 | 168 | [14 empty] | S | S | S | S | S
Powerhouse Generation | NIPH1 | 34
Powerhouse Generation | PG1 | 11
Rhode | RP1 | 52 | [33 empty] | S
Rhode | RP2 | 52 | [33 empty] | S
Seal Rock | SK3 | 85
Seal Rock | SK4 | 85 | [27 empty] | S
Seecon | SO1 | 105
Tarbert | TB1 | 54 | [21 empty] | S
Tarbert | TB2 | 54 | [21 empty] | S
Tarbert | TB3 | 241
Tarbert | TB4 | 243
Tawnaghmore | TP1 | 52
Tawnaghmore | TP3 | 52
Turlough Hill | TH1 | 73 | [28 empty] | S
Turlough Hill | TH2 | 73 | [28 empty] | S
Turlough Hill | TH3 | 73 | [26 empty] | S
Turlough Hill | TH4 | 73 | [26 empty] | S
Tynagh | TYC | 384 | [13 empty] | S
Viridian Energy | VE1 | 20
Viridian Energy DSU | VE2 | 13
West Offaly | WO4 | 137 |  | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F
Whitegate | WG1 | 444

## All Island Outages
Upcoming Outages including STMOs and Annual Outages
Station | Unit | NPR | Start Date | End Date | Value | Duration
North Wall | NW5 | 104 | 2019-10-01 | 2022-10-01 | S | 1096
Edenderry | ED1 | 118 | 2020-12-26 13:00 | 2021-01-02 08:00 | S | 6.75
West Offaly | WO4 | 137 | 2021-01-01 | 2023-01-01 | F | 730
Lanesboro | LR4 | 91 | 2021-01-01 | 2023-01-01 | F | 730
Seal Rock | SK3 | 85 | 2021-01-17 07:00 | 2021-01-19 17:00 | S | 2.42
Aghada | AD2 | 431 | 2021-01-22 | 2021-01-27 | S | 5
Ballylumford | NIB32 | 249 | 2021-02-01 | 2021-04-02 | S | 60
Seal Rock | SK4 | 85 | 2021-03-07 07:00 | 2021-03-09 17:00 | S | 2.42
Edenderry | ED1 | 118 | 2021-03-12 18:00 | 2021-03-18 08:00 | S | 5.58
Poolbeg | PB6 | 168 | 2021-03-23 | 2021-03-27 | 84 | 4
Poolbeg | PB4 | 154 | 2021-03-23 | 2021-03-27 | S | 4
Tynagh | TYC | 384 | 2021-03-28 22:00 | 2021-04-02 22:00 | S | 5
Poolbeg | PB6 | 168 | 2021-04-06 | 2021-05-11 | S | 35
Poolbeg | PB5 | 146 | 2021-04-06 | 2021-04-10 | S | 4
Coolkeeragh | NIC30 | 408 | 2021-04-10 | 2021-05-04 | S | 24
Indaver | IW1 | 17 | 2021-04-12 | 2021-04-27 | S | 15
Lee | LE2 | 4 | 2021-04-12 08:00 | 2021-04-16 20:00 | S | 4.5
Erne | ER1 | 10 | 2021-04-12 08:00 | 2021-04-16 20:00 | S | 4.5
Liffey | LI2 | 15 | 2021-04-12 08:00 | 2021-05-09 17:00 | S | 27.33
Liffey | LI1 | 15 | 2021-04-12 08:00 | 2021-05-09 17:00 | S | 27.33
Ardnacrusha | AA1 | 21 | 2021-04-12 08:00 | 2021-04-16 20:00 | S | 4.5
Huntstown | HN2 | 400 | 2021-04-15 23:00 | 2021-07-24 23:00 | S | 100
Ballylumford | NIBGT2 | 58 | 2021-04-19 | 2021-04-26 | S | 7
Whitegate | WG1 | 444 | 2021-05-07 | 2021-05-14 | S | 7
Kilroot | NIK2 | 258 | 2021-05-10 | 2021-07-05 | S | 56
Coolkeeragh | NICGT8 | 53 | 2021-05-10 | 2021-05-17 | S | 7
Lee | LE1 | 15 | 2021-05-10 08:00 | 2021-05-14 20:00 | S | 4.5
Erne | ER2 | 10 | 2021-05-10 08:00 | 2021-05-14 20:00 | S | 4.5
Ardnacrusha | AA2 | 22 | 2021-05-10 08:00 | 2021-05-14 20:00 | S | 4.5
Seal Rock | SK3 | 85 | 2021-05-10 21:00 | 2021-05-12 12:00 | S | 1.58
Seal Rock | SK4 | 85 | 2021-05-10 23:00 | 2021-05-11 21:00 | S | 0.92
Edenderry | ED3 | 58 | 2021-05-15 08:00 | 2021-05-15 18:00 | S | 0.42
Edenderry | ED5 | 58 | 2021-05-15 08:00 | 2021-05-15 18:00 | S | 0.42
Liffey | LI5 | 4 | 2021-05-17 08:00 | 2021-06-13 17:00 | S | 27.33
Ballylumford | NIBGT1 | 58 | 2021-05-20 | 2021-07-01 | S | 42
Tarbert | TB2 | 54 | 2021-05-24 | 2021-05-31 | S | 7
Tarbert | TB1 | 54 | 2021-05-24 | 2021-05-31 | S | 7
EWIC | EW1 | 500 | 2021-06-01 | 2021-06-03 21:00 | S | 2.83
Tarbert | TB3 | 241 | 2021-06-04 | 2021-06-11 | S | 7
Edenderry | ED1 | 118 | 2021-06-11 12:00 | 2021-07-06 08:00 | S | 24.83
Lee | LE3 | 8 | 2021-06-14 08:00 | 2021-06-18 20:00 | S | 4.5
Erne | ER3 | 22.5 | 2021-06-14 08:00 | 2021-07-04 20:00 | S | 20.5
Ardnacrusha | AA4 | 24 | 2021-06-14 08:00 | 2021-06-18 20:00 | S | 4.5
Moyle | MOYLE | 450 | 2021-06-16 | 2021-06-18 | 250 | 2
Turlough Hill | TH4 | 73 | 2021-06-27 08:00 | 2021-07-03 17:00 | S | 6.33
Turlough Hill | TH3 | 73 | 2021-06-27 08:00 | 2021-07-03 17:00 | S | 6.33
Seal Rock | SK4 | 85 | 2021-07-05 07:00 | 2021-07-09 17:00 | S | 4.42
Aghada | AT1 | 90 | 2021-07-05 08:00 | 2021-07-08 | S | 2.67
Turlough Hill | TH2 | 73 | 2021-07-11 08:00 | 2021-07-17 17:00 | S | 6.33
Turlough Hill | TH1 | 73 | 2021-07-11 08:00 | 2021-07-17 17:00 | S | 6.33
Aghada | AT2 | 90 | 2021-07-12 | 2021-07-15 | S | 3
Coolkeeragh | NIC30 | 408 | 2021-07-17 | 2021-07-19 | S | 2
Ardnacrusha | AA3 | 19 | 2021-07-27 08:00 | 2021-09-21 20:00 | S | 56.5
Moneypoint | MP2 | 285 | 2021-07-30 22:00 | 2021-08-11 22:00 | S | 12
Moneypoint | MP1 | 285 | 2021-08-01 22:00 | 2021-08-10 22:00 | S | 9
Ballylumford | NIB32 | 249 | 2021-08-02 | 2021-08-16 | 161 | 14
Ballylumford | NIB31 | 249 | 2021-08-02 | 2021-08-16 | 161 | 14
Rhode | RP2 | 52 | 2021-08-14 | 2021-08-22 | S | 8
Rhode | RP1 | 52 | 2021-08-14 | 2021-08-22 | S | 8
Moneypoint | MP3 | 285 | 2021-08-20 22:00 | 2021-08-29 22:00 | S | 9
Coolkeeragh | NIC30 | 408 | 2021-08-21 | 2021-08-23 | S | 2
Kilroot | NIK1 | 256 | 2021-08-28 | 2021-10-23 | S | 56
Liffey | LI4 | 4 | 2021-09-01 08:00 | 2021-09-03 17:00 | S | 2.33
Aghada | AT4 | 90 | 2021-09-06 | 2021-09-20 | S | 14
Seal Rock | SK3 | 85 | 2021-09-06 07:00 | 2021-09-09 07:00 | S | 3
Erne | ER4 | 22.5 | 2021-09-06 08:00 | 2021-09-10 20:00 | S | 4.5
Great Island | GI4 | 461 | 2021-09-18 | 2021-09-25 | S | 7
Huntstown | HNC | 342 | 2021-10-01 | 2021-10-12 | S | 11
Kilroot | NIKGT3 | 42 | 2021-10-04 | 2021-10-09 | S | 5
Kilroot | NIKGT4 | 42 | 2021-10-11 | 2021-10-16 | S | 5
Dublin Bay | DB1 | 405 | 2021-10-15 13:00 | 2021-10-19 06:00 | S | 3.67
Coolkeeragh | NICGT8 | 53 | 2021-10-30 | 2021-11-01 | S | 2
Coolkeeragh | NIC30 | 408 | 2021-11-06 | 2021-11-08 | S | 2
Seal Rock | SK4 | 85 | 2021-11-07 07:00 | 2021-11-09 17:00 | S | 2.42
Turlough Hill | TH1 | 73 | 2021-11-16 08:00 | 2021-11-18 17:00 | S | 2.33
Turlough Hill | TH2 | 73 | 2021-11-16 08:00 | 2021-11-18 17:00 | S | 2.33
Edenderry | ED1 | 118 | 2021-12-26 13:00 | 2022-01-02 08:00 | S | 6.75
|  |  | Scheduled Outage | S
|  |  | Forced Outage | F
|  |  | Unit partially available | 10