## Outage Plan EirGrid
2027 GENERATION OUTAGE PLAN (EIRGRID)
|  | Month | Jan '2027 |  |  |  |  | Feb '2027 |  |  |  | Mar '2027 |  |  |  |  | Apr '2027 |  |  |  | May '2027 |  |  |  |  | Jun '2027 |  |  |  | Jul '2027 |  |  |  | Aug '2027 |  |  |  |  | Sep '2027 |  |  |  | Oct '2027 |  |  |  | Nov '2027 |  |  |  |  | Dec '2027
|  | Week | 53 '2027 | 1 '2027 | 2 '2027 | 3 '2027 | 4 '2027 | 5 '2027 | 6 '2027 | 7 '2027 | 8 '2027 | 9 '2027 | 10 '2027 | 11 '2027 | 12 '2027 | 13 '2027 | 14 '2027 | 15 '2027 | 16 '2027 | 17 '2027 | 18 '2027 | 19 '2027 | 20 '2027 | 21 '2027 | 22 '2027 | 23 '2027 | 24 '2027 | 25 '2027 | 26 '2027 | 27 '2027 | 28 '2027 | 29 '2027 | 30 '2027 | 31 '2027 | 32 '2027 | 33 '2027 | 34 '2027 | 35 '2027 | 36 '2027 | 37 '2027 | 38 '2027 | 39 '2027 | 40 '2027 | 41 '2027 | 42 '2027 | 43 '2027 | 44 '2027 | 45 '2027 | 46 '2027 | 47 '2027 | 48 '2027 | 49 '2027 | 50 '2027 | 51 '2027 | 52 '2027
Station | Unit | NPR
Aghada | AD2 | 449 | [42 empty] | S
Aghada | AD3 | 19 | [14 empty] | S
Aghada | AD4 | 75 | [18 empty] | S | S
Aghada | AD5 | 75 | [20 empty] | S
Aghada | AT1 | 90 | [19 empty] | S
Aghada | AT2 | 90 | [20 empty] | S
Aghada | AT4 | 90 | [21 empty] | S
Ardnacrusha | AA1 | 21 | [14 empty] | S
Ardnacrusha | AA2 | 22 | [24 empty] | S
Ardnacrusha | AA3 | 19 | [37 empty] | S
Ardnacrusha | AA4 | 24 | [19 empty] | S | S | S
Aughinish Alumina | EB1 | 25
Banoge | OD1 | 9
Cloniffeen | SI1 | 50
Cloniffeen | SI2 | 50
Coolnanoonagh | KZ3 | 2
Coolnanoonagh | KZ4 | 27
Corduff | FG2 | 64 | [19 empty] | S
Crane | AV1 | 16
Derrycarney | LU1 | 50
Derrycarney | LU2 | 50
Drybridge | IW1 | 17 | [15 empty] | S | S
Dublin Bay | DB1 | 415
Dunsoghly | DG1 | 50
Edenderry | ED1 | 118 | [27 empty] | S | S | S | S | [21 empty] | S
Edenderry | ED3 | 58
Edenderry | ED5 | 58
Electric Ireland | EI1 | 14
Endeco Technologies | EC1 | 52
Endeco Technologies | EC2 | 13
Endeco Technologies | EC3 | 6
Endeco Technologies | EC4 | 5
Endeco Technologies | EC5 | 21
Enel X | AE1 | 87
Enel X | AE2 | 12
Enel X | AE3 | 14
Enel X | AE4 | 16
Enel X | AE5 | 16
Enel X | EN1 | 16
Enel X | EN2 | 17
Enel X | EN3 | 17
Enel X | EN4 | 16
Enel X | EN5 | 6
Enel X | EN6 | 31
Enel X | EN8 | 24
Enel X | EN9 | 16
Enel X | EX1 | 21
Energy Trading Ireland | ET1 | 5
Erne | ER1 | 10 | [14 empty] | S | S | S
Erne | ER2 | 10 | [19 empty] | S
Erne | ER3 | 23 | [25 empty] | S
Erne | ER4 | 23 | [29 empty] | S
EWIC | EW1 | 500 | [15 empty] | S | S
Gardnershill | GP1 | 8
Golagh | GO2 | 3
Gorman | GF1 | 50
Great Island | GI4 | 464
Huntstown | HN2 | 402 | [40 empty] | S | S | S | S | S
Huntstown | HNC | 342 | [25 empty] | S | S | S
Inchicore | IH1 | 30 | [41 empty] | S
Irishtown | IS2 | 30 | [13 empty] | S |  |  |  | S
Irishtown | IS3 | 64 | [13 empty] | S |  |  |  | S
Kilcumber | OE2 | 25
Kilteel | PN1 | 30
Knockacummer | KC1 | 100
Lee | LE1 | 15 | [18 empty] | S | S
Lee | LE2 | 4 | [13 empty] | S | S | S | S
Lee | LE3 | 8 | [21 empty] | S | S
Liffey | LI1 | 15 | [23 empty] | S | S
Liffey | LI2 | 15 | [23 empty] | S | S
Liffey | LI4 | 4
Liffey | LI5 | 4
Lisdrum | LF1 | 60
Loughtown | GLK | 500
Moneypoint | MP1 | 285 | [15 empty] | S | S
Moneypoint | MP2 | 285 | [20 empty] | S | S
Moneypoint | MP3 | 285 | [32 empty] | S | S
Moneypoint | MP5 | 1
Northwall | NW8 | 199
Poolbeg | PB4 | 156
Poolbeg | PB5 | 153
Poolbeg | PB6 | 168 | [22 empty] | S | S | S | S | S | S
Poolbeg | PB7 | 64 | [15 empty] | S | [30 empty] | S | S
Poolbeg | PB8 | 75 | [15 empty] | S | [30 empty] | S | S
Powerhouse Generation | PG1 | 10
Rhode | RP1 | 52 | [20 empty] | S | S
Rhode | RP2 | 52 | [20 empty] | S | S
Seal Rock | SK3 | 83 | [36 empty] | S
Seal Rock | SK4 | 83 | [22 empty] | S | S | S
Shannonbridge | SQ1 | 262
Tarbert | TB5 | 160
Tawnaghmore | KF2 | 11
Tawnaghmore | TP1 | 52 | [24 empty] | S
Tawnaghmore | TP3 | 52 | [25 empty] | S
Tobertoreen | XT2 | 11
Turlough Hill | TH1 | 73 | [18 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Turlough Hill | TH2 | 73 | [18 empty] | S | S | S | S | S | S | S | S | [15 empty] | S
Turlough Hill | TH3 | 73 | [18 empty] | S | S | S | S | S | S | S | S | [15 empty] | S
Turlough Hill | TH4 | 73 | [18 empty] | S | S | S | S | S | S | S | S | [15 empty] | S
Tynagh | TYC | 404 | [39 empty] | S
Uggool | SO1 | 105
Veolia Alternative Energy | DP1 | 18
Veolia Alternative Energy | DP2 | 20
Veolia Alternative Energy | DP3 | 9
VIOTAS | EE1 | 55
VIOTAS | EE2 | 28
VIOTAS | EE3 | 11
VIOTAS | EE4 | 13
VIOTAS | EE5 | 12
VIOTAS | EE6 | 14
VIOTAS | EE7 | 7
VIOTAS | EE8 | 15
VIOTAS | EE9 | 11
Whitebank | DW1 | 62 | [15 empty] | S
Whitegate | WG1 | 444 | [40 empty] | S

## EirGrid Outages
Upcoming Outages including STMOs and Annual Outages
Station | Unit | NPR | Start Date | End Date | Value | Duration
Edenderry | ED1 | 118 | 2026-12-26 12:00 | 2027-01-01 08:00 | S | 5.83
Seal Rock | SK3 | 83 | 2027-01-11 06:00 | 2027-01-13 18:00 | S | 2.5
Seal Rock | SK4 | 83 | 2027-03-01 06:00 | 2027-03-03 18:00 | S | 2.5
Aghada | AD2 | 449 | 2027-03-18 | 2027-03-21 | S | 3
Lee | LE2 | 4 | 2027-03-30 08:00 | 2027-04-23 20:00 | S | 24.5
Irishtown | IS2 | 30 | 2027-03-31 06:00 | 2027-04-05 20:00 | S | 5.58
Irishtown | IS3 | 64 | 2027-03-31 06:00 | 2027-04-05 19:00 | S | 5.5
Edenderry | ED1 | 118 | 2027-04-01 17:00 | 2027-04-07 08:00 | S | 5.58
Erne | ER1 | 10 | 2027-04-05 08:00 | 2027-04-23 20:00 | S | 18.5
Ardnacrusha | AA1 | 21 | 2027-04-05 08:00 | 2027-04-09 20:00 | S | 4.5
Whitebank | DW1 | 61.5 | 2027-04-05 08:00 | 2027-04-10 08:00 | 26 | 5
Poolbeg | PB6 | 168 | 2027-04-06 08:00 | 2027-06-12 21:00 | 84 | 67.5
Aghada | AD3 | 19 | 2027-04-07 07:00 | 2027-04-12 19:00 | S | 5.5
Moneypoint | MP1 | 285 | 2027-04-09 22:00 | 2027-04-24 22:00 | S | 15
Drybridge | IW1 | 17 | 2027-04-10 | 2027-04-23 | S | 13
Whitebank | DW1 | 61.5 | 2027-04-10 08:00 | 2027-04-20 20:00 | S | 10.5
EWIC | EW1 | 500 | 2027-04-12 09:00 | 2027-04-12 21:00 | S | 0.5
EWIC | EW1 | 500 | 2027-04-12 21:00 | 2027-04-22 23:00 | S | 10.08
Poolbeg | PB8 | 75 | 2027-04-14 06:00 | 2027-04-19 19:00 | S | 5.5
Poolbeg | PB7 | 64 | 2027-04-14 06:00 | 2027-04-19 19:00 | S | 5.5
Whitebank | DW1 | 61.5 | 2027-04-20 08:30 | 2027-04-25 19:00 | 26 | 5.42
Seal Rock | SK3 | 83 | 2027-04-26 06:00 | 2027-04-28 18:00 | S | 2.5
Irishtown | IS2 | 30 | 2027-04-28 06:00 | 2027-05-03 20:00 | S | 5.58
Irishtown | IS3 | 64 | 2027-04-28 06:00 | 2027-05-03 19:00 | S | 5.5
Turlough Hill | TH2 | 73 | 2027-05-02 08:00 | 2027-06-25 18:00 | S | 54.42
Turlough Hill | TH1 | 73 | 2027-05-02 08:00 | 2027-10-15 18:00 | S | 166.42
Turlough Hill | TH3 | 73 | 2027-05-02 08:00 | 2027-06-25 18:00 | S | 54.42
Turlough Hill | TH4 | 73 | 2027-05-02 08:00 | 2027-06-25 18:00 | S | 54.42
Lee | LE1 | 15 | 2027-05-04 08:00 | 2027-05-14 20:00 | S | 10.5
Aghada | AD4 | 75 | 2027-05-05 07:00 | 2027-05-14 19:00 | S | 9.5
Aghada | AT1 | 90 | 2027-05-10 | 2027-05-14 | S | 4
Ardnacrusha | AA4 | 24 | 2027-05-10 08:00 | 2027-05-28 20:00 | S | 18.5
Erne | ER2 | 10 | 2027-05-10 08:00 | 2027-05-14 20:00 | S | 4.5
Seal Rock | SK3 | 83 | 2027-05-10 18:00 | 2027-05-13 18:00 | S | 3
Seal Rock | SK4 | 83 | 2027-05-11 | 2027-05-13 12:00 | S | 2.5
Corduff | FG2 | 64 | 2027-05-12 06:00 | 2027-05-17 19:00 | S | 5.5
Moneypoint | MP2 | 285 | 2027-05-14 22:00 | 2027-05-30 22:00 | S | 16
Aghada | AD5 | 75 | 2027-05-15 07:00 | 2027-05-24 19:00 | S | 9.5
Aghada | AT2 | 90 | 2027-05-17 | 2027-05-21 | S | 4
Rhode | RP1 | 52 | 2027-05-17 08:00 | 2027-05-28 20:00 | S | 11.5
Rhode | RP2 | 52 | 2027-05-17 08:00 | 2027-05-28 20:00 | S | 11.5
Aghada | AT4 | 90 | 2027-05-24 | 2027-05-28 | S | 4
Lee | LE3 | 8 | 2027-05-25 08:00 | 2027-06-04 20:00 | S | 10.5
Poolbeg | PB6 | 168 | 2027-05-28 08:00 | 2027-07-10 17:00 | S | 43.33
Seal Rock | SK4 | 83 | 2027-05-30 06:00 | 2027-06-21 18:00 | S | 22.5
Poolbeg | PB5 | 153 | 2027-06-04 08:00 | 2027-06-12 17:00 | S | 8.33
Liffey | LI1 | 15 | 2027-06-07 08:00 | 2027-06-18 18:00 | S | 11.42
Liffey | LI2 | 15 | 2027-06-07 08:00 | 2027-06-18 18:00 | S | 11.42
Ardnacrusha | AA2 | 22 | 2027-06-14 08:00 | 2027-06-18 20:00 | S | 4.5
Tawnaghmore | TP1 | 52 | 2027-06-14 08:00 | 2027-06-21 20:00 | S | 7.5
Moneypoint | MP5 | 1 | 2027-06-16 | 2027-06-19 19:00 | S | 3.75
Huntstown | HNC | 342 | 2027-06-18 21:00 | 2027-07-08 21:00 | S | 20
Erne | ER3 | 23 | 2027-06-21 08:00 | 2027-06-25 20:00 | S | 4.5
Tawnaghmore | TP3 | 52 | 2027-06-21 08:00 | 2027-06-28 20:00 | S | 7.5
Edenderry | ED1 | 118 | 2027-07-02 12:00 | 2027-07-30 08:00 | S | 27.83
Cloniffeen | SI1 | 50 | 2027-07-05 08:00 | 2027-07-06 17:00 | S | 1.33
Cloniffeen | SI2 | 50 | 2027-07-05 08:00 | 2027-07-06 17:00 | S | 1.33
Erne | ER4 | 23 | 2027-07-19 08:00 | 2027-07-23 20:00 | S | 4.5
Derrycarney | LU1 | 50 | 2027-07-19 08:00 | 2027-07-20 17:00 | S | 1.33
Derrycarney | LU2 | 50 | 2027-07-19 08:00 | 2027-07-20 17:00 | S | 1.33
Moneypoint | MP3 | 285 | 2027-08-06 22:00 | 2027-08-22 22:00 | S | 16
EWIC | EW1 | 500 | 2027-08-20 11:00 | 2027-08-20 23:00 | S | 0.5
Seal Rock | SK3 | 83 | 2027-09-06 06:00 | 2027-09-10 18:00 | S | 4.5
Ardnacrusha | AA3 | 19 | 2027-09-13 08:00 | 2027-09-17 20:00 | S | 4.5
Edenderry | ED3 | 58 | 2027-09-17 08:00 | 2027-09-17 18:00 | S | 0.42
Edenderry | ED5 | 58 | 2027-09-17 08:00 | 2027-09-17 18:00 | S | 0.42
Lisdrum | LF1 | 60 | 2027-09-20 08:00 | 2027-09-22 17:00 | S | 2.33
Tynagh | TYC | 404 | 2027-09-29 22:00 | 2027-10-05 21:00 | S | 5.92
Huntstown | HN2 | 402 | 2027-10-01 21:00 | 2027-11-07 21:00 | S | 37
Whitegate | WG1 | 444 | 2027-10-02 21:00 | 2027-10-12 21:00 | S | 10
Whitebank | DW1 | 61.5 | 2027-10-04 08:00 | 2027-10-07 08:00 | 26 | 3
Turlough Hill | TH2 | 73 | 2027-10-10 08:00 | 2027-10-15 17:00 | S | 5.33
Turlough Hill | TH3 | 73 | 2027-10-10 08:00 | 2027-10-15 18:00 | S | 5.42
Turlough Hill | TH4 | 73 | 2027-10-10 08:00 | 2027-10-15 18:00 | S | 5.42
Whitebank | DW1 | 61.5 | 2027-10-11 08:00 | 2027-10-14 18:00 | 26 | 3.42
Inchicore | IH1 | 30 | 2027-10-13 07:00 | 2027-10-18 19:00 | S | 5.5
Dublin Bay | DB1 | 415 | 2027-10-15 12:00 | 2027-10-22 19:00 | S | 7.25
Aghada | AD2 | 449 | 2027-10-18 | 2027-10-25 23:00 | S | 7.92
Seal Rock | SK4 | 83 | 2027-11-01 06:00 | 2027-11-03 18:00 | S | 2.5
Poolbeg | PB8 | 75 | 2027-11-17 06:00 | 2027-11-28 19:00 | S | 11.5
Poolbeg | PB7 | 64 | 2027-11-17 06:00 | 2027-11-28 19:00 | S | 11.5
Edenderry | ED1 | 118 | 2027-12-26 12:00 | 2028-01-01 08:00 | S | 5.83
|  |  | Scheduled Outage | S
|  |  | Forced Outage | F
|  |  | Unit partially available | 10

## Outage Plan SONI
2027 GENERATION OUTAGE PLAN (SONI)
|  | Month | Jan '2027 |  |  |  |  | Feb '2027 |  |  |  | Mar '2027 |  |  |  |  | Apr '2027 |  |  |  | May '2027 |  |  |  |  | Jun '2027 |  |  |  | Jul '2027 |  |  |  | Aug '2027 |  |  |  |  | Sep '2027 |  |  |  | Oct '2027 |  |  |  | Nov '2027 |  |  |  |  | Dec '2027
|  | Week | 53 '2027 | 1 '2027 | 2 '2027 | 3 '2027 | 4 '2027 | 5 '2027 | 6 '2027 | 7 '2027 | 8 '2027 | 9 '2027 | 10 '2027 | 11 '2027 | 12 '2027 | 13 '2027 | 14 '2027 | 15 '2027 | 16 '2027 | 17 '2027 | 18 '2027 | 19 '2027 | 20 '2027 | 21 '2027 | 22 '2027 | 23 '2027 | 24 '2027 | 25 '2027 | 26 '2027 | 27 '2027 | 28 '2027 | 29 '2027 | 30 '2027 | 31 '2027 | 32 '2027 | 33 '2027 | 34 '2027 | 35 '2027 | 36 '2027 | 37 '2027 | 38 '2027 | 39 '2027 | 40 '2027 | 41 '2027 | 42 '2027 | 43 '2027 | 44 '2027 | 45 '2027 | 46 '2027 | 47 '2027 | 48 '2027 | 49 '2027 | 50 '2027 | 51 '2027 | 52 '2027
Station | Unit | NPR
AC Automation | NIACA | 8
Activation Energy | NIAEA | 2
Ballylumford | NIB10 | 94
Ballylumford | NIB31 | 249 | [9 empty] | S | S | S | S | S | S | S | S | S
Ballylumford | NIB32 | 249
Ballylumford | NIBGT1 | 58 | [40 empty] | S
Ballylumford | NIBGT2 | 58 | [41 empty] | S
Contour Global | NICG2 | 3
Contour Global | NICGA | 12
Coolkeeragh | NIC30 | 408 | [40 empty] | S | S
Coolkeeragh | NICGT8 | 53 | [18 empty] | S | S | S | S | S | S
Electricity Exchange | NIVN1 | 8
Empower | NIEMP | 13
Endeco Technologies | NIECA | 25
Endeco Technologies | NIECB | 9
Energy Trading | NIETB | 6
Energy Trading | NIETD | 5
Energy Trading | NIETR | 5
Energy Trading Ireland | NIETC | 5
Energy Trading Ireland | NIETE | 6
Energy Trading Ireland | NIETF | 6
iPower | NIAGU | 63
iPower | NIID1 | 5
iPower | NIID2 | 6
iPower | NIID3 | 10
Kilroot | NIKGT1 | 29
Kilroot | NIKGT2 | 29
Kilroot | NIKGT3 | 42 | [23 empty] | S
Kilroot | NIKGT4 | 42
Kilroot | NIKGT6 | 350
Kilroot | NIKGT7 | 350
Lisahally | NILPS | 18
Moyle | MOYLE | 450
PowerHouse | NIPH2 | 14
Powerhouse Generation | NIPH1 | 14

## SONI Outages
Upcoming Outages including STMOs and Annual Outages
Station | Unit | NPR | Start Date | End Date | Value | Duration
Coolkeeragh | NIC30 | 408 | 2027-02-06 | 2027-02-08 | S | 2
Ballylumford | NIB32 | 249 | 2027-02-19 | 2027-02-22 | S | 3
Ballylumford | NIB31 | 249 | 2027-03-01 | 2027-04-30 | S | 60
Coolkeeragh | NICGT8 | 53 | 2027-05-03 | 2027-06-13 | S | 41
Kilroot | NIKGT6 | 350 | 2027-05-07 | 2027-05-12 | S | 5
Kilroot | NIKGT7 | 350 | 2027-05-14 | 2027-05-19 | S | 5
Ballylumford | NIB10 | 94 | 2027-05-21 | 2027-05-25 | S | 4
Kilroot | NIKGT3 | 42 | 2027-06-07 | 2027-06-12 | S | 5
Kilroot | NIKGT4 | 42 | 2027-06-12 | 2027-06-17 | S | 5
Moyle | MOYLE | 450 | 2027-06-15 | 2027-06-18 | 250 | 3
Coolkeeragh | NIC30 | 408 | 2027-06-26 | 2027-06-28 | S | 2
Ballylumford | NIB32 | 249 | 2027-07-09 | 2027-07-16 | S | 7
Ballylumford | NIB31 | 249 | 2027-07-09 | 2027-07-16 | S | 7
Ballylumford | NIB10 | 94 | 2027-07-09 | 2027-07-16 | S | 7
Ballylumford | NIB32 | 249 | 2027-07-16 | 2027-09-19 | 161 | 65
Ballylumford | NIB31 | 249 | 2027-07-16 | 2027-09-16 | 161 | 62
Ballylumford | NIB31 | 249 | 2027-09-16 | 2027-09-19 | S | 3
Ballylumford | NIB32 | 249 | 2027-09-19 | 2027-09-22 | S | 3
Ballylumford | NIB31 | 249 | 2027-09-19 | 2027-09-22 | 161 | 3
Ballylumford | NIB10 | 94 | 2027-09-24 | 2027-09-28 | S | 4
Ballylumford | NIBGT1 | 58 | 2027-10-04 | 2027-10-10 | S | 6
Coolkeeragh | NIC30 | 408 | 2027-10-04 | 2027-10-16 | S | 12
Ballylumford | NIBGT2 | 58 | 2027-10-10 | 2027-10-16 | S | 6
Kilroot | NIKGT1 | 29 | 2027-10-17 | 2027-10-20 | S | 3
Kilroot | NIKGT2 | 29 | 2027-10-20 | 2027-10-23 | S | 3
|  |  | Scheduled Outage | S
|  |  | Forced Outage | F
|  |  | Unit partially available | 10

## Outage Plan All Island
2027 GENERATION OUTAGE PLAN (All Island)
|  | Month | Jan '2027 |  |  |  |  | Feb '2027 |  |  |  | Mar '2027 |  |  |  |  | Apr '2027 |  |  |  | May '2027 |  |  |  |  | Jun '2027 |  |  |  | Jul '2027 |  |  |  | Aug '2027 |  |  |  |  | Sep '2027 |  |  |  | Oct '2027 |  |  |  | Nov '2027 |  |  |  |  | Dec '2027
|  | Week | 53 '2027 | 1 '2027 | 2 '2027 | 3 '2027 | 4 '2027 | 5 '2027 | 6 '2027 | 7 '2027 | 8 '2027 | 9 '2027 | 10 '2027 | 11 '2027 | 12 '2027 | 13 '2027 | 14 '2027 | 15 '2027 | 16 '2027 | 17 '2027 | 18 '2027 | 19 '2027 | 20 '2027 | 21 '2027 | 22 '2027 | 23 '2027 | 24 '2027 | 25 '2027 | 26 '2027 | 27 '2027 | 28 '2027 | 29 '2027 | 30 '2027 | 31 '2027 | 32 '2027 | 33 '2027 | 34 '2027 | 35 '2027 | 36 '2027 | 37 '2027 | 38 '2027 | 39 '2027 | 40 '2027 | 41 '2027 | 42 '2027 | 43 '2027 | 44 '2027 | 45 '2027 | 46 '2027 | 47 '2027 | 48 '2027 | 49 '2027 | 50 '2027 | 51 '2027 | 52 '2027
Station | Unit | NPR
AC Automation | NIACA | 8
Activation Energy | NIAEA | 2
Aghada | AD2 | 449 | [42 empty] | S
Aghada | AD3 | 19 | [14 empty] | S
Aghada | AD4 | 75 | [18 empty] | S | S
Aghada | AD5 | 75 | [20 empty] | S
Aghada | AT1 | 90 | [19 empty] | S
Aghada | AT2 | 90 | [20 empty] | S
Aghada | AT4 | 90 | [21 empty] | S
Ardnacrusha | AA1 | 21 | [14 empty] | S
Ardnacrusha | AA2 | 22 | [24 empty] | S
Ardnacrusha | AA3 | 19 | [37 empty] | S
Ardnacrusha | AA4 | 24 | [19 empty] | S | S | S
Aughinish Alumina | EB1 | 25
Ballylumford | NIB10 | 94
Ballylumford | NIB31 | 249 | [9 empty] | S | S | S | S | S | S | S | S | S
Ballylumford | NIB32 | 249
Ballylumford | NIBGT1 | 58 | [40 empty] | S
Ballylumford | NIBGT2 | 58 | [41 empty] | S
Banoge | OD1 | 9
Cloniffeen | SI1 | 50
Cloniffeen | SI2 | 50
Contour Global | NICG2 | 3
Contour Global | NICGA | 12
Coolkeeragh | NIC30 | 408 | [40 empty] | S | S
Coolkeeragh | NICGT8 | 53 | [18 empty] | S | S | S | S | S | S
Coolnanoonagh | KZ3 | 2
Coolnanoonagh | KZ4 | 27
Corduff | FG2 | 64 | [19 empty] | S
Crane | AV1 | 16
Derrycarney | LU1 | 50
Derrycarney | LU2 | 50
Drybridge | IW1 | 17 | [15 empty] | S | S
Dublin Bay | DB1 | 415
Dunsoghly | DG1 | 50
Edenderry | ED1 | 118 | [27 empty] | S | S | S | S | [21 empty] | S
Edenderry | ED3 | 58
Edenderry | ED5 | 58
Electric Ireland | EI1 | 14
Electricity Exchange | NIVN1 | 8
Empower | NIEMP | 13
Endeco Technologies | EC1 | 52
Endeco Technologies | EC2 | 13
Endeco Technologies | EC3 | 6
Endeco Technologies | EC4 | 5
Endeco Technologies | EC5 | 21
Endeco Technologies | NIECA | 25
Endeco Technologies | NIECB | 9
Enel X | AE1 | 87
Enel X | AE2 | 12
Enel X | AE3 | 14
Enel X | AE4 | 16
Enel X | AE5 | 16
Enel X | EN1 | 16
Enel X | EN2 | 17
Enel X | EN3 | 17
Enel X | EN4 | 16
Enel X | EN5 | 6
Enel X | EN6 | 31
Enel X | EN8 | 24
Enel X | EN9 | 16
Enel X | EX1 | 21
Energy Trading | NIETB | 6
Energy Trading | NIETD | 5
Energy Trading | NIETR | 5
Energy Trading Ireland | ET1 | 5
Energy Trading Ireland | NIETC | 5
Energy Trading Ireland | NIETE | 6
Energy Trading Ireland | NIETF | 6
Erne | ER1 | 10 | [14 empty] | S | S | S
Erne | ER2 | 10 | [19 empty] | S
Erne | ER3 | 23 | [25 empty] | S
Erne | ER4 | 23 | [29 empty] | S
EWIC | EW1 | 500 | [15 empty] | S | S
Gardnershill | GP1 | 8
Golagh | GO2 | 3
Gorman | GF1 | 50
Great Island | GI4 | 464
Huntstown | HN2 | 402 | [40 empty] | S | S | S | S | S
Huntstown | HNC | 342 | [25 empty] | S | S | S
Inchicore | IH1 | 30 | [41 empty] | S
iPower | NIAGU | 63
iPower | NIID1 | 5
iPower | NIID2 | 6
iPower | NIID3 | 10
Irishtown | IS2 | 30 | [13 empty] | S |  |  |  | S
Irishtown | IS3 | 64 | [13 empty] | S |  |  |  | S
Kilcumber | OE2 | 25
Kilroot | NIKGT1 | 29
Kilroot | NIKGT2 | 29
Kilroot | NIKGT3 | 42 | [23 empty] | S
Kilroot | NIKGT4 | 42
Kilroot | NIKGT6 | 350
Kilroot | NIKGT7 | 350
Kilteel | PN1 | 30
Knockacummer | KC1 | 100
Lee | LE1 | 15 | [18 empty] | S | S
Lee | LE2 | 4 | [13 empty] | S | S | S | S
Lee | LE3 | 8 | [21 empty] | S | S
Liffey | LI1 | 15 | [23 empty] | S | S
Liffey | LI2 | 15 | [23 empty] | S | S
Liffey | LI4 | 4
Liffey | LI5 | 4
Lisahally | NILPS | 18
Lisdrum | LF1 | 60
Loughtown | GLK | 500
Moneypoint | MP1 | 285 | [15 empty] | S | S
Moneypoint | MP2 | 285 | [20 empty] | S | S
Moneypoint | MP3 | 285 | [32 empty] | S | S
Moneypoint | MP5 | 1
Moyle | MOYLE | 450
Northwall | NW8 | 199
Poolbeg | PB4 | 156
Poolbeg | PB5 | 153
Poolbeg | PB6 | 168 | [22 empty] | S | S | S | S | S | S
Poolbeg | PB7 | 64 | [15 empty] | S | [30 empty] | S | S
Poolbeg | PB8 | 75 | [15 empty] | S | [30 empty] | S | S
PowerHouse | NIPH2 | 14
Powerhouse Generation | NIPH1 | 14
Powerhouse Generation | PG1 | 10
Rhode | RP1 | 52 | [20 empty] | S | S
Rhode | RP2 | 52 | [20 empty] | S | S
Seal Rock | SK3 | 83 | [36 empty] | S
Seal Rock | SK4 | 83 | [22 empty] | S | S | S
Shannonbridge | SQ1 | 262
Tarbert | TB5 | 160
Tawnaghmore | KF2 | 11
Tawnaghmore | TP1 | 52 | [24 empty] | S
Tawnaghmore | TP3 | 52 | [25 empty] | S
Tobertoreen | XT2 | 11
Turlough Hill | TH1 | 73 | [18 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Turlough Hill | TH2 | 73 | [18 empty] | S | S | S | S | S | S | S | S | [15 empty] | S
Turlough Hill | TH3 | 73 | [18 empty] | S | S | S | S | S | S | S | S | [15 empty] | S
Turlough Hill | TH4 | 73 | [18 empty] | S | S | S | S | S | S | S | S | [15 empty] | S
Tynagh | TYC | 404 | [39 empty] | S
Uggool | SO1 | 105
Veolia Alternative Energy | DP1 | 18
Veolia Alternative Energy | DP2 | 20
Veolia Alternative Energy | DP3 | 9
VIOTAS | EE1 | 55
VIOTAS | EE2 | 28
VIOTAS | EE3 | 11
VIOTAS | EE4 | 13
VIOTAS | EE5 | 12
VIOTAS | EE6 | 14
VIOTAS | EE7 | 7
VIOTAS | EE8 | 15
VIOTAS | EE9 | 11
Whitebank | DW1 | 62 | [15 empty] | S
Whitegate | WG1 | 444 | [40 empty] | S

## All Island Outages
Upcoming Outages including STMOs and Annual Outages
Station | Unit | NPR | Start Date | End Date | Value | Duration
Edenderry | ED1 | 118 | 2026-12-26 12:00 | 2027-01-01 08:00 | S | 5.83
Seal Rock | SK3 | 83 | 2027-01-11 06:00 | 2027-01-13 18:00 | S | 2.5
Coolkeeragh | NIC30 | 408 | 2027-02-06 | 2027-02-08 | S | 2
Ballylumford | NIB32 | 249 | 2027-02-19 | 2027-02-22 | S | 3
Ballylumford | NIB31 | 249 | 2027-03-01 | 2027-04-30 | S | 60
Seal Rock | SK4 | 83 | 2027-03-01 06:00 | 2027-03-03 18:00 | S | 2.5
Aghada | AD2 | 449 | 2027-03-18 | 2027-03-21 | S | 3
Lee | LE2 | 4 | 2027-03-30 08:00 | 2027-04-23 20:00 | S | 24.5
Irishtown | IS2 | 30 | 2027-03-31 06:00 | 2027-04-05 20:00 | S | 5.58
Irishtown | IS3 | 64 | 2027-03-31 06:00 | 2027-04-05 19:00 | S | 5.5
Edenderry | ED1 | 118 | 2027-04-01 17:00 | 2027-04-07 08:00 | S | 5.58
Erne | ER1 | 10 | 2027-04-05 08:00 | 2027-04-23 20:00 | S | 18.5
Ardnacrusha | AA1 | 21 | 2027-04-05 08:00 | 2027-04-09 20:00 | S | 4.5
Whitebank | DW1 | 61.5 | 2027-04-05 08:00 | 2027-04-10 08:00 | 26 | 5
Poolbeg | PB6 | 168 | 2027-04-06 08:00 | 2027-06-12 21:00 | 84 | 67.5
Aghada | AD3 | 19 | 2027-04-07 07:00 | 2027-04-12 19:00 | S | 5.5
Moneypoint | MP1 | 285 | 2027-04-09 22:00 | 2027-04-24 22:00 | S | 15
Drybridge | IW1 | 17 | 2027-04-10 | 2027-04-23 | S | 13
Whitebank | DW1 | 61.5 | 2027-04-10 08:00 | 2027-04-20 20:00 | S | 10.5
EWIC | EW1 | 500 | 2027-04-12 09:00 | 2027-04-12 21:00 | S | 0.5
EWIC | EW1 | 500 | 2027-04-12 21:00 | 2027-04-22 23:00 | S | 10.08
Poolbeg | PB8 | 75 | 2027-04-14 06:00 | 2027-04-19 19:00 | S | 5.5
Poolbeg | PB7 | 64 | 2027-04-14 06:00 | 2027-04-19 19:00 | S | 5.5
Whitebank | DW1 | 61.5 | 2027-04-20 08:30 | 2027-04-25 19:00 | 26 | 5.42
Seal Rock | SK3 | 83 | 2027-04-26 06:00 | 2027-04-28 18:00 | S | 2.5
Irishtown | IS2 | 30 | 2027-04-28 06:00 | 2027-05-03 20:00 | S | 5.58
Irishtown | IS3 | 64 | 2027-04-28 06:00 | 2027-05-03 19:00 | S | 5.5
Turlough Hill | TH2 | 73 | 2027-05-02 08:00 | 2027-06-25 18:00 | S | 54.42
Turlough Hill | TH1 | 73 | 2027-05-02 08:00 | 2027-10-15 18:00 | S | 166.42
Turlough Hill | TH3 | 73 | 2027-05-02 08:00 | 2027-06-25 18:00 | S | 54.42
Turlough Hill | TH4 | 73 | 2027-05-02 08:00 | 2027-06-25 18:00 | S | 54.42
Coolkeeragh | NICGT8 | 53 | 2027-05-03 | 2027-06-13 | S | 41
Lee | LE1 | 15 | 2027-05-04 08:00 | 2027-05-14 20:00 | S | 10.5
Aghada | AD4 | 75 | 2027-05-05 07:00 | 2027-05-14 19:00 | S | 9.5
Kilroot | NIKGT6 | 350 | 2027-05-07 | 2027-05-12 | S | 5
Aghada | AT1 | 90 | 2027-05-10 | 2027-05-14 | S | 4
Ardnacrusha | AA4 | 24 | 2027-05-10 08:00 | 2027-05-28 20:00 | S | 18.5
Erne | ER2 | 10 | 2027-05-10 08:00 | 2027-05-14 20:00 | S | 4.5
Seal Rock | SK3 | 83 | 2027-05-10 18:00 | 2027-05-13 18:00 | S | 3
Seal Rock | SK4 | 83 | 2027-05-11 | 2027-05-13 12:00 | S | 2.5
Corduff | FG2 | 64 | 2027-05-12 06:00 | 2027-05-17 19:00 | S | 5.5
Kilroot | NIKGT7 | 350 | 2027-05-14 | 2027-05-19 | S | 5
Moneypoint | MP2 | 285 | 2027-05-14 22:00 | 2027-05-30 22:00 | S | 16
Aghada | AD5 | 75 | 2027-05-15 07:00 | 2027-05-24 19:00 | S | 9.5
Aghada | AT2 | 90 | 2027-05-17 | 2027-05-21 | S | 4
Rhode | RP1 | 52 | 2027-05-17 08:00 | 2027-05-28 20:00 | S | 11.5
Rhode | RP2 | 52 | 2027-05-17 08:00 | 2027-05-28 20:00 | S | 11.5
Ballylumford | NIB10 | 94 | 2027-05-21 | 2027-05-25 | S | 4
Aghada | AT4 | 90 | 2027-05-24 | 2027-05-28 | S | 4
Lee | LE3 | 8 | 2027-05-25 08:00 | 2027-06-04 20:00 | S | 10.5
Poolbeg | PB6 | 168 | 2027-05-28 08:00 | 2027-07-10 17:00 | S | 43.33
Seal Rock | SK4 | 83 | 2027-05-30 06:00 | 2027-06-21 18:00 | S | 22.5
Poolbeg | PB5 | 153 | 2027-06-04 08:00 | 2027-06-12 17:00 | S | 8.33
Kilroot | NIKGT3 | 42 | 2027-06-07 | 2027-06-12 | S | 5
Liffey | LI1 | 15 | 2027-06-07 08:00 | 2027-06-18 18:00 | S | 11.42
Liffey | LI2 | 15 | 2027-06-07 08:00 | 2027-06-18 18:00 | S | 11.42
Kilroot | NIKGT4 | 42 | 2027-06-12 | 2027-06-17 | S | 5
Ardnacrusha | AA2 | 22 | 2027-06-14 08:00 | 2027-06-18 20:00 | S | 4.5
Tawnaghmore | TP1 | 52 | 2027-06-14 08:00 | 2027-06-21 20:00 | S | 7.5
Moyle | MOYLE | 450 | 2027-06-15 | 2027-06-18 | 250 | 3
Moneypoint | MP5 | 1 | 2027-06-16 | 2027-06-19 19:00 | S | 3.75
Huntstown | HNC | 342 | 2027-06-18 21:00 | 2027-07-08 21:00 | S | 20
Erne | ER3 | 23 | 2027-06-21 08:00 | 2027-06-25 20:00 | S | 4.5
Tawnaghmore | TP3 | 52 | 2027-06-21 08:00 | 2027-06-28 20:00 | S | 7.5
Coolkeeragh | NIC30 | 408 | 2027-06-26 | 2027-06-28 | S | 2
Edenderry | ED1 | 118 | 2027-07-02 12:00 | 2027-07-30 08:00 | S | 27.83
Cloniffeen | SI1 | 50 | 2027-07-05 08:00 | 2027-07-06 17:00 | S | 1.33
Cloniffeen | SI2 | 50 | 2027-07-05 08:00 | 2027-07-06 17:00 | S | 1.33
Ballylumford | NIB32 | 249 | 2027-07-09 | 2027-07-16 | S | 7
Ballylumford | NIB31 | 249 | 2027-07-09 | 2027-07-16 | S | 7
Ballylumford | NIB10 | 94 | 2027-07-09 | 2027-07-16 | S | 7
Ballylumford | NIB32 | 249 | 2027-07-16 | 2027-09-19 | 161 | 65
Ballylumford | NIB31 | 249 | 2027-07-16 | 2027-09-16 | 161 | 62
Erne | ER4 | 23 | 2027-07-19 08:00 | 2027-07-23 20:00 | S | 4.5
Derrycarney | LU1 | 50 | 2027-07-19 08:00 | 2027-07-20 17:00 | S | 1.33
Derrycarney | LU2 | 50 | 2027-07-19 08:00 | 2027-07-20 17:00 | S | 1.33
Moneypoint | MP3 | 285 | 2027-08-06 22:00 | 2027-08-22 22:00 | S | 16
EWIC | EW1 | 500 | 2027-08-20 11:00 | 2027-08-20 23:00 | S | 0.5
Seal Rock | SK3 | 83 | 2027-09-06 06:00 | 2027-09-10 18:00 | S | 4.5
Ardnacrusha | AA3 | 19 | 2027-09-13 08:00 | 2027-09-17 20:00 | S | 4.5
Ballylumford | NIB31 | 249 | 2027-09-16 | 2027-09-19 | S | 3
Edenderry | ED3 | 58 | 2027-09-17 08:00 | 2027-09-17 18:00 | S | 0.42
Edenderry | ED5 | 58 | 2027-09-17 08:00 | 2027-09-17 18:00 | S | 0.42
Ballylumford | NIB32 | 249 | 2027-09-19 | 2027-09-22 | S | 3
Ballylumford | NIB31 | 249 | 2027-09-19 | 2027-09-22 | 161 | 3
Lisdrum | LF1 | 60 | 2027-09-20 08:00 | 2027-09-22 17:00 | S | 2.33
Ballylumford | NIB10 | 94 | 2027-09-24 | 2027-09-28 | S | 4
Tynagh | TYC | 404 | 2027-09-29 22:00 | 2027-10-05 21:00 | S | 5.92
Huntstown | HN2 | 402 | 2027-10-01 21:00 | 2027-11-07 21:00 | S | 37
Whitegate | WG1 | 444 | 2027-10-02 21:00 | 2027-10-12 21:00 | S | 10
Ballylumford | NIBGT1 | 58 | 2027-10-04 | 2027-10-10 | S | 6
Coolkeeragh | NIC30 | 408 | 2027-10-04 | 2027-10-16 | S | 12
Whitebank | DW1 | 61.5 | 2027-10-04 08:00 | 2027-10-07 08:00 | 26 | 3
Ballylumford | NIBGT2 | 58 | 2027-10-10 | 2027-10-16 | S | 6
Turlough Hill | TH2 | 73 | 2027-10-10 08:00 | 2027-10-15 17:00 | S | 5.33
Turlough Hill | TH3 | 73 | 2027-10-10 08:00 | 2027-10-15 18:00 | S | 5.42
Turlough Hill | TH4 | 73 | 2027-10-10 08:00 | 2027-10-15 18:00 | S | 5.42
Whitebank | DW1 | 61.5 | 2027-10-11 08:00 | 2027-10-14 18:00 | 26 | 3.42
Inchicore | IH1 | 30 | 2027-10-13 07:00 | 2027-10-18 19:00 | S | 5.5
Dublin Bay | DB1 | 415 | 2027-10-15 12:00 | 2027-10-22 19:00 | S | 7.25
Kilroot | NIKGT1 | 29 | 2027-10-17 | 2027-10-20 | S | 3
Aghada | AD2 | 449 | 2027-10-18 | 2027-10-25 23:00 | S | 7.92
Kilroot | NIKGT2 | 29 | 2027-10-20 | 2027-10-23 | S | 3
Seal Rock | SK4 | 83 | 2027-11-01 06:00 | 2027-11-03 18:00 | S | 2.5
Poolbeg | PB8 | 75 | 2027-11-17 06:00 | 2027-11-28 19:00 | S | 11.5
Poolbeg | PB7 | 64 | 2027-11-17 06:00 | 2027-11-28 19:00 | S | 11.5
Edenderry | ED1 | 118 | 2027-12-26 12:00 | 2028-01-01 08:00 | S | 5.83
|  |  | Scheduled Outage | S
|  |  | Forced Outage | F
|  |  | Unit partially available | 10