## Slide 1
Market Systems Release Update
Modifications Committee Meeting 47
February 12th 2012

## Slide 2
The following is the approved scope for SEM R2.2.0
SEM R2.2.0 – Approved Scope
Mod Ref | CR Ref | Description
Mod_17_11 | SEM_PC_CR281 | Addition of a D+3 DI report
Mod_03_12 | SEM_PC_CR290 | Alignment of T&SC with Revised VAT arrangements
Mod_17_12 | SEM_PC_CR300 | Report on Offered Capacity in Implicit Auctions **
SDS | SEM_PC_CR193 | TLAF Publishing in the MPI
SDS | SEM_PC_CR262 | Unit Under Test Submission Screen
SDS | SEM_PC_CR289 | Internal Submission Gates – Option 1
SDS | SEM_PC_CR295 | MA System Summary IC Flows

## Slide 3
SEM R2.2.0 Key Milestones
Vendor Design Approval 09 Jan 2013 √ Complete
MPUD Publication* 09 Jan 2013 √ Complete
Market Participant Workshop 24 Jan 2013 √ Complete
Vendor Code Delivery (Brady) 25 Jan 2013 √ Complete
Factory Test 14 Feb 2013 In Progress
Vendor Code Delivery (ABB) 15 Feb 2013
SIT Execution Commences 28 Jan 2013 In Progress
Market Test Execution 20 Mar - 19 Apr 2013
  Connectivity Testing 20-22 Mar 2013
  Functional Testing 25 Mar – 19 Apr 2013
Proposed Deployment** 10 May 2013
                * Revision V1.1 published on Jan 23rd
                ** Subject to successful completion of testing

## Slide 4
The release cut-off date for the October 2013 release to the Central Market Systems is:
Friday February 22nd, 2013.
All approved Modifications Proposals will be allocated to this release (subject to available capacity).
SEM R2.3.0 – October 2013

## Slide 5
Questions