## Slide 1
Market Systems Release Update
Modifications Committee Meeting 56
August 14th 2014

## Slide 2
The following table outlines the approved scope for the release:
* Added to scope on July 2nd
SEM R2.5.0 – November 2014
SEM R2.5.0 Approved Scope | 
CR Ref | Description
SEM_PC_CR322 | Eligible Availability for Energy Limited Units Under Test
SEM_PC_CR327 | Event Queuing
SEM_PC_CR333 | Functionality to apply PUGDOG TTariff on a Trading Day basis
SEM_PC_CR332 | Issue Zero Invoices
SEM_PC_CR330 | Changes to IART Report
SEM_PC_CR336 | HMRC VAT Change*

## Slide 3
Design closed Jun 30th Complete
Publication of MPUD Jul 17th Complete
Software delivery Jul 31st Complete
Publication of sample files Aug 1st Complete
from Vendor Testing
System Integration Test Execution Aug 5th to Oct 10th In Progress
Market Test Execution Oct 13th to Oct 24th
Deployment * Nov 14th
* subject to successful completion of all testing.
SEM R2.5.0 – November 2014 - Milestones

## Slide 4
Release Cut-Off Date is Friday September 5th, 2014.
SEM R2.6.0 – May 2015

## Slide 5
The current timelines are as follows:
  Entry into force of Implementing Acts ~ Q4 2014
  Start of data reporting ~ 6 months after adoption of Implementing Acts.
Requirements may necessitate a CMS release to ensure:
  That all relevant data is captured and
  Compliance with reporting obligations.
It is possible that a related CMS release may impact on interfaces between the CMS and Participant systems. SEMO are currently evaluating the draft requirements to determine likely impacts to the SEM.
REMIT Reporting

## Slide 6
Questions