## Slide 1
Market Systems Release Update
Modifications Committee Meeting 48
April 11th 2012

## Slide 2
The following is the approved scope for SEM R2.2.0
SEM R2.2.0 – Approved Scope
Mod Ref | CR Ref | Description
Mod_17_11 | SEM_PC_CR281 | Addition of a D+3 DI report
Mod_03_12 | SEM_PC_CR290 | Alignment of T&SC with Revised VAT arrangements
Mod_17_12 | SEM_PC_CR300 | Report on Offered Capacity in Implicit Auctions **
SDS | SEM_PC_CR193 | TLAF Publishing in the MPI
SDS | SEM_PC_CR262 | Unit Under Test Submission Screen
SDS | SEM_PC_CR289 | Internal Submission Gates – Option 1
SDS | SEM_PC_CR295 | MA System Summary IC Flows

## Slide 3
SEM R2.2.0 Key Milestones
Vendor Design Approval 09 Jan 2013 √ Complete
MPUD Publication* 09 Jan 2013 √ Complete
Market Participant Workshop 24 Jan 2013 √ Complete
Vendor Code Delivery (Brady) 25 Jan 2013 √ Complete
Factory Test 14 Feb 2013 √ Complete
Vendor Code Delivery (ABB) 15 Feb 2013 √ Complete
SIT Execution Commences 28 Jan 2013 √ Complete
Market Test Execution 13 Mar - 19 Apr 2013
  Connectivity Testing 20-22 Mar 2013 √ Complete
  Functional Testing 25 Mar – 19 Apr 2013 In Progress
Proposed Deployment** 10 May 2013
                * Revision V1.1 published on Jan 23rd
                ** Subject to successful completion of testing

## Slide 4
There are no approved Modification Proposals in scope for SEM R2.3.0 (Oct 2013)
A meeting of the Change Control Forum (CCF) was held on March 21st at which the following provisional scope was proposed for implementation.
SEM R2.3.0 – Potential Scope
CR Ref | Description
SEM_PC_CR174 | MPI Dropdown values for a Trading Site
SEM_PC_CR186 | Export Functionality in MA
SEM_PC_CR265 | Settlements Task Functionality
SEM_PC_CR297 | Wind Forecast Validation
SEM_PC_CR310 | Run Cancellation Initialisation
SEM_PC_CR312 | Run Cancellation Functionality
SEM_PC_CR168 | Unnecessary File Import Type Selection
SEM_PC_CR311 | VTOD Status Changes for Approval
SEM_PC_CR294 | DDF Linked to System Type within POMAX file import
SEM_PC_CR295 | Displaying UUC Penalty Costs in MA

## Slide 5
A proposal will be sent to the Regulatory Authorities this week seeking approval for the scope proposed at the CCF.
On receipt of Regulatory approval we will publish the release scope to the industry.
SEM R2.3.0 – Scope - Next Steps

## Slide 6
The release cut-off date for the April 2014 release to the Central Market Systems is:
Friday September 27th, 2013.
All approved Modifications Proposals will be allocated to this release (subject to available capacity).
SEM R2.4.0 – April 2014

## Slide 7
Questions